Phase 10: Multi-City Expansion 🌍🐾

Controlled City Replication, Operations and Phase 11 Gate

Executive decision

Approve Phase 10 with one major condition: launch the two new cities sequentially—not simultaneously.

Recommended six-month sequence:

Proven City

↓

City 2: controlled cluster launch

↓

City 2 reaches stability gate

↓

City 3: controlled cluster launch

↓

Network operating system validated

The strategic objective is not to display more city names on the website. It is to prove that the complete marketplace system can be reproduced in another geography:

- Demand acquisition

- Sitter recruitment

- Partner verification

- Scheduling

- Subscription fulfilment

- Society partnerships

- Payments and payouts

- Incident response

- Customer support

- Positive city-level contribution

India’s broader pet-care market is expanding rapidly, but market growth does not remove fulfilment risk. IBEF estimated the wider Indian pet-care industry at approximately ₹30,434 crore in CY2024, while projecting substantial growth through 2032. This makes expansion attractive, but operational reliability—not market size—will determine whether a multi-city service marketplace survives.

1. Phase 10 principle

Wrong expansion model

Launch six cities

↓

Recruit large numbers of applicants

↓

Run ads everywhere

↓

Accept bookings before local density exists

↓

Partners travel long distances

↓

Bookings fail

↓

Support and refunds increase

↓

Brand trust declines nationally

Correct expansion model

Select one city

↓

Select two or three micro-markets

↓

Validate demand before public launch

↓

Build verified local supply

↓

Run a closed beta

↓

Reach quality and contribution gates

↓

Expand inside the city

↓

Replicate in the next city

The actual expansion unit is not a city.

The expansion unit is a dense service cluster containing customers, societies, sitters, backup supply and local support.

Examples:

- Bengaluru → HSR–Koramangala

- Pune → Baner–Balewadi

- Mumbai → Powai–Chandivali

- Gurugram → Golf Course Road societies

- Ahmedabad → Thaltej–Bodakdev

- Surat → Vesu–VIP Road

2. Is the proposed duration realistic?

| Expansion version | Duration | Assessment |
| --- | --- | --- |
| Fast expansion | 3–6 months | Suitable for one mature city plus one or two tightly controlled additions |
| Standard expansion | 6–12 months | Best for three to five active cities |
| Strong expansion | 12–24 months | Appropriate for a five-to-ten-city network |

Recommended six-month target

Approve:

- One existing mature city

- Two additional city launches

- Maximum three operational cities by Month 6

But stagger them:

| Month | Expansion stage |
| --- | --- |
| Month 1 | Select and prepare City 2 |
| Month 2 | City 2 closed beta |
| Month 3 | City 2 cluster launch and stabilisation |
| Month 4 | Prepare City 3 |
| Month 5 | City 3 closed beta |
| Month 6 | City 3 cluster launch and network review |

Do not begin City 3 merely because City 2 has launched. Begin it only after City 2 passes its initial stability gate.

3. First-city replication readiness

The first city must prove that its performance comes from a repeatable system—not founder intervention.

Minimum stability period

Require 8–12 consecutive weeks of stable performance.

Demand gate

| Metric | Recommended threshold |
| --- | --- |
| Monthly completed bookings | 750–1,000+ |
| Active paying customers | 250–500+ |
| Repeat customer rate | 35–50% |
| Active subscribers | 100–250+ |
| Subscription renewal | 60%+ |
| Society partnerships | 3–5 paying or repeatable pilots |
| Organic/referral demand | Meaningful and measurable |

Quality gate

| Metric | Recommended threshold |
| --- | --- |
| Average rating | 4.6+ |
| Booking completion | 95%+ |
| On-time fulfilment | 95%+ |
| Partner cancellation | Below 5–7% |
| Refund/dispute rate | Below 3–5% |
| Critical unresolved incidents | Zero |
| Support SLA achieved | 90%+ |

Supply gate

- Active sitter pool is stable.

- Backup coverage exists by cluster.

- No single sitter controls an excessive share of fulfilment.

- Partner payouts are current.

- New sitters can be recruited and activated using a documented process.

- Founder is not manually assigning most bookings.

Economics gate

- Positive contribution per completed booking

- Positive contribution per subscriber

- CAC tracked by channel

- CAC payback understood

- City P&L reconciled

- No excessive founder-funded discounts

- Refund and service-recovery costs included

Do not expand because the city has revenue. Expand because the city has repeatable contribution.

4. Correcting the proposed Phase 10 targets

Active cities: 2–5

Approve as the long-term Phase 10 range.

For the first six months:

- Minimum: two active cities

- Base target: three active cities

- Five cities: only after the network system proves stable

Monthly bookings per city: 1,000+

This is appropriate for a mature city, but not for every newly launched city.

Use staged expectations:

| City stage | Monthly completed bookings |
| --- | --- |
| Closed beta | 50–150 |
| Early launch | 150–350 |
| Validated cluster city | 350–750 |
| Mature city | 1,000+ |
| Scaled city | 2,500+ |

A new city should not be labelled a failure because it has not reached 1,000 bookings during its first 60 days.

Active subscribers: 200–1,000+

Clarify whether this is:

- Per city

- Across the network

- Pet-parent subscriptions only

- Including society and partner subscriptions

Recommended network target by the end of the first six months:

| Level | Active consumer subscribers |
| --- | --- |
| Minimum | 200 |
| Base | 300–500 |
| Strong | 500–750 |
| Stretch | 1,000+ |

Also report subscribers by city. One mature city should not hide poor subscription adoption in the others.

Incident rate: below 3%

This target is too broad and potentially too permissive.

Three incidents per 100 services would be unacceptable if those incidents involve:

- Escaped pets

- Injuries

- Bites

- Fraud

- Unsafe handovers

- Privacy breaches

Separate incidents by severity.

| Incident category | Target |
| --- | --- |
| Critical preventable incident | Zero |
| Serious safety incident | Below 0.1–0.3% |
| Minor reportable incident | Below 1% |
| General service complaint | Below 3–5% |
| Refund/dispute | Below 3–5% |

Every city must use the same incident definitions. Otherwise, one city may classify an injury as a “complaint” while another classifies it as a safety incident.

Each city has a city manager

Approve the accountability principle, but use staged staffing.

| City stage | Local ownership |
| --- | --- |
| Research/pre-launch | City launch owner |
| Closed beta | Launch manager or operations lead |
| 300–500 monthly bookings | Dedicated city manager strongly recommended |
| 1,000+ monthly bookings | Dedicated city manager required |
| Multiple clusters | Cluster leads or operations coordinators |

Every public city must have one named accountable owner, even when the role is initially shared.

5. City-selection scorecard

Do not select cities based only on population, prestige or investor appeal.

Score every candidate out of 100.

| Factor | Weight |
| --- | --- |
| Existing customer demand or waitlist | 15 |
| Society/apartment density | 15 |
| Verified sitter supply potential | 15 |
| Customer willingness to pay | 10 |
| Existing founder/partner network | 10 |
| Competitive intensity | 8 |
| Traffic and travel feasibility | 8 |
| Local veterinary/grooming ecosystem | 5 |
| Hiring and city-management availability | 5 |
| Regulatory/operating complexity | 4 |
| Expected contribution margin | 5 |
| Total | 100 |

Recommended decision bands

| Score | Decision |
| --- | --- |
| 80–100 | Priority launch candidate |
| 70–79 | Launch after targeted validation |
| 60–69 | Run demand and supply tests first |
| Below 60 | Defer |

Required evidence

Do not assign scores based only on intuition.

Use:

- Search and landing-page demand

- Existing customer requests

- Society discussions

- Sitter applications

- Paid test campaigns

- Competitor availability

- Partner interviews

- Price tests

- Local travel-time analysis

6. Why cluster operations are mandatory

Indian metro traffic creates substantial fulfilment risk. TomTom’s 2025 India index reported Bengaluru at a 74.4% average congestion level, with Pune and Mumbai also among the country’s most congested operating environments. This makes city-wide sitter pools, cross-city assignments and broad exact-time guarantees operationally unsafe.

Correct city structure

City

├── Cluster A

│   ├── Societies

│   ├── Sitters

│   ├── Backup sitters

│   └── Local partners

├── Cluster B

│   ├── Societies

│   ├── Sitters

│   └── Local partners

└── Cluster C

A sitter should normally operate within one cluster during a service block.

Cluster launch criteria

Each launch cluster should have:

- 300–1,500 addressable pet households

- Three or more target societies or dense neighbourhood zones

- Five to ten active sitters or walkers

- Two or more backup sitters

- Local grooming/training partners where those services are live

- One veterinary referral network

- One operations owner

- Maximum travel-time rules

- Local service pricing

- Capacity limits by time window

7. Multi-city operating model

Central team responsibilities

The central team should own:

- Product and engineering

- Brand standards

- Verification framework

- Payment infrastructure

- Subscription architecture

- Customer-support platform

- Partner scorecard

- Incident classification

- Finance and reconciliation

- Training material

- Privacy and security standards

- National performance reporting

City team responsibilities

The local team should own:

- Sitter recruitment

- Document collection

- Practical assessments

- Society acquisition

- Local partnerships

- Daily fulfilment

- Backup activation

- City-specific pricing recommendations

- Local complaints

- Event operations

- Supply and capacity planning

Principle

Centralise standards and technology; decentralise fulfilment and local relationships.

Do not allow every city to invent different:

- Verification badges

- Incident definitions

- Refund policies

- Rating formulas

- Subscription-credit rules

- Pet-safety protocols

Localise only what genuinely varies:

- Price

- Travel radius

- Language

- Society access

- Partner availability

- Event format

- Customer-acquisition channel

8. City launch lifecycle

Stage 0: Market validation

Duration: two to four weeks.

Actions

- Create city waitlist page.

- Run small-area acquisition tests.

- Interview pet parents.

- Interview sitter candidates.

- Meet RWAs and facility managers.

- Validate price ranges.

- Map competitors.

- Assess traffic and service radii.

Gate

Proceed when:

- 100–300 qualified customer leads exist.

- 30–60 sitter/partner applicants exist.

- At least three societies show interest.

- Two target clusters are identifiable.

- Early unit economics are viable.

Stage 1: Supply build

Duration: three to six weeks.

Minimum target

| Supply measure | Target |
| --- | --- |
| Sitter applicants | 30–60 |
| Document-verified | 15–30 |
| Trial-completed | 10–20 |
| Launch-ready active sitters | 8–15 |
| Backup-capable sitters | 3–5 |
| Groomer/trainer partners | 3–8 as relevant |
| Vet referral partners | 2–5 |

Do not celebrate applicant count. Measure active partners who accept and complete work.

Stage 2: Closed beta

Duration: four to six weeks.

Audience

- Waitlisted customers

- Existing customers relocating to the city

- Friendly societies

- Employee or founder networks

- Limited invited neighbourhoods

Beta targets

- 50–150 completed bookings

- 30–75 paying customers

- 4.6+ rating

- 95%+ booking completion

- Less than 5% complaint/refund rate

- No critical incident

- Positive or improving booking contribution

Stage 3: Cluster public launch

Open:

- Specific pin codes

- Specific time windows

- Specific services

- Capacity-controlled subscriptions

Do not advertise “Now available across Mumbai” when only Powai is operational.

Use:

Available in Powai, Chandivali and selected neighbouring societies.

Stage 4: City stabilisation

Before opening a second cluster, require:

- 300–500 monthly bookings

- 100+ repeat customers

- 25–50 subscribers

- 4.6+ rating

- 95% fulfilment

- Positive cluster contribution

- Stable city support

- Backup pool

- No serious unresolved incident

9. Six-month execution blueprint

Month 1 — Select and prepare City 2

Deliverables:

- City scorecard

- Two launch clusters

- City-level financial model

- Local price table

- Waitlist

- Society pipeline

- Sitter recruitment pipeline

- Compliance register

- Named launch owner

Month 2 — Closed beta in City 2

Targets:

- 50–150 completed bookings

- 8–15 active sitters

- Three to five society pilots

- 4.6+ rating

- 95% completion

- Zero critical incidents

Month 3 — Stabilise City 2

Targets:

- 200–400 monthly bookings

- 20%+ repeat customers in early cohorts

- 15–30 subscription users

- Positive contribution trajectory

- City-manager decision

- Documented launch retrospective

City 3 is blocked unless City 2 passes the stability gate.

Month 4 — Prepare City 3

Repeat the same process without weakening City 2.

Month 5 — Closed beta in City 3

Keep the launch limited to one or two clusters.

Month 6 — Stabilise City 3 and review the network

Final state:

- One mature city

- One validated city

- One beta-to-early-growth city

- Shared reporting and incident systems

- Network expansion playbook version 2

10. Supply architecture

City sitter funnel

Applicant

↓

Contact verified

↓

Documents verified

↓

Skills assessed

↓

Trial completed

↓

Cluster assigned

↓

Active partner

↓

Performance scored

City supply dashboard

Track:

- Applicants

- Verified

- Trial-completed

- Active in last 30 days

- Booking acceptance

- Completion

- On-time rate

- Cancellation

- Earnings

- Capacity utilisation

- Customer rating

- Partner churn

- Backup availability

Concentration control

Do not let one sitter become responsible for too much city revenue.

Suggested limits:

- No sitter handles more than approximately 10–15% of city bookings.

- Every recurring schedule has backup coverage.

- Every cluster has at least two independently viable primary providers.

- High-risk services have specialist alternatives.

These are operational safeguards rather than universal legal thresholds.

11. Demand architecture

Every city should begin with the channels most likely to generate dense, high-trust demand.

Recommended order

- Existing customer referrals

- Society and apartment partnerships

- Local veterinary/grooming referrals

- Resident ambassadors

- Search demand

- Hyperlocal digital campaigns

- Corporate pilots after fulfilment works

Do not begin with broad city advertising

Broad advertising creates:

- Scattered customers

- Long travel distances

- Low density

- High partner cancellation

- Expensive backup

- Poor contribution

Advertising should be restricted to active:

- Pin codes

- Clusters

- Time windows

- Service types

- Capacity levels

12. Society replication

Society relationships are city infrastructure—not merely marketing.

AWBI maintains guidance for pet owners, caregivers, RWAs and apartment associations. The platform should therefore standardise gate protocols and resident coexistence practices while adapting them to each property’s reasonable operational needs.

Society launch pack

Every new city should have:

- Society proposal

- 30-day pilot agreement

- Resident announcement templates

- Gate protocol

- Partner-entry roster

- Event SOP

- Complaint escalation

- Monthly report

- Data-sharing notice

- Pilot-to-paid conversion proposal

Society metrics by city

- Societies listed

- Societies contacted

- Meetings

- Pilots

- Paid societies

- Resident leads

- Resident bookings

- Subscriptions

- Event conversion

- RWA rating

- Gate incidents

- Contribution

13. Technology architecture for multi-city operations

Required hierarchy

Country

↓

State

↓

City

↓

Service zone

↓

Cluster

↓

Society or locality

Every booking should contain

- City ID

- Cluster ID

- Service zone

- Society/locality

- Travel estimate

- Pricing version

- Partner assignment pool

- City operations owner

- Incident jurisdiction

- City P&L attribution

New entities

cities

city_service_zones

city_clusters

city_service_catalogues

city_prices

city_capacity_limits

city_operating_hours

city_partner_assignments

city_launch_stages

city_compliance_register

city_pnl_periods

Feature flags

Services should be enabled by city and cluster:

Bengaluru / HSR

- walking: active

- sitting: active

- grooming: active

- taxi: beta

Pune / Baner

- walking: active

- sitting: beta

- grooming: active

- taxi: disabled

Do not use one global service_active = true flag.

14. City-level P&L

Every city requires its own financial statement.

Revenue

- One-time service GMV

- Subscription GMV

- Platform service revenue

- Membership revenue

- Society subscription revenue

- Event revenue

- Partner software revenue

Direct city costs

- Partner payouts

- City operations staff

- Local support

- Local acquisition

- Events

- Verification

- Partner recruitment

- Travel and logistics

- Refunds

- Service recovery

- Payment costs

- Local office, where applicable

City contribution

City contribution=  city platform revenue-city direct operating costs

City contribution per booking

Contribution per booking=city contributioncompleted bookings

City maturity economics

A city should not be scaled merely because GMV is increasing.

Scale when:

- Contribution per booking is positive.

- CAC is declining or controlled.

- Repeat rate is improving.

- Partner utilisation is healthy.

- Refund and support costs are stable.

- Fixed city costs have a credible payback path.

15. City manager scorecard

A city manager should be accountable for more than booking volume.

| Dimension | Metric |
| --- | --- |
| Demand | Completed bookings and repeat customers |
| Supply | Active providers and backup coverage |
| Quality | Rating, complaints and incidents |
| Reliability | Completion and on-time rates |
| Economics | Contribution and CAC payback |
| Society | Pilots, conversions and RWA satisfaction |
| People | Partner retention and earnings |
| Compliance | Documents, reporting and grievance handling |

Avoid incentive distortion

Do not pay bonuses solely for:

- Number of new sitters

- GMV

- Number of city launches

- App downloads

Use a balanced city score:

City score=growth+quality+reliability+contribution+safety

A critical preventable safety incident should override growth bonuses.

16. Multi-city compliance system

Each city should have a compliance register covering:

- Legal entity and state registrations

- Local establishment requirements

- Partner classification

- Partner documents

- Veterinary professional controls

- Transport requirements if taxi launches

- Local event permissions

- Tax registration and invoicing

- Customer grievances

- Privacy and data access

- Insurance

- Incident reporting

Gig and platform workers

The Code on Social Security defines platform work, and a June 2026 Labour Ministry communication states that the Social Security Rules, 2026 require aggregators to share details of gig and platform workers electronically. A pet-care marketplace should obtain a formal opinion on whether it is an in-scope aggregator and implement eShram onboarding/reporting where applicable.

Privacy

The notified DPDP Rules, 2025 have phased commencement. Multi-city expansion increases the number of employees and partners accessing addresses, recurring schedules, pet-care instructions and health-related records, so role-based access, city-level permissions, processing notices and audit trails should be operational before expansion.

Consumer support

India’s E-Commerce Rules require consumer-facing grievance mechanisms. New cities must not launch until customers have a visible escalation channel and central support knows which local team owns each case.

GST and marketplace settlement

Where the platform collects customer consideration for supplies made through third-party providers, e-commerce-operator and TCS treatment depends on the actual transaction structure. Maintain city-, partner- and service-level ledgers and obtain a written tax position before expanding settlement flows across states.

17. Central multi-city dashboard

Executive row

- Active cities

- Mature cities

- Cities in beta

- Network bookings

- Network platform revenue

- Network contribution

- Active subscribers

- Critical incidents

City comparison

| City | Bookings | Rating | Completion | Repeat | Subscribers | Contribution |
| --- | --- | --- | --- | --- | --- | --- |
| City 1 |  |  |  |  |  | ₹ |
| City 2 |  |  |  |  |  | ₹ |
| City 3 |  |  |  |  |  | ₹ |

Supply

- Active sitters per city

- Backup coverage

- Partner cancellation

- Capacity utilisation

- Partner earnings

- Partner retention

- Expiring documents

Quality

- Complaints

- Refunds

- Minor incidents

- Serious incidents

- Critical incidents

- Support SLA

- Open investigations

Economics

- City CAC

- Contribution per booking

- Contribution per subscriber

- Society contribution

- City manager and local staffing cost

- City break-even forecast

18. City maturity classification

Use standard stages.

| Stage | Definition |
| --- | --- |
| C0 Research | Demand and supply study |
| C1 Pre-launch | Recruitment and waitlist |
| C2 Closed beta | Invitation-only services |
| C3 Cluster launch | Public in limited areas |
| C4 Validated city | Repeatable demand and positive cluster contribution |
| C5 Mature city | 1,000+ monthly bookings with stable operations |
| C6 Scaled city | Multiple stable clusters and local management |

Cities should not be marketed internally as “launched” merely because a landing page exists.

19. Main Phase 10 failure modes

Failure 1: Copying pricing without copying economics

A Mumbai price cannot automatically be used in Ahmedabad or Pune.

Correct control:

- City pricing versions

- Local partner payouts

- Travel assumptions

- Support costs

- Contribution review

Failure 2: Hiring city teams before demand

Correct control:

- Launch owner first

- Contractor/partner-led operations

- Dedicated hiring after validated volume

Failure 3: Running nationwide advertising

Correct control:

- Cluster-specific campaigns

- Capacity-aware budget

- Waitlists for inactive areas

Failure 4: Counting applicants as supply

Correct control:

Track active, accepting and completing partners.

Failure 5: Inconsistent quality standards

Correct control:

One national verification and incident framework.

Failure 6: Opening services without backups

Correct control:

No subscription or high-frequency service without cluster backup coverage.

Failure 7: Hiding weak cities inside network totals

Correct control:

Publish city-level retention, quality and P&L.

Failure 8: Founder becoming every city manager

Correct control:

Named local accountability and escalation ownership.

Failure 9: Expanding after GMV growth but before contribution

Correct control:

City contribution and payback gates.

Failure 10: Changing too many variables

Do not simultaneously test:

- New city

- New service

- New pricing

- New subscription

- New partner model

- New payment provider

Each city should launch with the simplest proven service stack.

20. Recommended Phase 10 success targets

Network

| Metric | Six-month target |
| --- | --- |
| Operational cities | 2–3 |
| Mature cities | At least 1 |
| Validated new cities | At least 1 |
| Network active subscribers | 200–500 base |
| Recurring platform-revenue share | 25–40% |
| Network average rating | 4.6+ |
| Critical unresolved incidents | Zero |

Mature city

| Metric | Target |
| --- | --- |
| Monthly completed bookings | 1,000+ |
| Repeat customer rate | 35–50% |
| Booking completion | 95%+ |
| On-time rate | 95%+ |
| Refund/dispute rate | Below 3–5% |
| Active subscribers | 100–300+ |
| Positive city contribution | Yes |

New validated city

| Metric | Target |
| --- | --- |
| Monthly completed bookings | 300–750 |
| Repeat customer rate | 25–40% |
| Booking completion | 95%+ |
| Rating | 4.6+ |
| Active sitters | 10–25 |
| Backup coverage | 90–95%+ |
| Critical incidents | Zero |
| Positive cluster contribution | At least one cluster |

Supply

| Metric | Target |
| --- | --- |
| On-time rate | 95%+ |
| Partner cancellation | Below 5–7% |
| Active-to-verified partner ratio | Tracked and improving |
| Backup coverage | 90–95%+ |
| Expired critical documents | Zero |
| Partner payouts on time | 98%+ |

21. Phase 11 go/no-go criteria

Move to Phase 11 only when all critical gates pass.

Replication gate

- At least one new city has reached C4 Validated City status.

- The city launch was not dependent on continuous founder intervention.

- The playbook produced similar quality to the original city.

- Sitter recruitment and activation are repeatable.

- Society acquisition is repeatable.

- Local support ownership is working.

Quality gate

- Every public city has a 4.6+ rating.

- Completion is 95%+.

- On-time performance is 95%+.

- Critical unresolved incidents are zero.

- Refund and dispute rate is below 5%.

Economics gate

- Original city is contribution-positive.

- At least one new city has a contribution-positive cluster.

- City CAC and payback are known.

- City P&Ls reconcile.

- Expansion is not funded through uncontrolled discounting.

Subscription gate

- Network has at least 200 active subscribers.

- Renewal remains 60%+.

- Recurring platform-revenue share has a credible path to 25–40%.

- Subscriptions remain within local sitter capacity.

Management gate

- Every public city has a named accountable operator.

- Mature cities have a dedicated city manager.

- Central quality and finance teams can compare cities consistently.

- Incident escalation works across city boundaries.

Compliance gate

- City compliance registers are complete.

- Partner documentation is current.

- Worker-reporting obligations have been assessed.

- Privacy access is city-scoped.

- Customer grievances have clear ownership.

- Tax and payout structures are documented.

Final approval

| Phase 10 proposal | Decision |
| --- | --- |
| Controlled city replication | Approved |
| Launch two new cities in six months | Approved sequentially |
| Launch all target cities together | Rejected |
| Require first-city stability | Approved—non-negotiable |
| 1,000 monthly bookings per city | Use for mature cities only |
| 4.6+ city rating | Approved |
| 95% on-time rate | Approved |
| Incident rate below 3% | Replace with severity-based targets |
| City manager in every city | Approved with stage-based staffing |
| Verified sitter pool per city | Approved |
| City-level P&L | Approved—mandatory |
| Five cities after operational proof | Approved |

Final Phase 10 recommendation

Build:

A controlled city-replication system that launches one micro-market at a time, proves demand before scaling supply, assigns accountable local ownership, standardises safety nationally and measures every city as an independent operating and financial unit.

Phase 10 win condition

The second and third cities achieve reliable bookings, repeat customers, subscription adoption and positive cluster economics using the documented operating system—not exceptional founder intervention.

Phase 10 status: GO—launch City 2 first, stabilise it, then launch City 3.

A monthly multi-city competitor, regulation, traffic and pricing watch would be valuable during Phase 10.

Phase 10 Expansion Readiness and City Sequence 🌍🐾

Executive decision

Your principle is correct:

Do not launch City 2 until City 1 functions as a repeatable operating system rather than a founder-managed project.

However, the proposed readiness table contains several internal inconsistencies. The biggest is this:

- 100 active walking subscribers receiving 12–20 walks each would generate approximately 1,200–2,000 monthly service fulfilments.

- Therefore, a target of only 1,000 total paid bookings per month cannot coexist with 100 walking-plan subscribers unless “booking” means a multi-walk order rather than an individual completed walk.

- Similarly, 50–100 sitters capable of 60–100 walks each would represent roughly 3,000–10,000 walks of theoretical monthly capacity, which is excessive for a city completing only 1,000 walks.

Before expansion, define precisely:

Order        = one commercial purchase

Booking      = one scheduled service

Fulfilment   = one completed walk/visit/session

Customer     = one paying account

Subscriber   = one active recurring plan

Final recommendation

- Approve the first-city stability requirement.

- Modify the subscriber, sitter and revenue thresholds.

- Reject one fixed national city order.

- Choose either a Gujarat-first or metro-first expansion thesis and follow it deliberately.

- Add one adjacent city first, then one structurally different city to prove that the playbook is genuinely transferable.

1. When City 1 is genuinely ready

The first city should meet readiness standards for at least three consecutive months, not merely during one unusually strong month.

Corrected readiness framework

| Area | Recommended minimum before City 2 |
| --- | --- |
| Completed service fulfilments | 1,000+ monthly for three months |
| Monthly paying customers | 300–500+ |
| 90-day active pet parents | 500+ |
| Walking-plan subscribers | 50–100+, depending on plan size |
| Repeat customer rate | 35%+ |
| Active service providers | 20–40 |
| Verified supply bench | 40–80 |
| Paid/active society partners | 5–10 |
| Qualified society pipeline | 10–25 |
| Average rating | 4.6+ with meaningful review volume |
| Booking completion | 95%+ |
| On-time fulfilment | 95%+ |
| Sitter no-show | Below 1% |
| Sitter cancellation | Below 5% |
| Refund/dispute rate | Below 3–5% |
| Critical unresolved incidents | Zero |
| City contribution | Positive for three months |
| Founder-dependent bookings | Below 5–10% |
| Support and escalation SLAs | Consistently achieved |

2. Autopsy of the proposed targets

Paid bookings: 1,000+ per month

Decision: Approve with a definition

Use:

1,000 completed service fulfilments per month

Do not count:

- Created bookings

- Cancelled bookings

- Unpaid requests

- Trial applications

- Subscription credits not yet consumed

Also report:

- Unique paying customers

- Orders

- Completed service occurrences

- Services per customer

- Repeat-customer contribution

A city with 1,000 fulfilments from 300 repeat customers is generally healthier than a city with 1,000 fulfilments from 950 one-time discount users.

Active pet parents: 500+

Decision: Approve

Define two customer groups:

Monthly active paying customers

Customers completing at least one paid service in the current month.

Ninety-day active pet parents

Customers completing a paid service during the previous 90 days.

Recommended readiness:

- 300–500 monthly active paying customers

- 500–800 ninety-day active customers

- At least 35% repeating within a defined period

Avoid counting:

- App registrations

- Event attendees without purchases

- Free pilot leads

- Dormant customer records

Active subscribers: 100+

Decision: Approve only after reconciling volume

If the average subscription contains:

- 12 walks: 100 subscribers create up to 1,200 monthly walk entitlements.

- 20 walks: 100 subscribers create up to 2,000 monthly walk entitlements.

Therefore, choose one corrected model:

Conservative readiness model

- 50–75 active walking subscribers

- 1,000–1,500 completed monthly services

Strong subscription model

- 100+ active walking subscribers

- 1,500–2,500 completed monthly services

- Credit utilisation of 70–90%

Do not use 100 subscribers as a vanity target while service capacity is unable to fulfil their credits.

Verified sitters: 50–100

Decision: Split verified and active supply

A large verified database is not the same as usable supply.

Track:

| Supply category | Meaning |
| --- | --- |
| Applicants | Submitted form |
| Verified | Documents and checks completed |
| Trialled | Practical assessment completed |
| Active | Accepted/completed work in 30 days |
| Core active | Consistently available |
| Backup | Holds usable reserve capacity |

Recommended first-city readiness:

- 40–80 verified providers

- 20–40 active providers

- 10–20 core active walkers

- 10–15% backup capacity

- No individual responsible for an excessive share of city fulfilment

If 50 active sitters each safely fulfil 60 monthly walks, the city has approximately 3,000-walk capacity. Maintaining that supply against only 1,000 completed walks may produce weak partner earnings and high partner churn.

Partner societies: 10–25

Decision: Separate live partners from pipeline

Use:

- 5–10 paid or operationally active societies

- 10–25 qualified societies in the pipeline

- At least three societies generating repeat resident bookings

- At least two societies producing positive contribution

A logo on a “partner society” page does not count unless the relationship generates:

- Resident registrations

- Paid bookings

- Events

- Subscriptions

- Operational access

- Repeat activity

AWBI maintains specific guidance covering pet owners, caregivers, RWAs and apartment associations, so the city playbook should include standard society-access, resident-responsibility and grievance procedures.

Monthly revenue: ₹5 lakh–₹20 lakh

Decision: Replace “revenue” with three metrics

At 1,000 bookings:

- ₹5 lakh represents an average customer payment of ₹500 per booking.

- ₹20 lakh represents an average customer payment of ₹2,000 per booking.

Both may be possible depending on whether the service mix is dominated by walking, grooming, boarding or training. But the range is too broad to prove expansion readiness.

Track:

City GMV

Total customer spending.

Platform revenue

Commission, fees and subscription income retained by the platform.

City contribution

Platform revenue minus direct city costs:

- Partner payouts where applicable

- Local support

- Refunds

- Payment costs

- City acquisition

- Verification

- Local operations

- Service recovery

- Events

Expansion should require:

Positive city contribution for three consecutive months.

Not merely:

₹5 lakh or ₹20 lakh received from customers.

Published Indian pet-care estimates differ significantly depending on whether they include food, products, healthcare and services, reinforcing why internal city economics are more useful than headline market-size figures.

Sitter no-show below 5%

Decision: Tighten

A 5% no-show rate means five completely missed arrivals per 100 assignments, which is too high for a trust-sensitive care marketplace.

Use:

| Reliability metric | Target |
| --- | --- |
| Sitter no-show | Below 1% |
| Sitter-initiated cancellation | Below 5% |
| Approved backup fulfilment | 90%+ |
| Overall completion | 95%+ |
| On-time arrival | 95%+ |

A cancellation with adequate notice and successful backup is materially different from a no-show.

Support system stable

Decision: Convert into measurable criteria

“Stable” should mean:

- 90%+ of standard cases answered within the stated SLA

- Urgent service failures acknowledged within 15–30 minutes during service hours

- Critical incidents escalated immediately

- Refund decisions resolved within a defined period

- Less than 5% case reopening

- No unresolved critical ticket older than 24 hours

- Every case has a city owner and central escalation path

Incident process working

Decision: Require proof

The incident system should demonstrate:

- Severity classification

- Immediate containment

- Pet-parent communication

- Provider suspension where required

- Evidence preservation

- Medical or legal escalation

- Root-cause analysis

- Corrective action

- Closure approval

- Cross-city learning

Before City 2, perform at least one tabletop simulation involving:

- Pet escape

- Sitter no-show

- Injury during walk

- Customer access/security failure

- Payment/refund dispute

- Privacy exposure

Positive unit economics

Decision: Approve—non-negotiable

Include all direct costs.

City contribution=  platform service revenue+subscription revenue+society revenue-local acquisition-city operations-support-verification-refunds and recovery-payment costs

Do not expand while relying on:

- Founder labour valued at zero

- Unpaid partner management

- Promotional prices

- Delayed payouts

- Unrecorded refund exposure

3. The final City 2 readiness test

City 1 should pass five gates.

Gate A — Demand

- 1,000+ monthly completed fulfilments

- 300–500 monthly paying customers

- 35%+ repeat customers

- 50–100 healthy service-plan subscribers

- Demand spread across at least two clusters

Gate B — Supply

- 20–40 active providers

- 40–80 verified supply bench

- 90%+ backup coverage

- Peak slots below 85–90% utilisation

- Partner payouts current

- Healthy provider earnings

Gate C — Quality and safety

- Rating 4.6+

- Completion 95%+

- On-time 95%+

- No-show below 1%

- Refund/dispute below 5%

- No critical unresolved incident

Gate D — Economics

- Positive contribution for three months

- CAC known by channel

- Contribution known by service

- Subscription contribution positive

- Society economics separated

- No unsustainable discount dependency

Gate E — Replicability

- Founder can step away for one to two weeks

- SOPs cover normal and exceptional cases

- A city owner operates the marketplace

- Finance reconciles without manual reconstruction

- Support can route cases without founder intervention

- New sitters can be activated through the documented process

City 2 should be blocked if any critical quality, capacity or incident gate fails—even if revenue is strong.

4. What is wrong with one universal expansion order

The proposed list is useful as a candidate pipeline, but it should not be treated as a fixed national sequence.

City selection depends on:

- Founder network

- Existing waitlist

- Local operations leader

- Sitter pipeline

- Society access

- Customer pricing power

- Travel friction

- Competition

- Local compliance

- Cross-city management cost

The correct next city is not necessarily the largest market.

It is:

The city with the highest probability of producing a dense, contribution-positive launch cluster using the fewest new assumptions.

5. Current city-operating signals

Ahmedabad

Ahmedabad’s 2025 average congestion level was 49%, lower than Bengaluru, Pune, Mumbai, Hyderabad, Chennai and Jaipur in TomTom’s current city data. That does not eliminate travel problems, but it can make controlled route operations more manageable. Ahmedabad Municipal Corporation also operates an official pet-dog registration system.

Existing dog-walking subscriptions are already publicly advertised in Ahmedabad, so the category is not completely undeveloped; differentiation must come from local trust, better reliability and society integration.

Best role: controlled first city or regional operating base.

Bengaluru

Bengaluru offers strong subscription-validation potential, but it is operationally difficult. TomTom recorded a 74.4% average congestion level in 2025 and approximately 36 minutes for a 10 km drive. Existing providers already market monthly, GPS-tracked walking subscriptions, demonstrating both customer familiarity and active competition.

Best role: strongest digital product-market-fit test, but only through micro-market clusters.

Pune

Pune recorded 71.1% average congestion in 2025, so cross-city sitter assignment would be risky. Current providers also advertise subscription-based walking, meaning value, continuity and society density—not merely subscription availability—must differentiate the offer.

Best role: balanced second metro and strong society/subscription market.

Hyderabad

Hyderabad had a 55.5% average congestion level in 2025—still significant, but lower than Bengaluru, Pune and Mumbai. Existing providers advertise daily monthly walking subscriptions there, indicating that the recurring-care category already has market visibility.

Best role: should move earlier in a metro-first sequence than your original order suggests.

Gurugram

Current providers advertise monthly walking subscriptions in Gurugram. Its strongest strategic fit is not merely walking volume, but premium society contracts, verified partner pools and corporate-adjacent demand.

Best role: premium society and B2B validation city.

Mumbai

Mumbai offers high-value convenience potential, but TomTom recorded a 63.2% average congestion level in 2025. Subscription competitors are already present, making tight service radii and locality-level supply essential.

Best role: later premium launch after route-density and backup systems are mature.

Chennai

Walking services are currently marketed in Chennai, and Greater Chennai Corporation operates an official pet-licensing system; it reported issuing 9,115 pet-animal licences during 2024. Chennai also recorded 58.6% average congestion in 2025.

Best role: attractive later metro, requiring local-language operations, city-specific licensing guidance and cluster planning.

Delhi NCR deeper expansion

The Municipal Corporation of Delhi operates an official annual pet-dog registration process tied to vaccination validity. This reinforces the need for city-specific documentation and resident guidance when expanding beyond Gurugram into Delhi’s municipal jurisdictions.

Best role: expand after Gurugram rather than treating all NCR jurisdictions as one operating city.

6. Corrected premium metro-first path

Recommended order

1. Bengaluru

Prove:

- Premium UX

- Walking subscriptions

- Preferred-walker system

- Digital acquisition

- Cluster technology

2. Pune

Prove:

- Value-led subscriptions

- Society resident plans

- Route density

- Lower-price economics

3. Hyderabad

Prove:

- Replication into another technology-oriented metro

- More manageable travel economics than Bengaluru/Pune

- Scalable monthly walking demand

4. Gurugram

Prove:

- Premium society desk

- B2B subscriptions

- Corporate partnerships

- High-trust verification

5. Mumbai

Prove:

- Premium hyperlocal economics

- Very narrow operational zones

- High-cost support model

Why Hyderabad moves ahead of Mumbai

Hyderabad currently combines visible subscription-market activity with lower measured congestion than Bengaluru, Pune and Mumbai, making it a stronger intermediate replication test before the most operationally difficult premium city.

Metro-first strengths

- Faster testing of premium pricing

- Greater digital-service familiarity

- Larger subscription opportunity

- Stronger corporate partnership potential

- More recognisable national growth narrative

Metro-first risks

- Higher competition

- Higher customer-acquisition cost

- High service expectations

- Traffic and narrow scheduling windows

- Higher city-team costs

- Faster reputational damage after quality failure

Metro-first readiness requirement

This path requires:

- Strong product engineering

- Paid acquisition discipline

- Central support

- Experienced city operators

- Capital for early supply density

- Strict cluster-level launch controls

7. Corrected Gujarat-first path

Recommended order

1. Ahmedabad

Build:

- Operating headquarters

- Trust-led local brand

- Society partnerships

- Walking subscriptions

- Grooming and camps

- Gujarati/Hindi support

2. Surat

Test:

- Replication using similar language and state context

- Society-first acquisition

- Smaller entry plans

- Strong local referrals

Surat Municipal Corporation provides current forms and municipal online-service infrastructure related to pet dogs, so the local launch playbook should include documentation guidance and municipal monitoring.

3. Pune

This is the critical cross-state replication test.

Pune proves whether the model works beyond the founder’s home-region advantage.

4. Bengaluru

Use the established product and supply systems to enter a more competitive, digitally mature market.

5. Vadodara or Rajkot

Choose based on:

- Customer waitlist

- Society pipeline

- Local operator

- Sitter supply

- Contribution forecast

Do not add both automatically.

Why Pune should enter before completing four Gujarat cities

Expanding Ahmedabad → Surat → Vadodara → Rajkot may build regional depth, but it does not quickly prove that the model can travel outside the founder’s strongest cultural and operating network.

A stronger replication sequence is:

Ahmedabad

↓

Surat

↓

Pune

↓

Bengaluru

↓

Vadodara/Rajkot

This provides:

- One adjacent-state replication

- One cross-state validation

- One major metro validation

- Later regional consolidation

Gujarat-first strengths

- Lower management distance

- Local network leverage

- More efficient founder oversight

- Potentially lower customer-acquisition cost

- Strong referral and society channels

- Easier local-language trust building

Gujarat-first risks

- Lower premium pricing ceiling in some clusters

- Greater reliance on offline education

- Potentially slower subscription adoption

- Risk of mistaking regional advantage for national product-market fit

- Fewer experienced marketplace operators in some cities

8. Recommended expansion path for your situation

Choose Gujarat-first when:

- You already have strong RWA, veterinary or pet-parent relationships in Gujarat.

- A trusted Ahmedabad city manager is available.

- You can recruit walkers through local references.

- Your acquisition advantage is offline trust rather than large paid-media budgets.

- Capital efficiency is more important than rapid national branding.

Recommended sequence

Ahmedabad → Surat → Pune → Bengaluru → Vadodara/Rajkot

Choose metro-first when:

- You have sufficient launch capital.

- Your product and UX are already polished.

- You can hire strong city operators.

- Your strongest acquisition channels are digital, corporate and apartment partnerships.

- You need fast validation of premium subscriptions.

Recommended sequence

Bengaluru → Pune → Hyderabad → Gurugram → Mumbai

9. City selection should use a score—not founder preference alone

Score each candidate city out of 100.

| Factor | Weight |
| --- | --- |
| Qualified customer waitlist | 15 |
| Founder/local network | 15 |
| Active sitter pipeline | 15 |
| Society partnership pipeline | 12 |
| Projected contribution | 12 |
| Local operating leader | 10 |
| Travel and cluster feasibility | 8 |
| Competitive intensity | 5 |
| Local service partners | 4 |
| Regulatory readiness | 4 |
| Total | 100 |

Decision bands

| Score | Decision |
| --- | --- |
| 80–100 | Launch next |
| 70–79 | Launch after targeted validation |
| 60–69 | Run demand and supply experiments |
| Below 60 | Defer |

A city should not launch without:

- One named accountable operator

- Two viable micro-markets

- 100–300 qualified leads

- 8–15 launch-ready providers

- Three or more society opportunities

- Local pricing

- A 90-day P&L forecast

- Incident and support coverage

10. City 2 launch sequence

Stage 1 — Validation

Before hiring a full city team:

- Launch a waitlist

- Interview 30–50 pet parents

- Test prices

- Recruit provider applicants

- Meet societies

- Map travel times

- Identify local vets and groomers

- Select two clusters

Stage 2 — Supply activation

Minimum closed-beta supply:

- 15–30 document-verified candidates

- 8–15 trial-approved active providers

- 3–5 backup providers

- One local operations owner

- Two veterinary referral options

- Three to five add-on partners if applicable

Stage 3 — Closed beta

Target:

- 50–150 completed services

- 30–75 paying customers

- 4.6+ rating

- 95% completion

- Below 5% refunds/disputes

- Zero critical preventable incidents

Stage 4 — Cluster public launch

Open only:

- Approved pin codes

- Available time slots

- Proven services

- Capacity-controlled plans

Do not market:

Available across Pune.

When the real service footprint is:

Baner, Balewadi and selected Wakad societies.

Stage 5 — Stabilisation

Before launching the next city, City 2 should reach:

- 300–500 monthly completed services

- 25–40% repeat rate

- 20–50 active subscribers

- 4.6+ rating

- Positive contribution in at least one cluster

- Dedicated local ownership

- Working backup coverage

11. Final approved readiness table

| Requirement | Final target |
| --- | --- |
| Completed monthly services | 1,000+ for three months |
| Monthly paying customers | 300–500+ |
| Ninety-day active pet parents | 500+ |
| Active walking subscribers | 50–100+, volume reconciled |
| Active service providers | 20–40 |
| Verified supply bench | 40–80 |
| Active paid societies | 5–10 |
| Qualified society pipeline | 10–25 |
| City GMV | Tracked, not used alone |
| Platform revenue | Positive and growing |
| City contribution | Positive for three months |
| Average rating | 4.6+ |
| Repeat customers | 35%+ |
| Service completion | 95%+ |
| On-time rate | 95%+ |
| Sitter no-show | Below 1% |
| Sitter cancellation | Below 5% |
| Refund/dispute rate | Below 3–5% |
| Critical unresolved incidents | Zero |
| Support SLA | 90%+ achieved |
| Founder dependence | Below 5–10% of bookings |
| City operating owner | Named and accountable |

Final decisions

| Proposal | Decision |
| --- | --- |
| Require first-city stability | Approved |
| Use 1,000 monthly bookings | Approved as completed service fulfilments |
| Require 500 active pet parents | Approved with active-user definitions |
| Require 100 subscribers | Approved only with corresponding fulfilment capacity |
| Require 50–100 verified sitters | Modify: 20–40 active and 40–80 verified bench |
| Require 10–25 societies | Split active partners from pipeline |
| Use ₹5L–₹20L revenue gate | Replace with GMV, platform revenue and contribution |
| Allow sitter no-shows below 5% | Reject; target below 1% |
| Premium metro-first path | Approved |
| Gujarat-first path | Approved when local advantage is real |
| One fixed national city order | Rejected |
| Mumbai as an early city | Defer until hyperlocal operations are mature |
| Hyderabad at position six | Move earlier in metro-first path |
| Chennai with local-rule review | Approved for later validation |
| Delhi NCR as one city | Reject; manage municipal clusters separately |

Final recommendation

Capital-efficient path

Ahmedabad → Surat → Pune → Bengaluru → Vadodara/Rajkot

Premium national-validation path

Bengaluru → Pune → Hyderabad → Gurugram → Mumbai

Phase 10 readiness principle

Do not expand because City 1 is large. Expand because City 1 can run reliably without extraordinary founder intervention, and because City 2 has enough local demand, supply and ownership to reproduce the operating model.

The real City 2 launch gate is:

Stable demand+reliable supply+positive contribution+documented systems+local accountability

Phase 10 expansion readiness: GO only after the corrected three-month stability gates pass.

Phase 10 City Launch Gate System 🌍🐾

End-to-End Validation, Supply Build, Soft Launch and City-Scale Playbook

Executive verdict

Approve the gated city-launch model, but strengthen it before using it operationally.

Your four gates are directionally correct, but the current version has three weaknesses:

- It measures too many vanity inputs—waitlist sign-ups and sitter applications—without proving that they will convert into paying demand and active supply.

- The proposed launch-quality thresholds are too weak. A 90% completion rate and 5–10% sitter no-show rate are not acceptable for a trust-sensitive pet-care marketplace.

- It omits explicit gates for economics, safety, compliance, privacy and launch capacity.

The corrected sequence should be:

Gate 0: City selection and compliance

↓

Gate 1: Qualified demand

↓

Gate 2: Active supply and backup capacity

↓

Gate 3: Operational readiness

↓

Gate 4: Closed-beta quality

↓

Gate 5: Cluster economics and repeat demand

↓

Gate 6: Public city expansion

The operating rule is:

A city is not launched because its landing page is live. It is launched only when customers can book, providers can fulfil, support can intervene, incidents can be managed and the city can generate positive contribution.

1. How the gate system should work

Gates must be sequential and blocking.

A city cannot compensate for weak supply with strong demand. It cannot compensate for poor service quality with high revenue. It cannot compensate for positive economics with unresolved safety incidents.

Each gate should produce one of three decisions:

| Decision | Meaning |
| --- | --- |
| Pass | All critical thresholds met; proceed |
| Conditional pass | Minor gaps exist with a dated corrective plan |
| Fail/Hold | Do not proceed; repair the failed gate |

Critical gate rule

The following cannot receive a conditional pass:

- No accountable local operator

- No emergency escalation process

- No usable backup provider pool

- Critical safety incident unresolved

- Payment or refund process not working

- Customer support unavailable

- Required local compliance not assessed

- Negative contribution with no credible correction

- Serious privacy or access-control weakness

2. Gate 0: City selection and compliance

This gate should occur before you spend materially on recruitment, marketing or city hiring.

Objective

Determine whether the city is strategically attractive and legally/operationally launchable.

Required city-selection score

Score the candidate city across:

| Factor | Weight |
| --- | --- |
| Qualified customer demand | 15 |
| Founder/local network | 15 |
| Society/apartment density | 12 |
| Sitter recruitment potential | 12 |
| Local city operator availability | 10 |
| Expected contribution economics | 10 |
| Travel and cluster feasibility | 8 |
| Local veterinary/grooming ecosystem | 6 |
| Competitive intensity | 5 |
| Compliance readiness | 4 |
| Language/support readiness | 3 |
| Total | 100 |

Decision bands

| Score | Decision |
| --- | --- |
| 80–100 | Priority launch candidate |
| 70–79 | Continue targeted validation |
| 60–69 | Run low-cost demand/supply experiments |
| Below 60 | Defer |

Compliance checklist

Before Gate 1, identify:

- Relevant municipal pet-registration or licensing processes

- State and local business requirements

- Service-provider documentation

- Veterinary professional boundaries

- Transport requirements if pet taxi is contemplated

- GST and marketplace settlement structure

- Customer grievance responsibilities

- Gig/platform-worker reporting obligations

- Privacy notices and city-level data access

Local requirements can vary materially. For example, Delhi, Ahmedabad and Chennai each maintain their own municipal pet-registration or licensing systems, so the city playbook must include a local compliance map rather than assuming one national process.

If the marketplace falls within India’s aggregator framework, current Social Security Rules and Labour Ministry directions require attention to platform-worker details and eShram onboarding/reporting. This should be evaluated before the provider network scales.

Gate 0 output

City Opportunity and Compliance Memo

- City score

- Recommended launch clusters

- Competitive map

- Local price hypothesis

- Operating-cost hypothesis

- Local compliance register

- Named launch owner

- 90-day city P&L scenario

- Go/hold recommendation

3. Gate 1: Qualified demand

Your proposed demand gate is useful, but the metrics need stronger definitions.

Corrected demand targets

| Metric | Recommended target |
| --- | --- |
| Qualified waitlist leads | 150–300 |
| Structured pet-parent interviews | 30–50 |
| Society meetings with decision-makers | 5–10 |
| Societies willing to pilot | 2–5 |
| Paid trial bookings or refundable deposits | 20–40 |
| Validated target clusters | At least 2 |
| Price acceptance | Demonstrated |
| Search/social demand | Demonstrated, not assumed |

Why 30–50 interviews may be better than 100

One hundred informal conversations can produce less information than 30 carefully structured interviews.

Each interview should capture:

- Current care arrangement

- Monthly service frequency

- Existing spend

- Main pain point

- Preferred schedule

- Service area

- Trust objections

- Willingness to trial

- Willingness to subscribe

- Preferred payment method

- Society restrictions

- Pet size, age and behaviour

Continue interviewing until new conversations stop producing materially new insights.

Defining a qualified waitlist lead

A qualified lead should include:

- Valid phone or email

- Confirmed city and area

- Pet profile

- Desired service

- Expected frequency

- Preferred time window

- Indicative budget

- Consent to receive launch communication

Do not count:

- Social-media likes

- Unverified giveaway entries

- People outside the service area

- Pet lovers who do not require care

- Duplicate contacts

- Event visitors with no booking intent

Demand quality formula

Qualified lead rate=qualified service-intent leadstotal waitlist sign-ups

A 200-person waitlist with 30 qualified leads is weaker than a 100-person waitlist with 70 qualified leads.

Society-interest definition

“Five interested societies” is too vague.

Classify societies:

| Stage | Meaning |
| --- | --- |
| S0 | Identified |
| S1 | Contacted |
| S2 | Decision-maker meeting completed |
| S3 | Resident-demand evidence shared |
| S4 | Pilot verbally approved |
| S5 | Pilot agreement signed |
| S6 | Pilot active |

Gate 1 should require:

- Five or more decision-maker meetings

- Two or more pilot-ready societies

- At least one society in each target cluster

AWBI guidance specifically addresses pet owners, caregivers, RWAs and apartment associations, so society outreach should incorporate responsible coexistence, resident duties and workable access procedures—not just discounts and sales offers.

Paid pre-bookings and deposits

Paid intent is stronger than survey intent, but deposits must be handled transparently.

Use:

- Refundable launch deposit

- Paid discounted trial

- Prepaid starter pack activated only after launch

- Clearly disclosed expiry and refund terms

Do not:

- Hold deposits indefinitely

- Hide geographic restrictions

- Convert deposits into subscriptions automatically

- Represent deposits as completed revenue before service is delivered

India’s E-Commerce Rules require appropriate consumer information, fair practices and an adequate grievance mechanism. Deposit, refund and cancellation terms should therefore be shown before payment.

Proving search and social demand

“Search/social demand proven” should mean at least three of the following:

- City landing page generates qualified leads

- Search advertisements convert within target CAC

- Organic local search impressions exist

- Society announcements produce registrations

- Local referral campaigns generate trial interest

- Retargeting produces booking-intent actions

- Price-test pages receive checkout starts

- Customers accept trial deposits

Gate 1 output

Demand Validation Report

- Leads by cluster

- Lead qualification rate

- Interview findings

- Price acceptance

- Society pipeline

- Paid-intent count

- Expected first 90-day demand

- Acquisition-cost scenario

- Pass/hold recommendation

4. Gate 2: Supply and backup capacity

The proposed target of 100 sitter applications is not a useful success measure by itself.

Applications are top-of-funnel activity. The city needs approved, active and schedulable providers.

Corrected supply targets

| Supply category | Recommended launch target |
| --- | --- |
| Sitter/walker applications | 50–100 |
| Contact-screened | 30–60 |
| Documents verified | 15–30 |
| Practical trial completed | 10–20 |
| Launch-ready active providers | 8–15 |
| Backup-capable providers | 3–5 |
| Grooming partners | 3–5 |
| Veterinary referral partners | 2–5 |
| Trainers | 2–4 if training launches |
| Boarding providers | 3–5 if boarding launches |

Do not onboard ten service categories simply to make the provider list appear large.

Launch the smallest proven service stack:

- Walking

- Sitting where supply is strong

- Grooming through verified partners

- Veterinary coordination/referral

- Boarding only after facility/host controls pass

Provider funnel

Applicant

↓

Contact screened

↓

Identity/documents checked

↓

Skill and behaviour assessment

↓

Practical trial

↓

Cluster assigned

↓

Capacity declared

↓

Launch-ready

↓

Active after completed service

Active supply definition

A provider counts as active only if they:

- Have current documents

- Have declared usable availability

- Operate inside the launch cluster

- Are willing to accept the planned pricing

- Have passed relevant trial requirements

- Have completed or accepted work recently

- Are not paused or under investigation

Backup sitter requirement

“Five backup sitters” is useful only when they match the actual demand.

Backup capacity must be mapped by:

- Area

- Day

- Time window

- Service type

- Pet size/handling requirements

- Gender preference where legitimately relevant

- Society access

- Travel radius

Five available afternoon walkers do not protect 20 subscriptions scheduled at 7:30 AM.

Backup coverage formula

Backup coverage=recurring schedules with usable backuptotal recurring schedules

Launch target:

90–95%+ backup coverage before selling recurring plans.

Grooming and vet partner target

The proposed combined “10+ grooming/vet partners” should be split.

Veterinary partners

Start with:

- Two general clinics

- One after-hours/emergency option where available

- One home-visit or teleconsult option where appropriate

- Registration and professional details checked

The platform should coordinate care rather than diagnose or prescribe.

Grooming partners

Start with:

- Three to five launch-ready groomers

- Defined package prices

- Hygiene and handling checklist

- Before/after reporting

- Backup arrangements

Ten weak or inactive partners create less value than four reliable ones.

Boarding host requirement

Boarding introduces materially higher custody and safety risk.

Before counting a host as launch-ready, verify:

- Facility/home inspection

- Pet capacity

- Separation rules

- Escape prevention

- Vaccination policy

- Emergency contact

- Trial process

- Resident/society permission where relevant

- Incident and evacuation process

If boarding controls are incomplete, launch the city without boarding.

Gate 2 output

City Supply and Capacity Report

- Funnel by provider type

- Active providers by cluster

- Peak-time capacity

- Backup coverage

- Provider payout economics

- Service permissions

- Document expiry risks

- Services approved for launch

- Services deferred

- Pass/hold decision

5. Gate 3: Operations readiness

Your existing operations gate is correct but incomplete.

Corrected operations checklist

| Requirement | Status required |
| --- | --- |
| Named city launch owner | Yes |
| Dedicated city manager | Stage-dependent |
| Service clusters configured | Yes |
| Operating hours configured | Yes |
| Prices and taxes configured | Yes |
| Provider pools configured | Yes |
| Capacity limits configured | Yes |
| Support routing ready | Yes |
| Emergency veterinary map ready | Yes |
| Incident SOP tested | Yes |
| Refund and grievance process ready | Yes |
| Payment and payout reconciliation ready | Yes |
| Society pipeline and gate SOP ready | Yes |
| Privacy access scoped by city | Yes |
| Local compliance register complete | Yes |
| City P&L tracking ready | Yes |
| Provider training completed | Yes |

City manager requirement

A dedicated full-time city manager may not be necessary during research, but every public beta must have one named accountable operator.

| Stage | Required owner |
| --- | --- |
| Research | City launch owner |
| Supply build | Launch/operations lead |
| Closed beta | Named accountable city operator |
| 300–500 monthly fulfilments | Dedicated city manager strongly recommended |
| 1,000+ monthly fulfilments | Dedicated city manager required |

Emergency veterinary mapping

Do not list only clinic names.

Store:

- Address

- Hours

- Telephone

- Services available

- Overnight availability

- Home-visit availability

- Geographic coverage

- Last verification date

- Escalation contact

- Limitations

The map should distinguish:

- General clinic

- 24-hour/after-hours option

- Diagnostic facility

- Home-visit partner

- Teleconsult option

Support readiness

Define SLAs before launch.

| Case type | Initial response target |
| --- | --- |
| Normal booking question | Within published business-hour SLA |
| Walker late/unreachable | 10–15 minutes |
| Service cannot be fulfilled | Immediate operational escalation |
| Pet lost/escaped | Immediate critical escalation |
| Injury or bite | Immediate escalation |
| Payment/refund issue | Same day or defined finance SLA |
| Privacy/security issue | Immediate compliance escalation |

Consumer grievance access must remain available regardless of customer tier or subscription status.

Incident readiness drill

Before soft launch, run tabletop exercises for:

- Sitter no-show

- Pet escape

- Dog bite

- Pet injury

- Customer lock/access problem

- Society gate denial

- Provider fraud

- Payment captured but booking not created

- Personal data sent to the wrong provider

- Emergency clinic unavailable

A city is not operationally ready merely because an SOP document exists. The team must demonstrate that it can execute it.

Privacy and access

City expansion increases the number of people accessing:

- Addresses

- Access instructions

- Recurring customer schedules

- Pet behaviour details

- Medical-related notes

- Payment and contact information

The DPDP Act and notified 2025 Rules establish a framework for lawful-purpose processing, notices, safeguards and grievance handling, with provisions commencing on a phased timetable. Build city-scoped access and auditability now rather than retrofitting it after national expansion.

Gate 3 output

City Operational Readiness Certificate

Signed by:

- Product/engineering

- City operations

- Support

- Finance

- Partnerships

- Safety/compliance

- Founder or expansion owner

6. Gate 4: Closed-beta launch

The original launch thresholds should be strengthened.

Recommended beta targets

| Metric | Corrected target |
| --- | --- |
| Paying beta customers | 30–75 |
| Completed paid services | 50–150 |
| Average rating | 4.6+ |
| Completion rate | 95%+ |
| On-time rate | 95%+ |
| Provider no-show | Below 1% |
| Provider cancellation | Below 5% |
| Refund/dispute rate | Below 5% |
| Critical preventable incidents | Zero |
| Support SLA achievement | 90%+ |
| Provider report completion | 95%+ |

Why 90% completion is too low

A 90% rate means that one in ten promised services fails to complete.

For 1,000 monthly services, that would mean 100 failures. A pet-care company should not scale a city with that failure profile.

Why 5–10% no-show is unacceptable

A no-show is not a minor schedule change. It means the provider fails to arrive without adequate handling.

Recommended distinction:

| Metric | Target |
| --- | --- |
| No-show | Below 1% |
| Provider cancellation | Below 5% |
| Cancellation covered by backup | 90%+ |
| Overall completion | 95%+ |

Beta cohort

Use:

- Existing waitlist

- Referred customers

- Pilot societies

- Friends-of-customer networks

- Limited employer/community partners

Do not begin with city-wide paid advertising.

Beta geography

Open only:

- One or two clusters

- Supported pin codes

- Defined time windows

- Proven services

Use accurate language:

“Available in Baner, Balewadi and selected Wakad societies.”

Not:

“Now available across Pune.”

7. Gate 5: City validation and economics

A successful beta does not automatically justify city-wide expansion.

The city must prove repeat demand and workable economics.

Validation targets

| Metric | Target |
| --- | --- |
| Monthly completed services | 300–500 |
| Paying customers | 100–200 |
| Repeat customer rate | 25–40% |
| Active subscribers | 20–50 |
| Active providers | 10–25 |
| Rating | 4.6+ |
| Completion | 95%+ |
| On-time rate | 95%+ |
| Positive cluster contribution | At least one cluster |
| Critical unresolved incidents | Zero |
| Founder intervention | Declining |

City financial model

Track separately:

GMV

Total customer spending.

Platform revenue

Retained commission, fees, memberships and society income.

Direct city costs

- Provider payouts where relevant

- Local marketing

- Verification

- City staff

- Support

- Refunds

- Service recovery

- Events

- Payment charges

- Travel and logistics

City contribution

City contribution=platform city revenue-direct city operating costs

Do not scale based only on GMV.

City-validation decision

| Result | Decision |
| --- | --- |
| Quality strong, economics positive | Expand cluster by cluster |
| Quality strong, economics weak | Reprice or improve density |
| Demand strong, supply weak | Pause acquisition and recruit |
| Demand weak, supply strong | Reduce provider pool and improve acquisition |
| Complaints high | Freeze growth |
| Critical incident unresolved | Stop city expansion |
| One cluster positive, another weak | Scale only the positive cluster |

8. Gate 6: Public city expansion

After Gate 5, expand gradually inside the city.

Expansion order

Validated Cluster A

↓

Adjacent Cluster B

↓

Cluster B stabilises

↓

Cluster C

↓

City-wide brand campaign only after real coverage

Do not expand by website checkbox

Adding another city to a dropdown is not expansion.

A public area requires:

- Active provider capacity

- Backup coverage

- Correct pricing

- Support ownership

- Local incident routing

- Service-level tracking

- City P&L attribution

9. Corrected city launch playbook

Stage 1: City research

Activities

- Market-size hypothesis

- Competitor map

- Customer pain points

- Local price references

- Regulatory map

- Service-partner ecosystem

- Traffic/travel analysis

- Local-language needs

Output

City research dossier

Stage 2: Area and cluster selection

Select two micro-markets using:

- Society density

- Addressable pet households

- Travel radius

- Customer waitlist concentration

- Provider availability

- Local pricing power

- Vet/groomer access

Output

- Cluster boundaries

- Service pin codes

- Peak-time map

- Travel-time policy

- Capacity model

Stage 3: Demand validation

- Landing page

- Waitlist

- Interviews

- Society meetings

- Trial deposits

- Price tests

- Referral campaign

Output

Qualified demand forecast.

Stage 4: Provider recruitment and verification

- Recruit

- Screen

- Verify

- Assess

- Trial

- Assign to clusters

- Train

- Reserve capacity

Output

Active launch roster plus backups.

Stage 5: Local partner onboarding

Onboard only services intended for the beta:

- Groomers

- Vet referral/coordination partners

- Trainers where relevant

- Boarding only if fully controlled

Output

Partner directory, permissions and escalation details.

Stage 6: Society outreach

- Prioritise target societies

- Conduct decision-maker meetings

- Agree gate protocol

- Run resident-demand survey

- Sign pilot

- Schedule event or trial campaign

Output

Two to five pilot-ready societies.

Stage 7: Product and operations configuration

Configure:

- City and cluster

- Service catalogue

- Prices

- Provider pools

- Capacity

- Operating hours

- Taxes

- Support routing

- Emergency directory

- Feature flags

- Payment and payout flows

Output

Operationally launchable environment.

Stage 8: Landing-page launch

The landing page should show:

- Exact supported areas

- Services live

- Starting prices

- Verification model

- How booking works

- Safety promise

- FAQs

- Waitlist for unsupported areas

Do not take payment for unavailable areas.

Stage 9: Soft launch

Launch to a controlled cohort.

Target

- 30–75 paying users

- 50–150 completed services

- Daily operations review

- Immediate service-recovery capability

Output

Closed-beta performance report.

Stage 10: Controlled public bookings

Open selected areas while maintaining:

- Booking caps

- Peak-slot limits

- Backup reserve

- Daily quality monitoring

- Customer feedback

- Incident review

Output

Validated cluster.

Stage 11: Subscription push

Do not introduce subscriptions on Day 1.

Use:

Successful trial

↓

Repeated service

↓

Starter pack

↓

Monthly subscription

Before selling subscriptions, verify:

- Repeat demand

- Primary and backup capacity

- Credit system operational

- Pause/cancel flow operational

- Payment renewal working

Stage 12: Society expansion

After individual booking quality is stable:

- Expand society pilots

- Launch resident plans

- Introduce management subscriptions

- Run targeted camps

- Produce monthly reports

Society expansion should not be used to conceal weak ordinary fulfilment.

Stage 13: City P&L review

Review:

- GMV

- Platform revenue

- Contribution

- CAC

- Partner payouts

- Customer repeat

- Refunds

- Support cost

- Cluster profitability

- Society economics

- Subscription economics

Output

Scale, repair, narrow or exit decision.

Stage 14: City retrospective

Document:

- What worked

- What failed

- Price changes

- Supply lessons

- Incident learnings

- Society objections

- Customer objections

- Support gaps

- Launch timeline variance

- Playbook changes

This becomes the input for the next city.

10. Final corrected gate table

Gate 1 — Demand

| Metric | Final target |
| --- | --- |
| Qualified leads | 150–300 |
| Structured interviews | 30–50 |
| Decision-maker society meetings | 5–10 |
| Pilot-ready societies | 2–5 |
| Paid trials/deposits | 20–40 |
| Target clusters | At least 2 |
| Pricing acceptance | Proven |

Gate 2 — Supply

| Metric | Final target |
| --- | --- |
| Applications | 50–100 |
| Document verified | 15–30 |
| Trial approved | 10–20 |
| Launch-active providers | 8–15 |
| Backup-capable providers | 3–5 |
| Grooming partners | 3–5 |
| Vet referral partners | 2–5 |
| Boarding providers | 3–5 only if launching |

Gate 3 — Operations

| Requirement | Status |
| --- | --- |
| Accountable city owner | Yes |
| Areas and capacity configured | Yes |
| Pricing configured | Yes |
| Support and escalation live | Yes |
| Emergency vet map verified | Yes |
| Payments/refunds tested | Yes |
| Incident drills completed | Yes |
| Privacy roles configured | Yes |
| Local compliance assessed | Yes |
| City P&L ready | Yes |

Gate 4 — Closed beta

| Metric | Final target |
| --- | --- |
| Paying customers | 30–75 |
| Completed services | 50–150 |
| Rating | 4.6+ |
| Completion | 95%+ |
| On-time | 95%+ |
| No-show | Below 1% |
| Provider cancellation | Below 5% |
| Refund/dispute | Below 5% |
| Critical incidents | Zero |

Gate 5 — City validation

| Metric | Final target |
| --- | --- |
| Monthly completed services | 300–500 |
| Repeat customers | 25–40% |
| Active subscribers | 20–50 |
| Active providers | 10–25 |
| Positive cluster contribution | Yes |
| Backup coverage | 90–95%+ |
| Founder dependence | Declining |
| Critical unresolved incidents | Zero |

Final approval decision

| Proposal | Decision |
| --- | --- |
| Sequential city gate system | Approved |
| 200+ waitlist leads | Approved only as qualified leads |
| 100 interviews | Reduce to 30–50 structured interviews initially |
| 20 paid deposits | Approved with transparent refund terms |
| 100 sitter applications | Useful funnel target, not a launch criterion |
| 20–30 approved sitters | Use 8–15 active plus verified reserve |
| Five backup sitters | Approved when matched by cluster and time |
| Ten vet/grooming partners | Split into smaller service-specific targets |
| Dedicated city manager before research | Not always necessary |
| Named city owner before beta | Mandatory |
| 90% completion | Reject; require 95%+ |
| 5–10% no-show | Reject; require below 1% |
| 4.5 rating | Increase to 4.6+ before scale |
| City P&L review | Mandatory |

Final city-launch principle

Do not launch a city when marketing is ready. Launch it when demand, active supply, backup capacity, local support, safety processes, payment systems and cluster economics are ready together.

Phase 10 city win condition

A new city reaches dependable repeat bookings and positive cluster contribution through the documented playbook, without founder firefighting or deterioration in safety and customer trust.

City Launch Gate System: GO—with six gates, stronger quality thresholds and cluster-level economics

Phase 10 City Operating System

Team Structure, City-Manager Scorecard, P&L, Unit Economics and Cluster Expansion 🌍🐾

Executive verdict

Your city operating model is directionally correct, but it should be organised by city maturity, not copied as a fixed seven-person team into every new market.

The recommended operating principle is:

Start with one accountable city leader and a small cross-functional launch pod. Add specialised roles only when booking volume, support load and society activity justify them.

The expansion hierarchy should be:

City

↓

Service cluster

↓

Society/locality

↓

Primary provider pool

↓

Backup provider pool

↓

Customer and subscription capacity

A city should never be opened merely because providers have applied. It should open only when the target cluster has:

- Qualified demand

- Active, schedulable supply

- Backup coverage

- Local operational ownership

- Emergency escalation

- Positive projected unit economics

- Capacity for the services being advertised

Part I — City Team Structure

1. Review of the proposed team

| Role | Proposed count | Decision |
| --- | --- | --- |
| City Manager | 1 | Mandatory before public beta |
| Sitter Onboarding Executive | 1–2 | Add according to recruitment volume |
| Customer Support Executive | 1–2 | Can initially be shared centrally |
| Society Partnership Executive | 1 | Add when the society pipeline is active |
| Operations Coordinator | 1 | Highly important from beta onward |
| Vet/Groomer Partner Manager | Shared/part-time | Appropriate initially |
| Marketing Executive | Shared/part-time | Appropriate initially |
| Safety/Quality owner | Not listed | Add as a central or regional function |
| Finance/reconciliation | Not listed | Keep central, with city-level reporting |

The city manager must own city outcomes, but should not personally execute every recruitment call, booking reassignment, complaint, event and financial reconciliation.

That creates a founder-style bottleneck inside each city.

2. Stage-based staffing model

Stage C0: Research and pre-launch

Volume: No public bookings

| Role | Staffing |
| --- | --- |
| City launch owner | 1 |
| Supply/operations generalist | 1 |
| Central support | Shared |
| Society partnerships | Shared |
| Marketing | Shared |
| Finance/compliance | Central |

Responsibilities

- Demand validation

- Area selection

- Sitter recruitment

- Society meetings

- Pricing research

- Local compliance mapping

- City P&L forecast

- Emergency-provider mapping

A full seven-person team is unnecessary at this stage.

Stage C1: Closed beta

Volume: Approximately 50–150 completed services monthly

| Role | Staffing |
| --- | --- |
| City Manager/Launch Manager | 1 |
| Operations and onboarding executive | 1 |
| Customer support | Shared central support |
| Society partnerships | Shared or part-time |
| Add-on partner manager | Shared |
| Marketing | Shared |

Minimum viable launch pod

One strong city manager + one operations/onboarding generalist + central support

This is the smallest sensible structure for a controlled beta.

The generalist may handle:

- Sitter screening

- Availability collection

- Booking assignments

- Backup activation

- Basic society coordination

But the city manager remains accountable.

Stage C2: Validated cluster

Volume: Approximately 150–500 completed services monthly

| Role | Staffing |
| --- | --- |
| City Manager | 1 |
| Operations Coordinator | 1 |
| Sitter Onboarding Executive | 1 |
| Customer Support | 0.5–1 dedicated equivalent |
| Society Partnerships | 0.5–1 |
| Add-on partner management | Shared |
| Marketing | Shared |

At this stage, onboarding and live operations should no longer be handled by one person.

Stage C3: Growth city

Volume: Approximately 500–1,000 completed services monthly

| Role | Staffing |
| --- | --- |
| City Manager | 1 |
| Sitter Onboarding Executives | 1–2 |
| Operations Coordinator | 1 |
| Customer Support Executives | 1–2 |
| Society Partnership Executive | 1 |
| Vet/Groomer Partner Manager | Shared or part-time |
| Marketing Executive | Shared or part-time |
| Quality/safety reviewer | Shared regional function |

This is close to your proposed team and is appropriate for a city approaching maturity.

Stage C4: Mature city

Volume: 1,000+ completed services monthly across several clusters

Add according to operational load:

- Cluster operations leads

- Dedicated society account manager

- Dedicated partner quality lead

- Second operations coordinator

- Local event coordinator

- Training and verification personnel

- City finance analyst or central finance business partner

Do not automatically add staff merely because revenue increases. Add staff when a measurable queue, SLA or control requirement justifies the role.

3. Shared versus city-local functions

Keep central

- Product and engineering

- Payment infrastructure

- Finance and reconciliation

- Tax policy

- Legal and compliance

- National verification standards

- Incident taxonomy

- Customer-support platform

- Partner score framework

- Data protection and security

- National marketing strategy

Keep city-local

- Provider recruitment

- Practical trials

- Availability and capacity

- Society relationships

- Live schedule management

- Backup activation

- Local event delivery

- Local partner relationships

- Customer-service recovery requiring physical intervention

Hybrid

- Customer support

- Partner training

- Marketing

- Veterinary/grooming partnership management

- Quality assurance

The operating rule is:

Centralise systems and standards; localise relationships and fulfilment.

Part II — City Manager Responsibilities

4. What the city manager should own

The city manager should be accountable for:

Demand

- Monthly completed bookings

- Paying customers

- Repeat customers

- Subscription adoption

- Society conversion

- Area expansion

Supply

- Active walker and sitter capacity

- Backup coverage

- Provider activation

- Partner retention

- Provider earnings health

- Document validity

Quality

- Booking completion

- On-time service

- Customer ratings

- Complaints

- Refunds

- Report completion

- Primary/backup continuity

Economics

- City GMV

- Platform revenue

- Direct contribution

- Acquisition cost

- Support cost

- Refund cost

- Society economics

- Cluster profitability

Safety

- Incident escalation

- Provider suspension

- Evidence preservation

- Root-cause reviews

- Corrective actions

- Emergency network readiness

Team

- Hiring

- Training

- Performance

- Shift coverage

- Operational discipline

5. What the city manager should not own alone

The city manager should not have unilateral authority to:

- Approve their own unsafe provider exception

- Delete or downgrade incident records

- Override expired documentation

- Hide refunds to improve city metrics

- Change clinical veterinary decisions

- Settle serious complaints without review

- Modify recognised revenue

- Access unnecessary customer medical information

- approve their own bonus score

Critical safety, compliance and financial controls need independent review.

Veterinary clinical decisions must remain with registered veterinary professionals. VCI professional regulations also prohibit veterinarians from offering or receiving commissions for procuring or referring clients, so city managers should not build veterinary revenue around ordinary lead commissions. Use transparent coordination, event-management or software fees subject to legal review.

6. City manager RACI

| Workstream | City Manager | Central Team |
| --- | --- | --- |
| Sitter recruitment | Accountable | Standards/support |
| Verification | Operationally responsible | Policy and audit |
| Booking fulfilment | Accountable | Product tools |
| Customer support | Escalation owner | First-line/shared |
| Pricing recommendation | Consulted/responsible | Final approval |
| City P&L | Accountable | Finance validates |
| Safety incidents | Immediate owner | Independent review |
| Veterinary services | Coordination only | Clinical boundaries |
| Privacy | Local compliance | Data-protection owner |
| Tax and payouts | Provides inputs | Finance owns |
| Society agreements | Accountable | Legal templates |

Part III — City Manager Scorecard

7. Why the proposed scorecard needs modification

The original metrics are useful, but three corrections are needed:

- Revenue growth cannot override poor quality or safety.

- “Incident rate below 3%” is too broad.

- Gross margin must have a defined denominator.

Use a balanced scorecard with hard safety overrides.

8. Recommended weighted scorecard

| Dimension | Weight |
| --- | --- |
| Quality and safety | 30% |
| Supply and fulfilment | 20% |
| Demand and retention | 20% |
| City economics | 20% |
| Society and strategic growth | 10% |

Quality and safety — 30%

| Metric | Target |
| --- | --- |
| Average customer rating | 4.6+ |
| Complaint/refund rate | Below 3–5% |
| Critical preventable incidents | Zero |
| Serious safety incidents | Below 0.1–0.3% |
| Minor reportable incidents | Below 1% |
| Incident reporting accuracy | 100% |
| Critical unresolved cases | Zero |

A city manager should lose safety-score eligibility for deliberately hiding or misclassifying an incident.

Supply and fulfilment — 20%

| Metric | Target |
| --- | --- |
| Booking completion | 95%+ |
| On-time arrival | 95%+ |
| Provider no-show | Below 1% |
| Provider cancellation | Below 5% |
| Cancellation covered by backup | 90%+ |
| Subscription plans with backup | 95%+ |
| Provider payouts on time | 98%+ |

“Sitter reliability” should not be one vague number. Separate no-shows, cancellations, on-time fulfilment and report completion.

Demand and retention — 20%

| Metric | Target |
| --- | --- |
| Monthly bookings | Stage-specific growth |
| Repeat customer rate | 35%+ in mature city |
| Subscription conversion | Increasing |
| Subscription renewal | 60%+ |
| Referral and organic share | Increasing |
| Customer concentration | Controlled |

Do not reward bookings generated entirely through unsustainable discounts.

City economics — 20%

| Metric | Target |
| --- | --- |
| Direct city contribution | Positive |
| Contribution per booking | Positive and improving |
| CAC payback | Stage-specific |
| Refund/service-recovery costs | Controlled |
| Marketing efficiency | Improving |
| Partner payout reconciliation | Complete |
| City P&L close | On time |

Society and strategic growth — 10%

| Metric | Target |
| --- | --- |
| Pilot societies | Stage-specific |
| Pilot-to-paid conversion | 30–50% starting target |
| Resident paid conversion | 15–25% |
| RWA satisfaction | 4.5+ |
| Society contribution | Positive |
| Gate/security incidents | Minimal and resolved |

AWBI’s published guidance specifically addresses pet owners, caregivers, RWAs and apartment associations. Society operations should support responsible coexistence and reasonable access rather than using the platform as a pet-restriction mechanism.

9. Hard scorecard overrides

A manager should not qualify for a growth bonus when any of these applies:

- Critical preventable incident

- Concealed safety event

- Expired provider credentials used knowingly

- Partner payouts materially delayed

- City P&L unreconciled

- Severe privacy breach

- Customer grievance process bypassed

- Systematic false completion reporting

Part IV — City P&L Structure

10. First separate GMV from revenue

A marketplace must distinguish:

GMV

Total customer spending through the city.

Platform revenue

The amount the platform recognises from:

- Commissions

- Service fees

- Subscription fees

- Society-management fees

- Event-management fees

- Software fees

Partner payouts

Amounts owed to walkers, sitters, groomers or other providers.

Depending on whether the company acts as principal or agent, recognised revenue may be gross or net. Obtain a written accounting position rather than deciding this only through product terminology.

11. Recommended city P&L

A. Customer spending/GMV memorandum

| Revenue-origin category | GMV |
| --- | --- |
| Walking | ₹ |
| Sitting | ₹ |
| Boarding | ₹ |
| Grooming | ₹ |
| Training | ₹ |
| Veterinary coordination | ₹ |
| Subscription service plans | ₹ |
| Society resident services | ₹ |
| Events | ₹ |

This is not automatically recognised revenue.

B. Recognised platform revenue

| Revenue stream | Accounting category |
| --- | --- |
| Walking commission/service margin | Platform service revenue |
| Sitting commission/service margin | Platform service revenue |
| Boarding margin | Platform service revenue |
| Grooming commission | Partner-service revenue |
| Training commission | Partner-service revenue |
| Vet coordination fee | Fixed coordination/software/event fee |
| Consumer membership | Recurring membership revenue |
| Walking subscription retained share | Recurring service revenue |
| Society management fee | B2B recurring revenue |
| Event-management fee | Event revenue |
| Partner software subscription | B2B software revenue |
| Sponsored placement | Advertising revenue, clearly disclosed |

Do not assume veterinary referral commission is an acceptable revenue line. VCI rules prohibit commissions or bonuses for procuring or referring clients.

C. Direct variable costs

- Sitter and partner payouts

- Payment-processing fees

- Refunds

- Service credits and make-goods

- Emergency replacement cost

- Customer acquisition directly attributable to bookings

- Society event delivery

- Background/document checks

- Per-booking support

- Provider travel subsidy

- Consumables where supplied

D. City operating costs

- City manager salary

- Onboarding staff

- Operations coordinator

- Local customer support

- Partnership executive

- Local marketing

- Recruitment campaigns

- Training and trials

- City travel

- Event setup

- Local office or coworking

- Telephone and field tools

- Insurance allocation

E. Central allocated costs

- Technology

- National customer support

- Finance

- Legal/compliance

- Brand marketing

- Leadership

- Data infrastructure

Show city performance both:

- Before central allocation

- After central allocation

This prevents strong cities from appearing unprofitable merely because all corporate overhead is allocated too early, while still showing the full business path to profitability.

12. City contribution levels

Contribution 1

C1=Platform revenue-direct service and payment costs

Contribution 2

C2=C1-variable city operations

City operating contribution

City operating contribution=C2-local fixed costs

Fully allocated city result

City result=City operating contribution-allocated central overhead

Use each level for a different decision:

| Metric | Decision use |
| --- | --- |
| C1 | Is the individual transaction viable? |
| C2 | Is the cluster operationally viable? |
| City contribution | Can the local city operation sustain itself? |
| Fully allocated result | Can the company scale profitably? |

13. Tax and settlement controls

If the platform collects customer consideration for services supplied by third-party providers, e-commerce-operator and TCS obligations may apply depending on the exact transaction structure. Maintain separate service, provider and city settlement ledgers, and obtain a written CA/GST position before scaling across states.

Tax payable is not ordinary operating revenue or contribution. Keep:

- GST collected

- TCS

- Provider settlements

- Refund liabilities

- Subscription deferred obligations

separate from commercial margin reporting.

Part V — Unit-Economics Targets

14. Review of proposed targets

| Metric | Proposed | Decision |
| --- | --- | --- |
| Gross margin | 25–35% | Define accounting basis first |
| Net contribution after support | Positive | Approve |
| CAC payback | Under 2–3 months | Strong mature-city target |
| Repeat rate | 35%+ | Approve for mature city |
| Subscription share | 25%+ | Define denominator |
| Society bookings share | 30%+ | Use as channel hypothesis, not universal gate |
| Refund/dispute | Below 5% | Approve; mature target below 3% |

15. Correct definitions

Take rate

Take rate=Platform revenueGMV

Gross margin

If the platform records only its fee as revenue:

Gross margin=Platform revenue-direct platform service costsPlatform revenue

If the platform records customer payments as revenue and provider payments as cost of service, the calculation differs.

Do not compare margins across cities until all cities use the same accounting convention.

16. Recommended maturity targets

Closed beta

| Metric | Target |
| --- | --- |
| Contribution per completed service | Improving, preferably positive |
| Refund/dispute | Below 5% |
| Repeat intent | Positive |
| CAC payback | Not yet definitive |
| Provider utilisation | Sustainable |

Validated cluster

| Metric | Target |
| --- | --- |
| Direct contribution | Positive |
| CAC payback | Below 4–6 months |
| Repeat customer rate | 25–40% |
| Subscription share | 15–25% of active recurring users/revenue |
| Refund/dispute | Below 5% |
| Support cost per booking | Stable or falling |

Mature city

| Metric | Target |
| --- | --- |
| Gross/direct margin | 25–35% under a clearly defined basis |
| City operating contribution | Positive |
| CAC payback | Under 2–3 months |
| Repeat customer rate | 35–50% |
| Recurring platform-revenue share | 25%+ |
| Refund/dispute | Below 3–5% |
| Provider payout reliability | 98%+ |
| Critical incidents | Zero |

A 2–3 month CAC payback is an excellent mature-city target, but requiring it during the first few weeks may lead to underinvestment in supply density and society relationships.

17. Society share target

“Society bookings should be 30%+” is appropriate only when society-first acquisition is the chosen local strategy.

Use:

| City model | Healthy society-origin share |
| --- | --- |
| Society-first Gujarat/Gurugram cluster | 25–40% |
| Digitally led Bengaluru cluster | 10–25% |
| Hyperlocal Mumbai premium cluster | Variable |
| Corporate-led cluster | Lower society share may be acceptable |

Avoid dependence on:

- One society

- One RWA decision-maker

- One corporate account

- One provider

- One acquisition channel

Recommended concentration control:

No single society should produce an excessive share of city contribution once the city matures.

Part VI — Area Expansion Inside a City

18. The city is not the launch unit

The correct expansion model is:

Cluster 1

↓

Cluster 1 passes quality and contribution gates

↓

Adjacent Cluster 2

↓

Cluster 2 passes gates

↓

Cluster 3

↓

Multi-cluster city operation

Cluster boundaries should be based on real travel time, not only postal codes or neighbourhood names.

19. Why travel-time clusters matter

TomTom’s 2025 data reports average congestion of approximately 74.4% for Bengaluru and 49% for Ahmedabad. Bengaluru therefore requires tighter operating radii and stronger peak-time capacity controls than Ahmedabad.

This is an operational inference:

- An Ahmedabad cluster may sometimes cover several adjacent residential areas.

- A Bengaluru cluster that appears close on a map may still be unworkable during morning and evening peaks.

- Walker routes should be defined using measured service-to-service travel times.

20. Ahmedabad cluster review

Proposed sequence

- Bopal, South Bopal, Ambli

- Satellite, Prahlad Nagar, SG Highway

- Vastrapur, Thaltej, Bodakdev

- Wider Ahmedabad

Assessment

This is a credible planning hypothesis, but the areas should be split or combined based on:

- Provider home locations

- Society density

- Peak-hour travel

- Gate-entry times

- Customer time windows

- Local pricing

- Emergency-vet coverage

Recommended Ahmedabad structure

Cluster A — Bopal corridor

- Bopal

- South Bopal

- Ambli

- Nearby societies within the validated travel radius

Cluster B — Prahlad–Satellite corridor

- Prahlad Nagar

- Satellite

- Selected SG Highway societies

Cluster C — West-central premium corridor

- Vastrapur

- Bodakdev

- Thaltej

Do not open “wider Ahmedabad” as one final step. Continue adding smaller operational zones.

Ahmedabad’s 2025 average congestion was lower than Bengaluru’s, but the city still averaged close to 29 minutes for a 10 km drive, so route design remains material.

21. Bengaluru cluster review

Proposed sequence

- Whitefield, Brookefield, Kundalahalli

- HSR, Sarjapur Road, Bellandur

- Indiranagar, Koramangala

- Wider Bengaluru

Assessment

The first cluster is directionally sensible because the areas are comparatively adjacent.

The second proposed cluster may be too broad during peak periods. HSR, Bellandur and different sections of Sarjapur Road may need to operate as separate capacity zones.

Recommended Bengaluru structure

Cluster A — Whitefield micro-market

- Whitefield

- Brookefield

- Kundalahalli

- Selected nearby societies

Cluster B1 — HSR

- HSR Layout

- Adjacent serviceable societies

- Separate peak-time provider pool

Cluster B2 — Bellandur/Sarjapur corridor

- Bellandur

- Selected Sarjapur Road communities

- Strict time-window and route rules

Cluster C1 — Koramangala

Cluster C2 — Indiranagar

Merge C1 and C2 operationally only when travel-time and provider-density data support it.

Bengaluru’s high measured congestion makes broad city-wide primary/backup pools particularly risky.

22. Cluster-status model

| Status | Meaning |
| --- | --- |
| Z0 Research | Demand and supply being assessed |
| Z1 Waitlist | Leads collected; not bookable |
| Z2 Closed beta | Invitation-only bookings |
| Z3 Public limited | Selected services and slots |
| Z4 Validated | Quality, repeat and economics proven |
| Z5 Growth | Additional supply and societies |
| Z6 Mature | Stable capacity and local management |

The website should display service availability based on cluster status.

Do not accept payment in Z0 or Z1 areas unless it is an explicitly refundable and clearly disclosed pre-launch deposit.

Part VII — Launch Density Rules

23. Why the proposed density rules need modification

Your target of ten approved walkers per area may be:

- Too high for a 50-customer beta

- Too low for a 300-subscriber cluster

- Irrelevant if the walkers are unavailable during peak times

Count active, schedulable capacity, not just approved profiles.

24. Corrected launch-density targets

Closed-beta micro-cluster

| Requirement | Recommended target |
| --- | --- |
| Launch-ready walkers | 5–8 |
| Peak-time backup walkers | 2–3 |
| Pet sitters | 3–5 |
| Boarding hosts | 0–3, only if boarding is launched |
| Vet referral options | 2 |
| Groomers | 2–3 |
| Target societies | 5–10 |
| Qualified customer leads | 100–200 |
| Paying beta customers | 30–75 |
| Backup coverage | 90%+ |

Public validated cluster

| Requirement | Recommended target |
| --- | --- |
| Active walkers | 8–15 |
| Backup-capable walkers | 3–5 |
| Active sitters | 5–10 |
| Boarding providers | 2–5 if operationally approved |
| Vet referral options | 2–5 |
| Groomers | 3–5 |
| Society pipeline | 10+ |
| Monthly paying customers | 100–200 |
| Monthly completed services | 300–500 |
| Backup coverage | 90–95%+ |

25. Do not double-count providers

One person may offer both walking and sitting, but their available capacity cannot be counted twice.

Example:

Riya capacity:

80 walking slots/month

or

10 overnight sitting assignments

You cannot report:

80 walking slots

+

10 sitting assignments

if the same calendar days are required for both.

Use a time-based provider capacity ledger.

26. Required density metrics

Demand density

- Qualified leads per cluster

- Paying customers per square kilometre

- Bookings per active customer

- Society-origin bookings

- Peak-time demand

- Subscription commitments

Supply density

- Active providers per peak window

- Provider minutes available

- Backup coverage

- Travel time between services

- Capacity utilisation

- Provider earnings per productive hour

Operational density

- Average provider travel time

- Bookings per route hour

- Society gate delay

- Service completion

- On-time arrival

- Support incidents per 100 bookings

Financial density

- CAC per activated customer

- Contribution per booking

- Contribution per provider hour

- Contribution per society

- Local marketing payback

27. Cluster-opening gate

Open a new area only when all critical criteria pass:

| Gate | Target |
| --- | --- |
| Qualified leads | 100–200 |
| Paid trial intent | 20–40 |
| Active launch providers | 5–8 |
| Peak-time backups | 2–3 |
| Vet escalation mapped | Yes |
| Support routing | Yes |
| Local pricing | Configured |
| Capacity limits | Configured |
| Refund/incident SOP | Tested |
| Projected contribution | Viable |

28. Cluster-scale gate

Scale beyond beta only when:

| Metric | Target |
| --- | --- |
| Completed paid services | 50–150 beta services |
| Rating | 4.6+ |
| Completion | 95%+ |
| On-time | 95%+ |
| Provider no-show | Below 1% |
| Provider cancellation | Below 5% |
| Refund/dispute | Below 5% |
| Backup fulfilment | 90%+ |
| Critical preventable incidents | Zero |
| Direct contribution | Positive or clearly improving |

29. Cluster-expansion gate

Open the next adjacent cluster only when the current cluster has:

- 300–500 monthly completed services

- 100–200 monthly paying customers

- 25–40% repeat rate

- Positive direct contribution

- Capacity utilisation below 85%

- Peak utilisation below 90%

- 90–95% backup coverage

- No critical unresolved incident

- Local operational owner

- Stable provider earnings

Do not use unused central-city provider capacity as evidence that a distant new cluster is ready.

Part VIII — Compliance Controls for City Teams

30. Gig and platform-worker operations

The Code on Social Security recognises gig and platform workers, and the Ministry of Labour’s June 2026 direction states that aggregators covered by the 2026 Rules must share required worker details through the eShram framework. A pet-care marketplace should obtain a formal classification opinion and build compliant provider-registration and reporting processes if it is in scope.

City onboarding should therefore maintain:

- Provider identity

- Engagement dates

- Active/inactive status

- Earnings and payouts

- Government registration identifiers where applicable

- Document expiry

- Reporting-sync status

31. Data access

The DPDP Rules, 2025 have phased commencement. City expansion increases access to recurring schedules, home addresses, gate instructions, pet records and payment information, so city-specific role controls should be implemented before scaling.

Recommended access:

| Role | Access |
| --- | --- |
| Walker | Assigned booking and necessary pet instructions |
| Operations | Scheduling and fulfilment |
| Support | Customer-service and booking data |
| City Manager | Aggregated city controls and escalations |
| Society Executive | Society relationship data, not medical records |
| Marketing | Aggregated campaign data |
| Finance | Payments and settlements |
| RWA | Aggregate society reports only |

Final Approval Matrix

| Proposal | Decision |
| --- | --- |
| One city manager per public city | Approved |
| One to two onboarding executives | Stage-dependent |
| One to two local support executives | Stage-dependent; central support first |
| Society partnership executive | Add when pipeline justifies it |
| Operations coordinator | Mandatory from validated-cluster stage |
| Shared add-on partner manager | Approved initially |
| Shared city marketing | Approved initially |
| City manager owns all outcomes | Approved |
| City manager personally performs everything | Rejected |
| Rating target 4.6+ | Approved |
| Repeat rate 35%+ | Approved for mature cities |
| Reliability target 95%+ | Approved with separate metrics |
| Incident rate below 3% | Replace with severity-based targets |
| Gross margin 25–35% | Approve only with a defined accounting basis |
| CAC payback under 2–3 months | Mature-city target |
| Society booking share 30%+ | Use where society-first strategy applies |
| Open whole city at once | Rejected |
| Ten approved walkers per cluster | Replace with active capacity targets |
| No supply, no area launch | Approved—non-negotiable |

Final Recommended City Operating Model

Pre-launch

1 City Lead + 1 Generalist + Shared Central Functions

Closed Beta

1 City Manager + 1 Ops/Onboarding Executive

Validated Cluster

City Manager + Ops Coordinator + Onboarding + Shared Support

Growth City

City Manager + 1–2 Onboarding + 1 Ops + 1–2 Support

+ Society Executive + Shared Add-on/Marketing

Mature City

Add Cluster Leads, Quality, Partnerships and Capacity

based on measured workload

Phase 10 City Win Condition

Each city and cluster has enough demand, active supply, backup capacity, local accountability and positive contribution to operate without founder firefighting or degradation in safety and customer trust.

City Team, P&L and Cluster Expansion System: APPROVED—with stage-based staffing, severity-based safety gates and capacity measured by area and time window rather than provider headcount alone.

Phase 10 Expansion Technology Architecture 🌍⚙️

Multi-City Configuration, Database, APIs and Command Centres

Executive verdict

Your proposed features are correct, but the current schema is too city-centric and too static for production multi-city operations.

A reliable architecture needs six layers:

Country

↓

City

↓

Service zone / cluster

↓

Society or locality

↓

Service configuration and capacity

↓

Bookings, partners, pricing and P&L

The critical design rule is:

City should be a first-class operational boundary, while the service zone should be the actual booking, pricing and capacity boundary.

A service may be available in Bengaluru without being available throughout Bengaluru. Similarly, Whitefield may have walking capacity at 7:00 AM but no boarding supply or evening backup.

1. Core multi-city architecture

Every city must independently configure:

- Launch stage

- Public availability

- Service zones

- Services offered

- Prices and partner payouts

- Operating hours

- Sitter capacity

- Support contacts

- Emergency veterinary directory

- Notification templates

- Society pipeline

- Staff access

- Subscriptions

- Financial attribution

- Incident ownership

The booking flow should become:

Customer enters address

↓

Resolve city and service zone

↓

Check whether service is active

↓

Check pet eligibility

↓

Check local price version

↓

Check partner and backup capacity

↓

Display available slots

↓

Create booking

↓

Attribute revenue, cost and incident ownership to city

Do not let customers select an arbitrary city from a dropdown and then assume the service is available.

2. City and area management

What the feature must do

City management should control:

- Whether the city is visible publicly

- Whether it accepts waitlist registrations

- Whether it accepts paid bookings

- Which clusters are active

- Which services are enabled

- Which payment and support workflows apply

- Which staff can access the city

Recommended city states

RESEARCH

WAITLIST

SUPPLY_BUILD

CLOSED_BETA

PUBLIC_LIMITED

VALIDATED

GROWTH

MATURE

PAUSED

EXITED

Do not use a simple Boolean such as:

is_active = true

That cannot distinguish:

- A city collecting leads

- A closed beta

- A city taking bookings in selected areas

- A temporarily paused city

- A fully mature operation

Recommended zone states

RESEARCH

WAITLIST

BETA

ACTIVE_LIMITED

ACTIVE

CAPACITY_PAUSED

SERVICE_PAUSED

CLOSED

A city may be GROWTH while one zone is ACTIVE, another is WAITLIST, and a third is paused because its morning capacity is full.

3. Geography model

Problem with the proposed areas table

This is too limited:

areas

- city_id

- name

- pincode

A neighbourhood can contain multiple postcodes, and a postcode may not precisely match your operational service boundary.

Use geographic polygons or multipolygons for operational zones.

Recommended model

service_zones

- id

- city_id

- code

- name

- slug

- boundary

- centroid

- status

- launch_stage

- priority

- timezone

- created_at

- updated_at

service_zone_pincodes

- service_zone_id

- pincode

Use boundary for accurate booking eligibility and pincodes for customer search, SEO and fallback matching.

PostGIS provides geographic data types and functions such as ST_DWithin; when geography values are used, distance is measured in metres. That makes it suitable for local service-radius checks.

Example radius matching

SELECT p.id

FROM partners p

JOIN partner_service_areas psa

ON psa.partner_id = p.id

WHERE psa.service_type = 'DOG_WALK'

AND psa.status = 'ACTIVE'

AND ST_DWithin(

psa.origin,

:booking_location,

psa.max_radius_meters

);

Distance is only the first filter. Final matching must also validate:

- Availability

- Time window

- Pet size and behaviour

- Required certification or permission

- Society access

- Travel time

- Existing workload

- Backup capacity

4. City-specific service catalogue

Do not use one global services table with an is_active flag.

A service can be:

- Active in one city

- Beta in another

- Active in only one cluster

- Available only during certain hours

- Disabled because local supply is exhausted

Recommended structure

services

- id

- code

- name

- category

city_service_configurations

- id

- city_id

- service_id

- status

- booking_mode

- minimum_notice_minutes

- maximum_advance_days

- operating_hours

- cancellation_policy_id

- support_policy_id

- created_at

zone_service_configurations

- id

- service_zone_id

- service_id

- status

- booking_mode

- capacity_policy_id

- price_book_id

- waitlist_enabled

- launch_limit

- created_at

Service status

DISABLED

WAITLIST

MANUAL_BETA

ACTIVE_LIMITED

ACTIVE

CAPACITY_PAUSED

SAFETY_PAUSED

This gives you feature control such as:

Ahmedabad / Bopal

Walking          ACTIVE

Sitting          ACTIVE_LIMITED

Grooming         ACTIVE

Boarding         MANUAL_BETA

Pet Taxi         DISABLED

5. City pricing architecture

Problem with the proposed table

This design is too simple:

city_pricing

- service_type

- base_price

- trial_price

- subscription_price

One service can have:

- Several durations

- Different pet sizes

- Peak and off-peak prices

- Society discounts

- Subscription prices

- Partner payouts

- Taxes

- Travel fees

- Multiple versions over time

Correct architecture

price_books

- id

- city_id

- service_zone_id nullable

- name

- currency

- status

- valid_from

- valid_until

- created_at

service_packages

- id

- service_id

- code

- name

- duration_minutes

- entitlement_quantity

- rules

price_book_items

- id

- price_book_id

- service_package_id

- customer_price_minor

- partner_payout_minor

- platform_fee_minor

- tax_rate

- peak_window_modifier

- additional_pet_price_minor

- trial_price_minor

- is_active

- valid_from

- valid_until

Store ₹2,499 as:

249900 paise

Do not use floating-point values for money.

Versioning rule

Never overwrite historical pricing.

When a price changes:

Price Book Version 1 → retired

Price Book Version 2 → published

Every booking should store a price snapshot:

customer_price_snapshot

partner_payout_snapshot

tax_snapshot

price_book_item_id

This prevents historical invoices and city P&Ls from changing when a new price is published.

6. Sitter service radius and local supply

Recommended partner geography model

A partner may work in multiple cities or zones. Therefore, do not put a single city_id directly on the partner profile as the complete service definition.

Use a many-to-many assignment:

partner_service_areas

- id

- partner_id

- city_id

- service_zone_id

- service_type

- origin

- coverage_boundary nullable

- max_radius_meters

- travel_mode

- status

- valid_from

- valid_until

partner_availability

- id

- partner_id

- service_zone_id

- weekday

- start_time

- end_time

- maximum_services

- status

partner_capacity_allocations

- id

- partner_id

- service_zone_id

- service_type

- capacity_date

- time_window

- gross_capacity

- reserved_subscription_capacity

- reserved_backup_capacity

- one_time_capacity

- remaining_capacity

Important principle

A sitter’s service radius is not constant throughout the day.

For example:

- 2 km during the 7:00–9:00 AM peak

- 5 km during the afternoon

- Same-society bookings only during high-density blocks

Your architecture should therefore support both:

- Geographic radius

- Time-window-specific operational radius

7. Capacity planning engine

Capacity planning is not merely a dashboard calculation. It must control checkout.

Sellable-capacity formula

Sellable capacity=  approved partner capacity-existing bookings-subscription reservations-leave allowance-backup reserve-operational buffer

Required entities

capacity_policies

- id

- city_id

- service_zone_id

- service_type

- backup_reserve_percent

- maximum_utilization_percent

- stop_sales_percent

capacity_slots

- id

- city_id

- service_zone_id

- service_type

- service_date

- window_start

- window_end

- gross_capacity

- reserved_capacity

- backup_capacity

- available_capacity

- status

capacity_reservations

- id

- capacity_slot_id

- booking_id nullable

- subscription_id nullable

- quantity

- reservation_type

- status

- expires_at

Checkout rule

Plan selected

↓

Zone capacity checked

↓

Recurring schedule capacity checked

↓

Primary capacity available?

↓

Backup capacity available?

↓

Only then allow payment

No capacity should mean:

- Alternative slot

- Another plan

- Waitlist

- Another zone

It should not mean collecting payment and manually solving the shortage later.

8. City-specific landing pages

Required page hierarchy

/cities/ahmedabad

/cities/ahmedabad/bopal

/cities/ahmedabad/bopal/dog-walking

/cities/bengaluru/whitefield/pet-sitting

Each city page should show

- Exact supported areas

- Services currently live

- Starting prices

- Local partner availability

- Local society coverage

- Service hours

- Local support contact

- Safety and verification process

- Local FAQs

- Waitlist for unsupported locations

Important trust rule

Do not publish:

Available throughout Bengaluru

when only Whitefield and Brookefield are active.

Use:

Available in Whitefield, Brookefield, Kundalahalli and selected nearby societies.

City and zone pages should read from the same configuration used by checkout. This prevents marketing pages from advertising services the operational system has disabled.

9. City admin roles and access control

Problem with the proposed structure

This is insufficient:

city_staff

- role

- permissions

Permissions should not be an uncontrolled list copied into every staff row.

Use separate role and permission definitions.

Recommended structure

staff_roles

- id

- code

- name

- scope_type

permissions

- id

- code

- description

role_permissions

- role_id

- permission_id

city_staff_assignments

- id

- user_id

- city_id

- service_zone_id nullable

- role_id

- is_primary

- status

- valid_from

- valid_until

Example roles

- National Admin

- Regional Manager

- City Manager

- City Operations

- Supply Onboarding

- Society Partnerships

- Customer Support

- Finance Viewer

- Safety Reviewer

- Marketing Viewer

Access principle

A Pune city operations user should not automatically access:

- Mumbai customer addresses

- Ahmedabad financial data

- Bengaluru partner documents

- National incident investigations

PostgreSQL supports row-level security policies that restrict which rows a role can read or modify. RLS should supplement—rather than replace—application-level authorisation.

Example security context

SET LOCAL app.user_id = '...';

SET LOCAL app.city_ids = '{city-uuid}';

Then apply policies to scoped tables such as:

- Bookings

- Partners

- Societies

- Incidents

- Subscription records

- City financial snapshots

Do not use database-owner or BYPASSRLS credentials for ordinary application requests.

10. City-level notifications

Notifications must be configurable by:

- City

- Zone

- Language

- Service

- Customer status

- Incident severity

- Launch stage

- Local support hours

Recommended tables

notification_templates

- id

- code

- channel

- locale

- template_body

- status

city_notification_overrides

- id

- city_id

- notification_template_id

- support_phone

- local_variables

- status

notification_events

- id

- city_id

- customer_id

- event_type

- channel

- template_version

- delivery_status

- sent_at

Example city-specific notification

Ahmedabad:

Support available in English, Hindi and Gujarati

Local number: +91-...

Bengaluru:

Support available in English, Hindi and Kannada

Local escalation window: ...

Do not hard-code support numbers or city names into application code.

11. Partner city tagging

Partners should be assigned through service-area records, not simple tags.

Correct hierarchy

Partner

├── City assignments

├── Zone assignments

├── Service permissions

├── Radius

├── Availability

└── Capacity

A grooming company may:

- Operate in two cities

- Serve only selected zones

- Offer cat grooming in one city

- Offer dog grooming in another

- Have separate staff pools and prices

Use:

partner_city_assignments

partner_service_areas

partner_service_permissions

partner_team_members

partner_availability

Do not duplicate the entire partner profile for each city unless they are legally separate branches.

12. Society grouping

Recommended structure

societies

- id

- city_id

- primary_service_zone_id

- name

- slug

- status

- address

- location

- household_count

- estimated_pet_households

- relationship_stage

society_towers

- id

- society_id

- name

society_gates

- id

- society_id

- name

- access_instructions

- operating_hours

society_city_programmes

- id

- society_id

- programme_type

- subscription_plan_id

- account_owner_id

- status

- start_date

- end_date

Why this matters

Society reporting must distinguish:

- Identified societies

- Contacted societies

- Decision-maker meetings

- Pilot societies

- Paid societies

- Resident leads

- Resident subscribers

- Event conversions

- Gate incidents

- Contribution

Do not store only:

society.city = "Ahmedabad"

The operational relationship needs account ownership, status history and programme configuration.

13. Corrected city schema

Cities table

cities

- id

- country_code

- state_code

- code

- name

- slug

- timezone

- currency

- lifecycle_stage

- public_status

- launch_date

- default_language

- support_phone

- emergency_support_phone

- created_at

- updated_at

Remove city_manager_id

The manager can change or multiple managers may exist during a transition. Keep manager assignments in city_staff_assignments.

A cached primary_manager_id may be added for read performance, but staff assignments remain the source of truth.

Service zones

service_zones

- id

- city_id

- code

- name

- slug

- boundary_geography

- centroid_geography

- status

- launch_stage

- priority

- created_at

- updated_at

Price books

price_books

price_book_items

service_packages

city_service_configurations

zone_service_configurations

This replaces the oversimplified city_pricing table.

City performance

Do not make city_performance the primary operational data source.

Bookings, payments, incidents and subscriptions remain the source of truth. Performance rows should be snapshots or aggregates.

city_metric_snapshots

- id

- city_id

- service_zone_id nullable

- period_type

- period_start

- period_end

- metric_version

- completed_bookings

- unique_paying_customers

- gross_booking_value_minor

- platform_revenue_minor

- contribution_minor

- active_partners

- repeat_customer_rate

- rating

- completion_rate

- on_time_rate

- refund_rate

- minor_incident_count

- serious_incident_count

- critical_incident_count

- generated_at

Use different columns for:

- GMV

- Platform revenue

- Contribution

Do not store them all as revenue.

14. Materialized dashboard views

National dashboards should not continuously aggregate millions of raw booking and payment rows.

Use:

- Operational queries for today’s live bookings

- Materialized views or analytics tables for historical city metrics

- A finance ledger for reconciled revenue

- A separate incident source for safety metrics

PostgreSQL materialized views persist query results and can later be refreshed. A concurrent refresh allows reads to continue, but it requires an appropriate unique index on the materialized view.

Suggested views

mv_city_daily_operations

mv_city_monthly_financials

mv_city_partner_reliability

mv_city_subscription_metrics

mv_city_society_pipeline

mv_national_city_scorecard

Refresh cadence

| View | Refresh |
| --- | --- |
| Today’s bookings | Real time or near real time |
| Capacity | Every few minutes |
| Failed payments | Near real time |
| City quality | Hourly |
| Subscription MRR | Hourly/daily |
| Financial P&L | Daily after reconciliation |
| Monthly scorecard | Daily until month close |

Every widget should display its last refresh timestamp.

15. Index strategy

Typical high-value indexes include:

CREATE INDEX bookings_city_status_time_idx

ON bookings (city_id, status, scheduled_at);

CREATE INDEX bookings_zone_date_idx

ON bookings (service_zone_id, scheduled_at);

CREATE INDEX partner_service_area_geo_idx

ON partner_service_areas

USING GIST (origin);

CREATE INDEX active_price_items_idx

ON price_book_items (price_book_id, service_package_id)

WHERE is_active = true;

PostgreSQL supports multicolumn indexes and partial indexes, but the column order and predicate should match real query patterns. Indexes improve reads while adding write and maintenance overhead, so they should be driven by observed workloads.

Use pg_stat_statements to identify expensive and frequent queries rather than guessing every index in advance.

16. Table partitioning

Do not create one physical bookings table per city.

Begin with a shared bookings table containing:

city_id

service_zone_id

scheduled_at

When the volume justifies partitioning, append-heavy tables are generally better partitioned by time, such as month, rather than by a growing and uneven set of cities.

Good partition candidates:

- Bookings

- Notification events

- Audit logs

- Payment events

- Capacity snapshots

- Location events

PostgreSQL supports declarative partitioning and partition pruning; however, partitioning adds operational complexity and should be introduced only when row volume and query behaviour justify it.

17. Corrected multi-city API design

Public city discovery

GET /v1/cities?public_status=BOOKABLE

GET /v1/cities/{citySlug}

GET /v1/cities/{citySlug}/service-zones

GET /v1/cities/{citySlug}/services

Address resolution

POST /v1/serviceability/resolve

Request:

{

"latitude": 23.027,

"longitude": 72.465,

"pincode": "380058",

"service_type": "DOG_WALK"

}

Response:

{

"city": {

"id": "city_ahmedabad",

"name": "Ahmedabad"

},

"service_zone": {

"id": "zone_south_bopal",

"name": "South Bopal"

},

"serviceability": "ACTIVE_LIMITED",

"available_services": ["DOG_WALK", "PET_SITTING"],

"waitlist_available": false

}

Plan and price discovery

GET /v1/service-zones/{zoneId}/services

GET /v1/service-zones/{zoneId}/service-packages

GET /v1/service-zones/{zoneId}/prices

GET /v1/service-zones/{zoneId}/availability

Prices must come from server-side published price books—not from client-submitted amounts.

National admin APIs

POST /v1/admin/cities

GET  /v1/admin/cities

GET  /v1/admin/cities/{cityId}

POST /v1/admin/cities/{cityId}/transition-stage

POST /v1/admin/cities/{cityId}/staff-assignments

GET  /v1/admin/cities/{cityId}/audit-log

Avoid a generic unrestricted:

PUT /api/admin/cities/:id

for every field. Use explicit commands for high-impact transitions such as public launch, pause and city closure.

Zone administration

POST /v1/admin/cities/{cityId}/service-zones

PATCH /v1/admin/service-zones/{zoneId}

POST /v1/admin/service-zones/{zoneId}/transition-stage

POST /v1/admin/service-zones/{zoneId}/services

POST /v1/admin/service-zones/{zoneId}/capacity-policies

Price administration

POST /v1/admin/cities/{cityId}/price-books

POST /v1/admin/price-books/{priceBookId}/items

POST /v1/admin/price-books/{priceBookId}/publish

POST /v1/admin/price-books/{priceBookId}/retire

Published price versions should be immutable.

City operations APIs

GET /v1/city-ops/dashboard

GET /v1/city-ops/bookings

GET /v1/city-ops/bookings/today

GET /v1/city-ops/partners

GET /v1/city-ops/capacity

GET /v1/city-ops/incidents

GET /v1/city-ops/subscriptions

GET /v1/city-ops/societies

The permitted city should be derived from the authenticated staff assignment.

Do not trust:

?city_id=another-city

as authorisation.

18. API security rules

Every write endpoint should support:

- Authentication

- City and zone authorisation

- Input validation

- Idempotency keys

- Audit records

- Version or concurrency checks

- Explicit transition validation

Example

A city manager may:

- Assign a backup sitter

- Pause sales in their zone

- Add a service-recovery credit within a limit

They should not necessarily be allowed to:

- Publish national prices

- Edit another city

- Delete an incident

- Override veterinary credentials

- Mark an unpaid invoice paid

- Change recognised finance data

PostgreSQL privileges and RLS provide database-enforced layers for these scopes.

19. National admin command centre

The national dashboard should compare cities without hiding lifecycle differences.

Executive row

| Widget | Correct definition |
| --- | --- |
| Total cities | Count by launch stage |
| Public cities | Cities accepting public bookings |
| Validated cities | Cities that passed quality and economics gates |
| Network bookings | Completed services, not created bookings |
| Platform revenue | Retained platform revenue |
| Network contribution | Revenue minus direct operating costs |
| Active subscribers | Paid active recurring plans |
| Critical incidents | Open and closed separately |

City comparison table

| City | Stage | Completed bookings | Rating | Completion | Repeat | MRR | Contribution |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ahmedabad | Mature |  |  |  |  | ₹ | ₹ |
| Pune | Validated |  |  |  |  | ₹ | ₹ |
| Bengaluru | Beta |  |  |  |  | ₹ | ₹ |

Do not compare a closed beta directly against a mature city without displaying the stage.

20. National dashboard widgets

Bookings by city

Display:

- Created

- Confirmed

- Completed

- Cancelled

- Refunded

- Failed fulfilment

Primary headline:

Completed paid services

Revenue by city

Display separately:

- GMV

- Platform revenue

- Partner payouts

- Contribution

- Allocated city costs

Ratings by city

Display:

- Average rating

- Number of reviews

- Rating distribution

- Low-rating count

- Verified service reviews

A city with 4.9 from ten reviews should not automatically outrank a city with 4.7 from 2,000 reviews.

Incidents by city

Separate:

- Minor

- Serious

- Critical

- Preventable

- Open

- Overdue

- Recurring root cause

Do not publish one ambiguous “incident rate.”

Sitter reliability

Display:

- Acceptance rate

- Completion rate

- On-time rate

- Cancellation rate

- No-show rate

- Report completion

- Backup fulfilment

City profitability

Display:

- Contribution 1

- Contribution 2

- City operating contribution

- Central allocation

- Fully allocated result

Society pipeline

Display by stage:

Identified

Contacted

Meeting completed

Pilot proposed

Pilot signed

Pilot active

Paid

Renewed

Subscription MRR

Display:

- Walking-plan MRR

- Membership MRR

- Society MRR

- New MRR

- Expansion MRR

- Downgrade MRR

- Churned MRR

21. City admin dashboard

Row 1 — Daily operations

Bookings due today

Completed

In progress

Unassigned

Late/check-in missing

Backup required

Row 2 — Supply

Active partners

Available now

Capacity utilisation

Partners on leave

Documents expiring

Plans without backup

Row 3 — Quality and safety

Pending reports

Low ratings

Open complaints

Open incidents

Critical escalations

Refund requests

Row 4 — Payments

Customer payment pending

Partner payouts pending

Refunds pending

Reconciliation mismatches

Subscription renewals due

Failed renewals

Row 5 — Growth

New customers

Repeat rate

Subscription conversions

Society pipeline

Event leads

Referral conversions

Row 6 — Financials

Today’s GMV

Platform revenue

Partner payout liability

Direct contribution

Marketing spend

CAC

22. City-dashboard drill-downs

Every widget should lead to an actionable queue.

Example: Pending reports

The queue should show:

- Booking

- Partner

- Completion time

- Report due time

- Missing fields

- Customer notification state

- Escalation owner

Example: Failed renewals

Show:

- Customer

- Plan

- Amount

- Failure reason

- Grace-period end

- Retry status

- Payment-link status

- Assigned support owner

Example: Incident widget

Show:

- Severity

- Pet/customer

- Provider

- Service

- Time

- Immediate action

- Investigation owner

- SLA

- Status

A dashboard number without an operational drill-down becomes a reporting ornament rather than a command centre.

23. Privacy and city-level data isolation

Multi-city operations increase access to:

- Customer addresses

- Recurring schedules

- Gate instructions

- Pet behaviour

- Medical-related records

- Payment references

- Sitter identity documents

The notified Digital Personal Data Protection Rules, 2025 have phased commencement. The architecture should nevertheless implement city-scoped access, purpose-specific processing, security controls and grievance handling before expansion.

Minimum controls

- Role-based permissions

- Row-level city scoping

- Field-level restrictions

- Audit logs

- Secure exports

- Time-limited temporary access

- No individual data in RWA dashboards

- No cross-city customer browsing

- Redacted analytics

- Data-retention jobs

Example

A society partnership executive may see:

- Society account

- Meeting notes

- Aggregate resident registrations

- Event conversions

They should not see:

- Customer health records

- Home-access codes

- Payment-card details

- Detailed pet incident reports unrelated to the society relationship

24. Migration plan

Stage 1 — Establish the geographic hierarchy

- Create cities

- Create service zones

- Assign existing data to one default city

- Add city_id and service_zone_id to bookings

- Backfill partners and societies

Stage 2 — Introduce service configuration

- City service catalogue

- Zone service availability

- Operating hours

- Feature flags

- Capacity policies

Stage 3 — Introduce price books

- Migrate existing prices

- Create version 1

- Store price snapshots on new bookings

- Stop using global price constants

Stage 4 — Introduce city access control

- Staff role definitions

- City assignments

- Application authorisation

- RLS policies

- Audit logs

Stage 5 — Build capacity and partner-area systems

- Partner geographic coverage

- Availability

- Capacity slots

- Subscription reservations

- Stop-sales logic

Stage 6 — Build dashboards

- Real-time operations

- Materialized city metrics

- Financial reconciliation

- National comparison

Stage 7 — Launch City 2 in waitlist mode

Do not begin with public booking.

Test:

- Landing page

- Address resolution

- Staff access

- Pricing

- Waitlist

- Supply dashboards

- Local notifications

25. Production acceptance tests

Before City 2 opens, test:

- Customer address resolves to the correct city and zone.

- Unsupported address receives waitlist—not checkout.

- Walking can be active while boarding remains disabled.

- City price differs without affecting existing bookings.

- Existing booking retains its historical price.

- Partner outside the radius is excluded.

- Partner in the radius but unavailable is excluded.

- Peak slot closes when capacity reaches the limit.

- Backup capacity remains reserved.

- City manager cannot access another city.

- National admin can access all authorised cities.

- RLS blocks direct cross-city database reads.

- City landing page reflects service configuration.

- Paused service disappears from checkout.

- Society is attributed to the correct city and zone.

- Booking revenue reaches the correct city P&L.

- Refund updates contribution metrics correctly.

- Incident routes to the correct city owner.

- Dashboard refresh shows a freshness timestamp.

- City closure disables new bookings without deleting historical data.

Final architecture decision

| Proposed component | Decision |
| --- | --- |
| City/area management | Approve with lifecycle stages and geographic zones |
| City pricing | Replace with versioned price books |
| Sitter service radius | Approve using spatial data plus availability |
| City landing pages | Approve; read from operational configuration |
| City admin roles | Approve with RBAC, assignments and RLS |
| City-level dashboards | Approve with actionable drill-downs |
| City notifications | Approve with city, locale and consent configuration |
| Partner city tagging | Replace with service-area assignments |
| Society city grouping | Approve with account and programme hierarchy |
| Capacity planning | Mandatory and checkout-enforced |
| city_manager_id on city | Use staff assignment as source of truth |
| Single pincode on area | Replace with polygons and postcode mappings |
| One mutable city-pricing row | Reject |
| Monthly city_performance as source of truth | Use reconciled snapshots/materialized views |
| Generic unrestricted PUT APIs | Replace with explicit commands and transitions |

Final recommended data model

cities

service_zones

service_zone_pincodes

services

service_packages

city_service_configurations

zone_service_configurations

price_books

price_book_items

partner_city_assignments

partner_service_areas

partner_availability

partner_capacity_allocations

capacity_policies

capacity_slots

capacity_reservations

staff_roles

permissions

role_permissions

city_staff_assignments

societies

society_towers

society_gates

society_city_programmes

city_metric_snapshots

city_pnl_periods

notification_templates

city_notification_overrides

audit_logs

Phase 10 technology win condition

The platform can activate, price, staff, monitor, pause and financially isolate every city and service zone without copying code, exposing cross-city data or manually rebuilding operations for each launch.

Multi-City Technology Architecture: GO—with service-zone geography, versioned price books, city-scoped access, capacity-enforced checkout and independent city P&Ls.

Phase 10 Multi-City Brand Strategy 🌍🐾

One National Brand, Six Local Market Playbooks

Executive verdict

Approve the national-master-brand model with city-specific positioning.

Do not create six independent brands. That would fragment:

- Trust and reviews

- Verification standards

- Product development

- Support systems

- Search authority

- Safety reputation

- Marketing expenditure

Use one national promise:

Verified local pet care, documented at every visit.

Then localise five elements for each city:

- Customer problem

- Flagship product

- Operational service area

- Pricing and offer

- Local trust evidence

India’s pet-care category continues to expand as pets are increasingly treated as family members and spending shifts toward professional services, digital discovery and premium care. However, national category growth does not prove that the same positioning or price will work in every neighbourhood.

1. National brand architecture

Recommended brand core

Your proposed core is:

Verified pet care with trusted sitters, live updates, report cards and emergency support.

A safer and stronger version is:

Verified local pet care with trusted caregivers, live service updates, detailed care reports and urgent-care coordination.

Why change “emergency support”?

“Emergency support” can sound like the platform provides veterinary treatment.

Your platform should promise:

- Emergency clinic information

- Human coordination

- Record-sharing assistance

- Transport coordination where available

- Customer escalation

It should not promise:

- Diagnosis

- Treatment

- Guaranteed clinic admission

- Guaranteed veterinary response time

- Medical prioritisation for paid members

Use:

Urgent-care coordination

rather than:

Emergency medical support

2. Four national brand pillars

Pillar 1: Verified people

Every provider profile should show exactly what was verified.

Valid badges

- Identity checked

- Contact verified

- Documents reviewed

- Practical trial completed

- Dog-walking skills assessed

- Cat-care skills assessed

- Society access approved

- Background check completed on [date]

Avoid vague badges

- 100% safe

- Government approved

- Fully certified

- Police verified

- Best sitter

unless the claim is literally true, current and documented.

A “police verification” badge should appear only when the relevant check was actually completed, with the type and date visible. It must not imply government endorsement or guarantee that the provider presents no risk.

Pillar 2: Visible service

The customer should be able to see that the promised care happened.

National service-proof standard

- Start check-in

- End check-out

- GPS route where appropriate

- Time and duration

- Photo or media proof with consent

- Toilet and behaviour notes

- Food, water or medication confirmation

- Incident flag

- Digital report card

GPS tracking and live updates are already promoted by existing Indian dog-walking services. In competitive metros, these are becoming expected product features rather than sufficient premium differentiators.

Your differentiation must therefore combine tracking with:

- Better caregiver continuity

- Better backup fulfilment

- Better reports

- Faster problem resolution

- Stronger society protocols

Pillar 3: Reliable continuity

Use:

Preferred caregiver with approved backup coverage

Do not use:

Guaranteed same sitter forever

Recommended service targets:

| Metric | Target |
| --- | --- |
| Preferred-caregiver fulfilment | 85%+ |
| Primary or approved backup fulfilment | 98%+ |
| Unintroduced replacement | Below 2% |
| Provider no-show | Below 1% |

The brand promise should be continuity with resilience—not dependence on one person.

Pillar 4: Local readiness

A city page should never imply city-wide coverage when only one cluster is operational.

Every local page must show:

- Exact active neighbourhoods

- Services currently available

- Current operating hours

- Starting prices

- Verified local provider count

- Backup coverage where applicable

- Local support contact

- Local urgent-care directory

- Waitlist for unsupported areas

This prevents national marketing from outrunning actual city operations.

3. What remains national versus local

Keep nationally consistent

- Brand name and logo

- Core colours and typography

- Verification framework

- Safety standards

- Service-report format

- Incident definitions

- Refund principles

- Preferred-caregiver wording

- Customer grievance process

- Subscription-credit rules

- Privacy standards

- Rating methodology

Localise by city

- Hero headline

- Supported areas

- Service catalogue

- Pricing

- Subscription mix

- Language

- Society offer

- Acquisition channels

- Local testimonials

- Urgent-care directory

- Local support details

- Events and campaigns

Localise by service cluster

- Time windows

- Provider radius

- Available capacity

- Same-day availability

- Society gate procedures

- Partner payout

- Backup reserve

- Stop-sales limits

4. City landing-page system

Recommended structure:

/cities/bengaluru

/cities/bengaluru/whitefield

/cities/bengaluru/whitefield/dog-walking

/cities/pune

/cities/pune/baner-balewadi

/cities/pune/baner-balewadi/dog-walking

City page

Explain:

- City-specific value proposition

- Active clusters

- Services

- Trust system

- Pricing range

- Local customer proof

- Society programme

- FAQs

Cluster page

Explain:

- Exact neighbourhood boundary

- Available time windows

- Local providers

- Cluster-specific prices

- Society coverage

- Capacity status

- Waitlist status

Service page

Explain:

- What is included

- Duration

- Price

- Caregiver verification

- How matching works

- Backup rules

- Report-card contents

- Cancellation

- Booking CTA

City SEO pages and operational serviceability must read from the same configuration. A marketing team must not be able to publish availability that checkout cannot fulfil.

5. National positioning matrix

| City | Recommended local position | Flagship offer |
| --- | --- | --- |
| Bengaluru | App-first recurring care for busy apartment pet parents | Weekday walking routine |
| Pune | Reliable, value-conscious monthly care for apartment communities | 12- and 20-walk plans |
| Mumbai | Hyperlocal premium care with tight geographic reliability | Locality-based walking |
| Gurugram | Verification-led care infrastructure for gated communities | Society premium desk |
| Ahmedabad | Trusted, accessible local care for families | 8- and 12-walk plans |
| Surat | Assisted, society-first care built around family trust | Starter care plan |

The labels “premium,” “high willingness to pay” and “strong digital conversion” should remain market hypotheses until paid conversion and contribution data validate them.

6. Bengaluru strategy

Recommended positioning

Reliable app-first pet care for busy Bengaluru pet parents—verified walkers, live updates and dependable backup coverage.

Recommended hero

Bruno’s routine, handled—even on your busiest days.

Flagship product

Active Weekday Walk Plan

- 20 × 30-minute walks

- Primary walker preference

- Approved backup

- Live check-in and report

- Monthly activity summary

- Pause and reschedule controls

Existing operators already advertise monthly walking plans and GPS-enabled service in Bengaluru. A new entrant therefore cannot compete only on “book from an app”; it needs visibly stronger fulfilment, continuity and service recovery.

Corrected cluster rollout

Cluster 1: Whitefield micro-market

- Whitefield

- Brookefield

- Kundalahalli

- Selected Hoodi/Mahadevapura-adjacent societies where travel times work

This is the strongest grouping in your original plan.

Cluster 2A: HSR

- HSR Layout

- Selected nearby societies

- Dedicated morning/evening provider pool

Cluster 2B: Bellandur–Sarjapur corridor

- Bellandur

- Selected Sarjapur Road communities

- Strict peak-window radii

Do not treat HSR, Bellandur and all of Sarjapur Road as one undifferentiated operating zone.

Cluster 3A: Koramangala

Cluster 3B: Indiranagar

They may share branding but should have separate peak-capacity calculations.

Cluster 4A: JP Nagar

Cluster 4B: Electronic City

Electronic City and JP Nagar should not be grouped as one fulfilment cluster simply because they are both in south Bengaluru.

Bengaluru recorded a 74.4% average congestion level in TomTom’s 2025 index. I therefore recommend smaller zones and time-window-specific provider radii rather than city-wide matching.

Acquisition sequence

- Successful-walk conversion

- Apartment society partnerships

- Google Search by supported locality

- Instagram proof-of-service content

- Referral programme

- Corporate benefit pilot after consumer fulfilment is stable

Local proof content

Show:

- GPS walk examples

- Real report cards

- Preferred-walker fulfilment rate

- Backup-response performance

- Whitefield or HSR customer reviews

- Exact neighbourhood availability

Main risk

High expectations combined with severe travel friction.

Control

- Strict operational zones

- No city-wide same-day promise

- Stop sales above 85% capacity

- Local backup pool

- Broad but explicit arrival windows

- No subscription checkout before schedule capacity is reserved

Bengaluru decision

GO, but split the proposed large clusters into smaller operational units.

7. Pune strategy

Recommended positioning

Dependable monthly dog-walking plans designed for Pune’s apartment communities.

Recommended hero

A consistent walking routine—without paying for more than your dog needs.

Flagship products

- Regular Plan: 12 walks

- Active Plan: 20 walks

- Optional grooming credit

- Society resident pricing

A current provider publicly advertises monthly Pune walking plans, including separate pricing for 20- and 40-minute walks. Customers can therefore compare unit price, making transparent value and service quality especially important.

Corrected cluster rollout

Cluster 1A: Baner–Balewadi

A coherent apartment and premium-residential cluster.

Cluster 1B: Wakad

Operate Wakad separately until measured travel-time and route data prove it can share capacity with Baner–Balewadi.

The delayed approach connection to the Balewadi–Wakad bridge illustrates why apparently adjacent neighbourhoods should not automatically be treated as one reliable service route.

Cluster 2: Kharadi–Viman Nagar

- Kharadi

- Viman Nagar

- Selected Kalyani Nagar coverage only when capacity permits

Cluster 3A: Hinjawadi

Cluster 3B: Pimple Saudagar

Do not assume one walker pool can efficiently cover both during peak periods.

Cluster 4A: Aundh

Cluster 4B: Koregaon Park

These are distinct micro-markets and should not share operational capacity by default.

Pune recorded a 71.1% average congestion level in 2025, with a 10 km trip averaging more than 33 minutes. That strongly supports micro-cluster operations.

Acquisition sequence

- Apartment and RWA partnerships

- Starter pack after a successful walk

- Grooming and preventive-care camps

- Resident referrals

- Local search campaigns

- IT-employer discount pilot later

Student caregiver strategy

Do not assume student availability equals reliable supply.

Students should pass the same:

- Identity and document checks

- Practical assessment

- Schedule commitment

- Backup process

- Report-quality requirement

Track exam periods, relocations and semester breaks as supply risks.

Pricing position

Use:

Managed-value care

rather than:

- Cheapest walker

- Luxury-only care

Show:

- Effective cost per walk

- What backup coverage includes

- Rollover limits

- Report proof

- Society-density discount

Main risk

Price comparison combined with traffic-heavy fulfilment.

Control

- 12-walk entry product

- Smaller downgrade option

- Cluster density discount

- Transparent per-walk economics

- Separate east and west Pune operations

Pune decision

GO, but separate Wakad, Hinjawadi, Aundh and Koregaon Park from the broader clusters proposed.

8. Mumbai strategy

Recommended positioning

Premium pet care delivered by walkers and sitters who operate within your locality.

Recommended hero

A trusted local caregiver—not someone travelling across Mumbai.

Flagship products

- 12-walk local routine

- 20-walk premium local plan

- At-home grooming

- Pet sitting where building and provider controls are proven

Current Mumbai providers already advertise monthly dog-walking plans. The defensible premium is therefore not simply a monthly subscription; it is locality-level reliability, better building access and low reassignment friction.

Corrected cluster rollout

Cluster 1: Powai

- Hiranandani Gardens

- Powai

- Selected Chandivali coverage

- Nearby societies only

Cluster 2: Bandra–Khar

Cluster 3: Andheri West–Juhu

Cluster 4: Lower Parel–Worli

Cluster 5: Thane premium micro-market

Treat Thane as a separate city operation or satellite market with:

- Its own manager or lead

- Own pricing

- Own partner pool

- Own P&L

- Own backup system

Do not use walkers from the main Mumbai clusters as routine Thane backup.

Mumbai’s average congestion level was 63.2% in 2025, and a 10 km drive averaged nearly 29 minutes. I therefore recommend travel-time polygons rather than a single universal 1–2 km radius.

Radius rule

Use:

- 1–2 km during the most congested periods where density permits

- 2–4 km during off-peak periods

- Same-building or same-society route blocks

- Maximum service-to-service travel-time limits

A fixed radius should not replace actual route-time data.

Acquisition sequence

- Building and society referrals

- Premium resident champions

- Locality-specific Google Search

- Grooming-to-walking cross-sell

- Existing-customer referrals

- Limited Instagram campaigns

Service priorities

- Walking

- Pet sitting

- Grooming at home

- Vet coordination

- Boarding only after host/facility controls are proven

Do not lead with home boarding merely because customer spending is high. Validate building restrictions, host capacity, escape prevention and emergency procedures first.

Main risk

Small operational delays can rapidly invalidate a premium promise.

Control

- Exact locality pages

- No cross-city provider matching

- Realistic arrival windows

- Local primary and backup pools

- Building-access records

- Stop-sales rules by peak window

Mumbai decision

GO later, after the first cities have mature routing, backup and support systems.

9. Gurugram strategy

Recommended positioning

Verification-led premium pet care built for gated communities.

Recommended hero

Society-approved caregivers, documented visits and dependable support.

Flagship offer

Premium Society Care Plan

- Walking subscription

- Preferred walker and approved backup

- Gate protocol

- Priority administrative support

- Grooming or training benefits

- Urgent-care coordination

- Monthly resident report

Existing providers already market monthly walking plans in Gurugram, so verification language must connect to real operational proof rather than decorative badges.

Corrected cluster rollout

Cluster 1A: DLF Phase 1–2

Cluster 1B: DLF Phase 5 and Golf Course Road

Cluster 2: Sectors 53–57

- Sector 56

- Sector 57

- Selected adjoining communities

Cluster 3: Sohna Road

Cluster 4: New Gurugram

New Gurugram should be treated as a separate operating corridor, not as spare capacity from Golf Course Road.

Golf Course Road and the adjoining sectors contain established premium residential areas, but they also face peak traffic constraints. Route and gate-entry measurements remain essential despite geographic proximity.

Verification message

Display:

- Identity checked

- Documents current

- Practical assessment completed

- Society entry approved

- Background check type and date

- Completed services

- Reliability

- Rating

Do not imply that payment for a membership or listing creates a safety credential.

Emergency message

Use:

Urgent-care coordination and verified clinic directory

Not:

Emergency treatment included

Acquisition sequence

- Facility manager and RWA agreements

- Society-approved provider lists

- Resident onboarding session

- Grooming and training events

- Walking-plan conversion

- Corporate benefits after society operations are stable

AWBI maintains guidance covering pet owners, caregivers, RWAs and apartment associations. Society messaging should emphasise responsible coexistence and workable access—not imply that the platform supports unreasonable pet restrictions.

Main risk

Trust claims that are stronger than the verification process.

Control

- Exact badge definitions

- Verification dates

- No paid safety badges

- Independent incident review

- Society-specific gate SOP

- Centralised verification standard

Gurugram decision

GO when society sales capability and verification operations are already mature.

10. Ahmedabad strategy

Recommended positioning

Trusted local pet caregivers for Ahmedabad families and apartment communities.

Recommended hero

Familiar local care, verified and documented every visit.

Flagship products

- Starter Plan: 8 walks

- Regular Plan: 12 walks

- Society resident plan

- Assisted renewal

- Grooming and care camps

Monthly walking services are already publicly promoted in Ahmedabad, including lower-priced recurring plans. A new brand therefore needs to justify “accessible premium” through trust, backup coverage, reports and local support.

Corrected cluster rollout

Cluster 1: Bopal corridor

- Bopal

- South Bopal

- Ambli

- Selected Shilaj coverage when viable

Cluster 2: Satellite–Prahlad Nagar

Cluster 3: SG Highway–Thaltej

Cluster 4: Vastrapur–Bodakdev

Cluster 5: Motera–Chandkheda

The north-city cluster requires its own supply and should not depend on west-Ahmedabad backup providers.

Ahmedabad’s 2025 residential market remained relatively affordable among large cities while higher-value demand increased around corridors such as SG Highway and SP Ring Road. This supports testing both accessible plans and premium micro-markets rather than one uniform city price.

Acquisition sequence

- Veterinary and grooming referrals

- Apartment/society partnerships

- Resident WhatsApp groups with approval

- Pet-care camps

- Local pet shops

- Customer referrals

- Search advertising after cluster demand is validated

Language strategy

Start with:

- English

- Hindi

- Gujarati-assisted WhatsApp and support

A full Gujarati app translation can follow measured demand, but essential information—price, cancellation, safety and support—should be understandable from the launch stage.

Support model

Offer:

- Assisted booking

- Manual renewal fallback

- WhatsApp support

- Call support for first-time users

- Simple plan comparison

WhatsApp marketing and renewal communication should follow clear opt-in and purpose-specific messaging. Customer data and recurring home schedules should also use purpose-limited access under the evolving DPDP framework.

Main risk

Building too much digital automation before local customers and partners consistently use it.

Control

- Assisted onboarding

- Smaller plans

- One clear CTA

- Human-supported first booking

- Society-led trust

- Automate only proven workflows

Ahmedabad decision

Strong GO for a Gujarat-first expansion model.

11. Surat strategy

Recommended positioning

Simple, trusted pet-care support for Surat families and society residents.

Recommended hero

Local pet care your family and society can trust.

Flagship entry offer

- One trial service

- 8-walk starter plan

- Pet-sitting pack

- Society resident benefits

- Manual renewal option

Existing marketplaces list walking, boarding, grooming and sitting options in Surat, which shows some provider/category presence. It does not prove that recurring digital subscriptions will convert at Bengaluru-style rates.

Corrected cluster rollout

Cluster 1: Vesu–Piplod

Cluster 2: City Light–Ghod Dod Road

Cluster 3: Adajan–Pal

Cluster 4: Adjacent areas based on proven lead and supply density

This is more operationally coherent than launching:

- Vesu–City Light

- Then Adajan–Pal

- Then Ghod Dod

- Then Piplod

as four disconnected marketing stages.

Current property-market sources consistently identify Vesu, Piplod, City Light, Ghod Dod, Adajan and Pal as significant apartment or premium residential areas, but property values should be treated only as a targeting signal—not proof of pet-service conversion.

Service priorities

- Walking

- In-home pet sitting

- Grooming camps

- Society care events

- Boarding beta only after strict host inspection

Your proposed focus on sitting and boarding should be modified:

Lead with walking and sitting; keep boarding controlled until custody and host-quality processes are proven.

Acquisition sequence

- Society events

- Veterinary and pet-shop partnerships

- Trusted local referrals

- Resident champions

- Gujarati/Hindi WhatsApp support

- Assisted booking

- Hyperlocal search after service education

Education content

Explain:

- Why verification matters

- How a walk report works

- What a service credit is

- How preferred caregivers work

- What backup coverage means

- How payment and cancellation work

Main risk

Acquiring broad awareness before the category and supply system are ready.

Control

- One or two clusters

- Low-commitment starter plans

- Society demonstrations

- Human-assisted bookings

- Referral-first growth

- No major city-wide ad campaign during education

Surat decision

GO as Ahmedabad’s adjacent replication city, not as a direct metro-style digital launch.

12. Corrected city rollout matrix

| City | First operational cluster | Second cluster | Flagship offer | Primary channel |
| --- | --- | --- | --- | --- |
| Bengaluru | Whitefield–Brookefield | HSR, separately Bellandur | 20-walk routine | App/search/societies |
| Pune | Baner–Balewadi | Wakad separately; Kharadi–Viman Nagar | 12/20 walks | Societies/referrals |
| Mumbai | Powai–Chandivali | Bandra–Khar | Hyperlocal premium walking | Building referrals/search |
| Gurugram | DLF/Golf Course micro-zones | Sectors 53–57 | Society premium desk | RWA/facility managers |
| Ahmedabad | Bopal–South Bopal–Ambli | Satellite–Prahlad Nagar | 8/12 walks | Society/WhatsApp/referrals |
| Surat | Vesu–Piplod | City Light–Ghod Dod | Starter family plan | Events/referrals |

13. Local marketing framework

Each city should use the same funnel.

Local awareness

↓

Trust proof

↓

Trial booking

↓

Service report

↓

Starter pack

↓

Recurring plan

↓

Referral or society expansion

Awareness content

- “Available in your area”

- Provider introduction

- Society event

- Local customer story

- Care-education content

Trust content

- Verification process

- Real report-card example

- Live tracking demonstration

- Backup process

- Local support

- Incident and complaint process

Conversion content

- Trial

- Starter pack

- Effective per-service cost

- Availability

- Cancellation terms

- Preferred-caregiver explanation

Retention content

- Monthly report

- Credit balance

- Schedule confirmation

- Grooming reminder

- Pause option

- Referral prompt

14. Local proof hierarchy

Use the strongest proof available in this order:

- Completed local services

- Local repeat customers

- Local verified reviews

- Local society partnerships

- Local provider fulfilment data

- Local service capacity

- National brand statistics

Do not make a new Surat page appear trusted by displaying only Bengaluru volume.

Use:

18 verified caregivers available in Vesu and Piplod.

rather than:

5,000 providers nationwide.

The local customer needs evidence that their booking can be fulfilled in their neighbourhood.

15. Brand and claims governance

Create a national claim registry.

| Claim | Evidence required |
| --- | --- |
| Verified sitter | Verification records |
| Background checked | Check type and completion date |
| Live tracking | Working product capability |
| Same-walker support | Continuity metrics and backup process |
| 24/7 support | Staffed service with documented SLA |
| Emergency support | Exact coordination scope |
| Best rated | Reliable comparative evidence |
| Starting at ₹X | Real bookable service at that price |
| Available in city | At least one active bookable zone |

Consumer-protection guidance prohibits deceptive interface and advertising practices. Claims, prices and availability must match the real product and should not use false urgency or misleading service badges.

16. Local social-media architecture

Early city

Use:

- One national account

- City-specific content series

- Local geo-targeted advertising

- Local landing pages

- City-tagged highlights

- Local testimonial library

Mature city

Consider a city-specific account only when the city has:

- Dedicated marketing owner

- Regular local events

- Sufficient content

- Local response capacity

- Strong follower demand

Do not create six mostly inactive city accounts.

Recommended content labels:

- Bengaluru Care Stories

- Pune Society Pets

- Mumbai Local Walkers

- Gurugram Verified Care

- Ahmedabad Pet Families

- Surat Society Care

17. Brand performance dashboard

Track by city:

Awareness

- Qualified reach

- Local page visits

- Search impressions

- Cost per qualified lead

- Society registrations

Trust

- Profile-to-booking conversion

- Verification-page views

- Report-card views

- Trial completion

- Review volume

Conversion

- Trial-to-starter conversion

- Starter-to-subscription conversion

- CAC

- Plan conversion

- Lead response time

Delivery

- Completion

- On-time rate

- Preferred-caregiver fulfilment

- Backup fulfilment

- Report completion

Retention

- Repeat rate

- Subscription renewal

- Pause

- Downgrade

- Churn

- Referral

Economics

- GMV

- Platform revenue

- Contribution

- CAC payback

- Support cost

- Refund cost

18. City-brand launch gate

Do not publish a public “Now live” campaign until:

| Requirement | Target |
| --- | --- |
| Supported clusters | Clearly configured |
| Active caregivers | 5–8 minimum per launch cluster |
| Peak-time backups | 2–3 |
| Trial customers | 20–40 |
| Completed beta services | 50+ |
| Rating | 4.6+ |
| Completion | 95%+ |
| No-show | Below 1% |
| Local support | Operational |
| Local urgent-care directory | Verified |
| Price and cancellation terms | Published |
| City-specific reviews | Available |
| Critical incidents | Zero unresolved |

Until then, use:

Join the [city] waitlist

rather than:

Book now across [city].

Final decisions

| Proposal | Decision |
| --- | --- |
| One national brand | Approve |
| Local city messaging | Approve |
| Core verification promise | Approve with exact badge definitions |
| Live updates and report cards | Approve; increasingly table stakes in metros |
| “Emergency support” | Rename urgent-care coordination |
| Bengaluru app-first positioning | Approve |
| Pune value-led plans | Approve |
| Mumbai hyperlocal premium model | Approve |
| Gurugram verification/society model | Approve |
| Ahmedabad family/local-trust position | Approve |
| Surat society/family position | Approve as an education-led launch |
| Premium same-sitter guarantee | Reject; use preferred-caregiver continuity |
| All listed areas as large combined clusters | Modify into smaller micro-markets |
| City-wide availability claims | Reject until operationally true |
| City-specific social accounts immediately | Defer |
| Boarding as an early Surat priority | Keep controlled beta only |

Final brand system

National brand

“Verified local pet care, documented every visit.”

Bengaluru

App-first recurring care

Pune

Reliable value-led apartment care

Mumbai

Hyperlocal premium reliability

Gurugram

Verification-led society care

Ahmedabad

Trusted accessible family care

Surat

Simple society-first local care

Phase 10 brand win condition

Customers recognise one trusted national company, while every city page, offer, provider pool and service promise feels genuinely local and is supported by real operational capacity.

Multi-City Brand Strategy: APPROVED—with one master brand, smaller service clusters, evidence-based local claims and no city-wide marketing ahead of fulfilment.

Phase 10: Six-Month Multi-City Expansion Plan 🌍🐾

End-to-End City 2 and City 3 Execution Blueprint

Executive verdict

Approve the six-month structure, but treat it as a controlled replication programme—not a commitment to fully scale two cities within six months.

A realistic Month 6 outcome is:

- City 1: mature and operating independently

- City 2: validated, with one or two stable clusters

- City 3: closed beta or early public launch

- National system: shared dashboards, SOPs, finance controls and quality standards

The plan should not force City 3 forward merely because the calendar reaches Month 4. City 3 preparation begins only after City 2 passes defined quality, supply and economic gates.

India’s pet-care category is growing, supported by pet humanisation, increasing consumer spending and expanding digital discovery. That creates a favourable market backdrop, but it does not eliminate the need for local density and reliable fulfilment.

Correct expansion sequence

City 1 readiness

↓

City 2 demand and supply validation

↓

City 2 closed beta

↓

City 2 quality and contribution gate

↓

City 3 preparation

↓

City 3 closed beta

↓

Network operating-system review

Critical changes to your original plan

1. Launch the City 2 landing page earlier

Do not wait until Week 8.

A waitlist-oriented page should go live during Weeks 2–3 to collect:

- Qualified leads

- Service requirements

- Areas

- Preferred schedules

- Pet profiles

- Price sensitivity

- Society information

Week 8 should upgrade the page from a research page into a launch-ready local page with verified services, prices and supported areas.

2. Do not treat 100 sitter applications as the Month 2 success metric

Applications are only top-of-funnel activity.

A healthier target is:

| Supply stage | Month 2 target |
| --- | --- |
| Applications | 50–100 |
| Contact screened | 30–60 |
| Documents verified | 15–30 |
| Practical trial passed | 10–20 |
| Launch-active providers | 8–15 |
| Usable backup providers | 3–5 |

Ten schedulable, trained providers are more valuable than 100 inactive applicants.

3. Do not require ten vet/groomer partners before beta

A better launch pool is:

- 3–5 reliable groomers

- 2–5 verified veterinary referral options

- 2–4 trainers only where training is launching

- Boarding providers only after inspections and custody controls pass

The city does not need a large directory. It needs a small, reliable local network.

4. Do not launch subscriptions automatically in Week 11

Subscriptions require:

- Successful individual services

- Positive ratings

- Repeat demand

- Stable primary and backup capacity

- Credit tracking

- Renewal, pause and cancellation controls

In a new city, Week 11 should begin with starter packs. Monthly subscriptions should launch only to customers with established usage and only in clusters with reserved capacity.

5. City 3 must be gated

City 3 preparation should be blocked unless City 2 has:

- 95%+ service completion

- 4.6+ rating

- Below 1% provider no-show

- Below 5% refunds or disputes

- Working backup coverage

- No unresolved critical incident

- Positive or clearly improving contribution

- A local operator who can run City 2 without founder firefighting

Month 1: Expansion Readiness

Weeks 1–4

Week 1: Analyse City 1 performance

Objective

Determine whether the existing city is genuinely replicable.

Do not examine only revenue and total bookings. Review five dimensions:

Demand

- Monthly completed services

- Monthly paying customers

- Repeat-customer rate

- Subscription adoption

- Society-origin demand

- Organic and referral demand

Supply

- Active walkers and sitters

- Verified provider bench

- Peak-time capacity

- Backup coverage

- Provider cancellation

- Provider no-show

- Provider retention

Quality

- Average rating

- Completion rate

- On-time rate

- Refunds

- Complaints

- Serious incidents

- Report completion

Economics

- Customer GMV

- Platform revenue

- Partner payouts

- Contribution per booking

- Contribution per subscriber

- CAC and payback

- City operating contribution

Replicability

- Founder intervention

- Manual scheduling

- Support dependence

- Payout reconciliation

- Training repeatability

- Incident-response maturity

Week 1 deliverable

City 1 Expansion Readiness Report

| Requirement | Suggested gate |
| --- | --- |
| Monthly completed services | 1,000+ |
| Monthly paying customers | 300–500+ |
| Repeat rate | 35%+ |
| Active subscribers | 50–100+ |
| Completion | 95%+ |
| On-time performance | 95%+ |
| Rating | 4.6+ |
| Provider no-show | Below 1% |
| Refund/dispute | Below 3–5% |
| Positive contribution | Three consecutive months |
| Critical unresolved incidents | Zero |
| Founder-dependent fulfilment | Below 5–10% |

Week 1 decision

- Pass: proceed with City 2 selection

- Conditional pass: repair specific non-critical gaps

- Fail: continue strengthening City 1

Week 2: Finalise the expansion city

Objective

Select City 2 using evidence rather than prestige or population.

City-selection scorecard

| Factor | Weight |
| --- | --- |
| Qualified demand/waitlist | 15 |
| Local founder or operator network | 15 |
| Sitter supply potential | 15 |
| Apartment/society density | 12 |
| Projected contribution | 12 |
| Available city leader | 10 |
| Traffic and cluster feasibility | 8 |
| Existing competition | 5 |
| Grooming/vet ecosystem | 4 |
| Local compliance readiness | 4 |

Required research

- Existing customer requests

- Local service prices

- Competitor coverage

- Society interviews

- Sitter interviews

- Traffic and route analysis

- Local language requirements

- Emergency veterinary coverage

- Three-year demand hypothesis

- Ninety-day financial forecast

Traffic is a material operating constraint. In 2025, TomTom reported average congestion of 74.4% in Bengaluru, 71.1% in Pune and 63.2% in Mumbai, supporting small service clusters rather than city-wide provider matching.

Week 2 deliverables

- Selected City 2

- Two target launch clusters

- City scorecard

- Competitor map

- Local pricing hypothesis

- Ninety-day P&L forecast

- Risk register

- Go/hold decision

Week 3: Hire or appoint the City 2 launch owner

Objective

Create clear local accountability.

At this stage, the role may be:

- Dedicated city manager

- City launch manager

- Strong operations lead who becomes city manager after validation

Required competencies

- Local network and geography knowledge

- Marketplace or field-operations experience

- Recruitment capability

- Customer problem resolution

- Society relationship management

- Basic financial ownership

- Incident-management discipline

- Data and dashboard literacy

Thirty-day objectives for the city lead

- Finalise service clusters

- Validate 100–200 qualified leads

- Recruit the first supply funnel

- Meet five or more society decision-makers

- Map emergency veterinary options

- Configure local prices

- Build the beta operating roster

Week 3 deliverables

- Named accountable launch owner

- Role scorecard

- Thirty-, sixty- and ninety-day objectives

- Escalation framework

- Hiring plan for the launch pod

- Compensation tied to quality and contribution—not bookings alone

Week 4: Build the City 2 launch list

Objective

Create a structured launch pipeline covering demand, supply and partners.

Society list

For each society record:

- Number of households

- Estimated pet households

- Decision-maker

- Current pet-care demand

- Gate requirements

- Event interest

- Pilot status

- Next action

- Account owner

Recommended pipeline:

- 20–40 societies identified

- 8–12 contacted

- 5–10 decision-maker meetings

- 2–5 pilot-ready societies

Sitter pipeline

Capture:

- Area

- Availability

- Experience

- Services

- Travel radius

- Documents

- Trial status

- Expected payout

- Morning/evening availability

- Backup capability

Partner pipeline

Capture:

- Groomers

- Veterinary clinics

- Home-visit vets

- Trainers

- Pet shops

- Boarding operators

- Event partners

Week 4 deliverable

City 2 Launch CRM

Qualified customers

Society pipeline

Sitter pipeline

Add-on partners

Emergency partners

Local influencers/referrers

Corporate prospects

Month 2: City 2 Preparation

Weeks 5–8

Week 5: Recruit sitters and walkers

Objective

Build a wide enough applicant funnel to produce 8–15 launch-active providers.

Recruitment channels

- Local pet-parent communities

- Veterinary and grooming referrals

- Existing provider referrals

- College/community networks

- Local job platforms

- Society resident groups

- Professional walkers

- Animal-welfare communities, where appropriate

Recruitment message

The proposition should clearly state:

- Service types

- Expected service areas

- Earnings structure

- Verification requirements

- Training requirements

- Payout schedule

- Behaviour and safety standards

- No guaranteed booking promise

Funnel target

| Stage | Target |
| --- | --- |
| Applications | 50–100 |
| Screened | 30–60 |
| Qualified for verification | 20–40 |

Week 5 deliverables

- Applicant funnel

- Recruitment-channel performance

- Estimated activation cost per provider

- Cluster-level availability map

- Peak-window supply gap report

Week 6: Verify and train providers

Objective

Convert applicants into safe, active and schedulable supply.

Verification workflow

Application

↓

Phone screening

↓

Identity and document review

↓

Reference/background process

↓

Practical handling assessment

↓

Training

↓

Supervised trial

↓

Cluster and service assignment

Training topics

- Safe pet handling

- Leash and gate procedures

- Handover

- Check-in and reporting

- Pet escape prevention

- Bite and aggression escalation

- Customer communication

- Data and access confidentiality

- Cancellation and leave procedure

- Incident reporting

Month 2 supply target

| Supply state | Target |
| --- | --- |
| Document verified | 15–30 |
| Trial passed | 10–20 |
| Launch-active | 8–15 |
| Backup-capable | 3–5 |
| Peak-slot coverage | 90%+ of planned beta demand |

If the business is classified as a covered aggregator under India’s current platform-worker framework, it should assess and operationalise applicable eShram onboarding and electronic worker-reporting obligations. The Labour Ministry issued specific aggregator onboarding directions in June 2026.

Week 6 deliverables

- Approved provider roster

- Backup roster

- Capacity by day/time

- Provider payout model

- Training completion records

- Document-expiry dashboard

Week 7: Onboard grooming and veterinary partners

Objective

Build a small partner network that supports trust and follow-on services.

Recommended targets

Grooming

- 3–5 launch-ready partners

- Package prices

- Home-visit radius

- Hygiene checklist

- Cancellation policy

- Before/after reporting

- Backup arrangement

Veterinary coordination

- 2–5 verified local options

- Clinic hours

- Contact numbers

- Emergency/after-hours status

- Home-visit availability

- Teleconsult availability

- Last verification date

Boarding

Launch only when:

- Facility or home inspection passed

- Escape controls are verified

- Capacity is defined

- Vaccination policy exists

- Emergency protocol exists

- Customer and provider responsibilities are documented

Week 7 deliverables

- Local partner directory

- Service permissions

- Commercial terms

- Escalation directory

- Partner scorecards

- Deferred-services list

Week 8: Launch the City 2 local page

Objective

Move from demand research into controlled public visibility.

The page should show

- Exact active or upcoming neighbourhoods

- Services available at launch

- Starting prices

- Waitlist versus bookable status

- Verification process

- Local support contact

- Launch offer

- Local FAQs

- Society programme

- Urgent-care directory

Important accuracy rule

Do not claim:

“Now available across Pune.”

when only Baner and Balewadi are operational.

Use:

“Launching in Baner, Balewadi and selected nearby societies.”

Week 8 targets

- 150–300 qualified leads

- 20–40 paid trial bookings or refundable deposits

- 2–5 society pilots

- Demonstrated price acceptance

- Beta schedule at 50–70% of safe capacity

Privacy requirement

The city waitlist, pet profiles, customer addresses and provider records should use clear notices, purpose-limited access and city-scoped permissions. India’s DPDP Rules were notified in November 2025 with phased commencement, making it prudent to build full data controls before—not after—multi-city scale.

Month 3: City 2 Controlled Launch

Weeks 9–12

Week 9: Soft launch

Objective

Complete the first controlled paid services.

Beta cohort

- Waitlisted customers

- Society residents

- Referrals

- Existing customers relocating to the city

- Employees or trusted community groups

Geography

- One or two clusters

- Limited operating hours

- Limited services

- Explicit capacity limits

Beta targets

| Metric | Target |
| --- | --- |
| Paying customers | 30–75 |
| Completed services | 50–150 |
| Rating | 4.6+ |
| Completion | 95%+ |
| On-time | 95%+ |
| Provider no-show | Below 1% |
| Refund/dispute | Below 5% |
| Critical preventable incidents | Zero |

Daily operating review

- Unassigned bookings

- Late check-ins

- Backup requirements

- Missing reports

- Complaints

- Refunds

- Capacity

- Partner earnings

- Customer rating

Week 10: Society outreach and pilots

Objective

Convert society interest into operating pilots.

Recommended target

- 5–10 decision-maker meetings

- 2–5 signed pilots

- 1–3 active pilots during Month 3

Five to ten active pilots may be too much for a newly launched team.

Pilot structure

- Society landing page

- Resident registration

- Gate-entry SOP

- Approved provider roster

- Trial/starter offer

- One event or orientation

- Pilot report

- Commercial conversion discussion

Week 10 deliverables

- Signed pilot agreements

- Resident leads

- Gate protocols

- Pilot calendar

- RWA escalation contacts

- Society conversion funnel

Week 11: Introduce starter packs and limited subscriptions

Objective

Convert successful repeat users—not first-time users.

Customer sequence

Successful first service

↓

Positive report and rating

↓

3- or 5-service starter pack

↓

Repeated successful fulfilment

↓

12- or 20-walk subscription

Subscription eligibility

- At least 3–5 completed walks

- Rating of four or five

- No unresolved complaint

- Demonstrated recurring need

- Primary and backup capacity available

- Credit ledger working

- Pause and cancellation working

Recommended Week 11 output

- 10–25 starter-pack customers

- 5–15 early subscription customers

- 100% of subscriptions assigned primary and backup coverage

- No subscription sales in saturated slots

Cancellation must remain easy. Indian dark-pattern guidance specifically identifies hidden or unnecessarily complex subscription cancellation as a prohibited subscription-trap pattern.

Week 12: Review and stabilise City 2

Objective

Decide whether City 2 is ready for continued growth.

City 2 review

Demand

- Paying customers

- Completed services

- Repeat intent

- Starter-pack conversion

- Society leads

Supply

- Active providers

- Acceptance rate

- Capacity

- Backup coverage

- Provider earnings

Quality

- Completion

- On-time performance

- Rating

- Reports

- Complaints

- Incidents

Economics

- GMV

- Platform revenue

- Partner payouts

- Direct contribution

- CAC

- Support and refund cost

City 2 stability decision

| Result | Decision |
| --- | --- |
| Quality and economics strong | Prepare City 3 |
| Quality strong, economics weak | Improve density or pricing |
| Demand strong, supply weak | Freeze acquisition |
| Supply strong, demand weak | Reduce provider expansion |
| Complaints high | Freeze growth |
| Critical incident unresolved | Stop expansion |

Month 4: City 2 Optimisation and City 3 Preparation

Weeks 13–16

Week 13: Improve City 2 operations

Objective

Repair weaknesses before management attention is divided.

Likely optimisation areas

- Reduce provider travel radius

- Change operating clusters

- Improve backup availability

- Refine prices

- Retrain low-performing providers

- Improve support scripts

- Remove weak services

- Improve society conversion

- Fix missing report cards

- Strengthen failed-payment handling

Week 13 exit gate

City 3 work proceeds only if City 2 reaches:

| Metric | Required |
| --- | --- |
| Completion | 95%+ |
| On-time | 95%+ |
| Rating | 4.6+ |
| No-show | Below 1% |
| Refund/dispute | Below 5% |
| Backup coverage | 90–95%+ |
| Critical unresolved incidents | Zero |
| Direct contribution | Positive or improving credibly |
| Named local owner | Operating independently |

Week 14: Select City 3

Objective

Run a fresh scorecard—not automatically choose the next city from a predetermined list.

City 3 should ideally test one of two things

Adjacent replication

Example:

Ahmedabad → Surat

This tests whether the playbook can spread efficiently using regional knowledge.

Different-market replication

Example:

Ahmedabad → Pune
Bengaluru → Hyderabad

This tests whether the model works beyond the original network and customer profile.

Week 14 deliverables

- City 3 scorecard

- Two proposed clusters

- Local leader shortlist

- Demand and supply forecast

- Compliance register

- Ninety-day P&L

- Go/hold decision

Week 15: Hire or appoint City 3 lead

Objective

Establish ownership before recruitment and partnerships expand.

Required Week 15 outputs

- Named City 3 lead

- Objectives

- City launch calendar

- Hiring needs

- Society target list

- Provider recruitment strategy

- Local emergency directory plan

- Dashboard access and permissions

Week 16: Build City 3 supply and demand lists

Objective

Prepare City 3 without weakening City 2.

City 3 launch-list targets

- 100–200 qualified customer leads

- 20–40 target societies

- 50–100 sitter applicants in pipeline

- 10–20 groomer/vet/trainer prospects

- Two launch clusters

- Local prices

- Operating-hour hypothesis

Month 4 management rule

City 2 team should not be reassigned to City 3 routinely.

Shared central functions may support both, but:

- Provider pools

- City operations

- Support ownership

- Incidents

- P&L

must remain separate.

Month 5: City 3 Controlled Launch

Weeks 17–20

Week 17: Recruit and activate supply

Target funnel

| Stage | Target |
| --- | --- |
| Applications | 50–100 |
| Screened | 30–60 |
| Verified | 15–30 |
| Trial passed | 10–20 |
| Launch-active | 8–15 |
| Backup-capable | 3–5 |

Output

- Active roster

- Capacity map

- Peak-slot coverage

- Backup coverage

- Provider training records

- Partner payout model

Week 18: Society partnerships and local demand

Objective

Build trust before public advertising.

Outputs

- 5–10 society meetings

- 2–5 pilot-ready societies

- Local event calendar

- Resident waitlist

- Gate procedures

- Referrer network

- Local landing page

Week 19: Controlled bookings

Objective

Run a City 3 closed beta.

Target

- 30–75 paying customers

- 50–150 completed services

- 4.6+ rating

- 95%+ completion

- 95%+ on-time performance

- Below 1% no-show

- Zero critical preventable incidents

Daily monitoring

- Booking assignment

- Check-in

- Travel delay

- Backup use

- Report completion

- Incident flags

- Customer satisfaction

- Provider payout liability

Week 20: Starter-pack and retention push

The original “subscription push” is too early if Week 19 produced only the first bookings.

Use Week 20 to introduce:

- 3- or 5-walk starter packs

- Rebooking reminders

- Preferred-provider requests

- Society resident offers

- Grooming cross-sell

Monthly subscriptions should begin only for customers with demonstrated frequency.

Week 20 target

- 10–25 starter packs

- 5–15 subscription-ready customers

- High-frequency schedules checked against capacity

- No subscriptions without backup support

Month 6: Build the Multi-City Operating System

Weeks 21–24

Week 21: Compare City 1, City 2 and City 3

Objective

Create a common city scorecard.

City comparison

| Metric | City 1 | City 2 | City 3 |
| --- | --- | --- | --- |
| Stage |  |  |  |
| Completed services |  |  |  |
| Paying customers |  |  |  |
| Repeat rate |  |  |  |
| Rating |  |  |  |
| Completion |  |  |  |
| On-time rate |  |  |  |
| Active providers |  |  |  |
| Backup coverage |  |  |  |
| Subscription MRR | ₹ | ₹ | ₹ |
| Platform revenue | ₹ | ₹ | ₹ |
| Contribution | ₹ | ₹ | ₹ |
| Refund rate |  |  |  |
| Critical incidents |  |  |  |

Correct financial separation

Track:

- GMV

- Platform revenue

- Partner payouts

- Contribution 1

- City operating contribution

- Allocated central costs

Do not report total customer payments as platform revenue.

Week 22: Standardise the expansion playbook

Objective

Turn founder knowledge into a repeatable city manual.

Playbook chapters

- City selection

- Demand validation

- Service-cluster selection

- City hiring

- Sitter recruitment

- Verification and training

- Capacity planning

- Add-on partner onboarding

- Society acquisition

- Local pricing

- Closed-beta launch

- Subscription activation

- Customer support

- Incident management

- Payment and payout operations

- Privacy and access

- City P&L

- Cluster expansion

- City pause or exit

- Post-launch retrospective

Version control

Use:

City Launch Playbook v1.0

City 2 retrospective

City Launch Playbook v1.1

City 3 retrospective

City Launch Playbook v2.0

Week 23: Improve national and city dashboards

National command centre

- Cities by maturity stage

- Completed services by city

- Ratings by city

- On-time performance

- Provider reliability

- Refunds

- Incidents by severity

- Subscription MRR

- Society pipeline

- City contribution

- Capacity utilisation

City command centre

- Today’s bookings

- Unassigned services

- Active providers

- Peak-slot capacity

- Late check-ins

- Missing reports

- Open complaints

- Incidents

- Failed payments

- Partner payouts

- Subscription renewals

- Society pipeline

Required dashboard controls

- City-scoped access

- Drill-down queues

- Refresh timestamps

- Metric definitions

- Historical comparisons

- Audit trails

- Incident-severity separation

Week 24: Decide the next two cities

Objective

Do not automatically approve two further launches.

Classify the decision:

- Launch City 4

- Continue stabilising City 2

- Continue City 3 beta

- Expand clusters inside existing cities

- Pause expansion

- Exit a weak cluster

Next-city approval criteria

Network

- City 1 remains stable

- City 2 has validated at least one contribution-positive cluster

- City 3 has passed closed-beta quality gates

- Central support is not overloaded

- Finance can reconcile each city independently

- No critical unresolved incident

- Management bandwidth exists

City candidate

- 150–300 qualified leads

- 8–15 launch-ready providers forecast

- 2–5 society pilots

- Named city owner

- Viable pricing

- Two launch clusters

- Local compliance assessed

Six-month target state

City 1

| Metric | Target |
| --- | --- |
| Monthly completed services | 1,000+ |
| Repeat rate | 35–50% |
| Rating | 4.6+ |
| Completion | 95%+ |
| Positive city contribution | Yes |
| Founder dependency | Low |

City 2

| Metric | Target |
| --- | --- |
| Monthly completed services | 300–750 |
| Paying customers | 100–250 |
| Repeat rate | 25–40% |
| Active subscribers | 20–50 |
| Active providers | 10–25 |
| Positive cluster contribution | At least one cluster |
| Rating | 4.6+ |

City 3

| Metric | Target |
| --- | --- |
| Completed beta services | 50–200 |
| Paying customers | 30–100 |
| Active providers | 8–15 |
| Rating | 4.6+ |
| Completion | 95%+ |
| Critical preventable incidents | Zero |
| Public expansion readiness | Evaluated |

Six-month deliverables

| Deliverable | Required |
| --- | --- |
| City 1 readiness report | Yes |
| City-selection scorecards | Yes |
| City 2 local team | Yes |
| City 2 active provider pool | Yes |
| City 2 closed beta | Yes |
| City 2 P&L | Yes |
| City 2 society pilots | Yes |
| City 3 launch owner | Yes |
| City 3 active provider pool | Yes |
| City 3 controlled beta | Yes |
| National city dashboard | Yes |
| City command centre | Yes |
| Expansion playbook v2 | Yes |
| City-specific compliance registers | Yes |
| City-level finance reconciliation | Yes |
| Phase 11 recommendation | Yes |

Six-month go/no-go system

Continue expansion when

- City 1 remains stable.

- City 2 reaches validated-cluster status.

- City 3 beta quality is strong.

- Each city has independent ownership.

- Each city’s P&L reconciles.

- Provider payouts remain current.

- Central support meets its SLA.

- No critical safety or privacy issue remains open.

Slow expansion when

- City 2 demand is strong but capacity is weak.

- City 3 supply recruitment is delayed.

- Support workload rises sharply.

- City contributions remain negative but are improving.

- Society pilots do not convert.

- Subscriptions exceed backup capacity.

Stop new-city launches when

- Completion falls below 95%.

- Provider no-show exceeds 1%.

- Critical incidents are concealed or unresolved.

- Partner payouts are delayed.

- Customer refunds increase materially.

- City finance cannot reconcile payments.

- The founder is again personally coordinating daily bookings.

- Cross-city data access is uncontrolled.

Final approval

| Proposed month | Decision |
| --- | --- |
| Month 1 readiness | Approved |
| Month 2 City 2 preparation | Approved with smaller active-supply targets |
| Month 3 controlled launch | Approved |
| Subscription launch in Week 11 | Conditional—starter packs first |
| Month 4 City 3 preparation | Only after City 2 passes its gate |
| Month 5 City 3 launch | Approved as controlled beta |
| City 3 subscription push in Week 20 | Replace with retention/starter-pack push initially |
| Month 6 operating-system standardisation | Approved—mandatory |
| Decide next two cities in Week 24 | Evaluate, do not automatically approve |

Phase 10 win condition

At the end of six months, the business has reproduced its operating model in City 2, started proving it in City 3, and can compare demand, quality, supply, subscriptions and contribution across all cities without relying on founder firefighting.

Six-Month Phase 10 Expansion Plan: GO—with sequential city gates, starter packs before subscriptions, and City 3 blocked until City 2 demonstrates stable quality and viable economics.

Phase 10 City Budget, Ownership and Quality-Control System 🌍🐾

Executive decision

Your direction is correct:

- Start new cities lean.

- Keep the first major cities company-owned.

- Use franchise or operating partners only after safety and operating systems are mature.

- Standardise quality centrally while allowing controlled local commercial flexibility.

The proposed budget ranges are useful as initial planning estimates, but they currently understate several costs:

- Field operations support

- Verification and training

- Partner-payout working capital

- Refund and service-recovery reserves

- Legal, accounting and compliance

- Insurance

- Staff travel and local transport

- Central technology and support allocation

The recommended structure is:

Company-Owned City

↓

Lean Closed Beta

↓

Validated Cluster

↓

Controlled Growth Budget

↓

Contribution-Positive City

↓

Premium Scale Budget

Do not begin with the premium budget merely because the city is Bengaluru, Mumbai or Gurugram.

Part I — Lean City Launch Budget

1. Review of the proposed lean budget

| Cost item | Proposed range | Assessment |
| --- | --- | --- |
| City manager/operations | ₹40,000–₹1,00,000 | Plausible for one lead, but may exclude an operations assistant |
| Sitter recruitment | ₹10,000–₹30,000 | Low but possible for referral-led recruitment |
| Local marketing | ₹30,000–₹1,00,000 | Appropriate for one or two micro-markets |
| Society events | ₹20,000–₹75,000 | Appropriate if events are limited and pre-booked |
| Tools/operations | ₹10,000–₹30,000 | May exclude travel, communications and verification |
| Emergency buffer | ₹25,000–₹50,000 | Useful, but should be separated from working capital |
| Proposed monthly total | ₹1.35L–₹3.85L | Bare operating range, not total city funding requirement |

Current salary references show why the city-manager range is broad. Indeed reported an Indian operations-manager average of about ₹32,426 monthly in June 2026, while Glassdoor’s broader self-reported range is considerably higher, reflecting differences in seniority, city, team size and P&L responsibility. A genuine city general manager in Bengaluru or Mumbai will usually require a different budget from a junior launch coordinator.

2. Corrected lean monthly operating budget

A. City team

| Item | Recommended monthly budget |
| --- | --- |
| City manager/launch owner | ₹40,000–₹1,00,000 |
| Operations/onboarding generalist | ₹25,000–₹60,000 |
| Shared central support allocation | ₹10,000–₹30,000 |
| Team subtotal | ₹75,000–₹1,90,000 |

At the earliest stage, one experienced city manager may perform part of the operations role. Once the city exceeds approximately 150–300 monthly services, separate live operations from supply recruitment.

B. Supply recruitment and activation

| Item | Recommended monthly budget |
| --- | --- |
| Recruitment campaigns | ₹8,000–₹25,000 |
| Referral incentives | ₹5,000–₹15,000 |
| Document/background processes | ₹5,000–₹20,000 |
| Training and practical trials | ₹5,000–₹20,000 |
| Supply subtotal | ₹20,000–₹60,000 |

Do not measure recruitment success by applications alone.

The real metric is:

[
\text{Cost per activated provider}

\frac{\text{Recruitment and verification cost}}
{\text{Providers passing trial and accepting work}}
]

A city that spends ₹30,000 and activates ten dependable providers is healthier than one that spends ₹15,000 and produces 100 inactive applications.

C. Local customer acquisition

| Item | Recommended monthly budget |
| --- | --- |
| Local search/social advertising | ₹20,000–₹75,000 |
| Referral and starter offers | ₹5,000–₹25,000 |
| Content and local creative | ₹5,000–₹20,000 |
| Marketing subtotal | ₹30,000–₹1,20,000 |

Paid campaigns should be restricted to:

- Supported postcodes

- Active service clusters

- Available services

- Time windows with usable supply

- Areas below capacity limits

Do not pay for city-wide demand when operations cover only one locality.

D. Society partnerships and events

| Item | Recommended monthly budget |
| --- | --- |
| Small resident workshop | ₹5,000–₹15,000 |
| Grooming/training event | ₹10,000–₹30,000 |
| Larger society camp | ₹20,000–₹50,000 |
| Printing/announcements | ₹3,000–₹10,000 |

Recommended monthly planning range:

₹20,000–₹75,000

Every event should have a funnel:

Registrations

↓

Attendance

↓

Trial booking

↓

Completed service

↓

Starter pack

↓

Subscription

Do not evaluate events using attendance alone.

AWBI guidance covers pet owners, caregivers, RWAs and apartment associations. Society campaigns should support responsible coexistence and workable gate procedures, rather than allowing local sales teams to promise restrictions or rules inconsistent with national animal-welfare standards.

E. Tools and field operations

| Item | Recommended monthly budget |
| --- | --- |
| Communications and support tools | ₹5,000–₹15,000 |
| Local staff/provider travel | ₹5,000–₹20,000 |
| Verification and report tools | ₹3,000–₹10,000 |
| Coworking/storage, if needed | ₹0–₹20,000 |
| Central software allocation | ₹5,000–₹20,000 |
| Operations subtotal | ₹15,000–₹50,000 |

The platform should avoid a city office during closed beta unless there is a clear operational requirement.

F. Risk, refunds and working capital

These should be separate balances.

Service-recovery reserve

Used for:

- Provider replacement

- Customer refunds

- Goodwill credits

- Emergency transport coordination

- Immediate operational response

Recommended:

₹25,000–₹75,000 monthly reserve

Partner-payout working capital

Used when:

- Partner payouts are due before payment-provider settlement

- Refunds are pending

- Subscription revenue covers future services

- Society invoices have longer payment terms

Recommended:

At least two to four weeks of forecast partner payouts

Do not use the incident reserve to pay ordinary partner earnings.

3. Corrected lean-city monthly burn

| Category | Recommended monthly range |
| --- | --- |
| City team | ₹75,000–₹1,90,000 |
| Supply activation | ₹20,000–₹60,000 |
| Local marketing | ₹30,000–₹1,20,000 |
| Society/events | ₹20,000–₹75,000 |
| Tools and field operations | ₹15,000–₹50,000 |
| Compliance/accounting allocation | ₹10,000–₹35,000 |
| Service-recovery reserve | ₹25,000–₹75,000 |
| Recommended operating burn | ₹1.95L–₹6.05L/month |

The upper end assumes:

- A two-person city team

- Significant local advertising

- Multiple society activities

- Dedicated support allocation

- Higher travel or verification costs

A highly founder-assisted launch may operate near ₹1.5L–₹2.5L temporarily, but that should not be mistaken for a scalable city cost.

4. One-time launch setup

Budget separately for:

| One-time item | Planning range |
| --- | --- |
| Hiring and recruitment setup | ₹25,000–₹75,000 |
| Provider verification/trials | ₹25,000–₹1,00,000 |
| Local page and creative localisation | ₹20,000–₹75,000 |
| Contracts/legal/accounting setup | ₹25,000–₹1,00,000 |
| Launch material and society kit | ₹20,000–₹75,000 |
| Initial incident and refund reserve | ₹50,000–₹1,50,000 |
| One-time setup | ₹1.65L–₹5.75L |

5. Recommended six-month lean-city funding

Using the corrected model:

[
\text{Six-month cash requirement}

\text{Setup}
+
6 \times \text{Monthly burn}
+
\text{Payout working capital}
]

Practical planning envelope

| Launch style | Six-month ring-fenced cash |
| --- | --- |
| Very lean adjacent-city beta | ₹12L–₹18L |
| Standard controlled city launch | ₹18L–₹30L |
| Higher-cost metro lean launch | ₹25L–₹40L |

This excludes major central product-development costs.

Spending rule

Do not release the entire budget on Day 1.

Use staged tranches:

20% — Market validation and hiring

25% — Supply activation

25% — Closed beta

20% — Validated-cluster growth

10% — Contingency

Part II — Premium City Launch Budget

6. What “premium launch” should mean

A premium budget should buy genuine capacity and operational capability:

- Full city launch team

- Multiple active clusters

- Strong customer acquisition

- Dedicated society sales

- Local support

- Provider training and quality audits

- Events

- Backup supply

- Faster service recovery

It should not simply mean spending ₹10 lakh monthly on advertising.

7. Review of the premium budget

| Cost item | Proposed range | Assessment |
| --- | --- | --- |
| Full city team | ₹2L–₹5L/month | Plausible for a 5–8-person mixed team |
| Marketing | ₹2L–₹10L/month | Too broad without CAC and capacity gates |
| Events/societies | ₹1L–₹5L | Appropriate only with multiple active clusters |
| Operations buffer | ₹1L–₹3L | Necessary, but should be split |
| Proposed total | ₹6L–₹23L/month | Broadly plausible for growth, not initial validation |

A complete premium budget should also explicitly include:

- Provider acquisition

- Quality audits

- Insurance/compliance

- Local support

- Payment and refund reserves

- Technology allocation

Corrected premium range

₹7L–₹25L per month

Indicative six-month cash envelope

₹50L–₹1.7Cr, including approximately 15–20% contingency.

The top end is justified only when the city already supports multiple dense clusters.

8. Premium-spend unlock gates

Premium spending should begin only after the city demonstrates:

| Requirement | Target |
| --- | --- |
| Monthly completed services | 300–500+ |
| Paying customers | 100–200+ |
| Repeat customers | 25–40% |
| Average rating | 4.6+ |
| Completion rate | 95%+ |
| Provider no-show | Below 1% |
| Refund/dispute rate | Below 5% |
| Active local supply | 10–25 providers |
| Backup coverage | 90–95%+ |
| Direct contribution | Positive or clearly improving |
| Critical unresolved incidents | Zero |

Marketing scale rule

Increase customer-acquisition spending only when:

[
\text{Incremental contribution}

\text{Incremental acquisition and fulfilment cost}
]

Do not scale advertising when:

- Peak slots are full

- Provider cancellations are rising

- Support SLAs are failing

- Customer ratings are falling

- Partner payouts are delayed

- Subscription capacity lacks backup

Part III — Company-Owned vs Franchise Expansion

9. Company-owned cities

Advantages

- Direct control over verification

- Consistent safety processes

- Better training

- Centralised customer experience

- Reliable data

- Easier pricing control

- Direct city P&L visibility

- Faster intervention after incidents

Disadvantages

- Higher capital requirements

- Slower geographic expansion

- Greater recruitment burden

- Higher central-management complexity

- Greater fixed-cost exposure

Best use

Company-owned operations should be used for:

- The first three to five cities

- Major brand-defining metros

- Cities containing new service experiments

- Markets with complex routing or high expectations

- Cities used to train future regional operators

Recommendation

Keep these company-owned initially:

- First/core city

- Bengaluru

- Pune

- Mumbai

- Gurugram

- Ahmedabad, if it is the core operating base

The exact list should follow the actual expansion sequence rather than an arbitrary population ranking.

10. Traditional franchise cities

Advantages

- Lower central capital requirement

- Faster local hiring

- Local relationship advantage

- Local society access

- Faster geographic coverage

Risks

- Provider-verification shortcuts

- Different refund practices

- Hidden incidents

- Inconsistent training

- Poor payment discipline

- Unauthorised pricing

- Customer-data leakage

- Weak sitter payouts

- Brand damage spreading nationally

A franchise arrangement in India requires a carefully drafted commercial contract and authorised trademark use. Franchise disputes are expressly recognised among commercial disputes, while the underlying relationship also involves ordinary contract and trademark law.

Franchise operation does not remove the need for consumer grievance handling, fair e-commerce conduct or transparent cancellation and refund rules.

11. Recommended hybrid: Managed City Operator

Before offering a conventional franchise, use a more controlled model:

Managed City Operating Partner

Central company owns

- Brand

- Technology

- Customer accounts and data

- Payment collection

- Provider payout infrastructure

- Verification standards

- Final provider approval

- Price architecture

- Refund rules

- Incident classification

- Customer-support standards

- National marketing

- Subscription and credit system

- Quality auditing

Local operating partner owns

- Field recruitment

- Practical trials under central standards

- Local availability management

- Society outreach

- Local events

- Partner relationships

- Daily schedule coordination

- Local service recovery

- Local team management

Central company must retain step-in rights

The central team must be able to:

- Pause a city

- Pause a service

- Suspend a provider

- Take over customer support

- Freeze acquisition

- Audit customer and provider records

- Replace the operator

- Terminate brand access

12. What a franchise or operating partner must never control alone

Do not delegate final authority over:

- Critical-incident classification

- Deletion of complaints or reviews

- Provider identity verification

- Safety-policy exceptions

- Customer refunds

- Customer funds

- Partner-payout records

- Medical claims

- Customer-data exports

- Subscription-credit adjustments

- City-quality reporting

The DPDP Rules, 2025 have phased commencement, but a multi-operator model should already use purpose-specific notices, role-based access, security safeguards and grievance handling.

Platform-worker and aggregator obligations must also be assessed consistently across company-owned and operator-managed cities. The Code on Social Security recognises gig and platform workers, and 2026 central-rule developments reinforce the need for worker registration, engagement and reporting systems.

13. Franchise-readiness gate

Do not offer franchise rights until:

| Requirement | Minimum condition |
| --- | --- |
| Successfully replicated cities | 2–3 company-owned cities |
| Operating history | 9–12 months of stable data |
| Verification process | Standardised and auditable |
| Training academy | Operational |
| City dashboards | Real-time and standardised |
| City P&L | Reconciled consistently |
| Incident system | Centralised |
| Provider payout system | Centralised |
| Customer support | Central or centrally monitored |
| Brand/trademark protection | Complete |
| Operator agreement | Legally reviewed |
| Audit and step-in rights | Contractual |
| Critical-incident playbook | Tested |
| Data-access system | City scoped |
| Franchise pilot | One controlled territory |

14. Recommended franchise economics

Avoid rewarding an operator on total customer GMV.

An operator should be rewarded for:

- Completed services

- Positive city contribution

- Customer retention

- Quality

- Society conversion

- Provider reliability

Better compensation model

Fixed local management fee

+

Performance share of city contribution

+

Quality and growth bonus

Illustrative structure:

- Small fixed operating fee

- 20–35% share of contribution after direct city costs

- Bonus for quality, repeat rate and society renewals

- No share on refunded or disputed transactions

- Penalties for concealed incidents or payout failures

This is strategically safer than giving a local operator a large percentage of GMV regardless of service quality.

Part IV — Multi-City Quality Control

15. Central non-negotiable standards

Every city must follow the same standards for:

Provider verification

- Identity

- Contact

- Required documents

- Skill assessment

- Practical trial

- Reference/background process

- Service permissions

- Expiry tracking

Pet-risk classification

- Low-risk routine

- Moderate handling requirements

- High behavioural risk

- Medical/senior care

- Specialist-only cases

- Not currently serviceable

Service evidence

- Check-in

- Check-out

- Duration

- Report card

- GPS where appropriate

- Media with consent

- Incident flag

- Customer confirmation where needed

Incident system

- Severity levels

- Immediate containment

- Evidence preservation

- Provider suspension criteria

- Customer communication

- Root-cause analysis

- Corrective action

- Closure approval

Continuity

- Primary caregiver

- Approved backup

- Leave process

- Handover

- Backup capacity reserve

- Customer notification

Payments and refunds

- Payment or payment authorisation before confirmation

- Transparent pricing

- Clear cancellation

- Refund ledger

- No unrecorded cash settlement

- Partner payouts on schedule

Partner quality

- Groomer scorecard

- Trainer scorecard

- Boarding scorecard

- Hygiene requirements

- Before/after evidence

- Complaint tracking

Veterinary clinical advice must remain with appropriately registered veterinary professionals. Partner economics must also avoid prohibited referral or procurement commissions under VCI professional-conduct rules.

Society protocol

- Gate entry

- Identity verification

- Allowed areas

- Handover process

- Resident communications

- Incident escalation

- Aggregate reporting

Subscription capacity

- Area-specific limits

- Peak-window capacity

- Primary and backup reservation

- Stop-sales rules

- Credit ledger

- Pause and cancellation

16. Local flexibility

Cities may adjust:

- Prices within approved margins

- Local language

- Supported services

- Service priorities

- Acquisition channels

- Society packaging

- Event format

- Launch neighbourhoods

- Operating windows

- Local partner mix

- Customer-support language

Example

Ahmedabad may use:

- WhatsApp-assisted booking

- 8- and 12-walk plans

- Society camps

- Gujarati/Hindi support

Bengaluru may use:

- Self-service app booking

- 20-walk weekday plans

- Search advertising

- Corporate-benefit tests

The safety standard remains identical.

17. Local decisions requiring central approval

Central approval should be mandatory for:

- New service categories

- Price below approved floor

- New subscription terms

- Boarding launch

- Pet-taxi launch

- Medical or veterinary claims

- Verification-rule changes

- Refund-policy changes

- Data exports

- Large events

- New franchise sub-operators

- Critical-incident closure

18. Quality audit system

Daily controls

- Missed check-ins

- Unassigned bookings

- Provider no-shows

- Critical incidents

- Missing reports

- Payment mismatch

- Customer complaints

Weekly controls

- Random booking audits

- Low-rating review

- Provider cancellation patterns

- Backup usage

- Refund review

- Capacity review

- Document expiry

Monthly controls

- City-quality score

- Provider regrading

- Society account review

- Subscription fulfilment

- Incident root causes

- City P&L

- Customer-support SLA

- Access-log review

Quarterly controls

- Reverification sample

- Mystery bookings

- Incident tabletop drill

- Operator/franchise audit

- Data-protection audit

- Consumer-flow audit

- Pricing and refund audit

- Training recertification

19. City quality score

Recommended score:

| Dimension | Weight |
| --- | --- |
| Safety and incident management | 30% |
| Completion and reliability | 25% |
| Customer rating and complaints | 20% |
| Provider quality and reporting | 10% |
| Subscription/society fulfilment | 10% |
| Audit and compliance | 5% |

Quality bands

| Score | Classification | Action |
| --- | --- | --- |
| 90–100 | Excellent | Eligible for controlled growth |
| 80–89 | Approved | Continue normal operations |
| 70–79 | Monitor | Restrict acquisition |
| 60–69 | Corrective action | Freeze new services/clusters |
| Below 60 | Critical | Pause city or replace operator |

Hard override

Regardless of numerical score, immediately pause affected operations after:

- Concealed critical incident

- Fraudulent provider verification

- Serious customer-data breach

- Systematic payout non-payment

- Falsified service completion

- Repeated pet escape or injury due to ignored controls

Part V — Final Approval Decisions

| Proposal | Decision |
| --- | --- |
| Lean monthly budget ₹1.35L–₹3.85L | Use as bare burn only; plan ₹1.95L–₹6.05L fully loaded |
| Emergency buffer | Approve; separate from payout working capital |
| Premium budget ₹6L–₹23L | Broadly approve; unlock only after city validation |
| Begin with premium budget in metros | Reject |
| Start lean | Approve |
| Company-owned top cities | Approve for first 3–5 cities |
| Franchise smaller cities immediately | Reject |
| Managed operating partner later | Approve after replication proof |
| Traditional franchise after safety maturity | Conditional approval |
| Central verification standards | Mandatory |
| Central incident ticketing | Mandatory |
| Central payment/refund controls | Mandatory |
| Local pricing flexibility | Approve within approved bands |
| Local marketing flexibility | Approve |
| Local safety-policy flexibility | Reject |
| Local clinical veterinary decisions | Reject; registered vets decide |
| Central audit and step-in rights | Mandatory |

Final recommended expansion ownership model

Cities 1–3

Company owned and directly operated

Cities 4–5

Company owned or tightly managed operating partners

Cities 6+

Selective managed operators/franchise pilots

only after central quality systems are mature

Phase 10 budget principle

Spend enough to create local service density and reliable backup capacity, but release growth capital only after demand, fulfilment and contribution have been proven.

Phase 10 ownership principle

Delegate local execution, but never delegate final control over safety, customer funds, verification, incidents, refunds, data or brand standards.

Phase 10 quality-control principle

Every city may speak differently and price differently, but every pet must receive the same minimum safety, verification, documentation and incident-response standard.

Final decision: START LEAN, KEEP THE FIRST MAJOR CITIES COMPANY-OWNED, AND DEFER FRANCHISING UNTIL THE OPERATING SYSTEM HAS BEEN PROVEN ACROSS MULTIPLE CITIES.

Phase 10: Central–Local Operating Model, KPIs and Expansion Risk System 🌍🐾

Executive decision

Your centralisation model is fundamentally correct. The strongest structure is:

Centralise trust, technology, money, data and safety. Localise fulfilment, relationships and market execution.

The corrected operating model is:

| Function category | Operating rule |
| --- | --- |
| Non-negotiable standards | Central |
| Customer funds and financial controls | Central |
| Data, permissions and security | Central |
| Daily service delivery | Local |
| Local relationships and supply | Local |
| Customer recovery and incidents | Hybrid |
| Pricing and marketing | Local within central guardrails |

This avoids two dangerous extremes:

- Over-centralisation: local teams cannot respond quickly enough.

- Over-localisation: every city develops different safety, refund and verification standards.

Part I — What should be centralised versus local

1. Final responsibility matrix

| Function | Recommended model | Central responsibility | Local responsibility |
| --- | --- | --- | --- |
| Brand | Central | Identity, positioning, claims, design system | Local proof and city messaging |
| Technology | Central | Product, APIs, dashboards, releases | Configuration and operational use |
| Payments | Central | Gateway, invoicing, refunds, reconciliation | Payment follow-up and local exception evidence |
| Data and security | Central | Access model, encryption, audits, retention | Follow access rules and report breaches |
| Safety standards | Central | Verification, risk rules, incident taxonomy | Execute protocols and escalate |
| Training content | Central | Curriculum, assessments, certification language | Training delivery and local coaching |
| City operations | Local | Tools and national SLAs | Scheduling, capacity and fulfilment |
| Society outreach | Local | Contract templates and policy guardrails | RWA relationships, events and pilots |
| Vet/groomer partnerships | Hybrid | Eligibility standards and commercial rules | Recruitment and relationship management |
| Customer support | Hybrid | Central Level 1 support and national policies | Physical recovery and city escalation |
| Emergency response | Hybrid | Incident command and national SOP | Immediate local containment |
| Marketing | Hybrid | Brand assets and claim approval | Channels, language and local campaigns |
| Pricing | Hybrid | Margin floor, price architecture and approvals | Local price recommendations |
| Provider payouts | Central | Ledger, payout rules and reconciliation | Validate service completion |
| Finance and tax | Central | Accounting model, tax controls and city P&L | Local expense evidence and forecasts |
| Quality audits | Central/hybrid | Audit methodology and independent review | Corrective action execution |

2. Brand: central strategy, local evidence

The national team should control:

- Brand identity

- Verification language

- Safety claims

- Report-card format

- Review methodology

- Refund principles

- Preferred-caregiver wording

- Advertising disclosures

The city team should provide:

- Local customer reviews

- Local society partnerships

- Active caregiver counts

- Supported neighbourhoods

- City-specific languages

- Local service photographs

- Local campaign stories

Correct example

National promise

Verified local pet care, documented every visit.

Ahmedabad expression

Trusted local care for Ahmedabad families and apartment communities.

Mumbai expression

Premium caregivers operating within your locality.

The local team may change the message’s emphasis, but not the underlying safety or verification meaning.

3. Technology: central platform, local configuration

Technology should remain centrally owned because multiple city-specific codebases would create:

- Inconsistent features

- Security gaps

- Expensive maintenance

- Different credit and refund logic

- Reporting incompatibility

Local teams should configure—not rewrite—the system:

- Active service zones

- Operating hours

- Service availability

- Provider pools

- Capacity limits

- Local prices

- Society programmes

- Notification language

- Support contacts

Central product platform

↓

City configuration

↓

Service-zone configuration

↓

Local provider and capacity assignment

No city should be allowed to create an unofficial spreadsheet-based payment, subscription or incident system outside the main platform.

4. Payments: fully centralised

Central payment control should include:

- Payment-provider accounts

- Subscription mandates

- Customer invoices

- Partner payout ledger

- Refund approval workflow

- Failed-payment recovery

- Tax records

- Reconciliation

- Fraud monitoring

- Payment-link generation

Local city teams may:

- Contact customers about an open invoice

- Submit service-failure evidence

- Request a refund

- Recommend a goodwill credit

- Confirm whether a service occurred

They should not:

- Mark an unpaid invoice as paid

- Collect unofficial cash

- Change provider payout records

- Issue undocumented refunds

- Create local bank or UPI accounts for customer collections

- Adjust subscription credits without an audit entry

5. Data and security: central and non-delegable

Multi-city operations process sensitive operational data such as:

- Customer addresses

- Recurring home schedules

- Society gate instructions

- Pet behavioural notes

- Provider identity documents

- Payment references

- Incident information

India’s notified DPDP Rules, 2025 establish the current national data-protection framework and include a phased enforcement timeline. City growth should therefore use central data governance, role-based access, security safeguards and auditable grievance handling rather than giving every city broad database access.

Recommended access model

| Role | Permitted access |
| --- | --- |
| Walker | Only assigned service and necessary pet instructions |
| City operations | Scheduling and service-recovery data |
| Customer support | Customer, booking and complaint data |
| Society executive | Society account data, not private pet records |
| City manager | City operations and aggregated performance |
| Finance | Payment and settlement information |
| Safety team | Incidents and required supporting records |
| National administration | Cross-city data according to role |

A Pune team member should not be able to browse Mumbai customer addresses merely because both cities use the same platform.

6. Safety: central standards, local execution

The national safety team should define:

- Provider verification levels

- Pet-risk classification

- Service permissions

- Backup requirements

- Boarding standards

- Grooming hygiene rules

- Incident severity

- Evidence requirements

- Suspension criteria

- Root-cause review

- Corrective actions

The local team should:

- Conduct practical assessments

- Verify local availability

- Execute emergency containment

- Contact the customer

- Coordinate local veterinary assistance

- Preserve evidence

- Remove unsafe providers from active schedules

- Implement corrective actions

Incident authority

A city manager can open and escalate an incident, but should not independently:

- Reduce the recorded severity

- Delete the incident

- Close a critical case

- Restore a suspended provider

- Hide a customer complaint

Critical closure should require central safety approval.

7. Training: central curriculum, local delivery

Centralised training content ensures every city teaches the same fundamentals:

- Pet handling

- Leash and gate safety

- Escape prevention

- Customer communication

- Service reports

- Privacy

- Incident reporting

- Medication boundaries

- Aggression escalation

- Cancellation and backup procedures

Local teams may add modules for:

- Society access

- Local language

- Climate and weather

- Local travel conditions

- City-specific service procedures

Certification language

The platform may issue:

- Platform course completed

- Practical assessment passed

- Dog-walking assessment passed

- Cat-care module completed

It should not call internal training a national or government certification unless that status is formally supported.

8. City operations: local ownership

City operations must be local because they require real-time knowledge of:

- Traffic

- Provider locations

- Society entry

- Weather disruption

- Local events

- Provider leave

- Customer availability

- Emergency providers

The city operations team should own:

Today’s services

↓

Assignment

↓

Check-in

↓

Completion

↓

Report

↓

Customer recovery

Central teams provide software and standards; the city team owns the actual outcome.

9. Society outreach: local within central guardrails

Society acquisition depends on local trust and cannot be managed entirely from a national office.

Local teams should own:

- RWA and facility-manager meetings

- Resident demand assessment

- Gate protocols

- Society events

- Pilot implementation

- Local escalation contacts

- Pilot-to-paid conversion

Central teams should supply:

- Agreements

- Data-sharing terms

- Safety presentation

- Event SOP

- Monthly report format

- Commercial boundaries

- Brand claims

AWBI publishes national guidance concerning pet owners, caregivers, RWAs and apartment associations. City teams may adapt operational arrangements, but they should not promise society policies that conflict with the national welfare framework.

10. Vet and groomer partnerships: hybrid

Local teams are best placed to find and manage:

- Groomers

- Trainers

- Veterinary clinics

- Home-visit professionals

- Boarding facilities

- Event providers

Central teams must control:

- Verification requirements

- Service permissions

- Contract templates

- Scorecards

- Customer-data access

- Medical-claim restrictions

- Payout and refund structures

Veterinary boundary

The platform coordinates access to registered professionals. It does not allow local staff, support agents or AI systems to give final diagnoses.

11. Customer support: hybrid three-level system

Level 1 — Central support

Handles:

- Booking questions

- Credit balance

- Payment status

- Subscription changes

- Basic cancellations

- Report access

- General service information

Level 2 — City operations

Handles:

- Walker late or missing

- Backup assignment

- Society gate denial

- Customer access issue

- Local rescheduling

- Physical service recovery

Level 3 — Central specialist escalation

Handles:

- Serious incidents

- Privacy cases

- Large refunds

- Legal complaints

- Fraud

- Medical-boundary issues

- Repeated city quality failure

India’s E-Commerce Rules require consumer-facing e-commerce entities to maintain grievance-handling arrangements. A hybrid model works only when the customer has one visible support path and the central system records the entire escalation.

12. Emergency response: local action, central command

The first response must be local because the incident is happening in that city.

Local responsibilities

- Secure the pet

- Contact the customer

- Stop the service

- Contact an appropriate clinic

- Activate local transport where available

- Preserve photographs, location and timeline

- Suspend the provider temporarily where required

Central responsibilities

- Classify severity

- Guide customer communication

- Review legal/privacy implications

- Approve major refunds

- Manage insurers or advisors

- Conduct root-cause analysis

- Issue network-wide corrective action

Local containment

+

Central governance

=

Effective incident response

13. Marketing: central creative system, local activation

Central marketing should own:

- Brand identity

- Master campaigns

- Safety claims

- Creative templates

- National website

- Analytics framework

- Attribution methodology

Local marketing should own:

- City language

- Local channels

- Society promotion

- Regional creators

- City events

- Local testimonials

- Neighbourhood-specific search campaigns

Local teams should not independently claim:

- “100% safe”

- “Guaranteed same sitter”

- “Best in the city”

- “Police verified”

without centrally approved evidence.

Part II — Correcting the city-level KPIs

14. Autopsy of the proposed KPI table

Your proposed targets contain three important mathematical issues.

1,000 bookings and 500 customers

This equals an average of:

1,000÷500=2

completed services per customer per month.

That may be reasonable for a mixed-service marketplace, but it is low for a walking-subscription-led city. Track customer frequency distribution—not only the average.

1,000 bookings and 50 active sitters

This equals:

1,000÷50=20

services per provider per month.

That may produce weak provider earnings and high supply churn unless many providers are intentionally part-time or provide other services.

₹5 lakh revenue and 1,000 bookings

This equals:

₹5,00,000÷1,000=₹500

per completed service.

This is meaningful only after defining whether ₹5 lakh means:

- Customer GMV

- Platform-recognised revenue

- Gross profit

- City contribution

15. Corrected mature-city KPI scorecard

| KPI | Proposed | Corrected recommendation |
| --- | --- | --- |
| Completed services/month | 1,000+ | Approve for a mature city |
| Monthly active paying customers | 500+ | 300–500+ |
| Ninety-day active customers | Not specified | 500–800+ |
| Active providers | 50+ | 15–30 core active; 30–60 verified bench |
| Repeat customer rate | 35%+ | Approve; target 35–50% |
| Rating | 4.6+ | Approve with sufficient review volume |
| Completion rate | Not specified | 95%+ |
| On-time rate | Not specified | 95%+ |
| Provider no-show | Not specified | Below 1% |
| Refund/dispute rate | Not specified | Below 3–5% |
| Recurring revenue | Growing | 20–40% of platform revenue where appropriate |
| Gross margin | 25–35% | Approve only with consistent accounting definition |
| City contribution | Positive | Positive for at least three months |
| Critical incidents | Included in 3% | Zero unresolved |
| Serious incident rate | Included in 3% | Below approximately 0.1–0.3% |
| Minor reportable incident rate | Included in 3% | Below 1% |

16. Bookings KPI

The primary city-volume metric should be:

Completed paid service occurrences

Report separately:

- Orders

- Scheduled bookings

- Completed services

- Cancelled services

- Refunded services

- Subscription credits consumed

A 20-walk subscription may be:

- One commercial order

- Twenty scheduled bookings

- Up to twenty completed services

Do not mix those units.

Stage targets

| City stage | Monthly completed services |
| --- | --- |
| Closed beta | 50–150 |
| Early public launch | 150–350 |
| Validated city | 300–750 |
| Mature city | 1,000+ |
| Scaled city | 2,500+ |

17. Revenue KPI

Every city dashboard must show:

Customer GMV

Total customer spending.

Platform revenue

Commission, platform fees, memberships and B2B fees retained by the company.

City contribution

City contribution=Platform revenue-direct city costs

Direct city costs include:

- Local staffing

- Payment processing

- Customer acquisition

- Refunds

- Service recovery

- Verification

- Society events

- Local support

Recommended gate

Do not expand the city based on ₹5 lakh of GMV alone.

Require:

- Positive contribution per completed service

- Positive cluster contribution

- Positive city operating contribution for three months before aggressive scaling

18. Active provider KPI

Replace a fixed “50 active sitters” target with:

- Active providers

- Capacity supplied

- Capacity consumed

- Provider earnings

- Provider retention

- Peak-window coverage

- Backup coverage

Better calculation

Required active providers=forecast completed servicessafe services per provider×reserve factor

Example:

- 1,000 services

- 50 safe services per provider

- 15% reserve

1,000÷50=20
20×1.15=23

Approximately 23 active providers may be sufficient, depending on service mix and peak-time concentration.

The target should therefore be:

Enough healthy provider capacity—not the largest possible provider headcount.

19. Repeat-rate KPI

Define repeat rate consistently:

Repeat customer rate=customers completing a second paid service within the selected periodeligible first-time customers

Report:

- 30-day repeat

- 60-day repeat

- 90-day repeat

- Subscription renewal

- Repeat rate by acquisition channel

A customer acquired one week ago should not be treated as a failed 90-day repeat customer.

20. Subscription KPI

“Subscription MRR growing” is insufficient.

Track:

- Active subscribers

- New MRR

- Upgrade MRR

- Downgrade MRR

- Churned MRR

- Renewal rate

- Credit utilisation

- Subscription contribution

- Backup capacity required

Recommended mature-city target

- First renewal: 60–80%

- Mature monthly churn: below 10–15%

- Recurring platform-revenue share: 25–40%

- Credit utilisation: 70–90%

- Subscription fulfilment: 95%+

21. Rating KPI

A city’s average should be accompanied by:

- Number of reviews

- Rating distribution

- Percentage of services reviewed

- Recent 30-day rating

- Low-rating count

- Complaint rate

A rating of 4.8 from 15 reviews is less reliable than 4.7 from 1,500 reviews.

Recommended gate:

- 4.6+ average

- At least 50 verified reviews for a validated city

- No major service category below 4.4

- No unresolved pattern of low ratings

22. Incident KPI

Reject one combined target of “below 3%.”

Use severity-based reporting:

| Category | Example | Target |
| --- | --- | --- |
| Critical | Pet escape, death, serious fraud, major data breach | Zero preventable and zero unresolved |
| Serious | Injury, bite, unsafe handover | Below 0.1–0.3% |
| Minor reportable | Small delay-related welfare concern, minor service issue | Below 1% |
| General complaint | Report quality, communication, timing | Below 3–5% |
| Refund/dispute | Financial/service dispute | Below 3–5% |

A city with 2.5% minor communication incidents is very different from a city with 2.5% pet escapes.

23. Gross-margin KPI

Gross margin is valid only when every city uses the same accounting basis.

If partner payouts are recorded as cost of service:

Gross margin=Recognised revenue-direct cost of serviceRecognised revenue

If the platform recognises only its commission as revenue, the denominator is different.

Therefore:

- Use a central finance definition.

- Do not allow each city manager to calculate margin independently.

- Show contribution alongside gross margin.

- Review margin by service, cluster and acquisition channel.

Part III — Correcting the national KPIs

24. Recommended national scorecard

| KPI | Proposed | Corrected interpretation |
| --- | --- | --- |
| Active cities | 2–5 | At least one mature and one validated city |
| Total completed services/month | 5,000+ | Strong network target |
| Total MRR | ₹5L–₹50L | Define platform MRR, not subscription GMV |
| Total revenue/month | ₹25L+ | Separate GMV, platform revenue and contribution |
| Average rating | 4.6+ | Volume-weighted; no public city materially below standard |
| Repeat rate | 35–50% | Report by city and customer cohort |
| City profitability | Improving | Count contribution-positive cities |
| CAC payback | Below 3 months | Mature-city target; allow longer launch payback |

25. Active-city KPI

A city should count as active only when it is accepting and completing paid bookings.

Classify cities:

- Research

- Waitlist

- Closed beta

- Public limited

- Validated

- Mature

- Paused

Recommended Phase 10 outcome:

| Stage | Target |
| --- | --- |
| Mature cities | At least 1 |
| Validated cities | At least 1 |
| Beta cities | 0–2 |
| Total public cities | 2–5 |

A city landing page does not make the city active.

26. Network-booking KPI

A total of 5,000 monthly completed services can hide concentration.

Report:

- Total network services

- Services per city

- Percentage from largest city

- Services per active provider

- Services by category

- Subscription services

- Society-origin services

Concentration warning

If City 1 produces 4,700 bookings and four other cities produce 75 each, the company has not yet built a functioning five-city network.

Recommended additional measure:

No validated city should remain below its minimum stage target without a corrective or exit decision.

27. National MRR KPI

Split recurring revenue into:

- Walking subscription platform revenue

- Consumer membership revenue

- Society subscription revenue

- Partner software revenue

Do not include:

- One-time prepaid packs

- One-time boarding

- Future unpaid invoices

- Subscription GMV owed to service providers

Better target

Instead of only ₹5L–₹50L, track:

- Absolute platform MRR

- MRR growth rate

- MRR contribution

- Recurring revenue as a percentage of platform revenue

- MRR concentration by city

A network where 90% of MRR comes from one society contract carries concentration risk.

28. National revenue KPI

Use four separate values:

| Metric | Meaning |
| --- | --- |
| Network GMV | Total customer spending |
| Platform revenue | Recognised company revenue |
| Contribution | Revenue after direct operating costs |
| Operating result | Contribution after central costs |

A ₹25 lakh GMV target can be commercially weak if provider payouts, marketing and refunds consume most of it.

Recommended national gate

- Network contribution positive or improving according to plan

- At least one mature city contribution-positive

- At least one new city with a contribution-positive cluster

- No city scaling through unreconciled discounts

29. National rating KPI

Use a volume-weighted average, but preserve city minimums.

Recommended:

- Network weighted rating: 4.6+

- Every validated/mature city: 4.6+

- No public city below 4.4 for more than one review period

- Critical service categories reviewed separately

A strong Bengaluru rating must not hide poor performance in a new city.

30. National CAC payback

Use different expectations by city stage:

| Stage | CAC payback target |
| --- | --- |
| Closed beta | Not yet reliable |
| Early launch | Below 6–9 months or clear improvement |
| Validated city | Below 4–6 months |
| Mature city | Below 2–3 months |
| Society channel | Evaluate using contract and resident contribution |

A universal three-month requirement during launch can cause underinvestment in supply, trust and society partnerships.

Part IV — Expansion risk matrix

31. Corrected risk-control framework

| Risk | Impact | Leading indicator | Prevention | Stop condition |
| --- | --- | --- | --- | --- |
| Expansion too fast | High | Support SLA drops, City 1 quality declines | Sequential city gates | Freeze new-city launches |
| Weak city manager | High | Poor reporting, unresolved queues | Structured hiring and probation scorecard | Replace or add operating support |
| Low sitter quality | High | Low ratings, missing reports | Central curriculum and local trials | Stop assigning weak providers |
| Scattered bookings | Medium-high | Travel time and cancellations rise | Small service clusters | Close distant slots |
| High CAC | Medium-high | Payback deteriorates | Society/referral-first acquisition | Pause low-return channels |
| Safety incident | Very high | Near misses and protocol breaches | Central standards and local drills | Immediate affected-service pause |
| Pricing mismatch | Medium | Low conversion or negative contribution | Local price tests within margin floor | Reprice or narrow service |
| Subscription overload | High | Peak capacity exceeds 85–90% | Capacity-controlled checkout | Stop subscription sales |
| Brand inconsistency | Medium | Different claims and policies | Central claim registry | Remove local campaign |
| Franchise failure | High | Audit gaps and incident concealment | Delay franchises and retain step-in rights | Suspend operator |
| Data leakage | Very high | Cross-city access anomalies | Central RBAC and audit logs | Revoke access and investigate |
| Delayed partner payouts | High | Provider complaints and churn | Central payout ledger and reserve | Freeze acquisition and clear arrears |
| Financial misreporting | High | GMV/revenue mismatch | Central definitions and reconciliation | Block scaling decision |
| Society concentration | Medium | One society drives excessive volume | Diversify clusters and channels | Limit dependency |
| Local partner poaching | Medium | Off-platform repeat services | Customer value, agreements and app incentives | Review or remove partner |
| Metric manipulation | High | Suspicious completions or rating patterns | Independent audits | Suspend responsible staff/provider |

32. Expansion-too-fast risk

Early signs

- City 1 support response worsens

- Founder becomes involved in daily booking assignments

- Provider payouts are late

- New-city dashboards are incomplete

- Training standards are shortened

- Unresolved complaints increase

Prevention

- One city at a time

- Gate-based budget release

- Dedicated local ownership

- Central capacity review

- No City 3 launch until City 2 passes stability gates

33. Weak city-manager risk

A poor city manager can create:

- Unsafe provider shortcuts

- Inflated booking numbers

- Unresolved customer complaints

- Society relationship damage

- Inaccurate P&L

- Hidden incidents

Prevention

Use a balanced scorecard:

| Dimension | Weight |
| --- | --- |
| Safety and quality | 30% |
| Fulfilment and supply | 20% |
| Retention and demand | 20% |
| City economics | 20% |
| Society and strategic growth | 10% |

No growth bonus should be paid after a concealed critical incident or materially unreconciled city P&L.

34. Platform-worker risk

Provider onboarding and worker reporting should not vary casually by city. The Code on Social Security recognises gig and platform workers, and a June 2026 Labour Ministry direction states that covered aggregators must share required worker details electronically under the 2026 Rules. Classification and reporting should therefore be centrally governed even though recruitment is local.

Centralise:

- Worker classification policy

- Required fields

- Engagement records

- Earnings and payouts

- eShram/reporting workflow where applicable

- Document retention

- Audit history

Part V — Final approvals

35. Central-versus-local decisions

| Rule | Final decision |
| --- | --- |
| Brand central | Approve |
| Technology central | Approve |
| Payments central | Approve—non-negotiable |
| Data and security central | Approve—non-negotiable |
| Safety standards central | Approve—non-negotiable |
| Training content central | Approve; delivery can be local |
| City operations local | Approve |
| Society outreach local | Approve within central policies |
| Vet/groomer partnerships local | Approve with central verification |
| Customer support hybrid | Approve |
| Emergency response local | Modify: local containment, central command |
| Marketing central and local | Approve |
| Pricing entirely local | Reject; use central guardrails |
| Provider payouts local | Reject; centralise |
| Incident closure entirely local | Reject |

36. KPI decisions

| Proposed KPI | Final decision |
| --- | --- |
| 1,000 monthly bookings per city | Approve for mature cities as completed services |
| ₹5 lakh monthly revenue | Separate GMV, platform revenue and contribution |
| 500 active customers | Approve as a mature-city range with definitions |
| 50 active sitters | Replace with capacity and utilisation targets |
| 35% repeat rate | Approve |
| Subscription MRR growing | Add renewal, churn and contribution metrics |
| 4.6+ rating | Approve with review-volume requirement |
| Incident rate below 3% | Reject; use severity-based reporting |
| 25–35% gross margin | Approve only with central accounting definition |
| Positive city contribution | Approve—required before aggressive scale |
| Five active cities | Conditional on maturity mix and independent ownership |
| 5,000 national bookings | Approve as completed services |
| ₹25 lakh total revenue | Separate financial layers |
| CAC payback below three months | Use for mature cities, not all launches |

Final operating doctrine

Centralise

Brand

Technology

Payments

Data and security

Safety standards

Training curriculum

Financial definitions

Provider payout ledger

Incident governance

Quality audits

Localise

Scheduling

Provider recruitment

Society relationships

Local partnerships

Events

Capacity execution

Immediate service recovery

Local campaign activation

Operate as hybrid

Customer support

Emergency response

Training delivery

Marketing

Pricing

Partner onboarding

Quality improvement

Phase 10 win condition

Every city can move quickly in local operations without being allowed to weaken national safety, payment, data, verification or consumer-protection standards.

A healthy multi-city network should demonstrate:

Local speed+Central control+Consistent metrics+Independent city economics

Final Phase 10 decision: APPROVED—with stage-specific KPIs, severity-based incident reporting and central non-negotiable control over money, data and safety.

A quarterly regulatory and city-scorecard review would help keep worker-reporting, privacy and consumer-support controls current.

Phase 10 Final Approval Report

Multi-City Expansion Engine, Deliverables and Phase 11 Gate 🌍🐾

Executive decision

Approve Phase 10—with controlled city gates, cluster-level launches, company-operated early cities, city-level P&Ls and centrally governed safety.

The official Phase 10 operating model should be:

Stable City 1

↓

City-selection scorecard

↓

Demand, supply, operations and safety gates

↓

One or two local clusters

↓

Closed paid beta

↓

Quality and contribution validation

↓

Cluster expansion

↓

City 3 preparation

The business is not ready for Phase 11 merely because multiple city names appear in the application. It is ready when the second city reproduces the first city’s quality, economics and operational discipline without continuous founder intervention.

1. What goes wrong in multi-city expansion

Mistake 1: Expanding before the first city works

Wrong model

100 cumulative bookings

↓

Launch five cities

↓

Demand and supply become fragmented

↓

Quality falls everywhere

A small number of historical bookings does not prove:

- Repeatable demand

- Stable provider capacity

- Subscription retention

- Positive contribution

- Reliable incident handling

- Independent city management

Correct expansion gate

City 1 should demonstrate, for approximately three consecutive months:

| Requirement | Recommended threshold |
| --- | --- |
| Completed paid services/month | 1,000+ |
| Monthly paying customers | 300–500+ |
| Repeat customer rate | 35%+ |
| Active walking subscribers | 50–100+, reconciled with service volume |
| Completion rate | 95%+ |
| On-time rate | 95%+ |
| Provider no-show | Below 1% |
| Average rating | 4.6+ |
| Refund/dispute rate | Below 3–5% |
| City operating contribution | Positive |
| Critical unresolved incidents | Zero |
| Founder-dependent fulfilment | Below 5–10% |

The key requirement is not just volume:

City 1 must operate as a system—not as a founder-managed collection of bookings.

Mistake 2: No accountable city owner

Wrong model

The central team remotely manages:

- Partner recruitment

- Scheduling

- Society entry

- Customer complaints

- Backup assignments

- Local emergencies

This becomes increasingly slow and inaccurate as the company adds cities.

Correct model

Every public city must have a named local owner.

Depending on maturity, that person may be:

| City stage | Ownership model |
| --- | --- |
| Research | City launch owner |
| Closed beta | Accountable launch/operations manager |
| 300–500 monthly services | Dedicated city manager strongly recommended |
| 1,000+ monthly services | Dedicated city manager required |
| Multiple clusters | City manager plus cluster/operations leads |

City manager accountability

The city manager owns:

- Local supply

- Fulfilment

- Backup coverage

- Society relationships

- Customer recovery

- City contribution

- Local growth

- Safety escalation

However, critical safety classification, recognised financial results, privacy controls and major refunds should remain independently governed by central teams.

Recommended city-manager scorecard

| Dimension | Weight |
| --- | --- |
| Quality and safety | 30% |
| Supply and fulfilment | 20% |
| Demand and retention | 20% |
| City economics | 20% |
| Society and strategic growth | 10% |

A manager should not earn a growth bonus after concealing an incident, using unverified providers or materially delaying partner payouts.

Mistake 3: No area density

Wrong model

“We have launched Mumbai.”

But customers are scattered across Powai, Bandra, Andheri, Worli and Thane, while providers travel long distances between low-value services.

This creates:

- Late arrivals

- Provider cancellations

- Expensive backup

- Low provider earnings

- Weak contribution

- Poor subscription continuity

Correct model

City

↓

Cluster 1

↓

Cluster 1 validated

↓

Adjacent Cluster 2

↓

Cluster 2 validated

↓

Additional local clusters

Example

For Mumbai:

Powai–Chandivali

↓

Bandra–Khar

↓

Andheri West–Juhu

↓

Lower Parel–Worli

These should remain separate provider and capacity pools until real route data proves that they can safely share supply.

Cluster-opening requirements

| Requirement | Recommended target |
| --- | --- |
| Qualified leads | 100–200 |
| Paid trial intent | 20–40 |
| Launch-active providers | 5–8 |
| Peak-time backups | 2–3 |
| Emergency referral network | Verified |
| Local support routing | Ready |
| Prices | Configured |
| Capacity limits | Configured |
| Projected contribution | Viable |

Cluster-validation requirements

| Metric | Target |
| --- | --- |
| Completed beta services | 50–150 |
| Average rating | 4.6+ |
| Completion | 95%+ |
| On-time performance | 95%+ |
| No-show rate | Below 1% |
| Provider cancellation | Below 5% |
| Refund/dispute | Below 5% |
| Critical preventable incidents | Zero |

Mistake 4: Same pricing everywhere

Wrong model

₹149 per walk in Ahmedabad, Bengaluru, Mumbai, Pune and Gurugram.

This ignores differences in:

- Partner payouts

- Travel time

- Building and gate delays

- Support expectations

- Customer willingness to pay

- Competition

- Peak-slot scarcity

- Backup costs

- Society density

Correct pricing formula

Customer price=  provider payout+travel/gate cost+payment cost+support cost+backup reserve+service-recovery reserve+target contribution-route-density saving

Pricing should be configured by:

City

↓

Service cluster

↓

Service package

↓

Time window

↓

Published price version

Existing bookings and subscriptions must retain the pricing terms they accepted. Do not overwrite historical prices when a city publishes a new price.

Mistake 5: Franchising too early

Wrong model

One partially proven city

↓

Sell franchise rights

↓

Local operators change verification and refund rules

↓

Safety and customer experience become inconsistent

Pet care is unusually sensitive to local execution because providers enter homes, handle animals and access recurring customer schedules.

Correct ownership sequence

Cities 1–3

Company-operated

Cities 4–5

Company-operated or tightly managed partners

Later cities

Selective managed-operator/franchise pilots

Traditional franchising should begin only after the company has:

- Replicated the model across at least two or three company-operated cities

- Standardised verification and training

- Centralised payments and provider payouts

- Built city-level dashboards

- Tested incident-management procedures

- Established audit and step-in rights

- Operated stable cities for a meaningful period

A safer intermediate structure is a managed city operator model: the local partner handles field execution, while the central company retains control over customer funds, technology, verification, safety, incidents, refunds and data.

2. Phase 10 upgrade decisions

Upgrade 1: Mandatory city-launch gates

Decision: APPROVE—NON-NEGOTIABLE

No public launch should occur until five areas are validated:

- Demand

- Active supply

- Operations

- Safety/compliance

- Economics

Official gate sequence

Gate 0: City selection

Gate 1: Qualified demand

Gate 2: Active supply

Gate 3: Operational readiness

Gate 4: Closed-beta quality

Gate 5: Cluster economics

Gate 6: Public expansion

A strong demand gate cannot compensate for a failed safety gate.

Upgrade 2: First three to five cities company-operated

Decision: APPROVE WITH FLEXIBILITY

Use “company-operated” rather than requiring one exact legal ownership structure.

The first major cities should remain under direct company operational control because they establish:

- Safety standards

- Training standards

- City staffing ratios

- Unit economics

- Society sales processes

- Support SLAs

- Incident patterns

- Technology requirements

A tightly managed operator may be tested later, but not before the central operating system is mature.

Upgrade 3: Mandatory area-cluster expansion

Decision: APPROVE—NON-NEGOTIABLE

City-wide availability must not be activated as one Boolean setting.

Every service requires cluster-level control over:

- Availability

- Partner pool

- Price

- Capacity

- Hours

- Backup reserve

- Support ownership

- Stop-sales threshold

The public landing page and checkout system must read from the same serviceability configuration.

Upgrade 4: Mandatory city-level P&L dashboard

Decision: APPROVE

Track four separate financial layers.

A. GMV

Total customer spending.

B. Platform revenue

The company’s recognised commissions, service fees, memberships, subscriptions, society fees and other retained revenue.

C. City contribution

City contribution=Platform revenue-direct city operating costs

D. Fully allocated operating result

City contribution after its share of central technology, finance, support and leadership expenses.

Required P&L categories

| Revenue | Direct and operating costs |
| --- | --- |
| Walking | Provider payouts |
| Sitting | Payment processing |
| Boarding | Refunds and service recovery |
| Grooming/training | City team |
| Consumer subscriptions | Local support |
| Society plans | Local acquisition |
| Events | Society events |
| Memberships | Verification and training |
| Partner software/listings | Tools and local travel |

If the platform collects customer consideration for services delivered by third-party providers, its GST e-commerce-operator and TCS treatment depends on the exact transaction and settlement structure. Maintain service-, city- and provider-level ledgers and obtain a written tax position.

Upgrade 5: Central safety standards with local operations

Decision: APPROVE AS THE OFFICIAL STRUCTURE

Central ownership

- Verification framework

- Pet-risk classification

- Safety rules

- Incident severity

- Service evidence

- Refund principles

- Training curriculum

- Customer-data security

- Provider payout system

- Quality audits

Local ownership

- Recruitment

- Practical assessments

- Daily scheduling

- Backup activation

- Society relationships

- Immediate incident containment

- Local events

- Local service recovery

Hybrid ownership

- Customer support

- Partner onboarding

- Training delivery

- Emergency response

- Pricing

- Marketing

- Quality improvement

AWBI maintains guidance addressing pet owners, caregivers, apartment associations and RWAs. Society operations should remain locally workable while respecting centrally governed animal-welfare principles.

3. Phase 10 final deliverables

P0 — Mandatory before City 2 public launch

| Deliverable | Required output |
| --- | --- |
| City expansion scorecard | Evidence-based city ranking |
| City launch-gate checklist | Signed gate status |
| City manager hiring plan | Role, scorecard and objectives |
| Launch-cluster map | Geographic boundaries and capacity |
| City pricing sheet | Published price-book version |
| Sitter recruitment playbook | Funnel, verification and activation |
| Society launch list | Decision-makers, stage and owner |
| Emergency vet directory | Hours, services and last verification |
| Local support process | Routing and SLA |
| City P&L model | Ninety-day forecast |
| Incident readiness drill | Completed |
| Privacy and access setup | City-scoped roles |
| Closed-beta plan | Customer cohort and booking limits |

P1 — Required during City 2 validation

| Deliverable | Requirement |
| --- | --- |
| City sitter pool | Active and backup supply |
| Groomer/trainer partner list | Verified and service-specific |
| Society pilots | Operational |
| City command centre | Live queues |
| City finance dashboard | GMV, revenue and contribution |
| Customer-support dashboard | Cases and SLA |
| Subscription-capacity model | Before subscriptions launch |
| Local marketing playbook | Cluster-specific |
| City retrospective | Documented |
| Playbook update | Version controlled |

P2 — Required before additional scale

| Deliverable | Requirement |
| --- | --- |
| National multi-city dashboard | Yes |
| Standardised city SOP manual | Yes |
| Cross-city audit programme | Yes |
| Central incident command | Yes |
| Worker-record/reporting process | Assessed and implemented if applicable |
| Franchise/operator framework | Later |
| Franchise audit and step-in rights | Before any pilot |

Modification to “first 2–3 expansion cities live”

Do not require three fully public, mature expansion cities by an arbitrary deadline.

A more responsible Phase 10 outcome is:

- City 1: mature

- City 2: validated

- City 3: beta or early public launch

The city count must follow the gates—not the presentation roadmap.

4. Corrected Phase 10 final report format

Phase 10 Multi-City Expansion Report

Programme information

Project name:
Reporting period:
Original city:
New cities evaluated:
New cities launched:
Public service clusters:
Beta clusters:
Paused or closed clusters:
Programme owner:

City maturity overview

| City | Stage | Local owner | Active clusters | Gate status |
| --- | --- | --- | --- | --- |
| City 1 | Mature |  |  |  |
| City 2 | Validated |  |  |  |
| City 3 | Closed beta |  |  |  |

Recommended stages:

Research

Waitlist

Supply Build

Closed Beta

Public Limited

Validated

Growth

Mature

Paused

Exited

Do not count a waitlist page as an operational city.

Demand by city

| Metric | City 1 | City 2 | City 3 |
| --- | --- | --- | --- |
| Qualified leads |  |  |  |
| Paying customers |  |  |  |
| Completed paid services |  |  |  |
| Repeat customer rate |  |  |  |
| Starter packs |  |  |  |
| Active subscribers |  |  |  |
| Subscription renewal |  |  |  |

Supply by city

| Metric | City 1 | City 2 | City 3 |
| --- | --- | --- | --- |
| Verified providers |  |  |  |
| Active providers |  |  |  |
| Core active walkers |  |  |  |
| Backup-capable providers |  |  |  |
| Capacity utilisation |  |  |  |
| Peak-window utilisation |  |  |  |
| Provider cancellation |  |  |  |
| Provider no-show |  |  |  |
| Partner payout timeliness |  |  |  |

Do not use verified profile count as a substitute for active, schedulable supply.

Quality and safety by city

| Metric | City 1 | City 2 | City 3 |
| --- | --- | --- | --- |
| Average rating |  |  |  |
| Number of verified reviews |  |  |  |
| Completion rate |  |  |  |
| On-time rate |  |  |  |
| Report completion |  |  |  |
| Refund/dispute rate |  |  |  |
| General complaints |  |  |  |
| Minor incidents |  |  |  |
| Serious incidents |  |  |  |
| Critical incidents |  |  |  |
| Open critical incidents |  |  |  |

Important correction

Do not use one generic “incident rate below 3%.”

Use:

| Category | Recommended target |
| --- | --- |
| Critical preventable incidents | Zero |
| Critical unresolved incidents | Zero |
| Serious safety incidents | Below approximately 0.1–0.3% |
| Minor reportable incidents | Below 1% |
| General complaints/refunds | Below 3–5% |

Three serious incidents per 100 services would not be an acceptable result.

Financial performance by city

| Metric | City 1 | City 2 | City 3 |
| --- | --- | --- | --- |
| GMV | ₹ | ₹ | ₹ |
| Platform revenue | ₹ | ₹ | ₹ |
| Provider payouts | ₹ | ₹ | ₹ |
| Payment costs | ₹ | ₹ | ₹ |
| Refund/service-recovery cost | ₹ | ₹ | ₹ |
| Local acquisition cost | ₹ | ₹ | ₹ |
| City-team cost | ₹ | ₹ | ₹ |
| Direct contribution | ₹ | ₹ | ₹ |
| City operating contribution | ₹ | ₹ | ₹ |
| Contribution per booking | ₹ | ₹ | ₹ |
| CAC | ₹ | ₹ | ₹ |
| CAC payback |  |  |  |

Do not label customer GMV as platform revenue.

Society performance by city

| Metric | City 1 | City 2 | City 3 |
| --- | --- | --- | --- |
| Societies identified |  |  |  |
| Decision-maker meetings |  |  |  |
| Pilots signed |  |  |  |
| Active pilots |  |  |  |
| Paid societies |  |  |  |
| Resident leads |  |  |  |
| Resident customers |  |  |  |
| Society-origin bookings |  |  |  |
| Society MRR | ₹ | ₹ | ₹ |
| RWA rating |  |  |  |
| Gate incidents |  |  |  |

City-manager performance

Score every manager across:

| Dimension | Score |
| --- | --- |
| Quality and safety | /30 |
| Supply and fulfilment | /20 |
| Demand and retention | /20 |
| Economics | /20 |
| Society growth | /10 |
| Total | /100 |

Also record:

- Strengths

- Corrective actions

- Staffing gaps

- Support needed

- Whether the city can run independently

Expansion findings

Best-performing mature city:
Best-performing new cluster:
Weakest city or cluster:
Highest-contribution service:
Lowest-contribution service:
Top expansion issue:
Top customer complaint:
Top provider problem:
Largest capacity constraint:
Most effective acquisition channel:
Best society model:
Most important playbook change:

Final decision

- Move to Phase 11

- Continue stabilising City 2

- Continue City 3 beta

- Expand inside current cities

- Pause new-city launches

- Reprice a city

- Close a weak service area

- Replace or strengthen local management

- Exit a city

5. Corrected Phase 11 go/no-go criteria

The original gate should be strengthened.

A. Network structure gate

| Requirement | Target |
| --- | --- |
| Operational cities | 2 minimum |
| Mature city | At least 1 |
| Validated new city | At least 1 |
| Additional beta cities | Optional |
| Local accountable owner | Every public city |
| National dashboard | Active |
| City command centre | Active in every city |

A network does not need five mature cities before building mobile applications and advanced product features. It does need at least one successful city replication.

B. Quality gate

| Requirement | Target |
| --- | --- |
| Average rating | 4.6+ in every validated/mature city |
| Completion rate | 95%+ |
| On-time performance | 95%+ |
| Provider no-show | Below 1% |
| Refund/dispute rate | Below 3–5% |
| Critical unresolved incidents | Zero |
| Incident definitions | Standardised nationally |
| Support SLA | Consistently achieved |

C. Demand and retention gate

| Requirement | Target |
| --- | --- |
| Mature-city completed services | 1,000+/month |
| New validated city | 300–750/month |
| Mature-city repeat rate | 35%+ |
| New-city repeat rate | 25–40% |
| Subscription renewal | 60%+ |
| Recurring platform-revenue share | Growing toward 25–40% |
| Organic/referral contribution | Meaningful |

D. Supply gate

| Requirement | Target |
| --- | --- |
| Stable active pool | Every public cluster |
| Backup coverage | 90–95%+ |
| Peak capacity | Below 90% |
| Overall sellable capacity | Below 85% |
| Partner payouts on time | 98%+ |
| Expired critical documents | Zero |
| Subscription sales beyond capacity | Zero |

E. Economics gate

| Requirement | Target |
| --- | --- |
| City P&L dashboard | Active |
| Original city contribution | Positive |
| New-city positive cluster | At least one |
| Contribution per completed booking | Positive or credible path |
| CAC by channel | Known |
| Mature-city CAC payback | Under 2–3 months target |
| New-city CAC payback | Improving toward 4–6 months |
| City finances reconciled | Yes |
| Discount dependency | Controlled |

F. Replication gate

| Requirement | Target |
| --- | --- |
| City-launch playbook | Documented and versioned |
| City 2 followed the playbook | Yes |
| City 2 independent of founder firefighting | Yes |
| City onboarding and training repeatable | Yes |
| Society acquisition repeatable | Demonstrated |
| Incident response tested in every city | Yes |
| Price and service configurations city-specific | Yes |
| Cross-city data isolation | Operational |

G. Compliance and governance gate

The DPDP Rules, 2025 were notified with a phased commencement schedule. Multi-city operations should already use clear processing notices, appropriate security safeguards, role-scoped access and auditable grievance handling for addresses, schedules, pet records and provider documents.

The Code on Social Security recognises gig and platform workers, and the Labour Ministry’s June 2026 aggregator direction states that covered aggregators must electronically share required worker details through the prescribed framework. Obtain a formal classification analysis and implement applicable worker-registration/reporting controls before wider scale.

Consumer flows must provide transparent terms, fair cancellation and an effective grievance mechanism. The CCPA’s dark-pattern guidance specifically identifies difficult or hidden subscription cancellation as a subscription trap, and it issued a 2025 self-audit advisory to e-commerce platforms.

6. Final Phase 10 recommendation

Build:

A city-by-city replication engine that uses mandatory launch gates, small service clusters, accountable city managers, versioned local pricing, society-led demand, independent city economics and centrally governed safety, payments and data.

Do

- Prove City 1 before expansion.

- Launch one or two clusters per city.

- Reserve provider and backup capacity.

- Track active supply—not applications.

- Measure GMV, platform revenue and contribution separately.

- Give every public city one accountable owner.

- Keep payments, safety, data and incident rules central.

- Use local society and partner relationships.

- Expand City 3 only after City 2 passes its gate.

- Close weak clusters instead of protecting vanity city counts.

Do not

- Launch five cities from 100 bookings.

- Call a waitlist page an active city.

- advertise city-wide availability from one neighbourhood.

- use one national price for every cluster.

- guarantee one permanent sitter.

- hide city losses inside network totals.

- weaken verification to recruit faster.

- issue franchise rights before the playbook is proven.

- let local teams manage customer money outside the central system.

- count all complaints and safety events under one ambiguous incident rate.

Final Phase 10 approval matrix

| Rule | Final decision |
| --- | --- |
| Mandatory city-launch gates | APPROVED—NON-NEGOTIABLE |
| First three to five cities company-operated | APPROVED AS THE DEFAULT STRATEGY |
| Area-cluster expansion | APPROVED—NON-NEGOTIABLE |
| City-level P&L dashboard | APPROVED—MANDATORY |
| Central safety standards plus local operations | APPROVED AS THE OFFICIAL OPERATING MODEL |

Phase 10 win condition

The business launches and validates a second city—and begins a third—using the same documented operating system while maintaining customer ratings, safety, provider reliability, subscription capacity and positive unit economics.

Decision before Phase 11

Move to Phase 11 only when one new city has reached validated status and the platform’s next constraint is genuinely product capability—not unresolved city operations.

Phase 11 should then focus on mobile applications, advanced tracking, matching, loyalty and automation without automating unstable operational behaviour.

Final Phase 10 decision: GO—with all five proposed rules approved and the strengthened Phase 11 gates above.

Phase 11: Mobile App and Advanced Product Phase 📱🐾

Customer App, Sitter App, Tracking, Automation and Product-Scale Architecture

Executive decision

Approve Phase 11, but split it into three controlled product waves:

Wave 1 — Sitter execution app

↓

Wave 2 — Customer mobile app

↓

Wave 3 — Advanced matching, loyalty, health records and automation

The central principle is correct:

Do not build mobile apps to look like a mature startup. Build them when native capabilities solve measurable operational and retention problems.

The strongest Phase 11 outcome is not “two apps published.” It is:

- Sitter execution becomes more reliable

- Customers receive better visibility and control

- Operations require fewer manual interventions

- Repeated bookings and subscriptions become easier

- Location, payment and personal data remain controlled

- Every advanced feature improves contribution or service quality

1. What changes in Phase 11

Until Phase 10, the operating stack consists mainly of:

- Website or PWA

- Admin dashboard

- Sitter web dashboard

- WhatsApp and SMS communication

- Manual scheduling and escalation

- Semi-automated assignment

- Browser-based subscriptions and payments

This can work during initial validation because human intervention helps discover the correct operating process.

However, at multi-city scale, several problems usually emerge:

- Sitters miss browser notifications

- Location tracking stops when the browser closes

- Media uploads fail on unstable networks

- Service reports are delayed

- Admins manually chase check-ins

- Customers repeatedly open WhatsApp for updates

- Subscription management is fragmented

- Booking data and real-world execution drift apart

- City teams develop informal workarounds

Phase 11 should turn the proven operating process into a dependable native product system.

2. Should Phase 11 start only at 3,000–10,000 bookings?

The proposed targets are directionally useful, but not absolute

| Requirement | Proposed target | Final recommendation |
| --- | --- | --- |
| Active cities | 2–5 | At least one mature city and one validated second city |
| Monthly bookings | 3,000–10,000+ | 3,000+ completed services is a strong customer-app gate |
| Active subscribers | 500+ | Strong target, but sitter app can begin earlier |
| Repeat booking rate | 35–50% | Approve |
| Customer rating | 4.6+ | Approve |
| Sitter reliability | 95%+ | Approve, but track completion, punctuality and no-show separately |
| PWA usage stable | Yes | Must be measurable |
| Admin operations stable | Yes | Mandatory |
| Unit economics positive | Yes | At least original city and one replicated cluster |
| Subscription system working | Yes | Mandatory before advanced mobile subscription controls |

Better approach: separate the sitter-app gate from the customer-app gate

Sitter app can begin earlier

A sitter app may be justified at approximately:

- 1,000–3,000 completed services per month

- 20–50 active field providers

- Two or more operating clusters

- Repeated check-in, GPS, report or notification failures

- Meaningful admin time spent monitoring service execution

The sitter app is primarily an operations and quality investment.

Customer app should usually wait longer

A customer app becomes commercially justified when:

- Monthly completed services exceed approximately 3,000

- Repeat rate is above 35%

- A meaningful subscriber base exists

- Customers regularly return to track, rebook or manage plans

- Push, loyalty and subscription controls can improve retention

- Customer acquisition and retention economics support app development

The customer app is mainly a retention, convenience and lifetime-value investment.

3. What “PWA usage stable” should mean

Do not use “the website works” as the definition.

Measure:

| Metric | Healthy signal |
| --- | --- |
| Booking completion rate | Stable or improving |
| Mobile checkout success | 95%+ technical success |
| Login success | 98%+ |
| Crash/error rate | Low and monitored |
| Customer repeat usage | 35%+ |
| Sitter dashboard adoption | 80–90%+ of active sitters |
| Report submission | 95%+ |
| Payment reconciliation | Stable |
| Subscription management | Working |
| Support issues caused by the PWA | Clearly categorised |
| App demand | Customers/sitters repeatedly requesting native capabilities |

Native-app problem test

Build the app when multiple problems genuinely require mobile-native capabilities:

- Background or session-based location

- Reliable camera and media capture

- Offline service reports

- Push notifications

- Native biometric authentication

- Live operational status

- Device-level secure storage

- Deep links

- Faster repeated workflows

Do not build it merely because competitors have apps.

4. Why the sitter app should come first

Your recommendation is correct.

Sitter performance affects every transaction

A customer app can improve booking convenience. A sitter app can improve:

- Arrival reliability

- Service evidence

- Location tracking

- Safety escalation

- Report submission

- Backup handling

- Customer communication

- Admin visibility

- Payout accuracy

If sitter execution fails, a polished customer interface only makes the failure more visible.

Native capabilities provide greater immediate value to sitters

A sitter app can provide:

- One-tap accept or reject

- Today’s schedule

- Navigation

- Start-service check-in

- Background route tracking during an active walk

- Photo/video capture

- Offline report drafts

- Incident button

- Customer handover confirmation

- Earnings and payout status

- Leave and availability management

These workflows are more difficult to implement reliably in a browser.

5. Important GPS-tracking rule

Do not track sitters continuously

The correct location model is:

Sitter accepts booking

↓

Sitter travels toward service area

↓

Sitter explicitly starts service

↓

Tracking session begins

↓

Walk or visit is completed

↓

Tracking session stops

↓

Route/report saved

Avoid:

Sitter installs app

↓

Platform tracks location all day

Recommended location states

LOCATION_OFF

PRE_SERVICE_OPTIONAL

ACTIVE_SERVICE_TRACKING

PAUSED

SERVICE_COMPLETED

LOCATION_UPLOAD_PENDING

Permission design

Request location only when the sitter activates the relevant feature.

Apple requires location use to be directly relevant to the app’s function and requires notice and consent before location data is collected or used. Apple also advises developers to use background updates only when real-time background information is genuinely needed.

On Android, background location requires a separate permission model; on Android 11 and later, users generally enable “Allow all the time” from system settings. Google Play permits background location only when it is important to the app’s core functionality and requires a declaration, prominent disclosure, privacy policy and review evidence.

Best implementation

Use background location only for an active, user-started walk session.

This produces a defensible core use case:

Tracking the pet’s service route while the sitter performs the booked walk, including when the screen is locked.

Do not use location for:

- Advertising

- General sitter monitoring

- Attendance outside booked services

- Unrelated analytics

- Persistent employee surveillance

Battery and accuracy

Background location can materially affect battery life, and Android may throttle background updates. Use:

- Moderate update intervals

- Distance-based updates

- Automatic timeouts

- Immediate stop after service completion

- Upload batching

- Location-quality indicators

- Offline storage with later synchronisation

Android’s official guidance recommends removing updates when no longer needed and setting reasonable timeouts to prevent continued battery consumption.

6. Sitter app MVP

P0 features

Authentication and device security

- OTP login

- Device registration

- Optional biometric unlock

- Session expiration

- Remote logout

- Suspicious-login flag

Booking queue

- New booking request

- Accept or decline

- Response deadline

- Pet summary

- Location and travel estimate

- Expected payout

- Special handling requirements

Today’s schedule

- Confirmed bookings

- Travel window

- Society/gate instructions

- Primary and backup assignment

- Late-arrival warning

- Navigation link

Service execution

Arrived

↓

Handover confirmed

↓

Start service

↓

GPS/session timer

↓

Photos and observations

↓

Complete service

↓

Submit report

Care report

- Duration

- Route

- Toilet activity

- Water/food

- Mood

- Behaviour

- Medication confirmation where authorised

- Media

- Concern flag

- Customer note

Incident handling

- Pet escaped

- Pet injured

- Bite/aggression

- Customer unavailable

- Gate denied

- Unsafe environment

- Medical concern

- Service cannot continue

The incident action should capture:

- Time

- Location

- Booking

- Provider

- Pet

- Immediate action

- Media/evidence

- Support call state

Earnings

- Completed services

- Pending earnings

- Adjustments

- Payout date

- Payout completed

- Dispute option

Availability

- Weekly schedule

- Leave

- Temporary unavailability

- Service zones

- Maximum daily assignments

- Morning/evening preferences

7. Offline-first sitter architecture

The sitter app must remain usable when mobile connectivity is weak.

Features that should work offline

- View cached booking details

- Start and stop an assigned service

- Capture location points locally

- Take photographs

- Draft report

- Open safety instructions

- Trigger emergency call actions

- Record incident evidence

Synchronisation states

LOCAL_ONLY

SYNC_PENDING

SYNCING

SYNCED

SYNC_FAILED

CONFLICT_REVIEW

Important controls

- Encrypt local sensitive data

- Store only currently relevant bookings

- Delete cached access details after the service retention window

- Retry uploads automatically

- Show whether the report was actually submitted

- Prevent duplicate completion events

- Reconcile GPS timestamps on the server

- Never mark the booking completed solely because the device displays success

8. Customer mobile app

The customer app should focus on recurring trust and convenience.

P0 customer modules

Home dashboard

- Next booking

- Sitter status

- Pet selector

- Remaining credits

- Subscription renewal

- Recommended action

- Support shortcut

Booking

- Select pet

- Select service

- Choose date/time

- View price

- Choose preferred sitter

- Pay or use credit

- Confirm instructions

Live service view

- Sitter assigned

- Sitter en route

- Service started

- Route/status where appropriate

- Media updates

- Service completed

- Report ready

Pet profiles

- Basic details

- Breed and age

- Care instructions

- Behaviour

- Feeding

- Medication instructions

- Emergency contacts

- Vaccination documents

- Service restrictions

Subscriptions

- Active plan

- Available credits

- Reserved credits

- Completed services

- Renewal date

- Pause

- Upgrade

- Downgrade

- Cancel future renewal

- Payment recovery

Support

- Booking issue

- Payment issue

- Safety concern

- Sitter late

- Refund request

- Account and privacy settings

9. Push-notification architecture

Push notifications should improve timeliness, but must not become the system of record.

Recommended events

Customer

- Booking confirmed

- Sitter assigned

- Sitter en route

- Walk started

- Service completed

- Report available

- Schedule changed

- Payment failed

- Renewal upcoming

- Credit expiring

- Safety/support update

Sitter

- New booking

- Acceptance deadline

- Upcoming booking

- Travel reminder

- Check-in overdue

- Report pending

- Backup request

- Payout processed

- Document expiring

- Support message

Firebase Cloud Messaging provides cross-platform message delivery for Android, iOS, web and Flutter clients. Apple uses APNs for remote notification delivery.

Notifications still require user permission. Android 13 and later require the POST_NOTIFICATIONS runtime permission for most notifications, while iOS requires notification authorisation before alerts, sounds or badges are shown.

Notification design rules

- Ask permission after explaining the value

- Let users control marketing separately

- Do not include sensitive home or pet-health details in lock-screen text

- Deep-link to the relevant booking

- Store every important event in the app inbox

- Use WhatsApp/SMS or support calls for critical operational fallback

- Never assume push delivery alone proves the user was informed

10. AI-assisted sitter matching

Correct use of AI

AI should recommend and rank candidates.

It should not autonomously assign every pet without operational constraints.

Booking request

↓

Hard eligibility filters

↓

Capacity and geography filters

↓

Risk and skill filters

↓

AI/rules-based ranking

↓

Recommended sitters

↓

Automatic or human confirmation based on risk

Hard filters before AI scoring

A sitter must first satisfy:

- Active verification

- Correct service permission

- Correct city/zone

- Available time

- Travel limit

- Pet-size capability

- Behaviour-risk eligibility

- Society access

- Capacity

- No quality suspension

AI must never rank an ineligible sitter above an eligible one.

Suggested ranking factors

| Factor | Example weight |
| --- | --- |
| Pet compatibility | 20 |
| Previous relationship | 20 |
| Reliability | 15 |
| Distance/travel time | 15 |
| Availability fit | 10 |
| Customer preference | 10 |
| Rating and report quality | 5 |
| Backup availability | 5 |

High-risk cases requiring human approval

- Aggressive pet history

- Senior/medical care

- Medication

- First boarding

- Previous incident

- Multiple large pets

- Special-access home

- Emergency booking

- Very young animals

Explainability

The operations team should see reasons such as:

Recommended because Riya has completed seven services with Bruno, has 98% punctuality, is 1.2 km away and has matching morning availability.

Avoid an unexplained “AI score: 92.”

11. Loyalty system

Do not begin with complex points and tiers.

Start with behaviour-linked benefits

Reward:

- Completed repeat bookings

- Subscription renewal

- Referrals after completed service

- On-time customer handover

- Honest reviews

- Society programme participation

Early loyalty model

Care Credits

- Earn after completed eligible service

- Apply to future service

- Non-transferable

- No cash value

- Expiry clearly disclosed

- Refund and reversal rules visible

Avoid

- Points for app opens

- Gamifying emergency or medical care

- Unlimited liability

- Confusing conversion rates

- Hidden expiry

- Rewards before service completion

- Referral abuse

12. Wallet versus service credits

Use the word credits rather than “wallet” in the initial release.

Recommended design:

- Non-transferable

- No cash withdrawal

- No peer-to-peer transfer

- Used only for eligible platform bookings

- Issued for subscription entitlement, refund, promotion or service recovery

- Separate balances by credit type

- Full transaction history

RBI distinguishes closed-system instruments used only to buy the issuer’s own goods or services from broader prepaid payment instruments. Because your marketplace may facilitate third-party service providers, a reloadable customer-funded balance can create additional regulatory questions. Obtain payments counsel before creating cash-like stored value, transferability or third-party merchant acceptance.

Recommended Phase 11 approach

Launch:

- Subscription service credits

- Promotional credits

- Refund credits with customer choice where lawful

- Loyalty credits

Defer:

- User-funded cash wallet

- Peer transfer

- Cash-out

- Cross-merchant usage

- Stored balances unrelated to an active service obligation

13. Pet health records

The app may become the owner-controlled record layer for:

- Vaccinations

- Allergies

- Medication instructions

- Veterinary consultation documents

- Lab reports

- Medical conditions

- Surgery history

- Follow-up reminders

Access design

| Role | Access |
| --- | --- |
| Pet parent | Full record |
| Assigned sitter | Only care information necessary for current service |
| Vet partner | Records explicitly shared for the consultation |
| Support | No routine clinical access |
| Society/RWA | No access |
| Marketing | No access |
| Admin | Restricted and audited |

Safety rules

- AI does not provide final diagnosis

- Support does not interpret medical reports

- Sitters see only operationally necessary instructions

- Every document share is logged

- Owners can revoke access

- Records have retention and deletion policies

- Urgent symptoms route to a vet, not an automated diagnosis

Location history, home schedules, provider records and pet-health documents require clear notices, access controls, security safeguards and grievance/deletion handling under the Indian data-protection framework. The DPDP Rules, 2025 were notified with phased commencement.

14. Account and privacy controls

Both apps should include:

- Download personal data

- Update profile information

- Communication preferences

- Location-permission status

- Active devices

- Logout from other devices

- Delete account

- Request data correction

- Request support

- Privacy policy

- Retention explanation

Apple requires apps that support account creation to let users initiate account deletion inside the app. Google Play requires a readily discoverable deletion option inside the app and a corresponding external web deletion path.

The deletion system must distinguish:

- Deleting the app

- Deactivating the account

- Cancelling a subscription

- Deleting the account and eligible associated data

These are different actions.

15. Do not build a basic wrapper

The proposed “fast app build in 2–3 months” is acceptable only for:

- Internal testing

- Sitter beta

- Limited native proof of concept

It is not a strong public app strategy if the result is just the website inside a mobile shell.

Apple’s App Review Guidelines state that apps should provide features, content and UI beyond a repackaged website.

A public mobile app should add real native value

At minimum:

- Native push

- Offline workflows

- Native camera/media capture

- Secure device sessions

- Native location during active services

- Deep linking

- Biometric unlock

- Smooth repeated booking

- Background upload/retry

- App-specific accessibility and navigation

16. Recommended technology strategy

One backend, multiple clients

Core API platform

├── Admin web application

├── Customer web/PWA

├── Customer mobile app

└── Sitter mobile app

Do not create separate business logic in every client.

Keep server-side:

- Pricing

- Eligibility

- Matching rules

- Capacity

- Booking status transitions

- Credit ledger

- Payment verification

- Refund rules

- Incident state

- Access control

- Subscription lifecycle

The apps should not be trusted to decide:

- Whether a payment succeeded

- Whether a sitter is eligible

- How many credits remain

- Whether a booking is completed

- Whether a refund is owed

- Whether an incident can be closed

17. Cross-platform versus native

Cross-platform is appropriate when

- The team is strong in TypeScript/Dart

- Most features share common UI and logic

- Faster simultaneous iOS/Android delivery matters

- Native bridges for GPS, camera, push and background jobs are tested carefully

Fully native may be justified when

- Background location is highly complex

- Device-level performance is critical

- The team already has strong iOS and Android specialists

- Platform-specific workflows differ significantly

- Reliability outweighs initial development speed

Practical recommendation

Use a well-supported cross-platform framework for both apps, but treat these as native-critical modules:

- Location

- Background service/session

- Push

- Camera and uploads

- Secure storage

- Biometrics

- Offline database

- Deep links

Do not choose the framework solely from developer familiarity. Run a technical proof of concept for:

- Screen locked during a 45-minute walk

- Location retained with expected battery use

- Network lost and restored

- Photo/report upload retry

- Push received across device states

- App killed and reopened

- Permission denied and later enabled

18. Corrected Phase 11 duration

Fast phase: 2–3 months

Realistic output:

- Sitter app MVP

- Android-first controlled pilot

- Basic customer app prototype

- Existing backend reused

Not realistic:

- Two polished apps

- Advanced GPS

- AI matching

- Health records

- Loyalty

- complete wallet

- mature offline support

- full multi-city rollout

Standard phase: 4–6 months

Recommended output:

- Production-ready sitter app

- Customer app MVP

- Push notification platform

- Session-based tracking

- Offline sitter reports

- Subscription controls

- Service credits

- City command-centre integrations

- Rules-assisted matching

- Controlled launch in two cities

Advanced phase: 6–12 months

Add:

- AI matching optimisation

- Loyalty

- deeper health records

- predictive capacity

- route optimisation

- dynamic availability

- fraud/risk detection

- advanced analytics

- experiment platform

- further accessibility and localisation

19. Recommended 6-month execution plan

Month 1 — Product foundation

- Analyse PWA and operations friction

- Define app personas

- Finalise mobile architecture

- Prototype location tracking

- Prototype offline sync

- Define app analytics

- Map permissions and privacy

- Design sitter MVP

- Prepare APIs and event model

Exit gate

- Background tracking proof works

- Offline report sync works

- Critical API gaps identified

- Privacy model approved

- Sitter workflows user-tested

Month 2 — Sitter app MVP

Build:

- Login

- Booking queue

- Schedule

- Service check-in

- Timer and location

- Media capture

- Report

- Incident button

- Earnings

- Availability

- Push notifications

Pilot

- Internal team

- 5–10 trusted sitters

- One service cluster

- Test devices across Android versions

Month 3 — Sitter pilot and hardening

Expand to:

- 20–50 sitters

- Two cities

- Multiple device brands

- Weak-network scenarios

Measure:

- Booking acceptance time

- Check-in rate

- Report completion

- GPS success

- Battery use

- Upload failures

- Crash-free sessions

- Support tickets

- Sitter satisfaction

Exit gate

- 95%+ service reports

- 98%+ successful check-in/out recording

- Low crash rate

- No uncontrolled background tracking

- Offline recovery proven

- Admin can resolve sync conflicts

Month 4 — Customer app MVP

Build:

- Login/onboarding

- Pet profiles

- Booking

- Payment

- Live status

- Care reports

- Subscriptions

- Credits

- Support

- Notification inbox

- Account and privacy controls

Begin with repeat customers and subscribers.

Month 5 — Customer beta

Launch to:

- 100–500 repeat customers

- Existing subscribers

- Two stable cities

- Society residents

Measure:

- App activation

- Booking conversion

- Repeat bookings

- Subscription self-service

- Push opt-in

- Support reduction

- Crash-free sessions

- App versus PWA retention

Do not force customers to install the app. Keep the PWA functional.

Month 6 — Production rollout and advanced foundation

- Improve app-store readiness

- Add explainable matching recommendations

- Add loyalty credits

- Add health-document MVP

- Expand sitter rollout

- Launch customer app publicly

- Harden account deletion

- Finalise dashboards

- Audit permissions

- Review app economics

- Prepare Phase 12 roadmap

20. Phase 11 success metrics

Sitter app

| Metric | Target |
| --- | --- |
| Active-sitter adoption | 85–95% |
| Booking acknowledgement | 95%+ |
| Digital check-in/out | 98%+ |
| Report completion | 95%+ |
| GPS-session success | 95%+ |
| Offline sync recovery | 99%+ |
| Provider no-show | Below 1% |
| Support cases per 100 bookings | Decreasing |
| Crash-free sessions | 99%+ target |
| Battery complaints | Below defined tolerance |

Customer app

| Metric | Target |
| --- | --- |
| Activation among invited repeat users | 40–60%+ |
| Monthly active app customers | Growing |
| App booking conversion | Above mobile-web baseline |
| Repeat booking rate | Increasing |
| Subscription self-service | 70%+ |
| Push opt-in | 50–75%, depending on platform and timing |
| Support contacts per booking | Decreasing |
| App rating | 4.5+ after meaningful review volume |
| Crash-free sessions | 99%+ target |
| Account deletion working | Yes |

Business

| Metric | Target |
| --- | --- |
| Manual operational touches/booking | Down 30–50% |
| On-time fulfilment | 95%+ |
| Repeat rate | 35–50% |
| Subscription renewal | 60–80% |
| City rating | 4.6+ |
| Contribution per booking | Stable or improving |
| Refund/dispute rate | Below 3–5% |
| Critical unresolved incidents | Zero |

21. Main Phase 11 risks

| Risk | Prevention |
| --- | --- |
| Building for prestige | Require measurable operational problem |
| Website wrapper rejection | Add genuine native utility |
| GPS privacy complaints | Session-based tracking and clear consent |
| Battery drain | Controlled intervals and automatic stop |
| Missed push notifications | In-app state and fallback channels |
| Offline data loss | Local encrypted queue and retry |
| AI matching errors | Hard eligibility filters and human override |
| Sensitive record exposure | Field-level access and audit logs |
| Credit disputes | Append-only transaction ledger |
| Wallet regulation risk | Start with non-cash service credits |
| Sitter adoption failure | Design with sitters and pilot gradually |
| Customer app abandonment | Target repeat users, preserve web access |
| Two-app complexity | Shared APIs, design system and event model |
| Store rejection | Privacy, account deletion and permission readiness |
| Overbuilding | Launch P0 modules before loyalty and advanced AI |

22. Final decisions

| Proposal | Decision |
| --- | --- |
| Build full customer app | Approve after repeat-use gate |
| Build sitter app first | Approve—recommended |
| Advanced GPS tracking | Approve only during active services |
| Push notifications | Approve with permission and fallback design |
| AI-assisted matching | Approve as recommendation system first |
| Loyalty system | Approve after core app adoption |
| Wallet | Defer cash-like wallet; use service credits |
| Advanced subscription management | Approve |
| Pet health records | Approve as owner-controlled record layer |
| App phase at 2–5 cities | Approve when one new city is validated |
| Require 500 subscribers before any app work | Modify—customer app gate, not sitter app gate |
| 4–6 month duration | Approve for production MVPs |
| 2–3 month wrapper | Not recommended for public launch |
| PWA replacement | Reject; retain PWA as a supported channel |

Final Phase 11 recommendation

Build:

A sitter-first mobile operating system that captures reliable check-ins, active-service location, offline reports, incidents and payouts—followed by a customer app focused on booking, live visibility, subscriptions, credits and pet-care records.

Do not:

- Build two giant apps simultaneously

- Track sitters continuously

- Request every permission during onboarding

- Put business rules only in the apps

- Let AI override eligibility and safety controls

- Build a cash-like wallet without regulatory analysis

- Hide account deletion

- abandon the website/PWA

- launch loyalty before core fulfilment works

- treat app downloads as the primary success metric

Phase 11 win condition

Mobile products reduce operational effort and service failures while increasing customer retention, without weakening privacy, battery performance, payment accuracy or sitter adoption.

Phase 11 status: GO—start with the sitter app, validate it operationally, then launch the customer app to repeat customers and subscribers.

Phase 11 Product Priority and Mobile Architecture 📱🐾

Executive decision

Approve the sitter-first strategy and React Native with Expo recommendation.

However, the proposed priority list needs two changes:

- Advanced GPS is not a separate fourth-stage product. Session-based tracking is part of the sitter-app foundation.

- Credits, loyalty and wallet must be separated. Service credits can launch early; loyalty comes later; a cash-like wallet should be deferred.

Corrected build order

0. Shared mobile platform foundation

↓

1. Sitter app + active-service GPS

↓

2. Advanced admin command centre

↓

3. Customer mobile app

↓

4. Rules-based matching → AI-assisted matching

↓

5. Service credits → loyalty

↓

6. Pet health timeline

↓

7. Society and corporate mobile features

The sitter app and command centre should be developed together because they are two sides of the same operating workflow:

Sitter app creates live operational events

↓

Admin command centre monitors and resolves them

1. Phase 11 main principle

Wrong approach

Build attractive customer app

↓

Add animations and loyalty points

↓

Customers book more

↓

Sitters still miss bookings and reports

↓

Operational failures increase

A polished customer application amplifies demand. It does not repair weak field execution.

Correct approach

Strengthen sitter execution

↓

Strengthen admin monitoring

↓

Reduce fulfilment failures

↓

Improve customer visibility

↓

Increase repeat usage

↓

Add intelligence and loyalty

For this marketplace, the sitter application is not a secondary partner portal.

The sitter app is the field operating system for every physical service.

It controls the transition between a digital booking and a real service:

Booking accepted

↓

Sitter arrives

↓

Pet handover confirmed

↓

Service begins

↓

Service is documented

↓

Incident reported if necessary

↓

Service completed

↓

Customer report delivered

↓

Provider payout released

2. Priority 0: Shared mobile foundation

Before building app screens, strengthen the common platform.

Required shared capabilities

- Versioned APIs

- Mobile authentication

- Device registration

- Push-token management

- Booking event model

- Offline synchronisation protocol

- Media-upload pipeline

- Location-session APIs

- Feature flags

- Analytics taxonomy

- Error monitoring

- App-version enforcement

- Remote configuration

- Role-based access

- Audit logs

Server-authoritative model

The backend—not either mobile app—must determine:

- Whether a booking is valid

- Whether a sitter is eligible

- Whether capacity exists

- Which price applies

- Whether a payment succeeded

- How many credits remain

- Whether a service can be completed

- Whether a refund is due

- Whether an incident can be closed

The applications should collect actions and display state. They should not become independent sources of business truth.

3. Priority 1: Sitter mobile application

Primary objective

Improve service completion, punctuality, evidence quality, safety and provider communication.

P0 sitter modules

Booking inbox

Show:

- New request

- Response deadline

- Service type

- Pet summary

- Location and estimated travel

- Service duration

- Expected payout

- Special handling conditions

- Accept or decline

A decline should request a structured reason:

- Too far

- Schedule conflict

- Pet-handling limitation

- Payout issue

- Temporary unavailability

- Other

This provides data for matching and pricing improvements.

Daily schedule

Show:

- Today’s services

- Travel windows

- Society gate instructions

- Customer handover method

- Primary or backup assignment

- Late-risk warning

- Navigation

- Support contact

The app should proactively flag impossible schedules.

Example:

Booking A ends: 8:00 AM

Travel to Booking B: 32 minutes

Booking B begins: 8:15 AM

Result: schedule conflict

Service execution

Navigate

↓

Arrive

↓

Confirm handover

↓

Start service

↓

GPS/timer begins

↓

Capture observations

↓

Complete service

↓

Submit report

Required safeguards:

- Cannot start too far from the service location without reason

- Cannot complete before minimum duration without explanation

- Duplicate completion blocked

- Offline actions assigned local timestamps

- Server reconciles conflicting events

- GPS limitations shown honestly

Report card

Capture:

- Start/end time

- Duration

- Route where applicable

- Distance

- Toilet activity

- Water or food

- Pet mood

- Behaviour

- Medication confirmation where explicitly authorised

- Photos

- Sitter note

- Concern flag

The report should be structured enough for analytics but retain a short human note.

Incident reporting

One-tap incident categories:

- Pet escaped or became lost

- Pet injury

- Bite or aggressive behaviour

- Sitter injury

- Medical concern

- Customer unavailable

- Society gate denied

- Unsafe environment

- Property/access issue

- Service cannot continue

Critical incident flow:

Incident selected

↓

Service timer preserved

↓

Immediate instructions shown

↓

City operations alerted

↓

Customer contact initiated

↓

Evidence captured

↓

Central safety review opened

The sitter should not have to complete a long form before receiving urgent instructions.

Earnings and payouts

Show:

- Completed services

- Pending validation

- Approved earnings

- Adjustments

- Bonuses

- Deductions with reasons

- Payout date

- Settlement status

- Dispute action

Financial transparency improves provider trust and reduces support contacts.

Availability and leave

Sitters should manage:

- Weekly availability

- One-time unavailability

- Planned leave

- Service zones

- Service types

- Maximum assignments

- Morning/evening preferences

Subscription schedules should warn operations before a primary sitter’s leave creates a coverage gap.

4. Advanced GPS belongs inside the sitter-app foundation

Correct tracking model

Track only during a user-initiated service session:

Sitter taps “Start Walk”

↓

Tracking begins

↓

App enters background if necessary

↓

Location points are stored locally

↓

Points sync to the server

↓

Sitter taps “Complete”

↓

Tracking stops

Expo supports background tasks and background-location updates through its TaskManager and Location APIs, but operating-system constraints still apply. Expo’s documentation notes, for example, that background location stops if the user terminates the app and resumes only after reopening it.

Never use continuous workforce surveillance

Do not track:

- Outside an accepted booking

- Throughout the sitter’s day

- During leave

- After service completion

- For advertising

- Without clear disclosure

GPS session schema

location_sessions

- id

- booking_id

- sitter_id

- device_id

- started_at

- stopped_at

- status

- tracking_reason

- consent_version

- point_count

- distance_meters

- quality_score

location_points

- id

- session_id

- recorded_at

- latitude

- longitude

- accuracy_meters

- speed

- heading

- source

- sync_status

GPS quality indicators

The customer should not see an apparently precise route when the location signal is poor.

Possible statuses:

- Accurate

- Approximate

- Temporarily unavailable

- Device offline

- Upload pending

- Route incomplete

GPS acceptance criteria

- Tracking starts only after explicit sitter action

- Tracking stops automatically after completion

- Offline points sync later

- Duplicate points are handled

- Poor-accuracy points are filtered or marked

- Battery impact is measured on real devices

- No location remains active after the booking

- Customer sees only the relevant booking route

5. Priority 2: Advanced admin command centre

Objective

Transform admin operations from manual monitoring into exception-based management.

Instead of staff checking every booking, the system should surface only bookings requiring intervention.

Main operational states

HEALTHY

AT_RISK

ACTION_REQUIRED

CRITICAL

National command centre

Display:

- Cities and operational stages

- Bookings in progress

- Unassigned services

- Late check-ins

- GPS-session failures

- Backup requests

- Open incidents

- Provider reliability

- Subscription capacity

- Payment failures

- City contribution

City command centre

Today’s operations

- Due today

- Confirmed

- In progress

- Completed

- Unassigned

- Late

- Backup required

- Report overdue

Live map

Show only operationally relevant states:

- Sitters travelling to accepted services

- Active service sessions

- Bookings at risk

- Critical incidents

Do not expose all providers’ continuous locations.

Automated alerts

Examples:

Booking unassigned 6 hours before start

Primary sitter cancelled

No approved backup

Sitter has not checked in after tolerance window

GPS stopped unexpectedly during active walk

Report missing 30 minutes after completion

Customer gave rating below 4

Operations actions

- Assign or replace sitter

- Contact customer

- Contact provider

- Adjust time window

- Restore service credit

- Open incident

- Pause provider

- Escalate to central support

Every high-impact action should create an audit record.

6. Priority 3: Customer mobile application

Objective

Improve repeated booking, service visibility, subscription self-service and customer retention.

P0 modules

Home

- Next booking

- Live service status

- Pet selector

- Remaining credits

- Renewal date

- Recommended action

- Support shortcut

Booking

- Choose pet

- Choose service

- Choose schedule

- View verified local availability

- Select preferred sitter where available

- Review transparent price

- Pay or use service credit

Live service

Show:

- Sitter assigned

- Sitter en route

- Service started

- Active route where appropriate

- Photos or updates

- Service completed

- Report available

Push notifications should be a delivery channel, not the system of record. Firebase Cloud Messaging supports cross-platform message delivery, while Expo provides a unified notification client and can use either the Expo push service or direct FCM/APNs delivery.

Pet profiles

- Identity and photograph

- Breed, age and weight

- Behaviour

- Feeding

- Medical/care instructions

- Emergency contacts

- Vaccination documents

- Approved services

- Risk flags

Subscription management

- Current plan

- Available credits

- Reserved credits

- Completed services

- Credit history

- Renewal amount/date

- Pause

- Upgrade

- Downgrade

- Cancel renewal

- Payment recovery

Support

- Sitter late

- Booking problem

- Payment issue

- Safety concern

- Refund request

- Privacy/account request

7. Priority 4: Matching engine before “AI matching”

Do not begin by training a complex model.

Build matching in three stages.

Stage 1: Deterministic eligibility

Remove every sitter who fails a hard requirement:

- Wrong city or zone

- Outside travel limit

- Unavailable

- No required service permission

- Incompatible pet-risk level

- Suspended

- No society access

- Capacity exhausted

- Required documents expired

Stage 2: Rules-based ranking

Rank remaining sitters using explainable factors:

| Factor | Suggested weight |
| --- | --- |
| Previous relationship with pet | 20 |
| Pet/skill compatibility | 20 |
| Travel time | 15 |
| Reliability | 15 |
| Schedule fit | 10 |
| Customer preference | 10 |
| Rating/report quality | 5 |
| Backup availability | 5 |

Stage 3: AI-assisted ranking

Once sufficient historical data exists, a model can estimate:

- Acceptance probability

- On-time probability

- Completion probability

- Customer satisfaction

- Repeat-sitter likelihood

- Cancellation risk

The model should generate recommendations—not bypass safety filters.

Explainable output

Operations should see:

Recommended because Riya has completed eight services with Bruno, has 98% punctuality, is 1.4 km away and has matching weekday availability.

Not:

AI score: 94.

Human approval required

- Behaviourally high-risk pets

- Medication

- Senior or medical care

- First boarding

- Previous incident

- Emergency request

- Multiple large pets

- Unusual property access

8. Priority 5: Credits, loyalty and wallet

These are three different products.

A. Service credits — early

Used for:

- Walking-plan entitlements

- Starter packs

- Service recovery

- Eligible refunds

- Promotions

Required ledger:

GRANT

RESERVE

CONSUME

RELEASE

RESTORE

EXPIRE

ROLLOVER

Service credits should already exist before the customer app because subscription fulfilment depends on them.

B. Loyalty — later

Reward meaningful behaviour:

- Completed repeat service

- Subscription renewal

- Successful referral

- Society participation

- Long-term retention

Do not reward app opens or encourage unnecessary pet services.

C. Cash-like wallet — defer

Do not initially build a customer-funded, transferable stored-value wallet.

Use:

- Non-transferable service credits

- No cash withdrawal

- No peer-to-peer transfer

- Clear expiry

- Full transaction history

- Usage only for eligible platform services

This reduces product complexity and financial-regulatory risk.

9. Priority 6: Pet health timeline

Objective

Create an owner-controlled continuity record, not an automated diagnostic product.

Timeline events

- Vaccination

- Deworming

- Allergy

- Medication instruction

- Veterinary consultation

- Test or report

- Surgery

- Grooming concern

- Injury or incident

- Follow-up reminder

Access controls

| User | Access |
| --- | --- |
| Pet parent | Full record |
| Assigned sitter | Current-service care instructions only |
| Vet partner | Explicitly shared records |
| Customer support | Minimal operational access |
| Society/RWA | No access |
| Marketing | No access |

AI boundaries

AI may:

- Extract a vaccination date from a document

- Organise records

- Generate reminders

- Summarise owner-provided notes

- Suggest contacting a veterinarian

AI must not:

- Diagnose

- Prescribe

- Interpret an emergency as safe

- Replace a registered professional

10. Priority 7: Society and corporate features

Keep them web-based during Phase 11

A separate society or corporate mobile app is unlikely to justify the maintenance cost initially.

Society web dashboard

- Resident registrations

- Upcoming events

- Aggregate bookings

- Society offers

- Gate roster

- Complaint status

- Monthly report

Corporate web dashboard

- Eligible employees

- Activated users

- Credits issued

- Aggregate utilisation

- Budget remaining

- Service categories

- Renewal report

Do not expose individual employee or resident care information to organisations.

Build native B2B features only when

- Users return frequently

- Push notifications provide real value

- Approvals occur regularly

- Web experience is demonstrably limiting adoption

- A dedicated B2B product owner exists

11. Recommended app ecosystem

Phase 11

| Product | Platform | Status |
| --- | --- | --- |
| Sitter app | React Native mobile | Build first |
| Customer app | React Native mobile | Build second |
| Admin command centre | Web | Upgrade in parallel |
| Partner dashboard | Responsive web/PWA | Retain |
| Society dashboard | Responsive web | Retain |
| Corporate dashboard | Responsive web | Retain |

Later phase

Create a partner mobile application only when groomers, trainers, boarding providers and other specialists have sufficiently frequent bookings to justify native workflows.

12. React Native with Expo vs Flutter

Option A: React Native with Expo

Advantages for your context

- TypeScript and React knowledge transfers directly

- Easier alignment with a Next.js team

- Shared domain types and API clients

- Faster hiring from JavaScript/React talent pools

- Expo provides an integrated framework and native-device APIs

- Native modules can still be added where required

React Native’s own setup documentation recommends using a framework for new applications, and Expo provides a React Native framework with routing, build tooling and native-device modules.

Risks

- Background-location behaviour still varies by operating system

- Some native libraries require development builds or custom configuration

- Poorly selected third-party packages can cause upgrade friction

- JavaScript knowledge does not remove the need to understand iOS and Android lifecycle behaviour

Expo’s current tooling supports React Native’s newer architecture, but third-party-library compatibility should still be checked before adoption.

Option B: Flutter

Advantages

- Strong UI consistency

- Highly controlled rendering

- Single Dart codebase

- Mature architecture guidance

- Excellent for custom interfaces and motion-heavy applications

Flutter officially positions itself as a framework for natively compiled multiplatform applications from one codebase and publishes detailed scalable-app architecture guidance.

Costs for your context

- Requires Dart expertise

- Less direct code and knowledge reuse from Next.js/React

- Separate frontend hiring profile

- Shared TypeScript domain packages cannot be consumed directly

- Web and mobile teams may diverge more quickly

Final framework decision

Use React Native with Expo when:

- Your existing stack is React/Next.js

- Your team is strongest in TypeScript

- Speed and shared engineering practices matter

- You are prepared to test native-critical modules thoroughly

Use Flutter when:

- You have a dedicated Flutter team

- Visual consistency is the dominant requirement

- You accept a separate language and mobile architecture

- You are not optimising for React/TypeScript reuse

For your current full-stack profile, React Native with Expo is the stronger default.

13. Corrected React Native stack

Mobile framework

- React Native

- Expo with development builds

- Expo Router

- TypeScript

Expo Router provides file-based routing and native, deep-linkable navigation across Android, iOS and web.

Do not rely only on Expo Go for production development. Features such as production push notifications require development builds, and native/background behaviour must be tested in real app binaries.

Backend

- Existing Node.js/Next.js API layer

- PostgreSQL

- Existing payment and subscription services

- Background workers/queues

- Object storage

- WebSocket or event-stream layer where justified

Authentication

Use the same identity system, but model mobile sessions separately:

user

device

mobile_session

push_token

refresh_token

last_seen_at

app_version

Store small secrets or tokens in secure device storage. Expo SecureStore provides encrypted local key-value storage; it should not be used as a general database for large payloads.

Navigation

- Expo Router

- Role-separated route groups

- Deep links from notifications

- Auth-protected layouts

Offline database

- Expo SQLite

- Local outbox queue

- Conflict-resolution layer

Expo SQLite persists its database across app restarts and is suitable as the local persistence layer for offline-first workflows.

Use it for:

- Assigned booking cache

- Pending service events

- Location points

- Unsynced reports

- Media-upload queue

Do not store highly sensitive records indefinitely on the device.

Push notifications

Recommended starting choice:

- expo-notifications

- Expo Push Service initially

- Direct FCM/APNs later if more control is required

Expo’s notifications API is push-service agnostic, so the client can later use native device tokens for direct FCM/APNs delivery.

Location and background tasks

- expo-location

- expo-task-manager

- Development-build testing

- Active-service sessions only

Maps

Evaluate:

- Google Maps

- Mappls

- Possibly separate maps for display and address intelligence

Mappls currently offers React Native mapping and live-location SDK documentation, making it a credible India-focused candidate. Selection should be based on address accuracy, route quality, geocoding, pricing, support and compatibility with your chosen Expo development-build workflow.

Run a proof of concept using real launch areas:

- Whitefield

- Baner

- Powai

- Gurugram sectors

- Bopal

- Vesu

Do not select a map provider from screenshots alone.

Media

Use:

- Native camera/image picker

- Local compression

- Temporary file queue

- Signed uploads

- Object storage such as S3-compatible storage or Cloudinary

Expo provides camera, image-picker and filesystem modules suitable for capturing and temporarily storing media before upload.

Analytics

Recommended:

- PostHog for product analytics, funnels and feature flags

- Firebase Analytics as an alternative or supplementary acquisition layer

- Strict event redaction

PostHog’s React Native SDK supports Expo projects, custom events and feature flags.

Do not send:

- Customer addresses

- Access codes

- Detailed health notes

- Raw GPS routes

- Payment credentials

- Incident narratives

to general analytics tools.

Error and performance monitoring

- Sentry

- Release tracking

- Source maps

- Navigation performance

- User/session correlation with privacy safeguards

Sentry provides dedicated React Native and Expo integrations, including Expo Router instrumentation.

14. Recommended repository architecture

apps/

admin-web/

customer-web/

customer-mobile/

sitter-mobile/

packages/

api-client/

domain-types/

validation/

auth-client/

analytics/

feature-flags/

design-tokens/

localization/

config/

Share aggressively

- TypeScript domain types

- API schemas

- Validation rules

- Event names

- Analytics contracts

- Formatting utilities

- Design tokens

- Feature-flag definitions

Share carefully

- Business logic that must remain server-authoritative

- Authentication helpers

- Error handling

- Query keys

Do not force-share

- Web UI components

- Mobile navigation

- Native form controls

- Camera/location workflows

- Offline synchronisation

- Device-permission screens

Shared code should reduce inconsistency, not force mobile experiences to behave like compressed web pages.

15. Advanced admin and app event architecture

All clients should use the same event vocabulary.

Examples:

booking.requested

booking.accepted

booking.declined

sitter.en_route

sitter.arrived

service.started

location.session_started

service.report_drafted

service.completed

service.report_submitted

incident.opened

backup.requested

payment.failed

subscription.renewal_due

Event requirements

Each event should contain:

- Event ID

- Entity ID

- Actor

- Device

- City

- Service zone

- Timestamp

- Idempotency key

- App version

- Offline/online source

- Correlation ID

This gives the command centre one reliable history across web, customer app and sitter app.

16. Four-to-six-month execution plan

Month 1: Foundation and prototypes

- Finalise mobile architecture

- Create monorepo applications

- Define event contracts

- Build development pipelines

- Prototype push

- Prototype background GPS

- Prototype offline SQLite queue

- Prototype signed media uploads

- Define analytics

- Complete privacy review

Exit gate

- GPS works on representative Android/iOS devices

- Offline completion syncs safely

- Push deep links work

- No duplicate booking completion

- API gaps documented

Month 2: Sitter MVP

Build:

- Authentication

- Booking inbox

- Schedule

- Check-in/out

- GPS session

- Report cards

- Incident reporting

- Earnings

- Availability

- Push notifications

Pilot with 5–10 high-performing sitters.

Month 3: Sitter rollout and admin command centre

- Expand to 20–50 sitters

- Connect live operational alerts

- Add backup workflows

- Add missing-report queue

- Add location-session health

- Add app-version dashboard

- Add provider adoption reporting

Exit targets

| Metric | Target |
| --- | --- |
| Digital check-in/out | 98%+ |
| Report completion | 95%+ |
| GPS-session success | 95%+ |
| Offline recovery | 99%+ |
| Crash-free sessions | 99%+ target |
| Provider adoption | 85%+ |

Month 4: Customer app MVP

Build:

- Authentication

- Pet profiles

- Booking

- Payment

- Service status

- Care reports

- Subscriptions

- Credits

- Support

- Privacy/account controls

Release first to repeat customers and subscribers.

Month 5: Customer beta and matching engine

- Invite 100–500 repeat customers

- Build deterministic sitter matching

- Add explainable ranking

- Add customer notification preferences

- Compare app and PWA conversion

- Track subscription self-service

- Retain PWA fallback

Month 6: Production launch and advanced foundation

- Public customer-app release

- Wider sitter rollout

- Add loyalty-credit pilot

- Add health-timeline MVP

- Harden matching recommendations

- Complete app-store compliance

- Improve analytics and experiments

- Finalise Phase 12 roadmap

17. Phase 11 go/no-go metrics

Sitter app

| Requirement | Target |
| --- | --- |
| Active sitter adoption | 85–95% |
| Booking acknowledgement | 95%+ |
| Digital check-in/out | 98%+ |
| Report completion | 95%+ |
| GPS-session success | 95%+ |
| Offline recovery | 99%+ |
| No uncontrolled tracking | Yes |
| Support burden | Decreasing |

Admin command centre

| Requirement | Target |
| --- | --- |
| Critical alerts delivered | 99%+ |
| Unassigned booking visibility | Complete |
| Backup response time | Improving |
| Incident audit trail | Complete |
| City-level access control | Working |
| Manual status reconstruction | Eliminated |

Customer app

| Requirement | Target |
| --- | --- |
| Repeat-user activation | 40–60%+ |
| Booking conversion | Above mobile-web baseline |
| Subscription self-service | 70%+ |
| Care-report views | Increasing |
| Support contacts/booking | Decreasing |
| Crash-free sessions | 99%+ target |
| Store rating | 4.5+ after meaningful volume |

Business impact

| Requirement | Target |
| --- | --- |
| Manual touches per booking | Down 30–50% |
| Completion rate | 95%+ |
| On-time rate | 95%+ |
| Customer repeat rate | 35–50% |
| Subscription renewal | 60–80% |
| Refund/dispute | Below 3–5% |
| Contribution per booking | Stable or improving |

Final approval matrix

| Proposal | Decision |
| --- | --- |
| Sitter app first | APPROVE |
| Advanced admin second | APPROVE—BUILD IN PARALLEL WITH SITTER APP |
| Customer app third | APPROVE |
| GPS as separate fourth product | MODIFY—INCLUDE CORE GPS IN SITTER MVP |
| AI matching | APPROVE AFTER RULES-BASED MATCHING |
| Wallet/credits/loyalty together | SPLIT INTO THREE STAGES |
| Pet health timeline | APPROVE AFTER CORE MOBILE ADOPTION |
| Corporate/society mobile apps | DEFER; USE WEB DASHBOARDS |
| React Native with Expo | APPROVE FOR YOUR STACK |
| Flutter | VALID ALTERNATIVE, NOT THE RECOMMENDED DEFAULT |
| Same backend and auth | APPROVE |
| FCM push | APPROVE |
| Google Maps/Mappls | RUN A LOCAL PROOF OF CONCEPT |
| PostHog/Firebase Analytics | APPROVE WITH DATA REDACTION |
| Sentry | APPROVE |

Final Phase 11 product doctrine

First digitise the work that creates trust. Then digitise the convenience that retains customers. Only after both work should the platform add intelligence, loyalty and deeper records.

Official Phase 11 focus

Sitter application

+

Active-service tracking

+

Admin command centre

+

Customer application

Everything else should follow measured adoption and operational benefit.

Phase 11 Product Priority: GO—with React Native and Expo development builds, sitter-first execution, admin visibility in parallel, and advanced features unlocked only after the operational core is stable.

Phase 11 Products 1–2: Mobile Apps and Advanced GPS System 📱🐾

Executive decision

Both product definitions are strong, with four important corrections:

- GPS tracking belongs inside the sitter-app P0, not as a later standalone feature.

- The sitter must not see more customer data than the current booking requires.

- The emergency button must use multiple escalation channels—not push or WhatsApp alone.

- Route and timing alerts should open operational reviews, not automatically accuse a sitter of misconduct.

The complete system should operate as:

Sitter app

↓ emits verified service events

Operations command centre

↓ monitors exceptions

Customer app

↓ displays trusted service state

Central backend

↓ controls bookings, payments, credits and incidents

Product 1: Sitter Mobile App

1. Product goal

The sitter app should make field delivery:

- More punctual

- More documentable

- Easier to monitor

- Safer during incidents

- Less dependent on WhatsApp

- More transparent for sitters

- Easier to reconcile financially

The sitter application is not merely a provider profile or job board.

It is the field-operations application through which a scheduled digital booking becomes a verified physical service.

2. Corrected sitter-app priorities

| Feature | Priority | Decision |
| --- | --- | --- |
| Login and device authentication | P0 | Mandatory |
| Today’s bookings | P0 | Mandatory |
| Accept/reject booking | P0 | Mandatory |
| Pet and care details | P0 | Mandatory, access-limited |
| Navigation and arrival | P0 | Add explicitly |
| Start service | P0 | Mandatory |
| End service | P0 | Mandatory |
| Active-service GPS | P0 | Mandatory for walks |
| Photo/video capture | P0 | Mandatory where appropriate |
| Report-card submission | P0 | Mandatory |
| Emergency Help | P0 | Mandatory |
| Support call/chat | P0 | Mandatory |
| Push notifications | P0 | Mandatory with fallback |
| Earnings dashboard | P0 | Mandatory |
| Offline event queue | P0 | Add explicitly |
| Availability calendar | P1 | Recommended |
| Leave management | P1 | Add explicitly |
| Training modules | P1 | Recommended |
| Reliability score | P1 | Show carefully |
| Profile/documents | P1 | Recommended |
| Preferred service areas | P1 | Recommended |

Missing P0 features

Your current scope should add:

- Arrival confirmation

- Offline service execution

- Backup-assignment flow

- Permission-status screen

- Media upload status

- App/device health status

- Incident history

- Service cancellation/escalation

- Document-expiry warning

- Secure session management

3. Sitter app end-to-end flow

Sitter logs in

↓

Device and account verified

↓

Views booking request

↓

Reviews payout, pet requirements and travel

↓

Accepts or rejects

↓

Booking added to schedule

↓

Reminder and travel-risk checks

↓

Navigates to customer location

↓

Marks “Arrived”

↓

Confirms handover

↓

Starts service

↓

GPS/timer/session evidence begins

↓

Captures structured observations and media

↓

Ends service

↓

Report submitted or queued offline

↓

Customer notified

↓

Earnings move to pending validation

↓

Payout released according to settlement rules

4. Sitter navigation structure

The proposed web-style paths are useful as conceptual routes. In React Native with Expo Router, organise them as mobile route groups rather than visually exposing /sitter/... URLs.

(sitter)/

home

bookings/

index

[bookingId]

service/

[bookingId]/

arrival

active

report

incident

earnings

availability

training

profile

support

permissions

Bottom navigation

Recommended primary tabs:

- Home

- Bookings

- Earnings

- Availability

- Profile

Emergency Help should remain contextually visible during an active service rather than becoming a buried tab.

5. Authentication and device security

Login flow

Phone/email entered

↓

OTP verified

↓

Account status checked

↓

Approved device registered

↓

Biometric unlock offered

↓

Home screen

Required controls

- OTP or secure authentication

- Short-lived access token

- Rotating refresh token

- Device registration

- Remote logout

- Session revocation

- Optional biometric unlock

- Blocked/paused sitter handling

- Minimum supported app version

Do not store:

- Raw passwords

- Customer gate codes indefinitely

- Full payment details

- Entire historical customer address lists

6. Booking request screen

Before acceptance, show enough information to make an informed decision without exposing unnecessary customer data.

Before acceptance

Show:

- Approximate locality

- Service type

- Date and time

- Duration

- Pet species, size and broad risk category

- Required skills

- Estimated travel time

- Expected payout

- Society-entry requirement

- Number of pets

Do not expose before acceptance:

- Exact flat number

- Personal access codes

- Full customer phone number

- Detailed health files

- Unrelated customer notes

After confirmed assignment

Show:

- Exact service address

- Relevant owner instructions

- Handover process

- Required pet-care notes

- Emergency contact method

- Society gate instructions

- Operations support

- Navigation

This follows data-minimisation principles: location, home access and pet records should be available only to people who need them for the current service. India’s DPDP framework requires digital personal data to be processed for lawful purposes with appropriate protections, and the notified 2025 Rules have phased commencement.

7. Booking accept/reject logic

Acceptance checks

Before confirming acceptance, the backend should verify:

- Sitter remains active

- Documents remain valid

- No time conflict exists

- Travel time is feasible

- Capacity remains available

- Pet risk is compatible

- Sitter has correct service permission

- Another sitter has not already accepted

Structured rejection reasons

- Schedule conflict

- Too far away

- Pet size/behaviour mismatch

- Society access issue

- Payout mismatch

- Personal emergency

- Temporarily unavailable

- Other

These reasons should feed:

- Pricing analysis

- Capacity planning

- Matching improvements

- Recruitment gaps

- Sitter-support decisions

A rejection should not automatically damage the sitter’s reliability score when it occurs promptly and for a valid reason.

8. Today’s bookings screen

Show each booking as an operational card

7:30 AM · Dog Walk

Bruno · Labrador

South Bopal

30 minutes

Travel estimate: 14 min

Status: Confirmed

Statuses

REQUESTED

ACCEPTED

CONFIRMED

TRAVEL_REMINDER

EN_ROUTE

ARRIVED

HANDOVER_CONFIRMED

IN_PROGRESS

REPORT_DUE

COMPLETED

CANCELLED

INCIDENT_OPEN

Risk indicators

- Tight travel window

- Missing owner instruction

- Gate approval incomplete

- Pet risk warning

- Backup assignment

- Location permission disabled

- Device battery low

- App update required

9. Booking-detail screen

Identity and task

| Field | Purpose |
| --- | --- |
| Pet name and photo | Confirm correct pet |
| Species/breed/size | Handling context |
| Service type | Scope of work |
| Date/time/duration | Schedule |
| Risk classification | Safety |
| Relevant care instructions | Service quality |
| Address and navigation | Arrival |
| Handover method | Access |
| Primary customer contact | Communication |
| Operations support | Escalation |
| Expected payout | Financial transparency |

Display risk safely

Avoid simplistic labels such as:

Dangerous dog

Use operational classifications:

- Standard handling

- Cautious introduction

- Leash-reactive

- No contact with other animals

- Two-handler requirement

- Specialist-only

- Temporarily not serviceable

Only show the instructions relevant to the sitter’s assigned service.

10. Arrival and start-service flow

Recommended start flow

Sitter approaches location

↓

App checks permission and GPS quality

↓

Sitter taps “I’ve Arrived”

↓

System compares position with service geofence

↓

Handover confirmed

↓

Sitter taps “Start Service”

↓

Active tracking and timer begin

Start-service preconditions

- Booking is assigned to this sitter

- Current time is within allowed range

- Required location permission exists

- Device has acceptable location signal

- Handover is confirmed

- No conflicting active service exists

- Safety instructions acknowledged

Starting outside the geofence

Do not automatically block every legitimate case.

Allow an exception with a reason:

- Customer requested another meeting point

- Society entrance differs from residence

- GPS is inaccurate

- Admin authorised start

- Emergency relocation

The exception should be logged and surfaced for review.

Android geofencing uses a latitude, longitude and radius to identify entry or exit from an area, but geofence events and background location are subject to platform timing and accuracy constraints.

11. GPS session architecture

Session-based tracking only

Booking assigned

↓

No continuous location collection

↓

Sitter starts eligible service

↓

Tracking session activated

↓

Location points collected during service

↓

Service ends

↓

Tracking stopped automatically

Do not track sitters continuously throughout the working day.

Apple permits background services only for their intended purposes and requires location use to be directly relevant to app functionality. Android requires appropriate location permissions, and apps targeting Android 14 or later must declare the correct foreground-service type for a location foreground service.

Important Expo limitation

Expo supports background location through its Location and TaskManager APIs, but background updates remain subject to platform constraints. Expo states that background location stops if the user terminates the application and resumes after the app is restarted.

Therefore, your product must detect and report:

- App terminated

- Background permission removed

- Location disabled

- Tracking task stopped

- Network unavailable

- Points pending upload

Do not falsely label these situations as a completed, continuously tracked route.

12. Adaptive tracking strategy

Do not hard-code one aggressive interval for every device and service.

Use adaptive profiles:

Walking profile

- Higher frequency while moving

- Lower frequency while stationary

- Distance-based updates

- Batch upload during weak connectivity

- Immediate upload for safety events

Sitting profile

Continuous route tracking is usually unnecessary.

Use:

- Arrival verification

- Periodic check-ins

- Service start/end

- Media and report evidence

Boarding profile

Do not continuously track the host.

Use:

- Check-in/check-out

- Scheduled care updates

- Media

- Incident reporting

Grooming profile

Use:

- Arrival

- Start

- Before media

- End

- After media

- Report

Android recommends limiting location work to what the feature needs because background location affects battery usage; Google’s location stack includes battery-optimised fused-location and geofencing capabilities.

13. Location data model

location_sessions

- id

- booking_id

- sitter_id

- device_id

- service_type

- started_at

- ended_at

- status

- permission_state

- app_version

- consent_version

- point_count

- distance_meters

- tracking_quality

- termination_reason

location_points

- id

- session_id

- recorded_at_device

- received_at_server

- latitude

- longitude

- horizontal_accuracy_m

- speed_mps

- heading

- source

- battery_level

- is_mock_location_flag

- sync_status

Session statuses

PENDING

ACTIVE

PAUSED_SYSTEM

OFFLINE

PERMISSION_LOST

APP_TERMINATED

COMPLETED

ABORTED

UNDER_REVIEW

14. Offline tracking and report sync

Local outbox

The sitter app should locally queue:

- Start-service event

- Location points

- Media files

- Observations

- End-service event

- Report submission

- Incident evidence

Sync states

LOCAL_ONLY

QUEUED

UPLOADING

SYNCED

FAILED_RETRYABLE

FAILED_PERMANENT

CONFLICT_REVIEW

Server rules

- Events require unique idempotency keys

- Duplicate completion must be ignored

- Device timestamps must be preserved

- Server-received timestamps must also be stored

- Conflicts should not silently overwrite records

- Media upload failure must not erase the written report

- Earnings should remain pending until completion is validated

15. Photo and video upload

Capture rules

- Compress media before upload

- Strip unnecessary metadata where appropriate

- Use signed upload URLs

- Store upload progress

- Retry failed uploads

- Show pending versus uploaded status

- Obtain customer consent for routine media

- Avoid showing unrelated people or private home areas

Suggested limits

- A small number of meaningful photographs

- Short video clips only when useful

- No forced high-resolution upload

- Media retained according to a documented policy

Location routes, customer homes and pet-related health or behaviour notes should not be sent to general-purpose analytics or error logs.

16. End-service validation

When the sitter taps End Service, evaluate:

- Minimum expected duration

- GPS/session health

- Distance where relevant

- Required observations

- Required media

- Open incident state

- Customer handover confirmation

Early-end flow

Early end detected

↓

Sitter selects reason

↓

Operations notified

↓

Service remains “Pending Review”

↓

Customer receives neutral update

↓

Admin validates completion and credit/payout

Do not immediately accuse the sitter or automatically release full payout.

Valid reasons may include:

- Pet became unwell

- Weather emergency

- Customer requested early return

- Unsafe animal encountered

- Service changed by operations

- GPS malfunction

- Incident opened

17. Report-card submission

Structured report

General

- Start/end time

- Completed duration

- Sitter note

- Mood

- Concern flag

Dog walk

- Approximate distance

- Toilet activity

- Water offered

- Interactions

- Leash behaviour

- Route summary

Pet sitting

- Food/water

- Medication confirmation

- Toilet/litter

- Play/activity

- Home condition

- Departure confirmation

Grooming

- Before/after media

- Services completed

- Skin/coat observations

- Behaviour

- Products used

- Concern flag

Workflow

Sitter completes draft

↓

Required fields validated

↓

Report saved locally

↓

Server sync

↓

Operations checks only flagged cases

↓

Customer notified

18. Earnings dashboard

Show financial states clearly

| State | Meaning |
| --- | --- |
| Estimated | Booking accepted |
| Pending completion | Service not completed |
| Pending validation | Report/service under review |
| Approved | Payable |
| Processing | Included in payout |
| Paid | Settlement confirmed |
| Adjusted | Changed with explanation |
| Disputed | Sitter raised a question |

Earnings detail

Dog Walk · Bruno

12 July, 7:30 AM

Service payout: ₹180

Peak bonus: ₹20

Adjustment: ₹0

Total: ₹200

Status: Approved

Never display a deduction without:

- Reason

- Related booking

- Policy reference

- Dispute option

- Audit history

19. Reliability score

A sitter-facing reliability score can help performance, but it must be transparent and contestable.

Recommended factors

- On-time arrival

- Accepted-booking completion

- Sitter-initiated cancellation

- No-shows

- Report completion

- Customer rating

- Incident outcomes

- Training/document status

Do not penalise

- Customer cancellation

- Admin reassignment

- App outage

- Verified GPS failure

- Medical emergency

- Prompt, valid rejection before acceptance

Show:

- Current score

- Component breakdown

- Improvement actions

- Dispute route

- Review period

Avoid a hidden black-box score that determines livelihoods without explanation.

20. Emergency Help system

Button placement

Display a persistent Emergency Help control:

- On the active-service screen

- On the booking-detail screen

- On the incident screen

Do not hide it in the general support menu.

Emergency categories

- Pet lost or escaped

- Pet injured or collapsed

- Bite/aggressive incident

- Sitter injured or unsafe

- Medical concern

- Customer unavailable

- Society/access emergency

- Property/security issue

- Other urgent issue

Emergency workflow

Sitter taps Emergency Help

↓

Large category choices appear

↓

Incident ticket created immediately

↓

Current booking and location attached

↓

City operations receive critical alert

↓

Central incident team notified by severity

↓

Sitter receives immediate action instructions

↓

Customer contact options shown

↓

Verified local veterinary options displayed

↓

Call escalation begins

↓

Evidence captured after immediate safety actions

Multi-channel escalation

The system should:

- Create an incident through the backend

- Send a critical operations alert

- Trigger an in-app alarm/queue

- Offer direct phone calling

- Send push notifications

- Use SMS/WhatsApp fallback where configured

- Escalate automatically if not acknowledged

FCM is a cross-platform push service, but push should not be your only emergency mechanism; operational state must be persisted on the backend and paired with direct calling/escalation.

Nearest-vet display

Use a verified emergency directory containing:

- Clinic name

- Distance

- Phone

- Recorded operating hours

- Last verification date

- Available capabilities

- Navigation

Show:

Call the clinic to confirm current availability.

Do not promise:

- Guaranteed admission

- Guaranteed open status

- Guaranteed response

- Medical suitability without verification

Product 2: Customer Mobile App

21. Product goal

The customer app should increase:

- Repeat bookings

- Subscription usage

- Service visibility

- Customer control

- Trust in field execution

- Self-service support

- Retention

It should not merely duplicate the website in a native shell.

22. Corrected customer-app priorities

| Feature | Priority | Decision |
| --- | --- | --- |
| Login/signup | P0 | Mandatory |
| Pet profiles | P0 | Mandatory |
| Book service | P0 | Mandatory |
| Active booking | P0 | Mandatory |
| Sitter profile | P0 | Mandatory |
| Live status | P0 | Mandatory |
| Report history | P0 | Mandatory |
| Reviews | P0 | Mandatory |
| Subscription management | P0 | Mandatory |
| Remaining credits | P0 | Mandatory |
| Push notifications | P0 | Mandatory |
| Support/safety escalation | P0 | Mandatory |
| Payments/history | P0 | Add explicitly |
| Notification inbox | P0 | Add explicitly |
| Account/privacy controls | P0 | Add explicitly |
| Favourite sitter | P1 | Use “preferred sitter” |
| Service credits | P1/P0 | P0 if subscriptions already exist |
| Loyalty credits | P1 | Later |
| Pet health timeline | P1 | Recommended |
| Society benefits | P1 | Recommended |
| Referrals | P1 | Recommended |

23. Customer app flow

Customer opens app

↓

Sees next booking and pet profile

↓

Selects a service

↓

Selects pet, time and package

↓

Serviceability and capacity checked

↓

Price displayed

↓

Customer pays or reserves credit

↓

Sitter matched and confirmed

↓

Customer receives pre-service updates

↓

Sitter arrives and starts service

↓

Customer sees live status

↓

Report delivered

↓

Customer rates the service

↓

Customer rebooks, renews or manages plan

24. Customer navigation

Recommended tabs:

- Home

- Book

- Bookings

- Pets

- Account

Contextual routes:

booking/[bookingId]

booking/[bookingId]/live

booking/[bookingId]/report

subscription

credits

health

referrals

support

privacy

Avoid putting every feature in a bottom navigation bar.

25. Customer home screen

Priority hierarchy

- Active service or next booking

- Important alert

- Pet selector

- Book service

- Remaining credits and renewal

- Recent report

- Recommended next action

Example:

Bruno’s next walk

Tomorrow · 7:30 AM

Preferred sitter: Riya

Status: Confirmed

[View Booking] [Reschedule]

During an active service:

Bruno’s walk is in progress

Started 7:34 AM

Current tracking: Available

Elapsed: 18 min

[View Live Status] [Contact Support]

26. Sitter profile

Show:

- Name and photograph

- Verification badges with definitions

- Experience

- Services

- Completed bookings

- Rating and review count

- Reliability indicators

- Training completed

- Repeat customer rate where appropriate

- Previous services with this pet

- Preferred/backup designation

Do not show:

- Full legal identity documents

- Personal home address

- Private phone number

- Irrelevant personal information

Badge language

Use:

- Identity checked

- Practical assessment completed

- Dog-walking module passed

- Background verification completed on [date]

Avoid:

- 100% safe

- Guaranteed

- Government approved

27. Booking and payment

The app should never trust price values sent by the client.

Server-side booking sequence

Pet and service selected

↓

Service zone resolved

↓

Eligibility checked

↓

Capacity checked

↓

Published price resolved

↓

Credit/payment option calculated

↓

Checkout session created

↓

Payment verified server-side

↓

Booking confirmed

Credit use

When the customer uses a subscription credit:

Booking created

↓

Credit reserved

↓

Service completed

↓

Credit consumed

If the service is cancelled according to an eligible policy:

Reserved credit

↓

Released/restored

28. Live service-status screen

Status timeline

Sitter assigned

↓

Sitter en route

↓

Sitter arrived

↓

Handover confirmed

↓

Service in progress

↓

Service completed

↓

Report ready

Live map

Display only while:

- The service type supports tracking

- The service is active

- Location quality is sufficient

- The customer has access to that booking

Map states

- Live tracking available

- Location updating

- Approximate location

- Sitter temporarily offline

- Tracking interrupted

- Service completed

- Route replay available

Do not show a moving marker with false precision when the latest location is stale.

29. Route replay

After completion, route replay should show:

- Start area

- End area

- Approximate route

- Duration

- Distance

- Tracking gaps

- GPS quality notes

Privacy protections

- Hide precise route segments before/after service

- Exclude the sitter’s travel from home

- Limit retention

- Restrict customer access to their own service

- Prevent public sharing by default

- Avoid exposing unrelated private locations

30. Customer emergency support

Use separate actions for:

Active-service safety concern

Examples:

- Sitter unreachable

- Pet appears distressed

- Unexpected route

- Service stopped

- Handover problem

Veterinary concern

The app may:

- Show verified local veterinary options

- Contact operations

- Share selected pet information with consent

- Coordinate a booking

It must not represent platform support as veterinary diagnosis.

General support

- Payment

- Schedule

- Report

- Subscription

- Refund

- Account

The word “Emergency” should be reserved for genuinely urgent safety situations so customers do not use the critical incident channel for ordinary support.

Advanced GPS Tracking

31. Correct GPS architecture

Sitter initiates service

↓

Permission and device-state check

↓

Server creates location session

↓

Foreground/background location begins

↓

Points collected adaptively

↓

Points stored locally

↓

Near-real-time batches sent to backend

↓

Customer and admin receive session state

↓

Alerts evaluate session events

↓

Service completion requested

↓

Backend validates and closes session

↓

Route summary generated

On Android, active background location normally requires the correct location foreground-service configuration and visible foreground-service behaviour; Android 13 and later also introduced runtime notification permission.

On iOS, the app must request appropriate location authorisation and configure background location for the actual use case.

32. Permission UX

Do not request background location immediately after login.

Recommended sequence

Sitter accepts first tracked walk

↓

App explains why location is needed

↓

Foreground permission requested

↓

Background-service explanation shown

↓

Background access requested/configured

↓

Test confirms tracking readiness

For notifications:

User sees value explanation

↓

System permission requested

Android 13+ uses the POST_NOTIFICATIONS runtime permission, while Apple requires explicit notification authorisation through UNUserNotificationCenter.

33. GPS alert engine

Alerts should use:

- Static rules

- Contextual thresholds

- Historical baselines

- GPS quality

- Service type

- Pet requirements

- Human review

Do not trigger based on a single noisy GPS point.

Alert state model

DETECTED

OBSERVING

CONFIRMED

NOTIFIED

ACKNOWLEDGED

RESOLVED

FALSE_POSITIVE

ESCALATED

34. Late-start alert

Trigger inputs

- Scheduled start

- Allowed grace period

- Sitter arrival status

- Current travel estimate

- Customer reschedule

- Society gate delay

- Weather/traffic disruption

Escalation

Approaching start and sitter not en route

↓

Sitter reminder

↓

Grace period exceeded

↓

Operations alert

↓

Backup assessment

↓

Customer update

Do not wait until the appointment is already severely late before evaluating backup capacity.

35. Wrong-location alert

Recommended logic

Open a review when:

- Start occurs outside the configured radius

- GPS accuracy is acceptable

- No authorised meeting-point exception exists

- Several points confirm the location

Avoid false positives from

- Apartment entrance versus tower

- Indoor GPS drift

- Dense urban buildings

- Customer-requested park meetup

- Inaccurate device location

The app should first ask the sitter to confirm:

You appear to be outside the expected start area. Are you meeting the customer at another location?

36. Route-anomaly alert

“Unusual route” requires careful definition.

Possible signals

- Route goes far outside expected service zone

- Sudden impossible movement

- Repeated circular GPS noise

- Service leaves approved boundaries

- Route deviates materially from historical pattern

- Pet-risk rule prohibits certain area

Response

A route anomaly should:

- Be labelled as a review signal

- Prompt sitter confirmation

- Show GPS-quality context

- Notify operations only after persistence

- Avoid alarming the customer prematurely

Never send:

Your sitter is taking your dog somewhere unsafe.

based only on an automated route deviation.

37. Long-pause alert

Context matters

No movement may be acceptable when:

- Pet rests

- Sitter gives water

- Traffic crossing is delayed

- Customer requested a stationary outdoor break

- GPS signal is weak

- Service is pet sitting rather than walking

Recommended rule

Use:

- No significant movement

- For a sustained period

- During a walking service

- With acceptable GPS accuracy

- Without a pause reason

First prompt the sitter:

You have been stationary for several minutes. Is everything okay?

Escalate only when the sitter fails to respond or another risk signal exists.

38. Early-end alert

Trigger

- Completed before minimum acceptable duration

- No approved exception

- GPS/session is valid

- No incident explains the end

Workflow

Early completion requested

↓

Reason required

↓

Booking marked Pending Review

↓

Operations evaluates

↓

Credit and payout resolved

Do not automatically deduct the sitter’s payout or customer credit.

39. Tracking-lost alert

Possible causes

- Permission revoked

- GPS disabled

- App force-closed

- Device battery exhausted

- Operating-system restriction

- Network unavailable

- Expo background task stopped

- App crash

Required response

- Attempt local tracking continuity.

- Notify sitter in-app if possible.

- Record session degradation.

- Alert admin after threshold.

- Inform customer neutrally if live tracking is materially interrupted.

- Preserve service evidence from timer, media and reports.

Customer copy:

Live location is temporarily unavailable. The service remains in progress, and operations has been notified.

Not:

Sitter stopped tracking.

40. Emergency alert

Emergency Help should override ordinary alert handling.

Immediate actions

- Create critical incident

- Attach last known location

- Lock the booking from normal completion

- Notify city operations

- Notify central incident team

- Offer direct call

- Display safety instructions

- Start acknowledgement timer

- Escalate to backup contacts

If the device is offline, the app should:

- Store the incident locally

- Present direct call options

- Attempt SMS/phone fallback

- Sync evidence when connectivity returns

41. Admin live monitor

The operations command centre should show:

| Booking | Pet | Sitter | Status | GPS | Alert | Action |
| --- | --- | --- | --- | --- | --- | --- |
| BKG-21 | Bruno | Riya | In progress | Healthy | None | View |
| BKG-22 | Max | Aman | Late | Available | Late start | Contact |
| BKG-23 | Simba | Neha | In progress | Lost | Tracking | Review |

Map privacy

Admin access should be:

- Role-controlled

- Limited to active operational sessions

- Logged

- Disabled for marketing/society roles

- Hidden after the operational retention period

42. APIs

Sitter booking APIs

GET  /v1/sitter/bookings

GET  /v1/sitter/bookings/{bookingId}

POST /v1/sitter/bookings/{bookingId}/accept

POST /v1/sitter/bookings/{bookingId}/reject

POST /v1/sitter/bookings/{bookingId}/en-route

POST /v1/sitter/bookings/{bookingId}/arrive

POST /v1/sitter/bookings/{bookingId}/confirm-handover

Service APIs

POST /v1/sitter/bookings/{bookingId}/start

POST /v1/sitter/bookings/{bookingId}/location-sessions

POST /v1/location-sessions/{sessionId}/points:batch

POST /v1/sitter/bookings/{bookingId}/complete-request

POST /v1/sitter/bookings/{bookingId}/reports

Incident APIs

POST /v1/bookings/{bookingId}/incidents

POST /v1/incidents/{incidentId}/evidence

POST /v1/incidents/{incidentId}/acknowledge

GET  /v1/incidents/{incidentId}/instructions

Customer APIs

GET  /v1/customer/home

GET  /v1/customer/bookings

GET  /v1/customer/bookings/{bookingId}

GET  /v1/customer/bookings/{bookingId}/live

GET  /v1/customer/bookings/{bookingId}/report

POST /v1/customer/bookings/{bookingId}/review

All writes should use idempotency keys so repeated offline or network retries do not create duplicate starts, incidents or completions.

43. Required database additions

mobile_devices

push_tokens

mobile_sessions

booking_events

service_sessions

location_sessions

location_points

service_reports

service_report_media

media_uploads

incidents

incident_events

incident_evidence

incident_acknowledgements

sitter_availability

sitter_leave

sitter_reliability_snapshots

notification_events

notification_preferences

offline_sync_conflicts

Booking events should be append-only

Example:

BOOKING_ACCEPTED

SITTER_EN_ROUTE

SITTER_ARRIVED

HANDOVER_CONFIRMED

SERVICE_STARTED

TRACKING_INTERRUPTED

INCIDENT_OPENED

SERVICE_COMPLETION_REQUESTED

SERVICE_COMPLETED

REPORT_SUBMITTED

This creates a defensible timeline for:

- Customer support

- Incident investigation

- Payout disputes

- Credit disputes

- Quality analytics

44. Rollout plan

Stage 1: Internal technical pilot

- Staff/test accounts

- Simulated bookings

- Weak-network testing

- Permission denial

- App killed

- Device reboot

- Low battery

- Duplicate actions

Stage 2: Trusted sitter pilot

- 5–10 experienced sitters

- One cluster

- Walking only

- Admin actively observing

Stage 3: Operational pilot

- 20–50 sitters

- Two clusters

- Real customers

- GPS and incident drills

- Customer live status

Stage 4: Customer beta

- Existing repeat users

- Subscribers

- App optional

- PWA remains available

Stage 5: Multi-city production

- Feature flags by city

- Minimum app version

- Device compatibility monitoring

- City-specific support

45. Success metrics

Sitter app

| Metric | Target |
| --- | --- |
| Weekly active sitter adoption | 85–95% |
| Booking acknowledgement | 95%+ |
| Digital arrival/start/end | 98%+ |
| Report submission | 95%+ |
| Location-session success | 95%+ |
| Offline sync recovery | 99%+ |
| Emergency acknowledgement | Under defined critical SLA |
| Crash-free sessions | 99%+ target |
| Provider support contacts | Declining |

Customer app

| Metric | Target |
| --- | --- |
| Invited-user activation | 40–60%+ |
| Booking conversion | Above PWA baseline |
| Report view rate | 70%+ |
| Subscription self-service | 70%+ |
| Repeat booking | Improving |
| Support contacts/booking | Declining |
| Push opt-in | Measured by platform |
| Crash-free sessions | 99%+ target |

GPS

| Metric | Target |
| --- | --- |
| Eligible walks with tracking started | 95%+ |
| Sessions closed correctly | 98%+ |
| Tracking interruptions | Below defined tolerance |
| False-positive alerts | Monitored and declining |
| Location collected outside service | Zero |
| Customer route-access violations | Zero |

Final decisions

| Proposal | Decision |
| --- | --- |
| Sitter mobile app as Product 1 | APPROVE |
| GPS as sitter-app P0 | APPROVE |
| Customer app as Product 2 | APPROVE |
| Persistent Emergency Help button | APPROVE |
| Nearest-vet directory | APPROVE with verification and availability disclaimer |
| Live customer map | APPROVE for eligible active services |
| Route replay | APPROVE with privacy limits |
| Geofence arrival | APPROVE as evidence, not absolute truth |
| Automatic route anomaly accusations | REJECT |
| Duration validation | APPROVE with human exception review |
| Offline tracking/reporting | MANDATORY |
| Admin live monitoring | APPROVE with role-scoped access |
| Continuous sitter tracking | REJECT |
| Push-only emergency escalation | REJECT |
| Exact customer data before acceptance | REJECT |
| Automatic payout penalties from alerts | REJECT |

Product doctrine

The sitter app should prove what happened, support the person delivering the service and surface exceptions early. The customer app should translate that operational evidence into confidence, visibility and convenient repeat care.

Phase 11 Product 1–2 win condition

At least 95% of eligible services are digitally acknowledged, started, monitored and reported, while customers gain live visibility without creating continuous worker surveillance, excessive battery use or unsafe dependence on automated alerts.

Phase 11: AI Matching, Loyalty Credits and Pet Health Timeline 🧠🐾

Executive decision

Your direction is strong. The correct Phase 11 model is:

Deterministic eligibility rules

↓

AI/rules rank eligible sitters

↓

Top three recommendations shown

↓

Admin reviews reasons and risks

↓

Admin confirms final assignment

↓

Actual outcome improves future ranking

For loyalty and records:

Service-credit ledger first

↓

Referral and promotional credits

↓

Simple loyalty benefits

↓

Pet health timeline

↓

Cash-like wallet only after regulatory review

Final verdict

| Proposal | Decision |
| --- | --- |
| AI recommends top three sitters | Approve |
| Admin approves final assignment | Approve—mandatory initially |
| Display “92% match” | Modify to “92/100 match score” unless statistically calibrated |
| Service credits | Approve |
| Referral and promotional credits | Approve with fraud and reversal controls |
| Customer-funded cash wallet | Defer |
| Cash withdrawal or transfers | Reject for early phase |
| Pet health timeline | Approve as an owner-controlled record system |
| AI diagnosis or treatment advice | Reject |

Product 3: AI-Assisted Sitter Matching

1. Product objective

The matching system should reduce:

- Manual search time

- Poor distance assignments

- Skill mismatches

- Schedule conflicts

- Repeated sitter changes

- Last-minute cancellations

- Subscription fulfilment risk

It should not remove human accountability.

NIST’s AI-risk guidance recommends defining where human oversight is necessary, documenting system limitations, providing understandable outputs and continuously monitoring performance and harmful outcomes. That is especially relevant here because matching affects both pet safety and sitter earning opportunities.

2. Why full auto-assignment is premature

A pet-care assignment contains context that may not be completely represented in structured data:

- The dog recently became reactive

- The customer distrusts a particular replacement

- A society gate has changed its rules

- A sitter has accepted too many consecutive walks

- A medical or behavioural note is ambiguous

- A location appears close geographically but is difficult to reach

- The sitter is technically available but is the only backup for another subscription

An automated system may produce a mathematically plausible match that is operationally unsafe.

Recommended responsibility

| Actor | Responsibility |
| --- | --- |
| System | Filters ineligible sitters |
| Ranking engine | Orders eligible candidates |
| Admin | Reviews context and confirms |
| Sitter | Accepts the assignment |
| Customer | Confirms where appropriate |
| Quality team | Audits results and failures |

3. Three-stage matching architecture

Stage 1: Hard eligibility filters

Before any AI scoring, eliminate sitters who do not satisfy mandatory conditions.

Hard filters

- Sitter account is active

- Required documents are current

- Correct service permission exists

- Correct city and service zone

- Available at requested time

- Travel time is feasible

- Daily capacity is available

- Pet-risk level is permitted

- Sitter has required skills

- Society access is valid

- No overlapping booking

- Sitter is not paused or under investigation

- Required backup coverage remains available

All sitters

↓

Hard safety and operational rules

↓

Eligible candidate pool

The AI should never “outscore” a failed safety rule.

Stage 2: Candidate ranking

Rank only the eligible pool.

Recommended factors

| Factor | Suggested importance |
| --- | --- |
| Previous relationship with pet | Very high |
| Pet-risk and skill compatibility | Very high |
| Availability fit | Very high |
| Travel time | High |
| Reliability | High |
| Service-specific experience | High |
| Customer preference | Medium-high |
| Society access familiarity | Medium-high |
| Rating and report quality | Medium |
| Price/payout compatibility | Medium |
| Backup implications | Medium |

Example scoring model

Match score=  20%×pet compatibility+20%×repeat relationship+15%×reliability+15%×travel fit+10%×availability fit+10%×customer preference+5%×service quality+5%×backup health

Weights should vary by service.

For example:

- Dog walking: distance, punctuality and previous pet relationship matter strongly.

- Boarding: environment, trial history and household compatibility matter more.

- Senior care: relevant skill and medical-instruction reliability dominate.

- Grooming: package skill, pet size and equipment matter more than distance alone.

4. Do not call an arbitrary score a probability

Avoid:

Riya — 92% probability of being the right sitter.

unless your model has been calibrated against real outcomes and 92% has a statistically validated meaning.

Use:

Riya — Match score 92/100

or:

Excellent operational match

Suggested bands

| Score | Label |
| --- | --- |
| 90–100 | Excellent match |
| 80–89 | Strong match |
| 70–79 | Acceptable match |
| 60–69 | Manual review required |
| Below 60 | Do not recommend automatically |

5. Admin recommendation interface

Recommended output

Recommended sitters

1. Riya — 92/100 · Excellent match

- 1.2 km from the customer

- Previously completed seven walks with Bruno

- Qualified for large-dog handling

- Available at 7:00 AM

- 98% on-time rate

- Approved for this society

- Backup remains available

2. Aman — 86/100 · Strong match

- 1.8 km away

- No previous history with Bruno

- Experienced with Labradors

- 96% completion rate

- Available at requested time

- Would require a first-service introduction

3. Neha — 82/100 · Strong match

- 2.4 km away

- Previously handled Bruno once

- Strong customer rating

- Available within a 30-minute flexible window

Admin actions

- Assign

- View complete profile

- Compare candidates

- Request sitter acceptance

- Select another candidate

- Record override reason

- Escalate for specialist review

6. Admin override system

Whenever the admin ignores the top recommendation, request a structured reason:

- Customer requested another sitter

- Existing pet relationship

- Risk information not represented

- Society access issue

- Schedule/travel concern

- Backup-capacity concern

- Sitter workload concern

- Quality concern

- Customer gender preference where legitimately applicable

- Other

This information becomes valuable training data.

Do not automatically treat the administrator’s choice as “correct.” Compare it with the actual outcome.

7. Matching workflow

Booking request received

↓

Pet and service requirements loaded

↓

Hard eligibility filters applied

↓

Travel and capacity checked

↓

Candidates ranked

↓

Top three displayed with reasons

↓

Admin selects sitter

↓

Sitter accepts or rejects

↓

Customer notified

↓

Service completed

↓

Outcome recorded

↓

Ranking performance evaluated

Outcome signals

- Sitter accepted

- Sitter arrived on time

- Service completed

- Report submitted

- Customer rating

- Customer requested same sitter again

- Complaint occurred

- Sitter cancelled

- Backup was required

- Incident occurred

8. Matching data model

matching_requests

- id

- booking_id

- city_id

- service_zone_id

- service_type

- pet_risk_level

- requested_start_at

- status

- algorithm_version

- created_at

matching_candidates

- id

- matching_request_id

- sitter_id

- eligibility_status

- exclusion_reasons

- match_score

- factor_scores

- explanation

- ranking_position

- created_at

matching_decisions

- id

- matching_request_id

- recommended_sitter_id

- selected_sitter_id

- decided_by

- override_reason

- decided_at

matching_outcomes

- id

- matching_request_id

- sitter_id

- accepted

- completed

- on_time

- customer_rating

- sitter_cancelled

- incident_id

- repeat_requested

- recorded_at

Every recommendation should store its algorithm version so historical decisions remain auditable after scoring logic changes.

9. Matching APIs

POST /v1/admin/matching/requests

GET  /v1/admin/matching/requests/{id}/recommendations

POST /v1/admin/matching/requests/{id}/assign

POST /v1/admin/matching/requests/{id}/override

GET  /v1/admin/matching/requests/{id}/explanation

POST /v1/admin/matching/requests/{id}/outcome

Example response:

{

"algorithm_version": "matching-v1.3",

"candidates": [

{

"sitter_id": "sitter_riya",

"match_score": 92,

"label": "excellent_match",

"reasons": [

"Completed 7 previous services with this pet",

"1.2 km estimated distance",

"Qualified for large dogs",

"Available at requested time",

"98% on-time rate"

],

"warnings": []

}

]

}

10. Matching fairness and worker controls

Matching can affect how many earning opportunities each sitter receives. Therefore, avoid creating a system that permanently sends all work to a small number of already successful providers.

Track:

- Recommendations per sitter

- Assignments per sitter

- Acceptance rate

- Earnings distribution

- New-sitter exposure

- Geographic distribution

- Admin overrides

- False exclusions

- Rating bias

- Customer-preference effects

NIST recommends defining human roles, measuring errors and negative effects, monitoring performance over time and maintaining processes to correct systems that exceed acceptable risk levels.

New sitter cold-start policy

A new sitter cannot have:

- Past relationship history

- Many ratings

- Large completed-service volume

Create a controlled trial mechanism:

- Low-risk first assignments

- Supervised or monitored first services

- Explicit “new approved sitter” status

- No automatic penalty for limited history

- Progressive capacity increase

11. Matching KPIs

| Metric | Purpose |
| --- | --- |
| Admin recommendation acceptance | Recommendation usefulness |
| Sitter acceptance rate | Operational fit |
| Assignment time | Efficiency |
| On-time performance | Service quality |
| Completion rate | Match viability |
| Repeat-sitter request | Relationship quality |
| Customer rating | Customer outcome |
| Override rate | Model/rule limitations |
| Incident rate | Safety |
| Candidate concentration | Fairness and supply health |
| Matching-related support tickets | Operational clarity |

Initial targets

- Top-three recommendation contains final selected sitter: 80%+

- Admin accepts top recommendation: 50–70% initially

- Eligible-candidate false exclusions: near zero

- Human review: 100% initially

- High-risk booking auto-assignment: zero

Product 4: Loyalty, Credits and Referral System

12. Separate the five balance types

Do not combine every balance into one number called “wallet.”

| Balance | Purpose | Recommended status |
| --- | --- | --- |
| Subscription service credits | Included walks/services | Launch |
| Referral credits | Earned from eligible referrals | Launch |
| Promotional credits | Marketing campaigns | Launch carefully |
| Society benefit credits | Resident/company benefits | Launch where applicable |
| Refund/service-recovery credits | Customer-selected or goodwill credit | Controlled |
| Customer-funded cash wallet | Stored monetary value | Defer |

13. Why the “cash wallet” should be deferred

RBI defines a closed-system instrument as one used to purchase goods or services from the issuing entity only; it cannot be used to settle third-party services and does not permit cash withdrawal. A marketplace using independent sitters, groomers or other providers should not automatically assume that a customer-funded wallet qualifies as an unregulated closed system.

Therefore, avoid initially building:

- User-reloadable money balances

- Peer-to-peer transfers

- Cash withdrawal

- Transferable balances

- Payments outside your platform

- Cross-merchant acceptance

- Wallet-to-bank settlement

Before introducing those features, obtain specialist Indian payments advice regarding PPI and marketplace-payment treatment.

14. Recommended early credit system

Use non-transferable ledgered credits.

Credit categories

SUBSCRIPTION

REFERRAL

PROMOTIONAL

SOCIETY_BENEFIT

SERVICE_RECOVERY

REFUND_ELECTED

MANUAL_ADJUSTMENT

Credit states

AVAILABLE

RESERVED

CONSUMED

RELEASED

EXPIRED

REVERSED

FROZEN

Core rule

Never store only:

customer.wallet_balance = 450

Use an immutable ledger and calculate the balance from transactions.

15. Credit ledger

credit_accounts

- id

- customer_id

- credit_type

- currency

- status

- created_at

credit_transactions

- id

- credit_account_id

- booking_id nullable

- referral_id nullable

- transaction_type

- amount_minor

- expires_at

- source_reference

- reason

- created_by

- created_at

Transaction types

GRANT

RESERVE

CONSUME

RELEASE

REVERSE

EXPIRE

ADMIN_ADJUSTMENT

Balance calculation

Available balance=grants+releases-reserves-consumption-reversals-expiry

16. Refund-credit rule

Do not automatically replace every monetary refund with platform credit.

Recommended options:

- Refund to original payment method

- Customer voluntarily selects faster platform credit

- Goodwill/service-recovery credit added separately

- Contractually valid non-cash benefit where clearly disclosed

The customer should see:

- Original amount

- Refund method

- Credit amount

- Expiry

- Eligible services

- Whether the decision can be changed

Indian dark-pattern guidance prohibits deceptive design, including subscription traps and hidden or unnecessarily complex cancellation practices. The same product principle should apply to credit expiry and refund choice: terms must be visible before acceptance and not designed to trap value.

17. Referral programme

Recommended offer

Give ₹150, Get ₹150

But define the ₹150 as an eligible platform credit—not withdrawable cash.

End-to-end flow

Existing customer receives referral code

↓

Customer shares code

↓

Friend signs up through code

↓

Friend completes first eligible paid service

↓

Refund/reversal window passes

↓

Friend discount is finalised

↓

Referrer receives ₹150 referral credit

Do not grant the reward merely because:

- The friend created an account

- The friend entered a code

- A payment attempt occurred

- A booking was cancelled

- A fully refunded service was completed

- The same person created another account

18. Referral eligibility rules

Recommended conditions:

- New paying customer

- First eligible completed service

- Minimum booking value

- No full refund

- Unique verified phone/account

- Referral code applied before checkout

- One referrer per new customer

- Referrer’s account remains active

- Reward issued after the fraud/reversal window

Anti-abuse signals

- Repeated devices

- Repeated payment instruments

- Repeated addresses

- High cancellation patterns

- Circular referrals

- Unusual referral velocity

- Multiple accounts with the same identity evidence

These signals should trigger a review rather than automatic punishment. Collect only the data required for fraud prevention and explain material account restrictions.

19. Referral states

CREATED

SHARED

REFERRED_USER_REGISTERED

FIRST_BOOKING_CREATED

FIRST_SERVICE_COMPLETED

UNDER_REVIEW

QUALIFIED

REWARD_GRANTED

REVERSED

REJECTED

Referral data model

referral_codes

- id

- customer_id

- code

- campaign_id

- status

- created_at

referrals

- id

- referral_code_id

- referrer_customer_id

- referred_customer_id

- qualifying_booking_id

- status

- referrer_reward_minor

- friend_reward_minor

- qualified_at

- rejection_reason

- created_at

20. Promotional-credit rules

Every promotional offer should specify:

- Value

- Eligibility

- Minimum spend

- Applicable services

- Applicable city

- Applicable users

- Expiry date

- Whether it combines with other offers

- Maximum usage

- Refund treatment

Avoid vague copy such as:

₹500 added to your wallet!

Use:

₹500 promotional credit for eligible dog-walking bookings in Ahmedabad, valid until 31 August 2026.

21. Society credits

Society credits may come from:

- Society management sponsorship

- Resident launch campaign

- Event participation

- Corporate or RWA care benefit

- Resident subscription

They need an identifiable funding source.

society_credit_grant

- society_id

- customer_id

- programme_id

- funded_by

- amount

- validity

- eligible_services

The society dashboard should display aggregate utilisation, not individual resident pet-care activity.

22. Loyalty system

Start with one simple loyalty mechanism:

Complete eligible services and earn Care Credits.

Example

- Earn one Care Point for every ₹100 of eligible platform spend

- 100 points = ₹100 promotional credit

- Points unlock only after service completion

- Refund reverses corresponding points

- Points expire after a clearly disclosed period

- No cash value

- No transfer

Better early rewards

Instead of only discounts, loyalty can offer:

- Priority booking

- Early access to peak slots

- Flexible rescheduling

- Grooming benefit

- Referral boost

- Society-event benefit

Avoid excessive discounting that damages unit economics.

23. Credit and loyalty KPIs

| Metric | Meaning |
| --- | --- |
| Credit issuance | Liability created |
| Credit redemption | Customer use |
| Breakage | Expired unused credit |
| Referral qualification | Real acquisition |
| Referral fraud rate | Programme abuse |
| Incremental booking rate | Behaviour change |
| Repeat-rate uplift | Retention value |
| Contribution after reward | Economic value |
| Service-recovery redemption | Recovery effectiveness |
| Expiry complaints | Transparency quality |

A referral programme should be evaluated using:

Referral CAC=friend reward+referrer reward+programme costactivated referred customers

Product 5: Pet Health Timeline

24. Product objective

The health timeline should make the app useful between bookings while improving care continuity.

It should become:

A pet-parent-controlled record of care events, documents, observations and reminders.

It should not become:

An automated veterinary diagnostic system.

25. Timeline categories

| Category | Example |
| --- | --- |
| Vaccination | Rabies vaccination |
| Preventive care | Deworming or tick treatment |
| Vet consultation | Skin-allergy consultation |
| Medication | Allergy medicine schedule |
| Grooming | Full grooming completed |
| Weight | 28 kg |
| Activity | Monthly walking summary |
| Behaviour | Pulling on leash |
| Training | Recall improvement |
| Incident/observation | Vomiting observed |
| Document | Lab report or prescription |
| Reminder | Vaccination due next month |

Use factual language.

Prefer:

Vomiting observed twice during sitting service.

Avoid:

Gastroenteritis diagnosed.

unless a registered veterinarian supplied that diagnosis.

26. Timeline sources

Every timeline entry needs a visible source:

PET_PARENT

SITTER_REPORT

GROOMER_REPORT

VET_DOCUMENT

VET_PARTNER

SYSTEM_ACTIVITY_SUMMARY

ADMIN_CORRECTION

Source examples

Rabies vaccination
Source: Document uploaded by pet parent

Weight: 28 kg
Source: Recorded during vet visit

Pulled strongly on leash
Source: Sitter report

Vaccination due 12 September
Source: System reminder generated from uploaded record

27. Health-record workflow

Pet parent uploads record

↓

Document stored securely

↓

Metadata entered or extracted

↓

Customer reviews extracted information

↓

Timeline event created

↓

Reminder scheduled

↓

Customer chooses whether to share with vet

If AI extracts details from a document:

- Mark them as machine-extracted

- Show the source document

- Require owner confirmation

- Allow correction

- Preserve the original

- Do not treat extracted text as verified medical advice

28. Timeline data model

pet_timeline_events

- id

- pet_id

- event_type

- title

- description

- event_date

- source_type

- source_user_id nullable

- source_booking_id nullable

- vet_partner_id nullable

- verification_status

- visibility

- created_at

- updated_at

pet_health_documents

- id

- pet_id

- timeline_event_id

- document_type

- file_url

- uploaded_by

- issued_by

- issued_date

- expiry_date

- extraction_status

- created_at

pet_health_reminders

- id

- pet_id

- timeline_event_id

- reminder_type

- due_date

- recurrence_rule

- status

- notification_preferences

- created_at

pet_record_access_grants

- id

- pet_id

- granted_by_customer_id

- grantee_type

- grantee_id

- scope

- valid_from

- expires_at

- revoked_at

29. Verification states

OWNER_REPORTED

SERVICE_OBSERVATION

DOCUMENT_UPLOADED

VET_VERIFIED

CORRECTED

DISPUTED

Do not display every entry as equally authoritative.

Example:

| Event | Verification |
| --- | --- |
| “Bruno weighs 28 kg” entered by owner | Owner reported |
| Vaccination certificate uploaded | Document uploaded |
| Diagnosis from partner vet | Vet verified |
| Sitter observed limping | Service observation |

30. Access control

| Role | Permitted access |
| --- | --- |
| Pet parent | Complete record |
| Assigned sitter | Current-service instructions only |
| Vet selected by owner | Explicitly shared records |
| Groomer | Relevant allergy/handling details |
| Customer support | Minimal operational information |
| Marketing | No access |
| Society/RWA | No access |
| General city admin | No routine clinical access |

The DPDP Act and notified Rules require lawful-purpose processing, clear notices, safeguards and mechanisms for exercising data rights. Pet records linked with an identifiable owner, address or account should therefore be governed as part of the customer’s personal-data environment.

31. Sharing records with a vet

Recommended flow:

Customer selects documents

↓

Customer sees recipient and purpose

↓

Time-limited access grant created

↓

Vet accesses selected records

↓

Access recorded in audit log

↓

Grant expires or customer revokes it

Do not give every partner vet access to every customer’s complete pet history.

32. Health reminders

The system can safely provide reminders such as:

- Vaccination record expires soon

- Customer-entered medicine reminder

- Grooming interval reached

- Follow-up date recorded in vet document

- Weight has not been updated recently

Wording should distinguish reminders from medical recommendations.

Use:

Bruno’s uploaded vaccination record shows the next date as 12 September. Confirm the schedule with your veterinarian.

Avoid:

Bruno must receive this vaccine on 12 September.

33. Timeline-derived recommendations

Recommendations should use clear rules and transparent reasons.

Examples:

Grooming

Bruno’s last recorded grooming was 10 weeks ago. View available grooming services.

Training

Several walk reports mention leash pulling. Consider an introductory training consultation.

Vet follow-up

The uploaded consultation document includes a follow-up date of 25 August.

Senior care

Bella’s profile identifies her as a senior dog. Review senior-care support options.

These are service recommendations—not diagnosis.

34. Pet health timeline privacy controls

Customers should be able to:

- Add an event

- Correct an event

- Delete an owner-created event

- Download their records

- Revoke sharing

- View access history

- Set reminder preferences

- Request account/data deletion

- Control which carers see specific instructions

Separate:

- Essential current-service instructions

- Historical records

- Veterinary documents

- Marketing recommendations

A sitter should not automatically receive a pet’s entire medical history because they are assigned one walk.

35. Pet health timeline KPIs

| Metric | Purpose |
| --- | --- |
| Profiles with timeline events | Adoption |
| Vaccination documents uploaded | Utility |
| Reminders created | Engagement |
| Reminder completion | Usefulness |
| Records shared with vets | Coordination value |
| Owner corrections | Extraction quality |
| Access revocations | Privacy control |
| Grooming reminder conversion | Commercial value |
| Training-consult conversion | Cross-sell |
| Support/privacy complaints | Trust risk |

Avoid optimising solely for:

- Number of health alerts

- Number of veterinary bookings

- Number of medical-related notifications

Too many reminders can create anxiety and destroy trust.

36. Recommended implementation order

Wave 1: Matching foundation

- Hard eligibility filters

- Rules-based top-three ranking

- Explanation UI

- Admin approval

- Override logging

- Outcome tracking

Wave 2: Credits and referrals

- Immutable credit ledger

- Subscription credits

- Service-recovery credits

- Referral programme

- Promotional-credit rules

- Fraud-review queue

Wave 3: Loyalty

- Care Points

- Non-cash benefits

- Referral tiers

- Contribution monitoring

Wave 4: Health timeline MVP

- Manual timeline entries

- Document uploads

- Reminders

- Owner-controlled sharing

- Activity summaries

Wave 5: Advanced intelligence

- Calibrated prediction models

- Matching optimisation

- Document extraction

- Personalised service recommendations

- Health-timeline summaries

Final approval matrix

| Proposal | Final decision |
| --- | --- |
| AI recommends top three | APPROVE |
| Admin selects final sitter | APPROVE—MANDATORY INITIALLY |
| Human review for every assignment | APPROVE during initial rollout |
| Use “92% match” | CHANGE TO 92/100 unless calibrated |
| Explain matching reasons | MANDATORY |
| Hard safety filters before AI | MANDATORY |
| High-risk auto-assignment | REJECT |
| Cash wallet | DEFER |
| Service credits | APPROVE |
| Referral credits | APPROVE after eligible completed service |
| Promotional credits with undisclosed expiry | REJECT |
| Wallet transfers | DEFER/REJECT EARLY |
| Customer cash withdrawal | REJECT EARLY |
| Force monetary refunds into credit | REJECT |
| Pet health timeline | APPROVE |
| Owner-controlled record sharing | MANDATORY |
| AI-generated diagnosis | REJECT |
| Sitter access to entire medical history | REJECT |
| Health-based service recommendations | APPROVE with transparent reasoning |

Phase 11 product doctrine

AI should improve the administrator’s decision—not hide the decision. Credits should reward repeat care—not become an unregulated cash substitute. Pet records should improve continuity—not become an automated medical authority.

Win condition

The three systems succeed when:

- Admin assignment time decreases

- Matching quality and repeat relationships improve

- Sitter opportunities remain explainable and auditable

- Credits increase profitable repeat usage

- Referral acquisition remains fraud-controlled

- Pet parents maintain useful care histories

- Medical, payment and privacy boundaries remain intact

AI Matching, Loyalty Credits and Pet Health Timeline: GO—with human approval, immutable ledgers, transparent scoring and owner-controlled records.

Phase 11 Advanced Command Center and B2B Dashboards 🧠📊🐾

Executive decision

Approve all four product directions, with several safeguards:

| Product | Decision |
| --- | --- |
| Advanced admin command center | Approve—highest priority with sitter app |
| Booking risk score | Approve as explainable rules first |
| Subscription churn intelligence | Approve as support-assistance, not pressure automation |
| Society web dashboard | Approve; do not build a native app yet |
| Partner web dashboard | Approve; use role-specific modules |

The command center should not become a screen full of charts. It should be an exception-management system:

Operational events

↓

Rules and risk evaluation

↓

Actionable queue

↓

Assigned human owner

↓

Resolution

↓

Audit trail and learning

Product 3: Advanced Admin Command Center

1. Core objective

The command center should help the team answer five questions immediately:

- What is happening now?

- What is likely to fail?

- Who must act?

- How long do they have?

- Was the issue resolved correctly?

It should combine:

- Live operations

- Booking-risk management

- Safety and incidents

- Supply and capacity

- Subscription retention

- Customer support

- City and financial performance

Use consistent application events, metrics, traces and logs rather than building every dashboard from unrelated manual spreadsheets. OpenTelemetry’s observability model similarly separates telemetry into traces, metrics and logs so teams can understand system behaviour from multiple connected signals.

2. Command-center information architecture

National command center

Used by:

- Founders

- National operations

- Safety team

- Finance

- Central support

- Expansion leaders

Main sections

Network Overview

Cities

Live Operations

Bookings at Risk

Safety and Incidents

Sitters and Partners

Subscriptions

Customer Support

Capacity

Finance

Societies

System Health

City command center

Used by:

- City manager

- Operations coordinator

- Local support

- Supply manager

- Society executive

It should automatically scope data to the staff member’s assigned city and zones.

PostgreSQL row-level security can restrict which rows a role may read, insert, update or delete. It is appropriate as a defence-in-depth layer for isolating city, society, booking and incident data, alongside application-level authorisation.

3. Live operations map

Purpose

Display operationally relevant live services—not the continuous location of every sitter.

Show

- Services in progress

- Sitters en route to accepted bookings

- Late arrivals

- Tracking interruptions

- Backup assignments

- Active incidents

- Unassigned urgent bookings

Do not show

- Sitters who are off duty

- Sitters outside an active or imminent booking

- Historical home locations

- Location to marketing or society users

- Precise routes after the operational retention period

Map states

| State | Meaning |
| --- | --- |
| Healthy | Service progressing normally |
| Watch | Minor risk signal |
| Action required | Operations intervention needed |
| Critical | Safety or fulfilment escalation |
| Offline | Live data temporarily unavailable |
| Completed | Service finished |

Example card

Bruno · Dog Walk

Sitter: Riya

City: Ahmedabad

Status: In progress

Started: 7:34 AM

Tracking: Healthy

Elapsed: 22 min

Risk: Low

[Open Booking] [Contact] [View Route]

Location, addresses, schedules and incident information should be access-limited, purpose-specific and auditable under the Indian digital-data protection framework. The notified DPDP Rules, 2025 have phased commencement, but the product should implement those controls before expanding access across cities and partner roles.

4. City health score

A city health score can be useful, but one number must never hide a safety failure.

Recommended score

| Dimension | Weight |
| --- | --- |
| Safety and quality | 30% |
| Fulfilment and supply | 20% |
| Retention and demand | 20% |
| Economics | 20% |
| Support and compliance | 10% |

Example

Ahmedabad City Health: 87/100 · Approved

Safety:       28/30

Fulfilment:   18/20

Retention:    16/20

Economics:    17/20

Support:       8/10

Hard overrides

The city cannot be labelled “healthy” when any of these is true:

- Unresolved critical incident

- Partner payouts materially overdue

- Critical documents expired

- Cross-city data exposure

- Booking completion below minimum

- Finance unreconciled

- Safety incidents deliberately misclassified

Recommended health bands

| Score | Status | Action |
| --- | --- | --- |
| 90–100 | Excellent | Eligible for controlled growth |
| 80–89 | Healthy | Normal operation |
| 70–79 | Monitor | Restrict expansion |
| 60–69 | Intervention | Freeze new clusters |
| Below 60 | Critical | Consider service/city pause |

5. Sitter risk list

Rename this module:

Sitter Quality Review Queue

“Risk list” can become an unfair blacklist if it combines weak, noisy or outdated signals.

Signals

- Repeated late arrivals

- Sitter-initiated cancellations

- No-shows

- Missing reports

- Unexplained GPS interruptions

- Low recent ratings

- Incident involvement

- Expired documents

- Unresolved payout dispute

- Abnormal workload

- Repeated customer complaints

Context required

Each signal should show:

- Severity

- Frequency

- Date

- Service volume denominator

- Whether the concern was verified

- Whether the sitter appealed

- Corrective training completed

- Current review status

A sitter with one complaint across 500 bookings should not be treated the same as a sitter with three complaints across ten bookings.

Review states

NORMAL

WATCH

COACHING_REQUIRED

BOOKING_LIMITED

TEMPORARILY_PAUSED

INVESTIGATION

REINSTATED

REMOVED

Required protections

- Clear reasons

- Human review

- Appeal/dispute mechanism

- No automatic lifetime penalty

- Separate verified incidents from allegations

- Exclude customer/admin-caused failures

- Model version and audit history

6. Delayed-service alerts

A delayed-service alert should create an actionable operational queue.

Alert progression

Booking approaching start

↓

Sitter not en route

↓

Sitter reminder

↓

Grace period exceeded

↓

Operations notified

↓

Backup checked

↓

Customer proactively updated

Alert record

- Booking

- Scheduled time

- Current sitter

- Latest acknowledgement

- Travel estimate

- Customer communication status

- Backup availability

- Assigned operations owner

- SLA deadline

Prometheus guidance recommends alerting on actionable symptoms and avoiding alerts where there is no meaningful response. The command center should therefore suppress duplicates, group related alerts and always present a next action.

7. Incident heatmap

The heatmap should help identify recurring operational causes—not publicly label neighbourhoods or sitters as dangerous.

Dimensions

- City and service zone

- Society

- Service type

- Time of day

- Incident category

- Pet-risk classification

- Provider-experience level

- Root cause

- Severity

Incident categories

| Category | Examples |
| --- | --- |
| Access | Gate denial, wrong address |
| Pet handling | Escape risk, aggression |
| Medical | Pet distress, injury |
| Scheduling | No-show, late arrival |
| Customer handover | Customer unavailable |
| Technology | Tracking/app failure |
| Partner quality | Hygiene or service concern |
| Security/privacy | Wrong data or access exposure |

Heatmap safeguards

- Minimum sample-size threshold

- No personally identifying labels

- Separate verified incidents from reports under investigation

- Show exposure rate, not just raw counts

- Compare against booking volume

- Retain drill-down only for authorised safety roles

Example:

Wrong:

Powai has 15 incidents.

Better:

Powai had 15 reportable events across 4,200 services:

0 critical, 2 serious and 13 minor.

8. Revenue by city and service

The financial module must distinguish:

| Metric | Meaning |
| --- | --- |
| GMV | Total customer spending |
| Platform revenue | Retained commission and fees |
| Partner payouts | Amount payable to providers |
| Direct contribution | Revenue minus direct costs |
| City operating contribution | Contribution minus local fixed costs |
| Fully allocated result | After central cost allocation |

Required views

- City

- Cluster

- Service

- Subscription plan

- Society

- Acquisition channel

- Customer cohort

- Partner category

Avoid one ambiguous “revenue” widget.

9. Capacity planning module

Purpose

Prevent the company from selling services or subscriptions that the city cannot deliver.

Show by city, zone and time window

- Gross provider capacity

- Existing booking commitments

- Subscription reservations

- Backup reserve

- Leave impact

- Remaining sellable capacity

- Stop-sales threshold

Capacity statuses

| Utilisation | Status |
| --- | --- |
| Below 70% | Healthy |
| 70–85% | Controlled selling |
| 85–90% | Restrict acquisition |
| Above 90% | Stop sales |
| No backup | Block high-frequency plans |

Command-center actions

- Pause a time slot

- Pause a plan

- Move demand to another window

- Recruit providers

- Increase backup reserve

- Waitlist customers

- Open an adjacent zone only after gate approval

10. Support SLA dashboard

Queues

- General questions

- Late sitter

- Booking failure

- Payment/refund

- Subscription

- Safety concern

- Privacy/account

- Society escalation

- Partner dispute

Metrics

| Metric | Purpose |
| --- | --- |
| First response time | Initial responsiveness |
| Resolution time | End-to-end service |
| SLA breach rate | Operational control |
| Reopen rate | Resolution quality |
| Escalation rate | Complexity |
| Backlog age | Capacity problem |
| Contacts per booking | Product friction |
| Customer satisfaction | Outcome quality |

Severity-based targets

| Severity | Example | Target |
| --- | --- | --- |
| P0 | Pet missing/serious danger | Immediate |
| P1 | Active service failure | Minutes |
| P2 | Same-day booking/payment | Defined short SLA |
| P3 | General query | Business-hour SLA |

Booking Risk Score

11. Product objective

Identify bookings that require additional preparation before they fail.

The score should:

- Be calculated before confirmation

- Update when conditions change

- Explain every risk factor

- Recommend actions

- Remain reviewable by humans

NIST’s AI Risk Management Framework recommends documenting human oversight, system limitations, explanations and monitoring of unexpected behaviour or performance degradation.

12. Corrected risk factors

| Factor | Recommended treatment |
| --- | --- |
| First-time customer | Low–medium context signal |
| First booking for pet | Medium |
| New sitter | Medium; do not automatically penalise heavily |
| High pet-risk classification | High |
| Long travel time | High |
| No approved backup | High/critical for subscriptions |
| Peak-time booking | Medium |
| Unpaid booking | Block confirmation rather than score it |
| Previous complaint | Depends on severity, recency and resolution |
| Boarding | Higher custody exposure |
| Medication/senior care | High or specialist review |
| Society access incomplete | High |
| Tight back-to-back schedule | High |
| Expired sitter document | Ineligible, not merely risky |
| Open sitter investigation | Ineligible or senior review |

Important correction

Some conditions should be hard blockers, not score factors:

Payment not verified

Required document expired

Sitter not qualified

No service capacity

Sitter under suspension

Service unavailable in zone

A 95/100 match must not override an expired document or failed payment.

13. Booking-risk score design

Use an explainable point score first.

Example

| Factor | Points |
| --- | --- |
| First booking for pet | +8 |
| New sitter | +8 |
| Yellow pet-risk level | +15 |
| Red/specialist pet | +30 |
| Travel above target | +15 |
| No backup | +20 |
| Peak-time slot | +8 |
| Prior unresolved complaint | +20 |
| Boarding service | +15 |
| Medication required | +20 |
| Gate approval missing | +15 |

Mitigating factors

| Mitigation | Adjustment |
| --- | --- |
| Previous successful pet-sitter relationship | −20 |
| Experienced specialist sitter | −10 |
| Named approved backup | −15 |
| Successful trial completed | −10 |
| Same society/locality sitter | −5 |
| Flexible time window | −5 |

Levels

| Score | Level | Action |
| --- | --- | --- |
| 0–19 | Low | Normal workflow |
| 20–39 | Medium | Operations visibility |
| 40–59 | High | Backup and admin review |
| 60+ | Critical | Senior approval or reject |
| Hard blocker | Blocked | Cannot confirm |

Do not call this a probability unless it has been calibrated against real booking outcomes.

14. Risk-score output

Booking Risk: 47/100 · High

Reasons

• First service with this pet: +8

• Yellow behavioural risk: +15

• Travel estimate 31 minutes: +15

• Peak-time booking: +8

• Approved backup available: −15

• Experienced large-dog sitter: −10

Required actions

✓ Admin review

✓ Confirm introduction notes

✓ Keep backup reserved

15. Dynamic risk updates

Risk should be recalculated when:

- Sitter changes

- Customer updates pet instructions

- Backup cancels

- Payment fails

- Weather or route conditions affect travel

- Society gate approval changes

- Primary sitter reports leave

- A provider investigation begins

Store risk snapshots instead of overwriting history.

booking_risk_snapshots

- booking_id

- score

- level

- factor_scores

- blockers

- recommended_actions

- model_version

- calculated_at

16. Risk-score governance

Track:

- High-risk false positives

- Low-risk bookings that failed

- Admin override rate

- Outcome by risk band

- Outcome by city

- New-sitter treatment

- Pet-risk classification accuracy

- Score drift

- Model/rule version

NIST recommends regular post-deployment monitoring to identify degradation, near-misses and unexpected behaviour.

Subscription Intelligence

17. Churn-risk objective

Identify subscribers who may need product or service recovery before renewal.

The goal is not:

Find users who can be pressured into paying.

The goal is:

Detect service-plan mismatch and offer a relevant remedy.

18. Corrected churn signals

| Signal | Likely interpretation |
| --- | --- |
| Unused credits | Plan may be oversized |
| Credits exhausted early | Upgrade opportunity |
| Low service rating | Quality problem |
| Repeated sitter changes | Continuity problem |
| Payment failure | Payment-method issue |
| Repeated missed walks | Timing mismatch |
| Multiple support complaints | Unresolved dissatisfaction |
| Repeated pauses | Seasonal or poor plan fit |
| Drop in app/report usage | Lower engagement |
| Cancellation-page visit | Strong churn intent |
| Preferred sitter unavailable | Trust risk |
| Travel dates | Temporary pause opportunity |

Do not use sensitive pet-health information for marketing or churn pressure without a clearly justified purpose and suitable customer controls.

19. Churn-risk model

Begin with rule-based scoring:

| Signal | Example points |
| --- | --- |
| Credit utilisation below 40% | +20 |
| Last rating below 4 | +25 |
| Two or more sitter changes | +20 |
| Payment failure | +25 |
| Two support complaints | +20 |
| Pause more than twice | +15 |
| Preferred sitter unavailable | +15 |
| Customer opened cancellation flow | +30 |

Levels

| Score | Level | Recommended action |
| --- | --- | --- |
| 0–19 | Healthy | No intervention |
| 20–39 | Watch | In-app education |
| 40–59 | High | Support review |
| 60+ | Critical | Human retention outreach |

20. Remedy engine

Do not immediately offer discounts.

Match the intervention to the cause:

| Churn cause | Best response |
| --- | --- |
| Low utilisation | Downgrade or pause |
| Travel | Skip cycle or temporary pause |
| Sitter changes | Primary/backup review |
| Timing issue | Reschedule recurring slot |
| Payment failure | Update method/manual link |
| Low rating | Service recovery |
| Too expensive | Smaller plan |
| Credits expiring | Reminder or limited rollover |
| Pet health change | Pause without sales pressure |

Workflow

Risk detected

↓

Cause ranked

↓

Support reviews context

↓

Relevant action offered

↓

Customer chooses

↓

Outcome recorded

21. Retention-message controls

- Customer communication preferences respected

- No repeated daily pressure

- Separate service messages from marketing

- Clear opt-out controls

- No false urgency

- Cancellation remains available

- Discounts require authorised limits

- Every manual offer is recorded

22. Churn dashboard

Show:

- Subscribers by risk level

- Renewal date

- Primary churn drivers

- Credits used

- Recent ratings

- Sitter continuity

- Failed-payment state

- Support owner

- Last contact

- Recommended action

- Outcome

KPIs

- Renewal rate

- Churn rate

- Save rate

- Downgrade rate

- Pause-to-reactivation

- Payment recovery

- Discount cost

- Contribution retained

- Complaint rate from retention outreach

Do not optimise only for “saved subscriptions.” A forced save followed by a refund is not success.

Society Web Dashboard

23. Product decision

Web dashboard is sufficient for Phase 11.

Society stakeholders generally need periodic reporting, gate lists and event management—not constant native-app engagement.

24. Society-dashboard modules

Overview

- Active resident accounts

- Paying residents

- Monthly completed services

- Subscription users

- Average rating

- Upcoming events

- Open society issues

Verified sitter list

Show only operational information:

- Name

- Photograph

- Verification status

- Approved services

- Society access status

- Validity dates

- Platform contact

Do not show:

- Identity documents

- Private sitter address

- Personal phone number

- Earnings

- Other customers’ activity

Gate-access list

Use time-bound access:

| Field | Purpose |
| --- | --- |
| Sitter name/photo | Gate identification |
| Booking date/window | Entry validity |
| Society/tower | Destination |
| Platform verification | Trust |
| Access expiry | Prevent ongoing access |
| Operations phone | Escalation |

Do not give RWAs unrestricted live location or resident booking histories.

Complaint summary

Show aggregated information:

- Complaint category

- Status

- Resolution time

- Recurring issue

- Corrective action

Avoid exposing personal complaint details unless necessary for resolving that society-specific case.

Monthly report export

Include:

- Resident registrations

- Completed bookings

- Service categories

- Rating

- Events

- Complaint categories

- Gate incidents

- Subscription adoption

- Aggregate revenue where contractually appropriate

Exclude:

- Individual health records

- Detailed pet behaviour

- Payment details

- Home-access instructions

- Individual GPS routes

25. Society data access

Use a separate role such as:

SOCIETY_ADMIN

SOCIETY_SECURITY

SOCIETY_VIEWER

Each role should have different permissions.

| Role | Access |
| --- | --- |
| Society admin | Aggregate programme reports and events |
| Gate/security | Temporary access list only |
| Society viewer | Summary metrics |
| Platform city manager | Full operational relationship |
| National admin | Authorised cross-city governance |

Partner Dashboard Upgrade

26. Product decision

Keep groomers, trainers, vets and other specialist partners on a responsive web dashboard during Phase 11.

Build a native partner app only when:

- Partners receive frequent daily bookings

- Push responsiveness becomes a bottleneck

- Offline reporting is necessary

- Web adoption materially damages completion

- The business can support another mobile release cycle

27. Shared partner modules

| Feature | Priority |
| --- | --- |
| Assigned bookings | P0 |
| Accept/reject | P0 |
| Booking detail | P0 |
| Complete service/report | P0 |
| Earnings and payouts | P0 |
| Availability | P0/P1 |
| Reviews | P1 |
| Profile management | P1 |
| Document management | P1 |
| Package management | P1 |
| Support | P0 |

Booking flow

Partner receives booking

↓

Reviews service and payout

↓

Accepts or rejects

↓

Views necessary pet details

↓

Completes service

↓

Uploads report/evidence

↓

Customer reviews

↓

Payout released

28. Partner-type customisation

Groomer

- Grooming package

- Pet size/coat

- Hygiene checklist

- Before/after media

- Products used

- Skin/coat observations

Trainer

- Behaviour objective

- Session plan

- Exercises

- Owner homework

- Progress report

- Package sessions remaining

Vet

- Appointment status

- Owner-shared records

- Consultation note

- Follow-up date

- Document upload

- Restricted clinical access

Generic city or customer-support users should not edit clinical records or publish medical conclusions.

Boarding provider

- Check-in/out

- Capacity

- Vaccination requirements

- Feeding schedule

- Daily updates

- Incident reporting

29. Package editing

Do not allow partners to instantly publish unrestricted prices or medical/service claims.

Use a draft-and-approval workflow:

Partner edits package

↓

Draft saved

↓

Validation checks

↓

Platform review where required

↓

Published version created

Partner may edit

- Description

- Availability

- Included services

- Duration

- Service radius

- Media

- Suggested price within configured limits

Central approval required for

- Price outside approved band

- New service category

- Medical claims

- Cancellation-policy changes

- High-risk package

- Boarding capacity changes

- Promotional claims

- Major refund terms

Published package versions should be immutable for historical bookings.

30. Dashboard and alert architecture

Recommended event model

booking.requested

booking.risk_calculated

booking.assigned

sitter.en_route

service.started

tracking.interrupted

service.delayed

incident.opened

report.submitted

subscription.churn_scored

support.sla_at_risk

partner.package_submitted

Every event should contain

- Event ID

- Actor

- Entity

- City and zone

- Timestamp

- Source application

- Correlation ID

- App/version

- Severity

- Idempotency key

Audit trail

Sensitive operations should be append-only:

- Assignment overrides

- Risk-score overrides

- Credit adjustments

- Incident changes

- Refund approvals

- Package publication

- Data exports

- Staff access changes

OWASP recommends integrity-controlled audit trails for high-value transactions and cautions against logging private or confidential data unnecessarily.

31. Recommended database additions

booking_risk_snapshots

booking_risk_factors

booking_risk_actions

subscriber_churn_snapshots

subscriber_churn_factors

retention_actions

retention_outcomes

city_health_snapshots

sitter_quality_snapshots

operational_alerts

alert_events

alert_assignments

alert_acknowledgements

support_sla_policies

support_sla_events

society_users

society_role_assignments

society_gate_access_entries

society_report_exports

partner_packages

partner_package_versions

partner_availability

partner_service_reports

32. Recommended APIs

Command center

GET  /v1/admin/command-center/overview

GET  /v1/admin/command-center/live-operations

GET  /v1/admin/alerts

POST /v1/admin/alerts/{alertId}/acknowledge

POST /v1/admin/alerts/{alertId}/assign

POST /v1/admin/alerts/{alertId}/resolve

Booking risk

GET  /v1/admin/bookings/{bookingId}/risk

POST /v1/admin/bookings/{bookingId}/risk/recalculate

POST /v1/admin/bookings/{bookingId}/risk/override

POST /v1/admin/bookings/{bookingId}/approve

Churn intelligence

GET  /v1/admin/subscriptions/churn-risk

GET  /v1/admin/subscriptions/{id}/churn-risk

POST /v1/admin/subscriptions/{id}/retention-actions

POST /v1/admin/retention-actions/{id}/outcome

Society

GET  /v1/society/dashboard

GET  /v1/society/resident-metrics

GET  /v1/society/gate-access

GET  /v1/society/events

GET  /v1/society/reports/{period}/export

Partner

GET  /v1/partner/bookings

POST /v1/partner/bookings/{id}/accept

POST /v1/partner/bookings/{id}/reject

POST /v1/partner/bookings/{id}/complete

POST /v1/partner/reports

GET  /v1/partner/earnings

GET  /v1/partner/packages

POST /v1/partner/packages

POST /v1/partner/packages/{id}/submit

Final approval matrix

| Proposal | Final decision |
| --- | --- |
| Live operations map | Approve—active services only |
| City health score | Approve with safety overrides |
| Sitter risk list | Rename Quality Review Queue |
| Booking risk predictor | Approve as explainable rules first |
| Subscription churn risk | Approve with human-reviewed remedies |
| Delayed-service alerts | Approve |
| Incident heatmap | Approve with severity and volume context |
| Revenue by city/service | Approve with GMV/revenue/contribution separation |
| Capacity planning | Mandatory |
| Support SLA dashboard | Mandatory |
| First-time customer as major risk | Reduce importance |
| Unpaid booking as risk | Treat as confirmation blocker |
| No backup sitter | High/critical risk |
| Senior approval for critical booking | Approve |
| Society native app | Defer |
| Society web dashboard | Approve |
| RWA access to resident details | Reject; aggregate data only |
| Partner web dashboard | Approve |
| Partner package editing | Approve with versioned approval workflow |
| Native partner app | Defer |

Phase 11 command-center doctrine

Predict only what can be explained, alert only when somebody can act, expose only the data a role needs and keep humans accountable for high-impact decisions.

Win condition

The system succeeds when:

- Operations intervene before bookings fail

- Safety alerts are faster and less noisy

- City performance is directly comparable

- Subscription remedies match actual churn causes

- Societies receive useful aggregate reports without resident surveillance

- Partners manage bookings and payouts independently

- Every override and sensitive action remains auditable

Advanced Admin Command Center: GO—with event-driven operations, explainable risk scores, human review and strict role-based data access.

Phase 11 Database, API, Security and Location-Privacy Architecture 🔐📱🐾

Executive decision

Your proposed foundation is good, but it needs several production-grade corrections:

- Separate devices, push tokens and authenticated sessions.

- Separate tracking sessions, GPS points and operational events.

- Store matching recommendations as versioned runs with explanations and admin decisions.

- Replace the mutable wallet.balance model with an immutable service-credit ledger.

- Split pet timeline events, documents, reminders and sharing permissions.

- Make all APIs object-authorized, idempotent and role-scoped.

- Treat live location as a temporary, purpose-limited operational data stream.

The corrected architecture should be:

Mobile device

├── authenticated session

├── push token

└── app/version state

Booking

├── service session

├── tracking session

├── tracking points

├── operational events

├── service report

└── incidents

Customer

├── credit accounts

├── immutable credit ledger

├── sitter preferences

└── pet timeline

1. Device and push-token schema

Problem with the current table

device_tokens

- user_id

- device_type

- token

- app_version

This combines three different concepts:

- The physical/app device installation

- The push-notification token

- The authenticated user session

One user may have several devices, multiple users may sequentially use the same device, and push tokens can rotate or become invalid. Firebase recommends storing a timestamp with registration tokens, refreshing token records periodically and removing tokens that are stale or rejected as invalid.

Recommended tables

mobile_devices

- id

- user_id nullable

- installation_id

- app_type                // CUSTOMER, SITTER

- platform                // IOS, ANDROID

- device_model

- os_version

- app_version

- build_number

- locale

- timezone

- status

- first_seen_at

- last_seen_at

- created_at

- updated_at

push_tokens

- id

- device_id

- provider                // FCM, APNS, EXPO

- token_encrypted

- environment             // DEVELOPMENT, PRODUCTION

- status                  // ACTIVE, INVALID, REVOKED

- notifications_enabled

- registered_at

- last_validated_at

- last_sent_at

- invalidated_at

- created_at

- updated_at

mobile_sessions

- id

- user_id

- device_id

- refresh_token_family_id

- refresh_token_hash

- status

- issued_at

- last_used_at

- expires_at

- revoked_at

- compromise_detected_at

- last_ip_hash

- created_at

Important rules

- Use a stable app-generated installation_id.

- Keep one push-token record per app installation and provider.

- Never treat a push token as an authentication credential.

- Encrypt the usable token at rest because the server must retrieve it to send notifications.

- Do not write push tokens into application logs.

- Mark tokens invalid after permanent provider errors.

- Detach or revoke the token when a user logs out of a shared device.

Refresh tokens should use rotation: each refresh issues a new refresh token and invalidates the previous one while retaining the token-family relationship for replay detection. This is the current OAuth security best practice.

On the device, refresh tokens should be stored in secure platform-backed storage, such as Expo SecureStore, rather than AsyncStorage or ordinary local files. Expo SecureStore is intended for small secrets such as tokens and keys.

2. Tracking schema

Problem with one tracking_events table

This table mixes:

- High-frequency GPS samples

- Service lifecycle events

- Alerts

- Tracking state

- Arbitrary metadata

tracking_events

- booking_id

- event_type

- lat

- lng

- metadata

Continuous location points and business events have different volume, retention, indexing and access requirements.

Corrected structure

Tracking session

tracking_sessions

- id

- booking_id

- sitter_id

- device_id

- service_session_id

- status

- permission_state

- consent_notice_version

- started_at

- ended_at

- last_point_at

- termination_reason

- point_count

- distance_meters

- duration_seconds

- tracking_quality

- created_at

- updated_at

Statuses:

PENDING

ACTIVE

OFFLINE

PERMISSION_LOST

APP_TERMINATED

COMPLETED

ABORTED

UNDER_REVIEW

GPS points

tracking_points

- id

- tracking_session_id

- sequence_number

- location geography(Point, 4326)

- recorded_at_device

- received_at_server

- accuracy_meters

- altitude_meters nullable

- speed_mps nullable

- heading_degrees nullable

- battery_percent nullable

- source

- is_mock_location_suspected

- created_at

PostGIS supports geography(Point,4326) for longitude/latitude coordinates and GiST spatial indexes, which is preferable to repeatedly processing separate unindexed lat and lng values.

For high-volume production use:

- Partition tracking_points by time once volume justifies it.

- Index tracking_session_id, recorded_at_device.

- Add a GiST index on location.

- Batch-upload points rather than making one HTTP request per point.

- Use sequence_number and idempotency keys to recover offline data safely.

- Store raw tracking data separately from derived distance and route summaries.

Operational tracking events

tracking_events

- id

- tracking_session_id

- booking_id

- event_type

- severity

- event_time_device

- received_at_server

- metadata_json

- created_by

- idempotency_key

- created_at

Event types:

TRACKING_STARTED

TRACKING_PAUSED_SYSTEM

TRACKING_RESUMED

LOCATION_PERMISSION_LOST

GPS_DISABLED

APP_TERMINATED

NETWORK_OFFLINE

NETWORK_RESTORED

GEOFENCE_ARRIVAL

ROUTE_ANOMALY_DETECTED

LONG_PAUSE_DETECTED

TRACKING_ENDED

The event does not need latitude and longitude unless the event itself requires a location snapshot.

3. Matching recommendation schema

Problem with the proposed table

matching_recommendations

- booking_id

- sitter_id

- score

- reasons

- accepted_by_admin

This does not record:

- Which algorithm produced the score

- Which other sitters were eligible

- Why candidates were excluded

- Which admin made the decision

- Whether the admin overrode the recommendation

- The eventual service outcome

Recommended model

matching_runs

- id

- booking_id

- algorithm_version

- policy_version

- requested_by

- status

- generated_at

matching_candidates

- id

- matching_run_id

- sitter_id

- eligible

- rank

- match_score              // 0–100 score, not probability

- factor_scores_json

- reasons_json

- warnings_json

- exclusion_reasons_json

- created_at

matching_decisions

- id

- matching_run_id

- selected_sitter_id

- selected_candidate_id nullable

- decided_by_admin_id

- decision_type            // RECOMMENDED, OVERRIDE, MANUAL

- override_reason

- decided_at

matching_outcomes

- id

- matching_run_id

- sitter_id

- sitter_accepted

- completed

- on_time

- customer_rating

- customer_requested_repeat

- sitter_cancelled

- backup_used

- incident_id nullable

- recorded_at

Scoring rule

Use:

Riya — Match score 92/100

Do not label it “92% probability” unless the model is statistically calibrated and validated as a probability.

Hard eligibility filters must execute before ranking:

- Current verification

- Valid documents

- Correct service permission

- Availability

- Pet-risk compatibility

- Capacity

- Service-zone access

- No suspension

- No schedule conflict

The admin should see explanations and retain final approval during the initial rollout.

4. Replace the wallet with a credit ledger

Problem with this schema

wallets

- user_id

- balance

A mutable balance does not provide a reliable audit trail and can become inconsistent during concurrent bookings, refunds and retries.

There is also a regulatory distinction between internal service credits and a cash-like prepaid wallet. RBI states that a closed-system instrument can only purchase the issuer’s own goods or services, cannot support cash withdrawal and cannot settle third-party services. A marketplace involving independent service providers should therefore obtain payments advice before creating reloadable cash balances.

Recommended early model

Name the feature Credits, not Wallet.

credit_accounts

- id

- customer_id

- credit_type

- currency

- status

- created_at

- updated_at

Credit types:

SUBSCRIPTION

REFERRAL

PROMOTIONAL

SOCIETY_BENEFIT

SERVICE_RECOVERY

REFUND_ELECTED

credit_ledger_entries

- id

- credit_account_id

- booking_id nullable

- subscription_id nullable

- referral_id nullable

- entry_type

- amount_minor

- source_reference

- reason_code

- expires_at nullable

- idempotency_key

- created_by_type

- created_by_id

- created_at

Entry types:

GRANT

RESERVE

CONSUME

RELEASE

RESTORE

EXPIRE

REVERSE

ADMIN_ADJUSTMENT

Balance calculation

Available credits

=

grants

+ releases

+ restores

− reservations

− consumption

− reversals

− expiry

A cached available_balance_minor may be maintained for performance, but the immutable ledger remains the financial source of truth.

Controls

- Store money in minor units, such as paise.

- Require idempotency keys for every adjustment.

- Every admin adjustment needs a reason.

- Require dual approval above a configured threshold.

- Do not allow customer transfers or cash withdrawal.

- Do not force eligible cash refunds into platform credits without customer choice.

5. Favourite-sitter schema

The basic table is acceptable but should support preference state and uniqueness.

sitter_preferences

- id

- customer_id

- pet_id

- sitter_id

- preference_type          // PREFERRED, DO_NOT_MATCH

- priority

- source                   // CUSTOMER, ADMIN, SYSTEM

- reason nullable

- status

- created_at

- updated_at

Constraints:

UNIQUE(customer_id, pet_id, sitter_id, preference_type)

Use customer-facing language such as Preferred sitter, not guaranteed sitter.

A DO_NOT_MATCH preference should be tightly access-controlled because it may contain complaint or safety context.

6. Pet health timeline schema

Problem with one table

A single event record containing a document URL and reminder date becomes difficult to manage when:

- One event contains several documents

- A document has access permissions

- Several reminders arise from one event

- A customer shares only selected files with a vet

- AI extracts metadata that needs owner confirmation

Corrected model

pet_health_events

- id

- pet_id

- event_type

- title

- description

- event_date

- source_type

- source_user_id nullable

- source_booking_id nullable

- vet_partner_id nullable

- verification_status

- visibility

- created_at

- updated_at

- deleted_at nullable

Verification statuses:

OWNER_REPORTED

SERVICE_OBSERVATION

DOCUMENT_UPLOADED

VET_VERIFIED

CORRECTED

DISPUTED

pet_health_documents

- id

- pet_health_event_id

- pet_id

- document_type

- storage_key

- original_filename

- mime_type

- size_bytes

- checksum

- issued_by

- issued_date

- expiry_date

- extraction_status

- uploaded_by

- created_at

pet_health_reminders

- id

- pet_id

- pet_health_event_id nullable

- reminder_type

- due_at

- recurrence_rule nullable

- status

- created_at

- updated_at

pet_record_access_grants

- id

- pet_id

- granted_by_customer_id

- grantee_type

- grantee_id

- scope_json

- purpose

- valid_from

- expires_at

- revoked_at

- created_at

The pet parent should control what a vet or specialist receives. Sitters should see only instructions necessary for the currently assigned service.

7. App feedback schema

The proposed table needs product and diagnostic context without capturing raw sensitive logs.

app_feedback

- id

- user_id nullable

- device_id nullable

- app_type

- category

- severity

- rating nullable

- comment

- screen_name

- app_version

- build_number

- platform

- os_version

- booking_id nullable

- attachment_storage_key nullable

- status

- assigned_to nullable

- resolved_at nullable

- created_at

Categories:

BUG

USABILITY

PERFORMANCE

BOOKING

TRACKING

PAYMENT

NOTIFICATION

ACCESSIBILITY

OTHER

Do not automatically attach:

- Authentication tokens

- Customer addresses

- Gate codes

- Pet medical records

- Complete GPS routes

- Payment details

OWASP recommends security logging while explicitly avoiding unnecessary confidential or private data in logs.

8. Corrected mobile authentication APIs

Use a versioned API namespace.

POST /v1/mobile/auth/login

POST /v1/mobile/auth/refresh

POST /v1/mobile/auth/logout

GET  /v1/mobile/auth/sessions

DELETE /v1/mobile/auth/sessions/{sessionId}

Login response

{

"access_token": "...",

"access_token_expires_at": "...",

"refresh_token": "...",

"session_id": "...",

"device_id": "..."

}

Security rules

- Short-lived access token

- Rotating, per-device refresh token

- Refresh-token reuse detection

- Server-side session revocation

- Rate limiting and OTP abuse protection

- Logout from one device or every device

- MFA for national and city administrators

- Separate mobile and admin session policies

OWASP identifies broken authentication and broken object-level authorization as major API risks. Every endpoint accepting an object identifier must verify that the authenticated actor is authorized to access that particular object.

9. Device-token APIs

Replace generic token endpoints with device-scoped endpoints:

PUT    /v1/mobile/devices/{deviceId}/push-token

DELETE /v1/mobile/devices/{deviceId}/push-token

PATCH  /v1/mobile/devices/{deviceId}

Example registration:

{

"provider": "FCM",

"token": "...",

"app_type": "SITTER",

"platform": "ANDROID",

"environment": "PRODUCTION",

"app_version": "2.3.0",

"build_number": "147"

}

The deviceId must belong to the current authenticated session.

10. Push-notification APIs

Do not expose this publicly

POST /api/notifications/push

A general client-callable push endpoint could be abused to send arbitrary notifications.

Use an internal event-driven service:

POST /internal/v1/notifications/events

POST /internal/v1/notifications/send

Only trusted backend services or tightly authorized admins should invoke it.

Customer-facing APIs:

GET   /v1/me/notification-preferences

PATCH /v1/me/notification-preferences

GET   /v1/me/notifications

POST  /v1/me/notifications/{notificationId}/read

Store critical booking state in the backend and in-app inbox. Push is a delivery mechanism, not proof that the user received or read an operational update.

11. Advanced tracking APIs

Corrected endpoints

POST /v1/sitter/bookings/{bookingId}/tracking-sessions

POST /v1/tracking-sessions/{sessionId}/points:batch

POST /v1/tracking-sessions/{sessionId}/events

POST /v1/tracking-sessions/{sessionId}/end

GET  /v1/customer/bookings/{bookingId}/live-tracking

GET  /v1/customer/bookings/{bookingId}/route-replay

GET  /v1/admin/bookings/{bookingId}/tracking

Why batch points?

Instead of:

POST /api/tracking/point

for every coordinate, send small batches:

{

"batch_id": "uuid",

"points": [

{

"sequence": 101,

"recorded_at": "...",

"latitude": 23.01,

"longitude": 72.52,

"accuracy_meters": 12

}

]

}

This is more resilient to weak connectivity and lowers network and battery overhead.

Required controls

- The booking must be assigned to the sitter.

- The service must permit tracking.

- Only one active session is allowed per booking.

- Start and end calls require idempotency keys.

- Points outside the active session are rejected.

- Customer access is limited to their booking.

- Admin access is limited to operations/safety roles.

- Route replay omits pre-service and post-service travel.

Expo supports location subscriptions and background-task integration, but background execution remains subject to mobile-platform restrictions, so the backend must explicitly represent interrupted or incomplete tracking rather than fabricating a continuous route.

12. Matching APIs

GET  /v1/admin/bookings/{bookingId}/matching-recommendations

POST /v1/admin/bookings/{bookingId}/matching-recommendations:refresh

POST /v1/admin/bookings/{bookingId}/assignments

Assignment payload:

{

"matching_run_id": "uuid",

"sitter_id": "uuid",

"candidate_id": "uuid",

"decision_type": "RECOMMENDED",

"override_reason": null,

"expected_booking_version": 14

}

Use optimistic concurrency through expected_booking_version so that two admins cannot assign different sitters simultaneously.

13. Credit APIs

Read APIs

GET /v1/me/credits

GET /v1/me/credit-transactions

Do not use a separate client-controlled apply endpoint

POST /api/wallet/apply-credit

Credit reservation and use should be part of the atomic booking checkout:

POST /v1/bookings/quote

POST /v1/bookings

Example:

{

"pet_id": "...",

"service_package_id": "...",

"scheduled_at": "...",

"payment_method": "SERVICE_CREDITS",

"credit_account_id": "...",

"idempotency_key": "..."

}

The backend must:

- Lock or safely reserve the available credit.

- Create the booking.

- Record the ledger reservation.

- Roll back the entire operation if any step fails.

Admin API:

POST /v1/admin/customers/{customerId}/credit-adjustments

Required fields:

- Credit type

- Amount

- Reason code

- Case or booking reference

- Idempotency key

- Approver where required

14. Health-timeline APIs

GET    /v1/pets/{petId}/health-timeline

POST   /v1/pets/{petId}/health-timeline

PATCH  /v1/pets/{petId}/health-timeline/{eventId}

DELETE /v1/pets/{petId}/health-timeline/{eventId}

Your proposed delete endpoint contains a typo:

:eventide

It should be:

:eventId

Additional endpoints:

POST   /v1/pets/{petId}/health-documents/upload-url

POST   /v1/pets/{petId}/health-reminders

PATCH  /v1/pets/{petId}/health-reminders/{reminderId}

POST   /v1/pets/{petId}/record-access-grants

DELETE /v1/pets/{petId}/record-access-grants/{grantId}

GET    /v1/pets/{petId}/record-access-log

An update should usually use PATCH, because clients commonly change only selected fields.

15. Feedback API

Add the missing endpoint:

POST /v1/mobile/feedback

GET  /v1/admin/mobile-feedback

PATCH /v1/admin/mobile-feedback/{feedbackId}

The mobile client should send only explicitly allowlisted diagnostic fields.

16. Security requirements

Authentication

- Rotating refresh tokens

- Short-lived access tokens

- Per-device sessions

- Session revocation

- OTP and login rate limits

- MFA for administrators

- Reauthentication for high-risk actions

- No tokens in URLs or logs

Authorization

Use RBAC plus contextual checks:

Role

+ city scope

+ service-zone scope

+ booking relationship

+ action permission

Examples:

- A sitter can read only currently assigned bookings.

- A customer can read only their own pets and bookings.

- A city manager can access only assigned cities.

- A society user can see aggregate society information.

- A vet can access only explicitly shared pet records.

PostgreSQL Row-Level Security can restrict which rows a database role may select or modify and provides a default-deny posture when enabled without an applicable policy. Use it as defence in depth, not as a replacement for application authorization.

Device integrity

Consider Play Integrity for high-risk Android actions such as:

- Login from a new device

- Credit adjustment attempts

- Suspicious tracking submissions

- Referral qualification

- High-value booking activity

Play Integrity allows the backend to assess whether requests originate from the genuine app installed through Google Play on a recognized device. It should provide a risk signal—not automatically block every unsupported device.

Secure local storage

Store in SecureStore or platform key storage:

- Refresh token

- Device-session identifier

- Small encryption keys

Do not store there:

- Large pet records

- GPS history

- Media

- Complete booking databases

Media uploads

OWASP recommends allowlisting file types, validating content rather than trusting the filename or HTTP content type, limiting sizes, generating safe filenames, storing files outside executable web roots and applying malware scanning where appropriate.

Required controls:

- Signed uploads

- MIME and magic-byte validation

- Size and duration limits

- Image/video transcoding

- Malware scanning

- Randomized storage keys

- No public buckets for private records

- Expiring download URLs

- Metadata stripping where appropriate

Logging

Never log:

- Refresh/access tokens

- Push tokens

- Gate codes

- Exact health documents

- Full GPS payloads

- Payment data

- Customer access instructions

Log:

- Actor

- Action

- Target entity

- Result

- Timestamp

- City

- Device/session ID

- Correlation ID

- Security reason

Forced updates

Support:

minimum_supported_version

recommended_version

update_mode

Modes:

OPTIONAL

RECOMMENDED

REQUIRED

SECURITY_BLOCK

Do not force an update during an active walk unless the existing app version presents an immediate security or safety risk. Allow completion of the live service, then block further bookings.

17. Location privacy policy

Mandatory rules

- Track only during a sitter-initiated eligible service.

- Stop tracking automatically when the service ends.

- Do not track during off-duty periods.

- Explain foreground and background use before requesting permission.

- Show tracking status visibly to the sitter.

- Give customers access only to their active or historical booking.

- Restrict admin access to authorized operations and safety roles.

- Log every sensitive administrative access.

- Define and enforce route-data retention.

- Delete or de-identify raw points after the retention purpose expires.

- Retain incident-related routes separately under a documented legal or investigation hold.

- Do not send raw routes to general analytics tools.

Android requires developers to accurately declare location-data collection and sharing, and background-location access is treated distinctly from ordinary foreground location.

The DPDP Act requires consent requests to be presented clearly and in plain language, while the notified Rules establish the current implementation framework. Location notices should therefore explain the purpose, duration, recipients, controls and grievance contact in straightforward language.

Recommended data separation

Exact GPS points

→ restricted tracking store

Derived distance/duration

→ ordinary booking report

Service zone and city

→ operational analytics

De-identified aggregate patterns

→ capacity and route analysis

Exact customer coordinates and access codes should not be available to marketing, finance or society roles.

18. User-facing location wording

Short permission explanation

Location during active services
Your location is collected only while you start and perform an active pet-care service. It helps verify arrival, share live service updates, document the service route and provide safety support. Tracking stops when the service ends.

Detailed wording

When you start an eligible pet-care service, the app may collect your location while the app is open and, where required for route continuity, while it runs in the background. The pet parent can view location updates only for their active booking. Authorized operations and safety staff may access the information when needed to manage the service, investigate an incident or provide support.

The app does not track your location outside an active service. Route data is retained only for the period described in our privacy notice and is then deleted or de-identified unless it is required for an open safety, support or legal matter.

Interrupted tracking message for customers

Live location is temporarily unavailable. The service remains in progress, and our operations team has been notified.

Avoid blaming the sitter when the cause may be:

- Network loss

- Permission change

- Device shutdown

- Operating-system restriction

- GPS inaccuracy

19. Final approval matrix

| Proposal | Decision |
| --- | --- |
| Single device_tokens table | Split devices, tokens and sessions |
| Store token timestamp/version | Approve |
| One tracking_events table | Split sessions, points and events |
| Raw latitude/longitude columns | Use PostGIS geography where available |
| One request per GPS point | Replace with batch ingestion |
| Matching score and reasons | Approve with algorithm versioning |
| accepted_by_admin Boolean | Replace with decision record |
| Mutable wallet balance | Reject as source of truth |
| Immutable credit ledger | Mandatory |
| User-funded cash wallet | Defer pending payment review |
| Favourite sitter table | Approve with preference status |
| Single health-event table | Split events, documents, reminders and access grants |
| Mobile feedback table | Approve with diagnostic metadata and redaction |
| Rotating refresh tokens | Mandatory |
| Public push-send endpoint | Reject |
| Object-level authorization | Mandatory on every ID endpoint |
| Media validation | Mandatory |
| Admin MFA | Mandatory for privileged roles |
| Tracking only during service | Mandatory |
| Customer access to another booking’s tracking | Reject |
| Unlimited location retention | Reject |
| Forced update capability | Approve with active-service safeguards |

Phase 11 technical win condition

Every mobile action is attributable to a device and session, every service has a defensible event history, every credit change is auditable, every record is role-scoped and location is collected only for a clearly defined active-service purpose.

Phase 11 database, API, security and privacy architecture: GO—with the corrected normalized schemas, immutable ledgers, rotating sessions and purpose-limited tracking model above

Phase 11 Six-Month Execution Plan 📱🐾

Executive verdict

Approve the six-month roadmap, with five structural corrections:

- Prototype background GPS in Month 1, rather than discovering technical limitations in Week 9.

- Build the admin command centre alongside the sitter app, because it must receive and act on sitter events.

- Replace “wallet” with an immutable service-credit ledger. Defer customer-funded cash balances.

- Launch rules-based, explainable matching first; advanced AI comes after sufficient outcome data exists.

- Security, privacy, physical-device QA and app-store preparation must run throughout the programme—not only during Week 23.

The corrected delivery sequence is:

Product and technical validation

↓

Sitter app foundation

↓

Tracking + emergency + admin operations

↓

Customer app

↓

Subscriptions + credits + referrals

↓

Matching assistance + hardening

↓

Controlled store launch

Expo background location and remote push notifications require development builds rather than relying only on Expo Go. Expo also documents that background location stops if the user terminates the application, so this limitation must be tested and represented truthfully in the operational state model from the first month.

Month 1: Product Planning and Architecture

Primary objective

Freeze what Phase 11 will solve, validate the technically risky features and prepare a production-grade delivery system.

Month 1 should not produce only wireframes. It should prove that the hardest mobile workflows are technically viable on real devices.

Week 1: Scope freeze and mobile PRD

Goal

Define the exact Phase 11 boundaries before designers and developers begin building screens.

Required product decisions

Sitter app P0

- Authentication and device registration

- Booking inbox and schedule

- Accept/reject

- Booking and pet instructions

- Arrival and handover

- Start/end service

- Active-service GPS

- Offline execution

- Media uploads

- Report cards

- Emergency escalation

- Earnings

- Push notifications

Customer app P0

- Authentication

- Pet profiles

- Booking and payment

- Active service status

- Report cards

- Reviews

- Subscription management

- Remaining service credits

- Notifications

- Support and account controls

Admin P0

- Live bookings

- Delayed-service queue

- Tracking-health states

- Incident queue

- Missing reports

- Backup assignment

- City and role scoping

Explicit non-goals

Keep these outside the initial release:

- Customer-funded cash wallet

- Fully automatic sitter assignment

- Native society app

- Native groomer/vet/trainer app

- AI veterinary diagnosis

- Continuous sitter tracking

- Complex loyalty tiers

- Full pet-health intelligence

Mobile PRD sections

- Product objectives

- User personas

- Operational problems

- P0/P1/P2 features

- Non-goals

- User journeys

- Booking-state model

- Offline behaviour

- Location and permission rules

- Emergency workflows

- Data-access matrix

- Analytics events

- Success metrics

- Release strategy

- Risks and dependencies

Week 1 output

- Approved mobile PRD

- Prioritised product backlog

- Success-metric baseline

- Non-goal register

- Risk and dependency log

Week 2: UX flows and prototypes

Goal

Design complete operational flows, including failure states—not only ideal screens.

Sitter flows to design

Login

↓

Booking request

↓

Accept/reject

↓

Schedule

↓

Arrival

↓

Handover

↓

Start service

↓

Tracking/media/report

↓

Complete service

↓

Earnings

Also design:

- Location denied

- Notifications denied

- Network unavailable

- App reopened after termination

- Late arrival

- Wrong-location warning

- Emergency incident

- Customer unavailable

- Gate access denied

- Upload failure

- Service ended early

- Duplicate start/end attempt

Customer flows to design

- Signup and login

- Pet creation

- Serviceability check

- Booking

- Payment or credit reservation

- Sitter assignment

- Live service

- Tracking interrupted

- Report and review

- Subscription pause/cancel

- Support

- Account deletion

Admin flows to design

- Unassigned booking

- Late sitter

- Tracking failure

- Backup assignment

- Emergency incident

- Missing report

- Credit restoration

- Assignment override

Deliverables

- Low-fidelity wireframes

- High-fidelity Figma screens

- Interactive prototypes

- Permission education screens

- Empty/loading/error states

- Accessibility annotations

- Design tokens

- Shared component inventory

Week 3: API readiness and backend-gap analysis

Goal

Ensure the backend can support authoritative, offline-safe mobile workflows.

API audit

Review whether existing APIs support:

- Versioning

- Mobile device sessions

- Refresh-token rotation

- Device and push-token registration

- Booking status transitions

- Idempotent start/end actions

- Batch GPS uploads

- Signed media uploads

- Offline event reconciliation

- Service-credit reservation

- Emergency incidents

- Role and booking-level authorization

- Feature flags

- Audit logs

State-machine review

The booking lifecycle should be explicit:

REQUESTED

ACCEPTED

CONFIRMED

EN_ROUTE

ARRIVED

HANDOVER_CONFIRMED

IN_PROGRESS

COMPLETION_REQUESTED

COMPLETED

REPORT_SUBMITTED

CANCELLED

INCIDENT_OPEN

The backend must reject invalid transitions. For example:

- A sitter cannot start an unassigned booking.

- A customer cannot view another customer’s route.

- A completed service cannot be started again.

- An expired document cannot be overridden by a high matching score.

Deliverables

- OpenAPI/API contract

- Backend-gap list

- Database migration plan

- Event catalogue

- Authorization matrix

- Offline reconciliation design

- Mock API environment

- Error-code standard

Week 4: Architecture, repositories and CI/CD

Goal

Create production-capable development environments for both apps.

Recommended repository structure

apps/

sitter-mobile/

customer-mobile/

admin-web/

packages/

api-client/

domain-types/

validation/

auth/

analytics/

design-tokens/

localization/

feature-flags/

Environments

Create:

- Local

- Development

- Staging

- Production

Each environment needs separate:

- API configuration

- Firebase/APNs credentials

- Map keys

- Storage buckets

- Analytics projects

- Sentry projects

- Feature flags

- Deep-link schemes

CI/CD requirements

- Type checking

- Linting

- Unit tests

- API-contract checks

- Dependency scanning

- Secret scanning

- Development builds

- Staging builds

- Signed production builds

- Release notes

- Build-number automation

Expo development builds allow native modules and configuration beyond Expo Go, and EAS Build can create signed binaries for Android and iOS. EAS Submit can later submit those binaries to the stores from the command line or CI/CD.

Critical technical prototypes

Before Month 1 ends, prove on physical Android and iOS devices:

- Secure login and refresh

- Push delivery and deep linking

- GPS session with the screen locked

- Tracking interrupted by app termination

- Offline event storage and recovery

- Photo upload retry

- Booking start/end idempotency

- Remote feature disable

- Crash reporting with source maps

- Account/session revocation

Month 1 exit gate

Proceed only when:

| Requirement | Target |
| --- | --- |
| Mobile PRD approved | Yes |
| Core prototypes validated | Yes |
| Background-location limitations understood | Yes |
| API gaps estimated | Yes |
| Development builds working | Android and iOS |
| CI/CD produces installable builds | Yes |
| Security architecture reviewed | Yes |
| Sprint backlog estimated | Yes |

Month 2: Sitter App MVP

Primary objective

Build the core operational app without prematurely adding sophisticated analytics or AI.

Week 5: Sitter authentication and home

Build

- OTP/login

- Device registration

- Secure refresh-token storage

- Biometric unlock option

- Minimum-version check

- Today’s schedule

- Upcoming booking cards

- Push-token registration

- Notification inbox

- Support shortcut

Home-screen priorities

Critical alerts

Next booking

Today’s schedule

Pending report

Earnings summary

Availability warning

Acceptance criteria

- Login survives normal app restarts.

- Revoked sessions stop working.

- Logout removes or detaches push tokens.

- Suspended sitters cannot see new bookings.

- Customer data is not cached beyond operational need.

- App version and build are visible to support.

Week 6: Booking detail and accept/reject

Build

- Booking request list

- Booking details

- Accept/reject

- Structured rejection reasons

- Travel estimate

- Expected payout

- Skill/risk warnings

- Schedule-conflict check

- Society-entry instructions

- Assignment acknowledgement

Privacy rules

Before acceptance, display:

- Approximate locality

- Service type

- Time

- Pet size and broad requirements

- Estimated payout

After assignment, reveal only the customer and address data needed to perform that booking.

Acceptance criteria

- Two sitters cannot accept the same assignment.

- Conflicting schedules are blocked.

- Expired credentials block acceptance.

- Rejections update matching and capacity data.

- Every action creates an auditable event.

Week 7: Arrival and service execution

Build

- En-route status

- Navigation

- Arrival button

- Geofence evidence

- Handover confirmation

- Start service

- Service timer

- End-service request

- Early-end explanation

- Offline start/end queue

Important rule

GPS collection infrastructure should already exist, but Week 7 may initially use a controlled development configuration before the full tracking engine is enabled in Week 9.

Acceptance criteria

- Only the assigned sitter can start the service.

- Duplicate starts are rejected.

- Offline events synchronize idempotently.

- Starting outside the geofence requires a reason.

- The server remains the authoritative state.

- Completion can remain pending review when evidence is incomplete.

Week 8: Report cards and media

Build

- Service-specific report forms

- Photos and short videos

- Local media queue

- Compression

- Signed uploads

- Retry status

- Concern flags

- Customer note

- Report submission

- Missing-report reminder

Media controls

- Allowlisted file types

- Size and duration limits

- MIME and file-content validation

- Randomized storage names

- Private storage

- Expiring access links

- Malware scanning where appropriate

- Metadata stripping where needed

Month 2 deliverables

- Sitter authentication

- Home and daily schedule

- Accept/reject

- Booking detail

- Arrival and handover

- Start/end service

- Offline event queue

- Report cards

- Media uploads

- Initial push notifications

Month 2 exit gate

| Requirement | Target |
| --- | --- |
| Core sitter flow works end-to-end | Yes |
| Internal testers | 5–10 |
| Duplicate service events | Zero |
| Failed offline events recover | 99% target |
| Media retry works | Yes |
| Unauthorized booking access | Zero |
| Critical crashes | Zero open |

Month 3: Tracking, Safety and Sitter Reliability

Primary objective

Turn the MVP into a field-operating system and connect it to the admin command centre.

Week 9: Production GPS tracking

Build

- Explicit location-permission education

- Foreground and background permission flow

- Tracking-session API

- Adaptive point collection

- Batch GPS synchronization

- Route quality

- Tracking interruption detection

- Customer live-status API

- Admin live map

- Route replay

- Retention and deletion jobs

Android background location requires platform-specific permissions, and Android 11+ generally routes “Allow all the time” access through system settings. Android 13+ also introduced runtime notification permission, which matters for visible foreground-service notifications.

Test scenarios

- Screen locked

- App backgrounded

- App force-closed

- GPS disabled

- Permission revoked

- Device offline

- Device reboot

- Low battery

- Poor GPS accuracy

- Duplicate point upload

- Service ends without network

Acceptance criteria

- Tracking occurs only during eligible active services.

- The app visibly indicates tracking state.

- Tracking stops after service completion.

- App termination creates an interrupted state, not a false continuous route.

- Customer sees only their booking.

- Admin access is role-scoped and audited.

Week 10: Emergency Help and incident escalation

Build

- Persistent Emergency Help button

- Incident categories

- Immediate backend incident creation

- Last-known location attachment

- Admin critical queue

- Direct phone action

- Customer contact

- Verified vet directory

- SMS/WhatsApp fallback where configured

- Acknowledgement timers

- Evidence capture

- Booking lock during critical incident

Required drills

Run tabletop and live simulations for:

- Pet escape

- Pet injury

- Bite

- Sitter injury

- Customer unavailable

- Gate denial

- Tracking interruption during an incident

- Device offline

Acceptance criteria

- Critical incident reaches operations within the defined SLA.

- Push is not the only escalation mechanism.

- Emergency contact information is available offline where appropriate.

- The sitter can access immediate instructions before completing a long form.

- Incidents cannot be deleted or silently downgraded.

Week 11: Earnings and payout transparency

Build

- Estimated earnings

- Pending-validation earnings

- Approved earnings

- Adjustments

- Payout batches

- Settlement status

- Downloadable statement

- Dispute action

Required payout states

ESTIMATED

PENDING_COMPLETION

PENDING_VALIDATION

APPROVED

PROCESSING

PAID

ADJUSTED

DISPUTED

Acceptance criteria

- Earnings derive from server-side pricing snapshots.

- Every adjustment has a reason and audit history.

- Sitter payout status matches finance records.

- The mobile app cannot alter earnings locally.

Week 12: Availability, training and reliability

Build

- Weekly availability

- Temporary unavailability

- Leave calendar

- Service zones

- Maximum daily assignments

- Training-module access

- Document-expiry status

- Transparent reliability breakdown

- Appeal/dispute option

Parallel admin modules

By the end of Month 3, the admin command centre should already have:

- Active services

- Unassigned bookings

- Late starts

- Tracking failures

- Open incidents

- Missing reports

- Backup actions

- Payout-review queue

- Sitter adoption and app versions

Month 3 exit gate

| Metric | Pilot target |
| --- | --- |
| Active sitter testers | 20–50 |
| Digital check-in/out | 98%+ |
| Report completion | 95%+ |
| Eligible tracking started | 95%+ |
| Offline recovery | 99%+ |
| No tracking outside service | 100% |
| Crash-free sessions | 99%+ target |
| Critical alerts acknowledged | Within defined SLA |
| Sitter adoption | 85%+ among pilot group |

Month 4: Customer App MVP

Primary objective

Give repeat customers native booking, live visibility and service-management tools.

Week 13: Customer authentication and home

Build

- Login/signup

- Device sessions

- Push registration

- Pet selector

- Next booking

- Active booking

- Remaining-credit summary

- Renewal reminder

- Support

- Notification inbox

- Privacy and account controls

- Account deletion initiation

Apple requires apps that offer account creation to allow users to initiate account deletion within the app. Google Play also requires deletion of account-associated data when a valid account-deletion request is completed, subject to clearly disclosed legitimate retention requirements.

Week 14: Pet profiles

Build

- Basic pet data

- Photos

- Behaviour notes

- Care instructions

- Feeding

- Emergency contacts

- Vaccination documents

- Service restrictions

- Risk-information review

- Owner-controlled editing

Access controls

- Customer: full profile

- Assigned sitter: necessary booking instructions

- Vet: explicitly shared records only

- Society: no pet-health access

- Marketing: no access

Week 15: Booking and payment

Build

- City and service-zone resolution

- Service catalogue

- Pet eligibility

- Availability

- Price quotation

- Payment checkout

- Service-credit reservation

- Preferred-sitter request

- Booking confirmation

- Cancellation and rescheduling

Backend transaction

Validate serviceability

↓

Check capacity

↓

Resolve published price

↓

Reserve credit or verify payment

↓

Create booking

↓

Confirm transaction

No customer-supplied amount should be trusted by the server.

Week 16: Active booking, reports and reviews

Build

- Assignment status

- En-route status

- Active-service timeline

- Live route where eligible

- Tracking-interrupted state

- Report-card history

- Media

- Review flow

- Safety-support entry

- Rebook action

Month 4 deliverables

- Customer authentication

- Home dashboard

- Pet profiles

- Booking and payment

- Active service

- Route/status visibility

- Report history

- Reviews

- Support

- Account/privacy controls

Month 4 exit gate

| Requirement | Target |
| --- | --- |
| Invited users | 100–500 repeat customers |
| Booking success | Above stable PWA baseline |
| Payment reconciliation | 100% |
| Cross-customer data exposure | Zero |
| Live-state accuracy | 98%+ |
| Report visibility | 100% after successful submission |
| Account deletion workflow | Tested |
| Critical crashes | Zero open |

Month 5: Subscriptions, Credits and Referrals

Primary objective

Enable customer self-service and retention without creating an unregulated or opaque wallet product.

Week 17: Subscription dashboard

Build

- Current plan

- Credits included

- Available and reserved credits

- Renewal date

- Payment method

- Pause

- Upgrade

- Downgrade

- Cancel renewal

- Failed-payment recovery

- Plan history

Rules

- Downgrades take effect in the next cycle unless otherwise disclosed.

- Pauses must be transparent.

- Cancellation must remain easy to find.

- Credits and expiry must be visible.

- Preferred sitter must not be presented as guaranteed unless operationally guaranteed.

Week 18: Service credits

Build

Use separate balances for:

- Subscription credits

- Referral credits

- Promotional credits

- Society benefits

- Service-recovery credits

Do not build a mutable cash-wallet balance.

Ledger operations

GRANT

RESERVE

CONSUME

RELEASE

RESTORE

EXPIRE

REVERSE

Every operation needs:

- Idempotency

- Source reference

- Reason

- Expiry

- Actor

- Audit history

Week 19: Referral programme

Build

Referral shared

↓

Friend registers

↓

Friend completes eligible paid service

↓

Refund/review window passes

↓

Friend and referrer credits granted

Required controls

- Verified new user

- Minimum eligible spend

- Completed service

- No full refund

- Duplicate-device and identity review

- Reward reversal

- Visible expiry and service restrictions

Week 20: Preferred sitter and retention tools

Rename “Favourite sitter” to Preferred sitter.

Build

- Preferred sitter per pet

- Do-not-match preference

- Previous relationship history

- Preferred-sitter availability

- Approved backup

- Same-sitter request after a successful service

- Clear availability disclaimer

Store-preparation work begins no later than Month 5

Prepare:

- Apple privacy disclosures

- Google Play Data Safety form

- Privacy policy

- Location-use descriptions

- Account-deletion support

- App icons and screenshots

- Support website

- Review credentials

- Store descriptions

- Permission explanations

Apple requires developers to declare data collected by their app and integrated third-party SDKs in App Store privacy details. Google Play also requires Data Safety disclosures.

Month 5 exit gate

| Requirement | Target |
| --- | --- |
| Subscription self-service | 70%+ of beta actions |
| Credit-ledger mismatches | Zero |
| Duplicate referral rewards | Zero |
| Refund-credit choice transparent | Yes |
| Preferred-sitter wording accurate | Yes |
| Store privacy declarations drafted | Yes |
| Data-retention policy implemented | Yes |

Month 6: Matching Assistance, Command Centre and Launch

Primary objective

Add operational intelligence, harden the platform and perform a staged release.

Week 21: Matching assistant and booking-risk rules

Matching assistant

Start with:

Hard eligibility filters

↓

Explainable weighted ranking

↓

Top three recommendations

↓

Admin approval

Output:

Riya — 92/100 · Excellent match

• Seven successful services with Bruno

• 1.2 km away

• Qualified for large dogs

• Available at 7:00 AM

• 98% on-time rate

• Society access approved

Do not use “92% probability” unless the score is genuinely calibrated.

Booking-risk score

Classify:

- Low

- Medium

- High

- Critical

- Blocked

Hard blockers include:

- Unverified payment

- Expired sitter credentials

- No service capacity

- Sitter suspension

- Unsupported service zone

High-risk bookings require admin action; critical bookings require senior approval.

Week 22: Advanced command centre

The basic command centre already exists from Month 3. Week 22 adds higher-level intelligence:

- City health score

- Booking-risk queue

- Sitter quality-review queue

- Subscription churn signals

- Incident heatmap

- Revenue by city/service

- Capacity forecasting

- Support SLA dashboard

- Mobile adoption

- App-version distribution

- Crash and tracking health

Every alert must contain:

- Why it fired

- Severity

- Assigned owner

- Response deadline

- Recommended action

- Acknowledge/resolve controls

- Audit history

Week 23: QA, security and performance hardening

Security testing must have occurred during every sprint, but Week 23 is the final integrated verification cycle.

OWASP MASVS is a recognised mobile security verification baseline and can be paired with the MASTG test catalogue for systematic testing.

Functional QA

- Sitter workflows

- Customer workflows

- Admin workflows

- Payment and credits

- Push deep links

- Offline transitions

- Tracking interruptions

- Emergency incidents

- Subscription lifecycle

- Account deletion

Device matrix

Test:

- Older supported Android

- Current Android

- Multiple OEMs

- Older supported iPhone

- Current iPhone

- Small and large screens

- Slow network

- No network

- Low battery

- Location denied

- Notification denied

Security

- Authentication and token rotation

- Object-level authorization

- Secure storage

- Root/jailbreak risk signals where appropriate

- File-upload validation

- Secret leakage

- Sensitive log review

- Deep-link validation

- API abuse/rate limiting

- Admin MFA

- Cross-city isolation

- Credit and referral fraud

- Location-data retention

Performance

- Cold start

- Booking list load

- Map rendering

- Media compression

- Upload recovery

- GPS battery usage

- Background execution

- Memory use

- Crash-free sessions

- API latency

Release-blocking defects

- Unauthorized data access

- Incorrect payment or credit consumption

- Tracking outside a service

- Unrecoverable offline data

- Missing critical emergency event

- Duplicate completion

- Crash during active service

- Broken account deletion

- Inaccurate privacy declaration

Week 24: Controlled app launch

Do not treat Week 24 as an immediate public rollout to every city and customer.

Stage 1: Internal alpha

- Employees

- Operations team

- Simulated services

- Production-like environment

Stage 2: Sitter closed beta

- 20–50 trusted sitters

- One or two cities

- Selected service zones

Stage 3: Customer closed beta

- Existing repeat customers

- Subscribers

- Society pilot users

- PWA remains available

Stage 4: Controlled production

- City feature flags

- Percentage rollout

- Real-time monitoring

- Rollback plan

- Minimum app version

- Support coverage

TestFlight supports pre-publication iOS beta distribution and tester feedback. Google Play similarly provides internal and closed testing tracks through Play Console. EAS Build and EAS Submit can automate production builds and store submission, but store metadata, privacy declarations and reviewer access still need to be prepared correctly.

Launch-day command centre

Monitor:

- Login failures

- Crash-free users

- Push delivery

- Booking completion

- GPS-session health

- Offline-sync failures

- Payment mismatches

- Credit mismatches

- Emergency events

- Support volume

- Store reviews

- Version adoption

Recommended Cross-Functional Team

| Role | Core responsibility |
| --- | --- |
| Product lead | Scope, outcomes and priorities |
| Mobile technical lead | App architecture |
| React Native engineers | Sitter and customer apps |
| Backend engineers | APIs, events and data |
| Product designer | Mobile and admin UX |
| QA automation engineer | Functional/device testing |
| DevOps/release owner | CI/CD and store builds |
| Security/privacy reviewer | Threat model and compliance |
| Operations representative | Real-world workflow validation |
| Sitter/customer pilot lead | Recruitment and feedback |

A minimum viable team may combine roles, but the operations representative and security reviewer must not be omitted.

Final Monthly Deliverables

| Month | Required outcome |
| --- | --- |
| Month 1 | Validated architecture and technical prototypes |
| Month 2 | Complete sitter-app operational MVP |
| Month 3 | Field-tested tracking, emergency and admin operations |
| Month 4 | Customer-app MVP for repeat users |
| Month 5 | Subscription self-service, credits and referrals |
| Month 6 | Explainable matching, hardened command centre and controlled release |

Final Approval Matrix

| Proposed item | Decision |
| --- | --- |
| Month 1 planning and architecture | Approve |
| GPS work beginning only in Week 9 | Modify—prototype in Month 1 |
| Sitter MVP in Month 2 | Approve |
| Tracking/emergency in Month 3 | Approve for production implementation |
| Customer MVP in Month 4 | Approve |
| Wallet in Month 5 | Replace with service credits |
| Referral programme | Approve with qualification and reversal rules |
| Favourite sitter | Rename preferred sitter |
| AI matching in Week 21 | Approve as explainable recommendation, not automation |
| Admin command centre only in Week 22 | Modify—basic version from Month 2–3 |
| Security review only in Week 23 | Reject—continuous security plus final audit |
| App-store preparation only in Week 23 | Start by Month 4–5 |
| Soft launch in Week 24 | Approve as a staged controlled release |
| Immediate forced migration from PWA | Reject |

Phase 11 six-month win condition

The sitter app reliably captures and proves service execution, the command centre surfaces failures before they affect customers, and the customer app increases self-service and retention—without introducing unsafe tracking, credit errors or uncontrolled operational complexity.

Final Phase 11 execution decision: GO—with GPS validation moved forward, admin operations developed in parallel, service credits replacing the cash wallet, and staged store release after continuous QA and security verification

Phase 11 App Launch, Store Preparation and City Rollout Strategy 📱🐾

Executive decision

Approve the staged app-launch model. Do not release the sitter and customer apps to every city and user simultaneously.

The recommended rollout is:

Internal alpha

↓

Sitter closed beta

↓

Customer closed beta

↓

Single-city production launch

↓

Selected-cluster expansion

↓

Multi-city rollout

Each stage must have a measurable exit gate. Progress should depend on product reliability, operational performance and safety—not merely the scheduled launch date.

1. End-to-end app launch strategy

Stage 0: Technical pre-alpha

Before team testing, validate the highest-risk capabilities on physical devices:

- Login and refresh-token rotation

- Push-notification delivery

- Deep links

- Start/end service idempotency

- GPS with the screen locked

- App termination during tracking

- Offline report recovery

- Media-upload retry

- Emergency alert delivery

- Remote logout

- Forced-update controls

This stage uses development and staging environments, not real customer bookings.

Exit gate

| Requirement | Target |
| --- | --- |
| Critical user flows technically complete | Yes |
| Duplicate start/end events | Zero |
| Offline event recovery | Working |
| Tracking outside active service | Zero |
| Critical security defects | Zero open |
| Emergency alert reaches admin | Within test SLA |

Stage 1: Internal alpha

Users

- Product team

- Developers

- QA

- Operations

- Support

- Selected city managers

Recommended scale

Approximately 10–30 internal testers is sufficient operationally, although the testing platforms allow larger groups. TestFlight supports up to 100 internal App Store Connect testers, while Google Play internal testing also supports up to 100 selected testers.

Goal

Find:

- Crashes

- Broken permissions

- Invalid booking transitions

- Incorrect role access

- Payment and credit errors

- Poor offline behaviour

- Notification failures

- Confusing emergency flows

- Accessibility problems

Test scenarios

Normal booking

Network unavailable

Location denied

Notification denied

App force-closed

Device restarted

Low battery

GPS inaccurate

Media upload interrupted

Customer cancels during service

Sitter opens emergency flow

Admin assigns backup

Exit gate

| Metric | Target |
| --- | --- |
| Crash-free sessions | 99%+ |
| Login success | 98%+ |
| Core booking-flow success | 98%+ |
| Critical data exposure | Zero |
| Credit/payment mismatches | Zero |
| P0 defects | Zero open |
| P1 defects | Corrective plan approved |

Stage 2: Sitter closed beta

Users

20–50 carefully selected sitters across one or two service clusters.

Choose sitters who:

- Already perform services reliably

- Use a variety of Android and iOS devices

- Work in different network conditions

- Are willing to provide structured feedback

- Understand that the product is still in beta

Goal

Validate field execution:

- Booking acknowledgement

- Arrival

- Start/end service

- GPS continuity

- Offline reporting

- Media upload

- Emergency escalation

- Earnings accuracy

- Battery performance

- Support workload

Rollout sequence

5–10 trusted sitters

↓

20 sitters

↓

50 sitters

↓

Second cluster

Do not enrol all sitters immediately. A defect in tracking, earnings or booking state can affect real pet-care operations.

Required metrics

| Metric | Exit target |
| --- | --- |
| Weekly sitter adoption | 85%+ |
| Booking acknowledgement | 95%+ |
| Digital check-in/out | 98%+ |
| Report submission | 95%+ |
| Eligible GPS session success | 95%+ |
| Offline sync recovery | 99%+ |
| Provider no-show | Below 1% |
| Critical alerts acknowledged | Within defined SLA |
| Tracking outside service | Zero |
| Earnings mismatches | Zero unresolved |

Apple TestFlight supports external beta testing and allows up to 10,000 external testers, while Google Play closed testing allows controlled tester groups before production.

Stage 3: Customer closed beta

Users

100–500 customers selected from:

- Repeat users

- Active subscribers

- Society pilot residents

- Customers who regularly read report cards

- Customers comfortable providing feedback

Do not begin with newly acquired or high-risk customers. Loyal customers understand the existing service and can distinguish product issues from normal service behaviour.

Goal

Validate:

- Signup and login

- Pet-profile management

- Booking conversion

- Payment and service-credit use

- Live service visibility

- Report-card experience

- Reviews

- Subscription self-service

- Support

- Account and privacy controls

Beta principle

The app remains optional. Customers must still be able to use:

- PWA/web

- WhatsApp operational updates

- Phone support

- Existing payment fallbacks

Do not force migration during beta.

Exit metrics

| Metric | Target |
| --- | --- |
| Invited-user activation | 40–60%+ |
| Booking technical success | 98%+ |
| Payment reconciliation | 100% |
| Live-status accuracy | 98%+ |
| Report availability | 100% after submission |
| Subscription self-service | 70%+ |
| Crash-free sessions | 99%+ |
| Cross-customer data exposure | Zero |
| Support contacts per booking | Stable or decreasing |
| Beta rating | 4.5+ |

For new personal Google Play developer accounts, Google currently documents a production-access requirement involving a closed test with at least 12 opted-in testers maintained for 14 continuous days. Confirm whether the specific developer account falls under that requirement before setting the launch date.

Stage 4: Single-city production launch

Recommended launch city

Select the city with:

- The strongest city operations team

- Stable sitter-app adoption

- 4.6+ service rating

- Strong support coverage

- Working subscription operations

- Manageable cluster geography

- Reliable incident escalation

Launch only in configured service clusters—not automatically across the entire city.

Rollout controls

- City-level feature flag

- Customer eligibility flag

- Percentage-based invitation cohorts

- Supported app-version policy

- Tracking kill switch

- Mobile-booking kill switch

- Credit-system kill switch

- Matching-assistant kill switch

- PWA fallback

- Rollback procedure

First production cohorts

10% of eligible repeat users

↓

25%

↓

50%

↓

100% of eligible users in launch clusters

Google Play’s staged rollout feature applies to updates rather than an app’s first production publication. For the initial release, use closed testing, controlled country availability, invitations and backend feature flags. Later updates can be released to percentages of production users.

Apple allows manual release after approval, which gives the team control over the exact production-launch moment.

Stage 5: Multi-city rollout

A second city should not receive the app merely because the first city’s store reviews are positive.

Each city must pass:

| Requirement | Target |
| --- | --- |
| Sitter-app adoption | 85%+ |
| Digital check-in/out | 98%+ |
| Report completion | 95%+ |
| Customer rating | 4.6+ |
| Local support coverage | Working |
| Emergency directory | Verified |
| City admin dashboard | Active |
| GPS support | Operational |
| Subscription capacity | Stable |
| PWA fallback | Active |
| Critical unresolved incidents | Zero |

Roll out cluster by cluster:

City 1 production

↓

City 1 stable for 2–4 weeks

↓

City 2 strongest cluster

↓

City 2 remaining validated clusters

↓

City 3

2. App-store preparation

Corrected asset checklist

| Asset or configuration | Status | Explanation |
| --- | --- | --- |
| App icon | Required | Store and device identity |
| Splash/launch screen | Product requirement | Not a store-listing asset, but needed for polished startup UX |
| Screenshots | Required | Show real application functionality |
| App description | Required | Accurate product explanation |
| Short description | Required on Google Play | Concise store summary |
| Feature graphic | Required/relevant on Google Play | Store promotional asset |
| Privacy policy | Required | Must match actual data practices |
| Terms of Service | Operationally required | Service, booking, tracking and credit terms |
| Support contact | Required | Apple support URL; Google contact email |
| Demo/reviewer account | Conditional but usually needed | Required when reviewers cannot access the app normally |
| Age rating | Required | Store content classification |
| Permission explanations | Required for sensitive permissions | In-app and store disclosures |
| Apple privacy details | Required | Declared data collection and use |
| Google Data Safety form | Required outside internal-only testing | Declared collection, sharing and protection |
| Account-deletion flow | Required for apps with account creation | In-app and applicable web controls |
| Background-location declaration | Required on Google Play when used | Includes disclosure and review materials |
| Reviewer notes | Strongly required | Explain test scenarios and background tracking |
| Export-compliance answers | Conditional | Apple encryption-related submission questions |

Apple requires a privacy-policy URL, description, support URL and age rating as part of its app information. It also requires app screenshots for the product page, while a preview video is optional.

Google Play requires a contact email and uses assets such as the icon, screenshots, feature graphic and descriptions in the store listing.

App icon

Prepare separate icons for:

Customer app

- Friendly pet-parent identity

- Clear brand mark

- Simple silhouette

- Legible at small size

Sitter app

You may use the same national brand with a controlled visual distinction, such as:

- Sitter submark

- Different internal accent

- Small “Pro” or caregiver identifier

Avoid creating two unrelated brands.

Apple’s icon is packaged with the application build and appears across the Home Screen, search, settings, notifications and TestFlight.

Splash/launch screen

The splash screen is not a separate store-listing requirement, but it remains important product work.

It should:

- Load quickly

- Use a simple brand mark

- Avoid advertising

- Avoid fake progress bars

- Transition smoothly

- Respect light/dark appearance if supported

Do not make the user wait for animation before accessing an urgent active-service screen.

Store screenshots

Create screenshots around benefits, not generic menus.

Customer app screenshot sequence

- Book verified local pet care

- Track an active walk

- Receive detailed report cards

- Manage walking subscriptions

- Keep every pet profile organised

- Access support when needed

Sitter app screenshot sequence

- Manage today’s bookings

- Start and document a service

- Submit professional care reports

- Access emergency support

- Track earnings transparently

- Manage availability

Do not use fake screens or functionality unavailable in the submitted build. Google’s store-listing guidance requires descriptions and assets to represent the app accurately and avoid misleading claims.

Description and claims

Customer app positioning

Book verified local pet-care services, follow active service updates, receive care reports and manage your recurring pet-care plans.

Sitter app positioning

Manage assigned pet-care bookings, document services, submit care reports, access safety support and track approved earnings.

Avoid claims such as:

- 100% safe

- Guaranteed sitter

- Always accurate GPS

- Instant veterinary emergency response

- Best pet-care app

- Government-approved sitters

Claims should correspond to measurable, available functionality.

Privacy policy

The policy must explain:

- Account information

- Pet-profile information

- Addresses and society-access details

- Location collection

- Media uploads

- Booking and payment data

- Health-document storage

- Push notifications

- Analytics and crash reporting

- Data sharing with assigned providers

- Retention periods

- Customer rights and deletion

- Security and grievance contact

Apple requires privacy details that account for data collected by the app and integrated third-party SDKs. Google similarly requires the Data Safety form for apps on closed, open and production tracks.

Terms and service policies

Include:

- Booking confirmation

- Provider assignment

- Preferred-sitter limitations

- Cancellations

- Refunds

- Subscription credits

- Expiry and rollover

- GPS limitations

- Media consent

- Emergency-coordination limitations

- Veterinary boundaries

- Pet-parent responsibilities

- Sitter responsibilities

- Incident handling

- Account suspension

- Governing law and dispute process

Apple supplies a standard EULA unless the developer provides a custom agreement, but this does not replace your marketplace-specific booking and service terms.

Demo accounts and review instructions

When the app requires authentication, provide:

- Customer demo account

- Sitter demo account

- Admin-assisted test booking

- Test pet profile

- Test subscription or credits

- Instructions to start a simulated walk

- Explanation of background location

- Test emergency flow

- Review contact

Apple states that review demo-account credentials should remain valid and not expire. Google Play provides a section for special app-access instructions for reviewers.

Do not provide reviewers with access to real customer or sitter records.

3. Permission strategy

Main principle

Request a permission at the moment the user activates the related feature—not during first launch.

Android recommends associating runtime permission requests with the specific user action requiring them. Google Play also restricts sensitive permissions to current, disclosed and genuinely necessary features.

Location

Sitter-app use

Location is required for:

- Arrival confirmation

- Active-walk tracking

- Route proof

- Safety support

- Customer active-service updates

Rules

- Request when the sitter prepares for the first tracked service

- Track only between service start and end

- Show an active tracking indicator

- Stop automatically after completion

- Store routes for a documented period

- Do not use routes for marketing

- Do not track general sitter availability

- Allow operations access only when required

Google Play requires background location to be core to the app, visibly disclosed in-app, documented in the privacy policy and supported by a permissions declaration and demonstration for review.

Recommended sitter disclosure

Location during active services
The app uses your location only while you perform an eligible pet-care service. This verifies arrival, provides service-route updates and supports safety assistance. Tracking stops when the service is completed.

Customer-app location

The customer app usually does not require continuous location permission.

Use:

- Address entry

- Map pin

- Optional one-time current-location selection

Do not request persistent customer location merely to make booking slightly faster.

Camera

Use for:

- Pet photos

- Service-proof images

- Report cards

- Incident evidence

- Health-document capture

Recommended disclosure

Camera access lets you capture pet-care updates, service reports and documents when you choose.

Request permission only when the user taps:

- Take photo

- Record update

- Scan document

Photo library

Use for:

- Uploading existing pet photos

- Selecting vaccination records

- Adding service-proof media

- Uploading profile images

Prefer a system media picker and limited selection rather than asking for unrestricted library access where platform capabilities permit it.

Disclosure

Photo access lets you select specific pet photos and care documents to upload.

Notifications

Operational notifications include:

- Booking request

- Assignment

- Sitter en route

- Service started

- Report available

- Payment failed

- Renewal due

- Emergency update

Ask after explaining the value:

Enable notifications for booking assignments, service updates, reports and urgent support messages.

Separate:

- Operational notifications

- Subscription reminders

- Product announcements

- Promotions

A user who disables marketing should still be able to receive necessary service communications through permitted channels.

Microphone and video

Keep these optional.

Use for:

- Short pet-care video update

- Incident evidence

- Optional sitter introduction

Do not request microphone access for ordinary photo capture.

Disclosure

Microphone access is used only when you record a video or audio update.

Request the permission only after the user explicitly starts recording.

4. City-specific Phase 11 strategy

National product rule

Do not build six separate applications.

Use:

One customer app

One sitter app

One backend

One design system

↓

City-specific configuration

Localise:

- Services

- Prices

- Languages

- Landing content

- Plans

- Support channels

- Operational radii

- Society benefits

- App feature flags

Google Play supports custom store listings with different names, descriptions and graphic assets for selected audiences, while Apple supports localised app information. Use these carefully for regional language or segment campaigns rather than producing separate apps.

Bengaluru

Product focus

- Reliable sitter execution

- Polished customer experience

- Real-time walk visibility

- Walking subscriptions

- Explainable matching

- Corporate benefit tools later

Operational features

- Tight schedule-conflict detection

- Peak-window capacity

- Travel-time-aware matching

- Preferred and backup sitter system

- Strong push-notification flows

- Fast self-service subscription management

Bengaluru recorded a 74.4% congestion level in TomTom’s 2025 data, supporting smaller operational zones and travel-time-aware scheduling rather than broad city-radius matching.

Release approach

- Sitter beta: Whitefield/Brookefield cluster

- Customer beta: subscribers and repeat users

- Expand to HSR as a separate capacity zone

- Corporate features only after consumer operations remain stable

Main risk

A visually polished application can increase bookings faster than the provider network can fulfil them.

Pune

Product focus

- Monthly walking-plan management

- Recurring sitter scheduling

- Leave and backup management

- Society resident benefits

- Transparent value and credit use

Sitter-specific tools

- Student/part-time availability

- Exam and leave calendar

- Restricted maximum schedules

- Morning/evening commitment tracking

- Backup assignment

- Provider-earnings transparency

Pune’s 2025 congestion level was reported at 71.1%, with an average 10 km journey exceeding 33 minutes. The product should therefore treat Baner–Balewadi, Wakad, Kharadi and other clusters as distinct capacity zones where necessary.

Main risk

Presenting a city-wide schedule while sitters are actually concentrated in only a few apartment clusters.

Mumbai

Product focus

- Hyperlocal matching

- Travel-time and radius warnings

- Late-arrival prediction

- Same-locality caregiver preference

- Building and gate instructions

- At-home grooming workflows

Essential controls

- Peak-time operational radius

- Maximum travel-time filter

- Building-access records

- Automatic impossible-schedule detection

- Local backup pools

- Stale-location warnings

Mumbai recorded a 63.2% average congestion level in 2025, with a 10 km trip averaging nearly 29 minutes. Matching should therefore use route time and cluster boundaries—not only straight-line distance.

Main risk

A sitter who appears geographically close may still be operationally unavailable because of traffic, building entry and route direction.

Gurugram

Product focus

- Verification evidence

- Society gate list

- Emergency Help

- Premium support

- Grooming/training packages

- Society subscription features

Safety badge design

Show exact verification facts:

- Identity checked

- Documents reviewed

- Practical assessment completed

- Society access approved

- Background check type and date

Do not show:

- 100% safe

- Government guaranteed

- Permanently verified

Society features

- Time-limited gate entries

- Approved sitter roster

- Resident benefits

- Monthly aggregate report

- Event registrations

- Gate-incident escalation

Main risk

Decorative badges that imply a stronger safety guarantee than the underlying verification process supports.

Ahmedabad

Product focus

- App and WhatsApp hybrid

- Assisted first booking

- Simple 8/12-walk plans

- Society events

- Family-oriented reports

- Hindi and Gujarati support based on measured demand

Product configuration

- Prominent call/WhatsApp support

- Manual-payment-link fallback

- Fewer onboarding steps

- Large, clear booking actions

- Simple credit explanation

- Human-supported subscription setup

- Local-language notification templates

Ahmedabad’s 2025 congestion level was 49%, lower than Bengaluru, Pune and Mumbai but still operationally meaningful, with an average 10 km journey of approximately 29 minutes. Cluster-based scheduling remains necessary.

Main risk

Building an entirely self-service experience before local customers and providers consistently use it.

Surat

Product focus

- Simple booking

- Family-care updates

- Pet-sitting and boarding report cards

- Society event registration

- Assisted support

- Reliable offline sitter workflows

Product strategy

- One dominant home-screen action

- Starter plans rather than complex subscriptions

- Strong report cards and photos

- Human-supported first booking

- Society/referral onboarding

- Gujarati/Hindi communication where validated

- Controlled boarding workflows

Treat assumptions about slower app-first adoption as hypotheses. Validate them through:

- Assisted versus self-service conversion

- WhatsApp-to-app activation

- Repeat booking behaviour

- Language selection

- Support contacts per booking

- Subscription conversion

Main risk

Overbuilding native functionality before sufficient repeat demand exists.

5. What goes wrong in app phases

Mistake 1: Building apps before product-market and operational fit

Wrong

Low repeat usage

Unstable city operations

Few subscriptions

↓

Large mobile investment

Correct

Build mobile products after recurring workflows exist and native capabilities solve measurable friction.

Gate

- Repeat rate above 35%

- Stable admin operations

- Active provider network

- Subscription lifecycle working

- App-specific operational need documented

Mistake 2: Customer app before sitter execution

Wrong

Customers book through a polished interface, while sitters still:

- Receive assignments through WhatsApp

- Submit reports manually

- Miss schedule changes

- Lack safety escalation

- Have unclear earnings

Correct

Sitter app

↓

Operational command centre

↓

Customer app

Customer trust comes from field performance, not animation quality.

Mistake 3: Fully automated AI assignment

Wrong

The model assigns high-risk pets without human review.

Correct

Hard eligibility rules

↓

Top-three recommendation

↓

Reasons and warnings

↓

Admin approval

Keep senior approval for:

- High-risk pets

- Medication

- First boarding

- Previous incidents

- Multiple large pets

- Unusual property access

Mistake 4: Tracking without privacy boundaries

Wrong

The sitter is tracked:

- Before the service

- Between bookings

- During breaks

- After the service

- Without visible status

Correct

Track only during an explicitly started eligible service, disclose the purpose, limit access and enforce retention.

Google Play requires sensitive permissions to be necessary for disclosed current features and requested in context.

Mistake 5: Building every advanced product simultaneously

Wrong scope

Two apps

AI auto-matching

Cash wallet

Insurance

E-commerce

Corporate benefits

Social feed

Pet health diagnosis

Correct scope

Sitter execution

↓

Admin operations

↓

Customer booking and subscriptions

↓

Service credits and referrals

↓

Matching assistance

↓

Health timeline

↓

Advanced B2B features

Mistake 6: Treating store approval as a final-week task

Background location, privacy disclosures, demo accounts, screenshots and reviewer instructions need preparation before submission.

Google Play’s background-location review can require:

- Permission declaration

- Prominent disclosure

- Privacy policy

- Video demonstration

- A store listing that visibly describes the core location feature.

Mistake 7: Removing the PWA immediately

The PWA should remain available for:

- Customers who do not install apps

- Unsupported devices

- Booking during store outages

- New customers

- Emergency fallbacks

- Search acquisition

- Society-specific links

The app is an additional high-retention channel—not the only access channel.

6. Final launch scorecard

Sitter app release gate

| Requirement | Target |
| --- | --- |
| Sitter adoption | 85%+ |
| Check-in/out success | 98%+ |
| Report completion | 95%+ |
| GPS-session success | 95%+ |
| Offline recovery | 99%+ |
| Crash-free sessions | 99%+ |
| Tracking outside service | Zero |
| Earnings mismatches | Zero unresolved |
| Critical incident delivery | Within SLA |

Customer app release gate

| Requirement | Target |
| --- | --- |
| Repeat-user activation | 40–60%+ |
| Booking success | 98%+ |
| Payment reconciliation | 100% |
| Live-status accuracy | 98%+ |
| Subscription self-service | 70%+ |
| Cross-user data incidents | Zero |
| Crash-free sessions | 99%+ |
| App rating | 4.5+ after meaningful volume |

Multi-city release gate

| Requirement | Target |
| --- | --- |
| First city stable | Yes |
| City admin ownership | Yes |
| City-specific capacity | Configured |
| Local emergency process | Working |
| Support SLA | Achieved |
| PWA fallback | Active |
| Critical unresolved incidents | Zero |
| City app configuration | Audited |

Final approval matrix

| Proposal | Decision |
| --- | --- |
| Internal alpha | Approve |
| Sitter beta with 20–50 sitters | Approve |
| Customer beta with 100–500 users | Approve |
| Single-city production launch | Approve |
| Immediate multi-city release | Reject |
| App icon | Required |
| Splash screen | Required for product polish, not a store-listing asset |
| Screenshots and descriptions | Required |
| Privacy policy and disclosures | Required |
| Terms | Required for marketplace operations |
| Demo accounts | Required when login blocks review |
| Age rating | Required |
| Permission explanations | Required |
| Location during active sitter service | Approve |
| Continuous sitter location | Reject |
| Camera and library access | Request contextually |
| Microphone access at onboarding | Reject |
| City-specific feature configuration | Approve |
| Separate city apps | Reject |
| Customer app before sitter app | Reject |
| AI auto-assignment | Reject initially |
| Service credits before cash wallet | Approve |
| Keep PWA active | Approve |

Phase 11 launch doctrine

Release to the smallest group that can prove the next level of product reliability, then expand only after the data shows that service quality, privacy and operations remain stable.

Phase 11 launch win condition

Sitters execute most services through the mobile workflow, customers receive reliable live visibility and self-service controls, and each new city can activate the apps without increasing incidents, support burden or operational failure.

Final app-launch decision: GO—with progressive cohorts, city-level feature flags, contextual permissions, complete store disclosures and no forced migration from the web platform.

Phase 11 Final Approval Report

Mobile Apps, Advanced Product, Risks and Phase 12 Readiness 📱🐾

Executive decision

Approve Phase 11 with all five proposed rules.

The official build sequence should be:

Sitter app

↓

Operational command centre

↓

Customer app

↓

Service credits and referrals

↓

Explainable AI matching

↓

Pet health timeline and advanced features

The phase succeeds only when mobile products improve fulfilment, customer retention and operational control. Publishing two apps is not itself a successful outcome.

1. Phase 11 risk register

Corrected risk matrix

| Risk | Impact | Prevention | Stop condition |
| --- | --- | --- | --- |
| Development delays | High | Sitter-first scope, vertical releases, strict P0/P1 separation | Delivery repeatedly misses critical milestones |
| GPS battery drain | High | Adaptive intervals, movement detection, session-only tracking | Material battery complaints or device overheating |
| Location privacy concerns | Very high | Explicit disclosure, active-service-only tracking, limited retention | Any off-service tracking or unauthorised route access |
| Bugs during live bookings | Very high | Closed beta, feature flags, rollback and PWA fallback | Duplicate bookings, incorrect credits or failed emergency flow |
| Low sitter adoption | High | Training, simple UX, device support and gradual enforcement | Adoption remains below 80% after remediation |
| Customer app unused | Medium-high | Target repeat users and subscribers first | App performs worse than PWA without operational benefit |
| Incorrect AI recommendations | High | Hard eligibility filters and admin approval | Unsafe recommendation or systematic false exclusion |
| Credit disputes | High | Immutable ledger, visible expiry and adjustment history | Unreconciled balance or repeated duplicate consumption |
| App-store rejection | Medium-high | Early permission review, disclosures and reviewer accounts | Background location or privacy requirements remain unresolved |
| Offline-sync failure | High | Local outbox, idempotency and conflict resolution | Lost service evidence or duplicate completion |
| Push-notification failure | High | Token hygiene, in-app inbox and SMS/call fallback | Critical workflow depends on push alone |
| Security or data exposure | Very high | OWASP MASVS verification, RBAC and secure storage | Any cross-user or cross-city data exposure |
| Forced-update disruption | Medium | Graceful upgrade policy and active-service protection | Update blocks a live service |
| Mobile demand overload | High | Capacity-gated checkout and city feature flags | App growth reduces completion or punctuality |
| Third-party SDK leakage | High | SDK inventory, data-flow review and privacy declarations | Undeclared collection or sensitive-data leakage |

Risk 1: App development delays

Root causes

- Building sitter and customer apps simultaneously

- Adding AI, loyalty and health features before the core workflow works

- Discovering GPS limitations late

- Rebuilding backend logic inside the app

- Treating every feature as P0

Prevention

Use four controlled release units:

- Sitter service-execution vertical slice

- Admin exception-management workflow

- Customer booking and live-status workflow

- Retention and intelligence features

The first production-quality vertical slice should cover:

Login

→ Assigned booking

→ Arrival

→ Start service

→ GPS/session evidence

→ End service

→ Report submission

→ Admin visibility

Do not begin customer loyalty or advanced AI while this flow remains unreliable.

Leading indicators

- Increasing unfinished work each sprint

- More than 20–25% of sprint work carried forward

- Backend contracts changing after mobile development begins

- Native-location prototype still unproven after Month 1

- P0 defect count growing rather than shrinking

Risk 2: GPS battery drain and unreliable tracking

A single aggressive location interval is not appropriate for every service. Use adaptive collection based on movement, accuracy, battery condition and service type.

Expo supports background-location tasks through development builds, but its documentation notes that updates stop if the user terminates the app and resume when the app is reopened. The product must represent this as an interruption rather than showing a falsely continuous route.

Required controls

| Control | Requirement |
| --- | --- |
| Tracking period | Active eligible service only |
| Update strategy | Time- and distance-adaptive |
| Offline behaviour | Queue points locally |
| End behaviour | Stop automatically |
| App terminated | Mark tracking interrupted |
| Customer map | Display freshness and quality |
| Sitting/grooming | Arrival and check-ins, not continuous routes |
| Battery monitoring | Test real devices and OEMs |

Stop condition

Pause tracking rollout when:

- Tracking continues after service completion

- Battery or thermal issues materially affect devices

- More than 5% of eligible sessions fail without a recovery path

- Location points are silently lost

- Staff cannot distinguish network loss from deliberate tracking disablement

Risk 3: Privacy concerns

The official rule must be:

Location is collected only during an explicitly started active pet-care service and is stopped when that service ends.

Google Play requires background-location access to support an important core feature, accompanied by prominent in-app disclosure, a privacy policy and an accurate permissions declaration. Apple also requires location collection to be directly relevant to app functionality and accurately disclosed.

The Indian DPDP framework requires digital personal data to be processed for lawful purposes with clear notices and appropriate safeguards. The 2025 Rules use phased commencement, so product controls should be built before wider enforcement and scale.

Mandatory safeguards

- No off-duty or between-booking tracking

- Visible tracking indicator

- Customer access only to their booking

- Admin access limited to operations and safety roles

- Access audit history

- Defined raw-route retention

- Incident-related legal hold handled separately

- Raw routes excluded from ordinary analytics

- Sitter can see permission and tracking status

- Privacy notice states purpose, access and retention

Approved user-facing wording

Location during active services
Your location is collected only while you perform an eligible pet-care service. It helps verify arrival, provide service updates, document the route and support safety assistance. Tracking stops when the service is completed.

Risk 4: Bugs during real bookings

A mobile defect can cause more than inconvenience. It can affect pet custody, customer access, payment, provider earnings and incident handling.

Required protections

Internal alpha

→ Sitter closed beta

→ Customer closed beta

→ One-cluster production

→ One-city production

→ Multi-city rollout

Use independent feature flags for:

- Mobile booking

- GPS

- Route sharing

- Credit payments

- AI recommendations

- Emergency workflows

- City and service-zone availability

Keep the PWA operational as a fallback.

Apple TestFlight supports up to 100 internal testers and up to 10,000 external testers. Google recommends moving from internal testing to a controlled closed test; certain newer personal Play developer accounts must complete a closed test with at least 12 testers opted in for 14 continuous days before applying for production access.

Release blockers

- Duplicate service start or completion

- Cross-customer access

- Incorrect credit consumption

- Incorrect payout calculation

- Unrecoverable offline report

- Emergency alert not delivered to the backend

- Tracking outside active service

- Crash during the main service flow

- Missing account-deletion path

Risk 5: Low sitter adoption

The sitter app will fail if it feels like surveillance, adds unnecessary steps or works poorly on common Android devices.

Adoption strategy

| Stage | Approach |
| --- | --- |
| First 5–10 sitters | Guided pilot and direct observation |
| 20–50 sitters | Training plus structured feedback |
| One city | App becomes default, with support |
| Stable production | App required for eligible services |

Product principles

- Three-tap access to the next booking

- Large Start, Emergency and Complete actions

- Offline support

- Earnings transparency

- Clear tracking status

- No hidden scoring

- Training in local languages where needed

- No reliability penalty for verified app outages

- No requirement for premium personal devices

Adoption metrics

- Weekly active sitter adoption

- Booking acknowledgement

- Check-in/out completion

- Report submission

- Support contacts per sitter

- Time required to submit a report

- Device-specific failure rate

Risk 6: Customer app remains unused

A customer app should initially target:

- Repeat customers

- Active subscribers

- Society-plan users

- Customers who regularly track services

- Multi-pet households

The strongest value proposition is not “we now have an app.” It is:

- Faster repeat booking

- Live service status

- Report history

- Subscription self-service

- Remaining-credit visibility

- Preferred-sitter management

- Better support

Do not force installation. Continue to support the PWA, deep links and assisted booking.

Risk 7: Incorrect AI matching

AI matching must remain an admin decision-support tool.

Hard eligibility rules

↓

Explainable candidate ranking

↓

Top three recommendations

↓

Admin approval

↓

Sitter acceptance

The model must never override:

- Expired documentation

- Pet-risk incompatibility

- Sitter suspension

- Service-zone restrictions

- Capacity limits

- Society-access requirements

- Schedule conflicts

Required governance

- Display a match score, not an uncalibrated probability

- Explain positive and negative factors

- Record algorithm version

- Record admin override reasons

- Monitor new-sitter exposure

- Audit assignment and earnings concentration

- Require human approval for all assignments initially

- Never auto-assign high-risk cases

Initial success targets

| Metric | Target |
| --- | --- |
| Top-three list includes selected sitter | 80%+ |
| Human approval | 100% |
| High-risk auto-assignments | Zero |
| False eligibility exclusions | Near zero |
| Recommendation outcome audit | Monthly |

Risk 8: Wallet and credit disputes

The early product should be called Credits, not Wallet.

Use:

- Subscription service credits

- Referral credits

- Promotional credits

- Society benefits

- Service-recovery credits

Do not initially support:

- Customer-funded cash storage

- Transfers between users

- Cash withdrawal

- Open merchant usage

RBI distinguishes closed-system instruments used only for the issuer’s own services from broader prepaid instruments, and closed systems cannot be used for third-party settlement or cash withdrawal. A marketplace with independent providers should obtain specialist payments advice before introducing a cash-like stored-value product.

Ledger requirements

Every credit movement must be append-only:

GRANT

RESERVE

CONSUME

RELEASE

RESTORE

EXPIRE

REVERSE

ADMIN_ADJUSTMENT

Every transaction needs:

- Idempotency key

- Reason

- Source booking/subscription

- Actor

- Expiry

- Timestamp

- Reversal link where applicable

Risk 9: App-store rejection

Store preparation should start while the apps are being built—not in the final week.

Common rejection areas

- Background location lacks a core use case

- Permission disclosure is vague

- Screenshots show unavailable features

- Demo account fails

- Privacy policy does not match actual SDK behaviour

- Account deletion is missing

- App crashes or has incomplete flows

- Data Safety or App Privacy declarations are inaccurate

Apple requires apps supporting account creation to let users initiate account deletion inside the app. Google Play requires an in-app deletion path and an external web resource for account-deletion requests.

Apple requires developers to disclose data collected by the application and integrated third-party partners. Google Play similarly requires accurate Data Safety declarations and may take enforcement action when app behaviour conflicts with the declaration.

Risk 10: Push notifications are treated as guaranteed delivery

Push is useful but should not be the only operational channel.

Firebase recommends storing token timestamps, refreshing tokens and removing stale or invalid registrations.

For critical events use:

Backend event

+ in-app inbox

+ push

+ operations queue

+ SMS/call fallback where necessary

Do not define “push reliability” only as messages submitted to FCM or APNs.

Measure:

- Active-token coverage

- Provider acceptance

- Application receipt where measurable

- User acknowledgement

- Fallback activation

- Stale-token rate

2. Phase 11 upgrade decisions

Upgrade 1: Build the sitter app before the customer app

Decision: APPROVE — NON-NEGOTIABLE

The sitter app directly improves:

- Booking acknowledgement

- Arrival reliability

- Service evidence

- GPS tracking

- Report quality

- Incident response

- Payout transparency

The customer app should follow after the sitter workflow and command centre are operationally stable.

Upgrade 2: Use React Native with Expo

Decision: APPROVE AS THE OFFICIAL DEFAULT STACK

As of 2026, the official React Native documentation recommends using a framework such as Expo for new applications and describes Expo as a production-grade React Native framework.

Approved stack

| Layer | Decision |
| --- | --- |
| Mobile framework | React Native with Expo development builds |
| Language | TypeScript |
| Navigation | Expo Router |
| Backend | Existing Node.js/Next.js APIs |
| Database | PostgreSQL/PostGIS |
| Push | Expo Notifications with FCM/APNs |
| Secure token storage | Platform-backed secure storage |
| Offline queue | SQLite/local outbox |
| Error monitoring | Sentry |
| Product analytics | PostHog or Firebase with redaction |
| Build/release | EAS or equivalent CI/CD |

Condition

Run native proofs for:

- Background GPS

- App termination

- Push deep links

- Offline media

- Battery impact

- Android OEM behaviour

- iOS background execution

Expo development builds are required for background location and other production native behaviour that Expo Go does not support.

Upgrade 3: AI remains admin-approved

Decision: APPROVE — MANDATORY FOR THE INITIAL RELEASE

AI should recommend candidates and explain the ranking. It should not autonomously assign every booking.

Human approval is especially required for:

- High-risk pets

- Medication

- Senior or specialist care

- First boarding

- Previous incidents

- Multiple large pets

- Unusual home access

- No established backup

Upgrade 4: Track location only during active service

Decision: APPROVE — NON-NEGOTIABLE

The official policy should state:

No active booking

→ no tracking

Service explicitly started

→ tracking permitted

Service completed or aborted

→ tracking stops

This must be enforced technically, not only written in the privacy policy.

Upgrade 5: Beta-first app launch

Decision: APPROVE — NON-NEGOTIABLE

Official progression:

| Stage | Users | Exit purpose |
| --- | --- | --- |
| Internal alpha | Team and QA | Functional and security validation |
| Sitter beta | 20–50 sitters | Field-execution validation |
| Customer beta | 100–500 loyal users | Booking and retention validation |
| City rollout | One validated city | Production stability |
| Multi-city | Gate-qualified cities | Repeatable scale |

3. Corrected Phase 11 deliverables

P0 — Mandatory

| Deliverable | Required outcome |
| --- | --- |
| Mobile PRD | Approved scope, users, states and non-goals |
| Mobile architecture | Backend, device, offline and event design |
| Sitter app | Production field-execution workflow |
| Customer app | Repeat booking and subscription workflow |
| Admin command centre | Live exceptions and incident queues |
| Push platform | Tokens, inbox and fallback handling |
| Active-service GPS | Session-bound and privacy controlled |
| Emergency Help | Multi-channel escalation |
| Report-card workflow | Offline-capable and service specific |
| Subscription dashboard | Pause, change, renew and cancel |
| Service-credit ledger | Immutable and auditable |
| Privacy and terms update | Apps, location, media and records covered |
| Account deletion | In-app plus required web process |
| Store assets | Complete and accurate |
| Beta plan | Cohorts, gates and rollback |
| Security assessment | OWASP MASVS-based |
| PWA fallback | Maintained |

OWASP MASVS provides a recognised baseline for mobile authentication, storage, cryptography, network, platform and privacy controls, while MASTG supplies corresponding testing guidance.

P1 — Recommended after the operational core

| Deliverable | Decision |
| --- | --- |
| Referral programme | Build after credit ledger |
| Preferred sitter | Build after assignment history is stable |
| AI matching assistant | Rules first, AI ranking later |
| Loyalty programme | Simple benefits before complex points |
| Pet health timeline | Owner-controlled MVP |
| Churn intelligence | Human-reviewed interventions |
| Society web dashboard | Web, not native |
| Partner dashboard upgrade | Responsive web |

Deferred

- Customer-funded cash wallet

- Native partner app

- Native society app

- Fully autonomous matching

- Pet medical diagnosis

- Social feed

- Full e-commerce

- Insurance marketplace

4. Corrected Phase 11 final report

Phase 11 Mobile App and Advanced Product Report

Programme information

Project name:
Reporting period:
Cities enabled:
Service zones enabled:
Mobile stack:
Customer app version:
Sitter app version:
Programme owner:

Release status

| Product | Stage | Current users | Release decision |
| --- | --- | --- | --- |
| Sitter app | Alpha/Beta/Production |  |  |
| Customer app | Alpha/Beta/Production |  |  |
| Command centre | Internal production |  |  |
| Matching assistant | Test/Beta/Active |  |  |

Sitter-app performance

| Metric | Result |
| --- | --- |
| Eligible active sitters |  |
| Weekly active sitter users |  |
| Adoption rate |  |
| Booking acknowledgement |  |
| Digital check-in/out |  |
| GPS sessions started |  |
| GPS-session success |  |
| Report completion |  |
| Offline recovery |  |
| Emergency alerts |  |
| Sitter-app crash-free sessions |  |
| Support cases per 100 services |  |

Customer-app performance

| Metric | Result |
| --- | --- |
| Eligible repeat customers |  |
| Activated app users |  |
| Adoption rate |  |
| Monthly active customers |  |
| App bookings completed |  |
| App booking conversion |  |
| Subscription self-service |  |
| Report-card view rate |  |
| Preferred-sitter usage |  |
| Customer-app crash-free sessions |  |
| App-store rating and review count |  |

Service and notification performance

| Metric | Result |
| --- | --- |
| App-originated bookings |  |
| GPS-tracked eligible services |  |
| Tracking interruption rate |  |
| Raw routes outside active service | Must be zero |
| Reports submitted through app |  |
| Active valid push tokens |  |
| Push provider acceptance |  |
| Critical-message acknowledgement |  |
| Fallback notifications required |  |

Do not use one ambiguous “push success” number. Sending, provider acceptance, device receipt and human acknowledgement are different states.

Subscription and credits

| Metric | Result |
| --- | --- |
| Subscribers using app |  |
| Credit reservations |  |
| Credit consumption |  |
| Credit reversals |  |
| Ledger mismatches | Must be zero |
| Referral-qualified users |  |
| Referral CAC | ₹ |
| Subscription renewals through app |  |
| Pause/downgrade requests |  |

Matching assistant

| Metric | Result |
| --- | --- |
| Bookings receiving recommendations |  |
| Top-three includes selected sitter |  |
| Top-one accepted by admin |  |
| Admin override rate |  |
| High-risk auto-assignments | Must be zero |
| Matching-related incidents |  |
| New-sitter recommendation share |  |

Quality and safety

| Metric | Result |
| --- | --- |
| Customer service rating |  |
| App-related booking failures |  |
| App-related refunds |  |
| Critical mobile incidents |  |
| Cross-user access incidents | Must be zero |
| Tracking privacy incidents | Must be zero |
| Open P0 security defects | Must be zero |

Findings

Top overall app issue:
Top sitter-app issue:
Top customer-app issue:
Top device/OEM issue:
Top tracking problem:
Top notification problem:
Top support request:
Highest-value app feature:
Lowest-adoption feature:
Most important architecture change:

Decision

- Move to Phase 12

- Continue sitter beta

- Continue customer beta

- Improve app stability

- Delay public launch

- Pause GPS rollout

- Correct credit ledger

- Improve sitter adoption

- Rebuild weak module

- Roll back a city or app version

5. Corrected Phase 12 go/no-go criteria

Sitter-app gate

| Requirement | Target |
| --- | --- |
| Active-sitter adoption | 80% minimum; 85%+ preferred |
| Digital booking acknowledgement | 95%+ |
| Check-in/out success | 98%+ |
| Report completion | 95%+ |
| Eligible GPS-session success | 95%+ |
| Offline-sync recovery | 99%+ |
| Crash-free sessions | 99.5%+ target |
| Tracking outside active service | Zero |
| Earnings mismatches | Zero unresolved |
| Critical emergency flow | Tested and operational |

Customer-app gate

| Requirement | Target |
| --- | --- |
| Adoption among invited repeat users | 40–60%+ |
| Booking technical success | 98%+ |
| Payment reconciliation | 100% |
| Credit-ledger reconciliation | 100% |
| Live-status accuracy | 98%+ |
| Subscription self-service | 70%+ |
| Crash-free sessions | 99.5%+ target |
| Cross-user data incidents | Zero |
| Account deletion | Tested on both platforms |

Notification gate

Replace “push reliable at 95%” with:

| Metric | Target |
| --- | --- |
| Active valid-token coverage | 95%+ |
| Provider send acceptance | 98%+ |
| Critical operational acknowledgement | Within SLA |
| Critical fallback process | Working |
| Invalid/stale-token cleanup | Automated |

Push delivery alone cannot be treated as guaranteed; critical operational state must also exist in the backend and command centre.

AI matching gate

| Requirement | Target |
| --- | --- |
| Matching assistant tested | Yes |
| Hard eligibility filters | 100% enforced |
| Admin approval | 100% initially |
| Top-three contains final selection | 80%+ |
| High-risk automatic assignment | Zero |
| Override reasons captured | 95%+ |
| Bias/concentration review | Completed |

Security and compliance gate

- No unresolved P0 security defects

- No unresolved high-severity privacy defects

- OWASP MASVS testing completed

- App Privacy and Data Safety declarations validated

- Background-location disclosures approved

- Account deletion operational

- Privacy policy matches real SDK behaviour

- Store-review/demo accounts functional

- Data-retention jobs tested

Business gate

| Requirement | Target |
| --- | --- |
| Customer service rating | 4.6+ |
| Manual touches per booking | Reduced 30%+ |
| Support contacts per booking | Stable or decreasing |
| Completion rate | 95%+ |
| On-time rate | 95%+ |
| App contribution impact | Neutral or improving |
| Critical unresolved safety incidents | Zero |
| Public rollout city stable | Yes |

6. Final Phase 11 recommendation

Build:

A sitter-first mobile operating system connected to an advanced command centre, followed by a customer application for repeated booking, live service visibility, subscriptions, credits and preferred-caregiver continuity.

Do

- Build sitter execution first.

- Use React Native with Expo development builds.

- Validate GPS on real Android and iOS devices early.

- Keep AI recommendations explainable and admin-approved.

- Use an immutable service-credit ledger.

- Launch through controlled cohorts.

- Keep the PWA operational.

- Maintain kill switches and rollback controls.

- Treat security and privacy testing as continuous engineering work.

Do not

- Track sitters outside active services.

- Build a cash-like wallet without regulatory analysis.

- auto-assign high-risk bookings.

- depend on push alone for emergency communication.

- expose exact customer data before assignment.

- publish both apps to every city simultaneously.

- add social, insurance or e-commerce distractions.

- call app downloads the primary success metric.

Final approval matrix

| Phase 11 rule | Decision |
| --- | --- |
| Build sitter app before customer app | APPROVED |
| Use React Native with Expo | APPROVED |
| AI matching remains admin-approved | APPROVED |
| Location tracking only during active service | APPROVED — NON-NEGOTIABLE |
| App launch remains beta-first | APPROVED — NON-NEGOTIABLE |

Phase 11 win condition

Sitters execute services more reliably, operations detect failures earlier, customers gain trustworthy visibility and self-service controls, and repeat users adopt the apps without increasing safety incidents, privacy exposure or financial disputes.

Phase 11 final decision

GO — with all five rules approved.

Move to Phase 12: Brand, Community and Content Engine only after the sitter app, customer app, GPS system, credit ledger, notifications and command centre pass the measurable gates above.