PetSaathi Phase 7 — Society Partnership Phase 🏢🐾

Executive decision

Approve Phase 7, with one important framing:

Phase 7 is not mainly a marketing phase. It is a B2B2C operating-density phase.

PetSaathi will partner with an apartment society, RWA, AOA or residential facility manager, but the actual service relationship remains between:

PetSaathi

+ resident pet parent

+ authorised sitter

The society provides controlled access, local credibility, communication channels and demand concentration. It should not become responsible for individual bookings, pet-care decisions or customer payments unless a specific corporate contract says otherwise.

1. What Phase 7 changes

Before society partnerships

Customer in Area A

Sitter in Area B

Long travel time

Low booking density

Expensive customer acquisition

Irregular repeat demand

Difficult gate access

After a successful partnership

Several customers in one society

↓

Locally approved sitter pool

↓

Predictable service windows

↓

Lower travel time

↓

More daily bookings per sitter

↓

Same-sitter continuity

↓

Walking packs and recurring demand

The advantage is not simply that the society promotes PetSaathi. The real advantage is operational density.

2. Why society partnerships can become a moat

Higher trust

Residents may be more comfortable when:

- The service has been reviewed by the society committee.

- Sitter identity and training checks are visible.

- Security has an approved-entry process.

- A local support contact exists.

- Other residents have already used the service.

However, use precise wording:

Society access approved

Identity verification reviewed

Pet-care training completed

Do not claim:

100% safe

Risk-free sitter

Society guarantees the service

Lower customer-acquisition cost

Instead of acquiring every customer separately, PetSaathi can reach residents through:

- Society WhatsApp or communication apps

- Lobby posters

- Pet-parent meetings

- Resident events

- Management announcements

- Existing customer referrals

The actual benefit must be measured:

Society CAC =

Total society acquisition and activation cost

÷

First-time paying residents

A partnership with many leads but few paid bookings is not automatically successful.

Better booking density

The strongest Phase 7 metric is:

Completed bookings

per active society

per week

Density can reduce:

- Sitter travel time

- Transport cost

- Late arrivals

- Idle gaps

- Replacement time

- Support complexity

It can also allow one sitter to complete several non-overlapping services in the same society without travelling across the city.

Better repeat demand

Society-based services are especially suitable for:

- Daily dog walking

- Five- and ten-walk packs

- Weekly pet sitting

- Festival care

- Travel-period support

- Same-sitter schedules

- Controlled boarding referrals

Repeat behaviour should be measured through completed second services—not only package purchases.

Easier gate and access operations

Society partnerships can create a structured process for:

- Sitter registration

- Visitor approvals

- ID verification display

- Entry and exit records

- Approved service hours

- Pet-lift or common-area instructions

- Emergency-entry escalation

- Replacement-sitter approval

This reduces situations where a sitter is technically assigned but cannot enter the property.

3. Important legal and operational boundary

PetSaathi must keep commercial pet-care services separate from a society’s responsibilities relating to community animals.

The Animal Welfare Board of India’s July 2025 guidance addresses RWAs and AOAs directly and states that they have responsibilities under the Animal Birth Control Rules, including structured feeding arrangements and maintaining records relating to community animals. The guidance discusses designated feeding areas and times, vaccination/sterilisation records and coordination with local bodies.

Therefore, PetSaathi must not position its paid partnership as:

- A method to remove or exclude community dogs

- A replacement for an RWA’s statutory or community-animal duties

- A system for harassing feeders or pet owners

- A promise to make a society “animal-free”

- A tool for imposing blanket pet restrictions

PetSaathi may offer a separate optional coordination module for community-animal records, vaccination drives or approved feeding-point coordination, but this should be contractually and operationally separate from paid dog walking, sitting and boarding.

AWBI has also repeatedly issued guidance involving RWAs, apartment associations and community-animal care, including the need to avoid harassment and to coordinate designated feeding arrangements.

4. Society partnership stakeholders

A partnership usually requires more than approval from one committee member.

Society stakeholders

| Stakeholder | Responsibility |
| --- | --- |
| RWA/AOA committee | Partnership approval and policy alignment |
| Facility manager | Daily operational coordination |
| Security supervisor | Sitter entry and replacement procedures |
| Residents | Individual service registration and payment |
| Pet-parent group | Feedback, demand validation and referrals |
| Non-pet residents | Safety, cleanliness and common-area concerns |
| Local veterinarian | Optional emergency coordination |
| PetSaathi operations owner | Booking, incident and service accountability |

PetSaathi should identify one authorised society contact and one backup contact.

5. Recommended partnership models

Model A — Referral partnership

The society permits PetSaathi promotion to residents.

Society shares service information

Residents book individually

PetSaathi handles payment and service

Society receives aggregate updates only

Best for

- First pilot

- Smaller societies

- Low legal and financial complexity

- Demand validation

Model B — Resident-benefit partnership

Residents receive a society-specific offer.

Examples:

- ₹99 first walk

- Reduced package price

- Priority support

- Free first meet-and-greet

- Same-sitter preference

PetSaathi still contracts and collects payment from individual customers.

Best for

- Medium and premium societies

- Repeat walking programmes

- Simple commercial structure

Model C — Managed society pet-care desk

PetSaathi operates approved local service windows.

Example:

Morning walks: 6:30–9:00

Evening walks: 5:00–8:00

Dedicated local sitter roster

Daily operations owner

Society-specific support contact

Best for

- High pet-parent density

- Multiple daily walks

- Strong society cooperation

- Proven demand

Model D — Society-paid programme

The RWA, developer or property-management company pays a monthly amount for defined services.

Possible inclusions:

- Resident helpline

- Sitter-access management

- Emergency coordination

- Pet-parent onboarding sessions

- Monthly service credits

- Pet-care events

- Aggregate safety reporting

Important

Define whether this is:

- A sponsorship

- A service retainer

- A resident subsidy

- A minimum booking commitment

- A corporate amenity

Do not leave payment responsibility ambiguous.

6. Recommended Phase 7 partnership package

Resident services

Dog walking

Pet sitting

Controlled boarding referrals

Same-sitter repeat booking

Five/ten-walk packs

Festival and travel care

Trust features

Verified sitter profile

Service permissions

Society-access approval

Pet-care training badges

Photo/video updates

Automated Report Cards

Basic GPS walk proof

Emergency escalation

Society controls

Approved sitter registry

Entry and exit process

Service-hour configuration

Replacement approval process

Incident escalation contact

Society-specific booking code

Aggregate monthly dashboard

What the society should not access

The society should not automatically receive:

- Resident phone numbers

- Exact individual booking instructions

- Pet medical information

- Emergency family contacts

- Payment details

- Individual complaint content

- Full GPS routes

- Private photos or videos

The DPDP Act establishes a framework for lawful processing of digital personal data, and the final DPDP Rules were published in November 2025 with staged commencement provisions. PetSaathi should apply purpose limitation, appropriate access, resident notices and controlled retention to society-level data sharing.

The society dashboard should therefore be aggregated by default.

7. End-to-end society acquisition flow

Select target area

↓

Identify suitable societies

↓

Qualify society demand and operations

↓

Meet committee/facility manager

↓

Present partnership proposal

↓

Complete legal and operational review

↓

Sign pilot agreement

↓

Configure society and security access

↓

Survey residents and import leads

↓

Train local sitter roster

↓

Launch controlled resident pilot

↓

Monitor daily operations

↓

Review metrics

↓

Renew, expand or stop

8. Step 1 — Select the right societies

Do not approach every residential property.

Recommended qualification criteria

| Criterion | Why it matters |
| --- | --- |
| 300+ occupied homes, or strong pet density | Sufficient demand potential |
| Active RWA/AOA or facility team | Clear decision-maker |
| Controlled security access | Partnership creates operational value |
| Existing pet-parent group | Faster activation |
| Local sitter supply | Service can actually be fulfilled |
| Nearby vet/emergency support | Better incident readiness |
| Suitable walking environment | Practical dog-walking operation |
| Committee willingness | Reduced implementation friction |

A smaller society with 30 active pet parents may be more valuable than a large society with low interest.

9. Step 2 — Society discovery survey

Before proposing a contract, collect:

Number of occupied homes

Estimated pet-owning households

Dogs/cats/other pets

Current walking arrangements

Common service times

Travel-care demand

Current sitter or domestic-help use

Access restrictions

Pet-related complaints

Resident language preferences

Interest in packages

Do not ask the committee to hand over a list of pet owners without an appropriate resident-facing notice or lawful basis.

Use an opt-in survey:

“I am interested in PetSaathi society services.”

10. Step 3 — Partnership proposal

The proposal should contain:

Business terms

- Pilot duration

- Active services

- Resident pricing

- Society fee or commission, if any

- Payment responsibility

- Minimum commitment

- Renewal and termination

Operational terms

- Approved service areas

- Entry procedure

- Approved service hours

- Sitter roster

- Backup process

- Incident contacts

- Escalation time

- Festival/peak policy

Safety terms

- Sitter verification

- Pet Profile requirement

- Service-specific risk review

- Handling controls

- Emergency process

- Incident investigation

- Insurance position, if applicable

Data terms

- What PetSaathi collects

- What the society receives

- Permitted use

- Retention

- Security

- Resident requests

- Breach and incident communication

11. Step 4 — Pilot agreement

The agreement should clearly state:

Society is not the pet-care provider.

PetSaathi controls sitter selection and service operations.

Residents remain responsible for accurate pet information.

The society does not guarantee sitter performance.

PetSaathi does not guarantee zero risk.

Individual payments remain between PetSaathi and customers unless otherwise agreed.

Emergency coordination is not veterinary diagnosis.

Also define:

- Contract term

- Termination rights

- Branding approval

- Promotional access

- Dispute escalation

- Liability allocation

- Indemnity and insurance, after legal review

- Applicable local and state requirements

Because society structures and by-laws vary by state and property type, the partnership template should receive local legal review before being used across India.

12. Step 5 — Society setup

Create a society record:

societies

- id

- name

- city

- area

- address

- geofence

- status

- partnership_model

- agreement_start

- agreement_end

- primary_contact

- facility_contact

- security_contact

- emergency_contact

- booking_cap

Create access configuration:

society_access_rules

- society_id

- visitor_approval_required

- sitter_registration_required

- identity_document_required

- allowed_entry_times

- approved_gates

- pet_lift_rules

- replacement_sitter_process

- emergency_entry_process

- last_verified_at

13. Step 6 — Local sitter network

Do not launch resident marketing before adequate sitter supply exists.

Recommended initial roster per society cluster

| Role | Suggested starting coverage |
| --- | --- |
| Primary dog walkers | 3–5 |
| Pet sitters | 2–3 |
| Backup candidates | 2–3 |
| Boarding partners | 1–2 controlled |
| Operations owner | 1 |
| Emergency support contact | 1–2 |

One sitter should not become the only person capable of serving the society.

Society sitter badge

Use:

Society access approved

This means:

- Their identity is registered with security.

- Required access steps are complete.

- The approval is active.

- Expiry or revocation is tracked.

It does not mean the society guarantees every action of the sitter.

14. Step 7 — Resident launch

Recommended launch sequence

Pet-parent survey

↓

Resident information session

↓

Sitter introduction

↓

Trial booking offer

↓

First 10–20 services

↓

Collect Report Cards and reviews

↓

Offer five/ten-walk plans

↓

Introduce recurring slots

Launch assets

- Society landing page

- QR booking link

- WhatsApp template

- Lobby poster

- Sitter-introduction profiles

- Safety explanation

- FAQ

- Pricing sheet

- Incident contact

- Cancellation/refund policy

15. Society-specific booking flow

Resident verifies society/unit

↓

Creates Pet Profile

↓

Selects society-supported service

↓

Chooses date/time

↓

System applies society access rules

↓

Admin assigns approved local sitter

↓

Payment captured

↓

Security entry prepared

↓

Service completed

↓

Report Card delivered

↓

Repeat plan offered

The resident’s unit number should not be visible to candidate sitters before final assignment.

16. Society dashboard

The society should see aggregate information such as:

Active resident registrations

Completed services

Service types used

Average customer rating

On-time rate

Resolved society-access issues

Open society-level incident count

Sitter access approvals

Upcoming resident event

Do not display individual resident health or booking details.

Example

PetSaathi — Green Meadows

Registered pet parents: 32

Completed services this month: 86

Dog walks: 71

Pet-sitting visits: 15

On-time services: 96%

Average rating: 4.7

Open society-access issues: 1

Critical incidents: 0

17. Commercial models

Resident-paid

Resident pays PetSaathi

PetSaathi pays sitter

Society may receive no fee or disclosed referral fee

Best for the first pilot.

Minimum monthly guarantee

Society guarantees minimum programme revenue

Residents receive subsidised pricing

Useful only after proven demand.

Monthly management retainer

The society pays for:

- Local operations

- Access registry

- Support desk

- Resident events

- Aggregate reporting

Individual care services may still be resident-paid.

Revenue share

Use cautiously.

A revenue share can create:

- Complex accounting

- Higher resident prices

- Disputes about refunds

- Committee transparency concerns

- Incentives to promote unsuitable services

Any fee or commission should be disclosed contractually and accounted for clearly.

18. Phase 7 pilot recommendation

Initial scope

One city

Two or three nearby societies

Dog walking as hero service

Pet sitting active

Boarding controlled

Twenty to thirty trained sitters across the cluster

Daily operational monitoring

Recommended duration

45–60 days

The first two weeks should use a booking cap.

| Stage | Suggested cap |
| --- | --- |
| Week 1 | 5–10 bookings/day across pilot |
| Week 2 | 10–15/day |
| Weeks 3–4 | 15–25/day |
| Later | Increase only after quality review |

19. Phase 7 success metrics

Acquisition

Societies contacted

Meetings completed

Pilot agreements signed

Resident leads

Registered pet parents

First paid bookings

Society acquisition cost

Density

Paid residents per society

Bookings per society per week

Bookings per active sitter

Median sitter travel time

Same-society consecutive bookings

Quality

| Metric | Initial target |
| --- | --- |
| Completed services | 90%+ |
| On-time services | 95%+ |
| Report Cards delivered | 98%+ |
| Average rating | 4.6+ |
| No-show rate | Below 3–5% |
| Serious incidents | Zero preferred; all handled correctly |
| Priority booking continuity | 90%+ |

Retention

Second completed booking

Five-walk-plan conversion

Credit utilisation

Same-sitter repeat rate

30/60-day repeat rate

Society health

Resident complaints

Security access failures

Non-pet resident complaints

Committee satisfaction

Partnership-renewal interest

Society-level support load

Economics

Revenue per society

Contribution margin

Sitter travel cost

Support minutes per booking

Acquisition payback

Revenue concentration risk

20. Major risks

One committee member is not full approval

Secure written, authorised approval according to the society’s governance process.

Committee changes

A new committee may review or cancel the partnership. Store agreement term, authorised signatories and termination process.

Access approval is mistaken for safety guarantee

Keep factual verification language and clear responsibility boundaries.

Resident data is overshared

Provide aggregate reports and role-restricted access.

Society exclusivity is accepted too early

Avoid long exclusive contracts before demand and operational quality are proven.

One sitter dominates the society

Maintain backup coverage and prevent single-sitter dependency.

Non-pet residents feel ignored

Provide cleanliness, common-area and complaint procedures without creating discriminatory restrictions against lawful pet ownership or community-animal care.

Society services are confused with community-dog management

Keep commercial pet services contractually separate from ABC/community-animal coordination.

21. What is wrong in many society launches

Mistake 1 — Signing partnerships without resident demand

Correct:

Survey → waitlist → pilot bookings → contract expansion

Mistake 2 — Treating the RWA as the customer and ignoring residents

The committee approves access, but residents decide whether the service is valuable.

Mistake 3 — Marketing before sitter supply

Do not create 100 resident leads with only one available walker.

Mistake 4 — No security-gate workflow

A booking is not operationally confirmed if the sitter cannot enter.

Mistake 5 — Sharing too much data with the society

Aggregate metrics should be the default.

Mistake 6 — No non-pet-resident communication

Explain:

- Sitter access rules

- Waste-cleanup expectations

- Service hours

- Complaint route

- Emergency escalation

Mistake 7 — Promising society-wide emergency veterinary care

PetSaathi may coordinate listed contacts; it should not claim veterinary or ambulance capability it does not control.

22. Phase 7 definition of done

Phase 7 is ready for broader society expansion only when:

Partnership

- Agreements are authorised and documented.

- Commercial terms are clear.

- Data sharing is limited.

- Termination and dispute rules exist.

Operations

- Society access procedures work.

- Local sitter supply is sufficient.

- Backup coverage exists.

- Daily service windows are manageable.

- Security staff understand the process.

Customer

- Residents can register and book easily.

- Pet Profiles and payments work.

- Report Cards are delivered.

- Same-sitter repeats work.

- Support is responsive.

Safety

- Society partnerships do not bypass PetSaathi risk controls.

- Incidents remain structured and auditable.

- Community-animal responsibilities are not misrepresented.

- Sensitive data is role-restricted.

- Emergency communication is tested.

Economics

- Booking density improves.

- Travel time falls.

- Repeat demand is demonstrated.

- Contribution margin is positive or moving toward it.

- Support workload remains sustainable.

Final Phase 7 operating model

Select 2–3 suitable societies

↓

Validate resident demand

↓

Sign controlled pilot agreement

↓

Configure access and data rules

↓

Prepare local sitter and backup roster

↓

Launch trial bookings

↓

Convert successful trials into repeat plans

↓

Track density, quality and economics

↓

Renew successful societies

↓

Expand to nearby society clusters

Final operating principle

The society partnership is valuable only when it improves trust, local booking density and operational reliability. A signed agreement without active residents, nearby sitters and repeat services is not a moat.

Simple explanation for professor

“Phase 7 focuses on partnering with apartment societies, RWAs and gated communities.

Instead of accepting random bookings from different parts of a city, PetSaathi will build a local network inside selected societies. The society will help with resident communication and sitter access, while PetSaathi will remain responsible for booking, payment, sitter assignment, tracking, Report Cards and incidents.

This model can reduce travel time and customer-acquisition cost because many pet parents live in one place. It also makes daily walking plans and same-sitter bookings easier.

The process starts by selecting societies with enough pet-owner demand. PetSaathi will conduct a resident survey, meet the society committee, sign a pilot agreement, register approved sitters with security and launch limited trial bookings.

The society dashboard will show aggregate information such as completed services and on-time rates, but it will not show private resident medical, payment or emergency information.

We will first test the system in two or three nearby societies for 45 to 60 days. Success will be measured through paid residents, bookings per society, on-time services, Report Cards, repeat bookings, travel time, customer rating and positive unit economics.

The main objective is to create a trusted local pet-care network that can serve many residents reliably without expanding randomly across the whole city.”

PetSaathi Phase 7 — Legal Context, Duration and Society Targets 🏢🐾

Executive decision

Your central positioning is approved:

PetSaathi helps pet parents, non-pet residents, security teams and society management coexist safely through verified pet-care support, clear operating procedures and fast issue escalation.

Do not position PetSaathi as:

- Controlling pets inside societies

- Removing “problem dogs”

- Making societies pet-free

- Enforcing blanket pet restrictions

- Replacing municipal community-animal responsibilities

- Guaranteeing that a sitter or pet is completely risk-free

Phase 7 should run for 60 days in one city, but the proposed goal of 20–50 societies needs clarification:

- 20–50 societies can be the qualified outreach pipeline.

- 5–10 societies can be signed pilots.

- 3–5 societies should become fully operational during the first 60 days.

Trying to activate 20–50 societies simultaneously would likely reduce service quality, sitter density and operational control.

1. Verified legal position

Blanket pet bans

The AWBI’s 2015 guidelines state that RWAs and apartment-owner associations cannot introduce a ban on keeping pet dogs. The guidelines also reject restrictions based merely on dog size or a majority vote of residents.

BMC’s current published guidelines expressly repeat that RWAs and AOAs cannot impose bans on keeping pet dogs or cats, cannot treat barking alone as a sufficient ground for a ban, and cannot create such a ban merely through majority approval.

Important legal nuance

Do not market the rule as:

“Every RWA pet restriction anywhere in India is automatically illegal.”

A safer and more accurate statement is:

AWBI guidance states that blanket pet bans by RWAs and AOAs are not permissible. BMC expressly adopts that position in Mumbai. PetSaathi will review relevant state, municipal and society requirements before each city launch.

AWBI guidance is an important official animal-welfare position, but city-specific municipal requirements, state cooperative-housing laws, court orders, licences and valid conduct rules may still differ.

2. What societies may reasonably regulate

Pet ownership and responsible conduct must be treated separately.

A society should not prohibit residents from keeping pets, but reasonable operational arrangements may cover matters such as:

- Common-area cleanliness

- Waste collection

- Service timings

- Security entry

- Leash and handling expectations

- Alternate lift usage where available

- Vaccination or municipal licence evidence where legally required

- Response to a specific nuisance or safety event

BMC’s guidance states that pets cannot be excluded from lifts, although residents may be advised to use an accessible alternate lift. It also supports mutually acceptable walking timings rather than a complete park or walking ban.

For Mumbai specifically, BMC also requires dog licensing, advises timely vaccination and leashing in public areas, and places responsibility on owners or dog walkers to clean up pet waste. These exact requirements must not be assumed for every Indian city without local verification.

PetSaathi product implication

The society configuration should support:

Pet ownership permitted

+

Responsible conduct rules

+

Security-access procedure

+

Incident escalation

It should not support:

Pet ownership banned

Pet size banned

All pets banned from lifts

All pets banned from walking areas

Pet owner forced to surrender animal

3. Pet animals and community animals must remain separate

This distinction is critical.

Resident pets

These have an identified owner responsible for:

- Accurate Pet Profile information

- Health and vaccination information

- Safe equipment

- Waste cleanup

- Handling instructions

- Service booking and payment

Community animals

These are animals for which no individual ownership has been claimed. The Animal Birth Control Rules, 2023 and later AWBI guidance address community-animal feeding, sterilisation, vaccination and conflict-resolution arrangements.

AWBI’s July 2025 guidance states that RWA, AOA or local-body representatives have responsibilities around structured feeding provisions for community animals. It also directs maintenance of information such as estimated population, sterilisation status, anti-rabies vaccination records and identified feeders or caregivers.

Product boundary

PetSaathi’s commercial society partnership should cover:

Resident pet services

Sitter access

Bookings

Payments

Dog walking

Pet sitting

Report Cards

Service incidents

A separate optional module may later cover:

Community-animal register

Feeding-point coordination

Vaccination-drive coordination

Municipal or NGO referrals

PetSaathi must not imply that a paid dog-walking partnership replaces the society’s responsibilities relating to community animals.

4. Approved society messaging

Recommended primary message

PetSaathi helps societies create a safer and more organised pet-care environment through verified caregivers, controlled entry, service updates, Report Cards and responsive support.

Resident-facing version

Book trusted local pet-care support within your society, with verified caregiver profiles, photo updates, walk proof, Report Cards and emergency escalation.

Committee-facing version

PetSaathi provides a structured resident pet-care programme with approved-access caregivers, booking records, service monitoring, incident handling and aggregate society reporting.

Non-pet-resident version

The programme supports responsible service timings, controlled sitter entry, waste-cleanup expectations and a clear complaint process while respecting lawful pet ownership.

Avoid these phrases

- “Pet control programme”

- “Pet menace solution”

- “Dog-free society”

- “Guaranteed safe pets”

- “Zero-risk walkers”

- “RWA-certified safe sitter”

- “Removal of community dogs”

- “Ban difficult breeds”

Use factual badges instead:

Identity verified

Training completed

Society access registered

Large-dog handling approved

Police-verification document reviewed

5. Resident-data protection

A society should not casually send PetSaathi a spreadsheet containing resident names, telephone numbers, flat numbers and pet information.

The safer acquisition process is:

Society shares QR code or announcement

↓

Interested resident opens PetSaathi form

↓

Resident receives privacy notice

↓

Resident voluntarily registers

↓

PetSaathi records consent and purpose

The Digital Personal Data Protection Act, 2023 establishes a framework for lawful processing of digital personal data. The final DPDP Rules, 2025 were published with staged commencement dates, so PetSaathi should map society onboarding, notices, security, grievance handling and retention against the provisions applicable at launch.

Society dashboard rule

Show aggregate information by default:

Registered residents: 28

Completed services: 73

On-time rate: 96%

Average rating: 4.7

Open access issues: 1

Do not expose:

- Individual pet medical information

- Full customer phone numbers

- Emergency contacts

- Exact booking instructions

- Full GPS routes

- Payment data

- Private photos or videos

- Complaint narratives

6. Phase 7 duration decision

| Version | Assessment |
| --- | --- |
| 15–20 days | Suitable for discovery, meetings and a small proof of concept |
| 45–60 days | Best for signing, activating and evaluating society pilots |
| 90 days | Better for renewals, repeat-plan maturity and deeper city clustering |

Approved duration

Run a 60-day society partnership phase in one city.

Twenty days is usually insufficient to measure:

- Repeat-plan conversion

- Package-credit usage

- Sitter reliability

- Committee satisfaction

- Resident referrals

- Partnership renewal interest

Ninety days may later be used to deepen a successful cluster, but it should not delay the first controlled pilot.

7. Correction to the “20–50 societies” target

Wrong interpretation

Launch operational services in 20–50 societies within 60 days

This would require:

- Large sitter supply

- Many security onboarding processes

- Multiple committee negotiations

- Distributed support coverage

- Society-specific operating procedures

- More replacement capacity

It would recreate the same low-density problem that Phase 7 is meant to solve.

Correct interpretation

Build a list of 50 qualified societies

↓

Contact 40–50

↓

Complete 15–20 meetings

↓

Identify 8–12 interested societies

↓

Sign 5–10 pilot agreements

↓

Fully activate 3–5 clustered societies

The next group should be activated only after the first cluster demonstrates stable operations.

8. Recommended 60-day execution plan

Days 1–10 — Legal and commercial preparation

Complete:

- Partnership proposal

- Pilot agreement

- RWA/AOA legal-language review

- Data-sharing schedule

- Resident privacy notice

- Society access SOP

- Incident and escalation procedure

- Commercial model

- Society dashboard design

- Outreach materials

Output

Society Partnership Kit v1

Days 11–20 — Targeting and outreach

Build a qualified list of 50 societies based on:

- Geographic clustering

- Occupied units

- Estimated pet-parent density

- Active committee or facility manager

- Security-access complexity

- Nearby sitter supply

- Walking environment

- Veterinary accessibility

Begin outreach through:

- Existing customers

- Facility managers

- Resident pet-parent groups

- Local veterinarians

- Pet shops

- Property-management networks

Target

40–50 societies contacted

10–15 meetings booked

Days 21–30 — Meetings and society qualification

During each meeting, validate:

- Estimated number of pet-owning households

- Hero service demand

- Preferred service times

- Security process

- Sitter registration requirements

- Existing pet complaints

- Committee concerns

- Resident communication channels

- Partnership approval authority

- Commercial expectations

Target

15–20 meetings completed

8–12 qualified interested societies

Days 31–40 — Agreements and setup

For each selected pilot society:

- Sign authorised agreement

- Create society record

- Configure access rules

- Train security/facility staff

- Build local sitter roster

- Verify backup coverage

- Launch resident opt-in survey

- Create society landing page

- Publish pricing and policies

- Verify emergency contacts

Target

5–10 signed pilots

3–5 launch-ready societies

Days 41–50 — Controlled resident launch

Launch in small batches:

5–10 services

↓

Operational review

↓

Next 10–20 services

↓

Quality review

↓

Repeat-plan offer

Monitor:

- Entry failures

- Sitter punctuality

- Customer support

- Tracking

- Report Cards

- Resident complaints

- Society complaints

- Repeat interest

Days 51–60 — Optimization and decision

Evaluate each society separately.

Possible decisions:

RENEW_AND_EXPAND

CONTINUE_PILOT

FIX_OPERATIONS

CHANGE_SERVICE_MIX

PAUSE_SOCIETY

TERMINATE_PILOT

Do not expand a weak society merely to increase the signed-partnership count.

9. Success-target analysis

Societies contacted — 50+

Approve.

This should mean qualified outreach, not mass unsolicited messaging.

Society meetings — 15–20

Approve.

This represents a 30–40% meeting rate from 50 qualified targets, which is ambitious but possible with warm introductions, local networks and targeted outreach.

Interested societies — 8–12

Approve with definition.

“Interested” should require:

- Identified decision-maker

- Confirmed resident demand

- Operational feasibility

- Willingness to review pilot terms

- Suitable service cluster

A committee member saying “send details” is not a qualified opportunity.

Signed or pilot societies — 5–10

Approve as an ambitious range.

Use:

Minimum success: 5

Strong result: 8

Stretch target: 10

Only 3–5 need to be fully activated during the initial 60 days.

Society pet-parent leads — 200–500

Approve only for opt-in leads.

Define a valid lead as a resident who has:

- Submitted the society registration form

- Provided contact information voluntarily

- Identified a pet or service need

- Accepted the relevant privacy notice

Do not count poster views or WhatsApp-group members as leads.

Paid bookings — 100–300

Approve, but define whether this means total booking transactions or unique customers.

Across five pilot societies:

100 bookings = 20 bookings per society over 60 days

300 bookings = 60 bookings per society over 60 days

Across ten pilot societies:

100 bookings = 10 bookings per society

300 bookings = 30 bookings per society

A society with three one-time bookings is not yet a strong partnership.

Add the density metric:

Completed bookings per active society per week

Monthly repeat plans — 20–50

Approve as the strongest commercial validation target.

Track:

- Plans purchased

- Credits issued

- Credits used

- Plan completion

- Same-sitter fulfilment

- Cancellation

- Expired credits

The real success metric is not only plan sales:

Plan credits successfully consumed

Society revenue — ₹50,000 to ₹2 lakh per month

Modify the definition.

“Society revenue” is ambiguous. Track four separate values:

Society-sourced GMV

PetSaathi platform revenue

Gross contribution

Net operating contribution

For example:

50 plans × ₹1,499

= ₹74,950 monthly GMV

At a 30% platform gross margin:

PetSaathi gross margin

= approximately ₹22,485

before support and operating costs

Therefore:

- ₹50,000–₹2 lakh monthly GMV is achievable with moderate booking density.

- ₹50,000–₹2 lakh monthly platform revenue requires substantially more bookings, higher-value sitting/boarding services or society retainers.

- The report must not call GMV “revenue.”

Recommended target

End-of-phase monthly society-sourced GMV:

₹50,000–₹2 lakh

Positive contribution margin:

Required for strongest societies

Platform net revenue:

Reported separately

Customer rating — 4.6+

Approve with sample-size protection.

Report:

Average rating

Number of reviews

Review response rate

Rating distribution

Service type

Society

A 4.8 rating from five customers is not equivalent to 4.8 from one hundred customers.

Society complaints — low/manageable

Reject the vague wording and replace it with measurable rules.

Recommended metrics:

| Metric | Target |
| --- | --- |
| Critical unresolved society complaints | 0 |
| Security-entry failures | Below 3% of bookings |
| Society complaints | Below 5 per 100 bookings |
| Complaint acknowledgement | Same day |
| Active-service complaint response | Under 10 minutes |
| Repeated unresolved complaint pattern | 0 |
| Complaints with owner and status | 100% |

Classify complaints as:

Access

Cleanliness

Noise

Sitter conduct

Common-area use

Community-animal conflict

Privacy

Safety

Billing

10. Revised Phase 7 success scorecard

| Metric | Minimum | Strong | Stretch |
| --- | --- | --- | --- |
| Qualified societies contacted | 40 | 50 | 75 |
| Meetings completed | 12 | 15–20 | 25 |
| Qualified opportunities | 6 | 8–12 | 15 |
| Signed pilots | 5 | 8 | 10 |
| Fully activated societies | 3 | 5 | 8 |
| Opt-in resident leads | 200 | 350 | 500 |
| Paid bookings | 100 | 200 | 300 |
| Monthly repeat plans | 20 | 35 | 50 |
| Rating | 4.5+ | 4.6+ | 4.7+ |
| Critical unresolved complaints | 0 | 0 | 0 |
| Society-sourced monthly GMV | ₹50k | ₹1L | ₹2L |
| Positive contribution societies | 1 | 3 | 5 |

11. Additional success metrics

Add these to prevent vanity reporting.

Activation rate

Societies producing at least five paid bookings

÷ signed pilot societies

Resident conversion

Residents completing first paid booking

÷ opted-in resident leads

Density

Completed bookings

÷ active society

÷ week

Repeat completion

Customers completing a second paid service

÷ customers whose repeat window has matured

Sitter travel improvement

Phase 5 median travel time

versus

Phase 7 society-cluster travel time

Society health

Renewal interest

Committee satisfaction

Security-entry success

Resident complaint rate

Non-pet-resident complaint rate

12. Phase 8 go/no-go recommendation

Move to Phase 8 only when:

| Requirement | Target |
| --- | --- |
| Fully active pilot societies | 3–5+ |
| Society bookings | 100–300 |
| On-time rate | 95%+ |
| Report Cards delivered | 98%+ |
| Repeat-plan customers | 20–50 |
| Critical unresolved society complaints | 0 |
| Security-entry success | 97%+ |
| Customer rating | 4.6+ with meaningful sample |
| Positive contribution | Demonstrated in strongest cluster |
| Society renewal interest | Majority of active pilots |
| Sitter backup coverage | Stable |
| Privacy and access SOP | Operational |

Decision options

MOVE_TO_PHASE_8

DEEPEN_CURRENT_SOCIETY_CLUSTER

FIX_PARTNERSHIP_OPERATIONS

CHANGE_SOCIETY_SEGMENT

CHANGE_SERVICE_MIX

REPEAT_PHASE_7

Final approved recommendation

Run:

One city, 50 qualified society targets, 15–20 meetings, 5–10 signed pilots and 3–5 fully activated society partnerships over 60 days.

The operating position should be:

PetSaathi supports lawful pet ownership, responsible pet-care practices, controlled sitter access, transparent service proof and constructive coexistence between pet parents, other residents and society management.

The Phase 7 win condition is not:

50 society logos on the website

It is:

Several nearby societies

+

Active resident customers

+

Reliable local sitters

+

Repeat service plans

+

Fewer travel and access failures

+

Positive contribution

+

Low, well-managed complaints

Legal review remains necessary before using a common agreement or policy across different states and municipal jurisdictions.

A monthly AWBI, municipal and RWA-policy change watch would be useful before expanding this programme beyond the first city.

PetSaathi Phase 7 — Positioning and Society Service Model 🏢🐾

Executive decision

Your positioning is strong, but the official offer should distinguish pet-care services, veterinary coordination, partner-led events, and optional community features.

Recommended official positioning

Verified pet-care support for apartment communities—dog walking, in-home pet sitting, screened boarding, service updates, emergency veterinary coordination and pet-parent community support.

Committee-facing version

PetSaathi helps residents access safe, verified and reliable pet-care services while supporting organised sitter access, transparent service proof, responsive issue handling and smoother coexistence within the community.

Avoid

“We manage all pets in your society.”

That wording suggests that PetSaathi or the RWA controls residents’ animals. AWBI guidance states that RWAs and apartment-owner associations should not impose blanket bans on residents keeping pet dogs, while the Animal Birth Control Rules separately address the management of community animals.

1. Revised Phase 7 service model

| Service | Final status | Important condition |
| --- | --- | --- |
| Daily dog walking | Active—core | Approved-access sitter, Pet Profile and Report Card |
| Pet sitting at home | Active—core | Strong address, key and privacy controls |
| Controlled pet boarding | Restricted beta | Screened hosts, separate compatibility review |
| Emergency veterinary coordination | Active—coordination only | No diagnosis or treatment by PetSaathi |
| Grooming camp | Partner-led pilot | Qualified partner and premises approval |
| Vaccination camp | Registered-veterinarian partner only | Medical consent and veterinary records |
| Pet training workshop | Partner-led pilot | Humane methods and screened trainer |
| Lost-pet alert | Basic controlled feature | Time-limited, privacy-safe alert |
| Pet-parent community | Active—moderated | Not an emergency or medical channel |
| Society pet directory | Optional opt-in | Private, minimal and purpose-limited |

2. Daily dog walking

Decision: Active and primary society service

Dog walking should be the hero offering because it creates:

- Repeat demand

- Predictable service windows

- Same-sitter continuity

- High society-level booking density

- Easier package conversion

Required operating flow

Resident creates Pet Profile

↓

Dog-walking risk assessment completed

↓

Society-approved sitter assigned

↓

Payment verified

↓

Security entry prepared

↓

Sitter arrives and starts walk

↓

Basic GPS proof + media

↓

Pet returned safely

↓

Report Card delivered

Society-specific controls

Record:

- Approved gate

- Entry procedure

- Visitor pass requirement

- Permitted service timings

- Lift/common-area instructions

- Pet handover point

- Waste-cleanup expectations

- Replacement-sitter procedure

A society badge should state “Society access registered”, not “Society guarantees this sitter.”

3. Pet sitting at home

Decision: Active with stronger privacy controls

Pet sitting involves access to the resident’s home and therefore requires more protection than dog walking.

Required controls

- Exact address visible only after final assignment

- Access instructions released only when operationally necessary

- Key or smart-lock handover logged

- Entry and exit confirmation

- Private media storage

- Relevant emergency contacts

- Customer-defined home restrictions

- Medication tasks limited to approved instructions and sitter capability

- Access revoked immediately after completion or sitter removal

The society should not see:

- Apartment access codes

- Interior photographs

- Pet medication details

- Customer emergency contacts

- Private sitter notes

- Full service history

4. Controlled pet boarding

Decision: Restricted beta

Use the term:

Screened boarding beta

rather than implying that every society or sitter can provide boarding.

Boarding requirements

Pet Profile complete

↓

Current health declaration

↓

Vaccination records reviewed according to policy

↓

Other-animal compatibility reviewed

↓

Host and property approved

↓

Feeding, sleeping and medication instructions

↓

Emergency contact and veterinary plan

↓

Meet-and-greet where required

↓

Payment/deposit

Boarding host controls

- Maximum pet capacity

- Resident-animal information

- Safe separation area

- Escape prevention

- Feeding separation

- Cleaning process

- Emergency transport plan

- Local veterinarian

- Daily Report Cards

- Backup host or alternative-care plan

- Property-owner/society permission where applicable

Do not operate boarding from society common areas.

Premises, trade, animal-welfare and local municipal requirements can differ by city and state, so every boarding location needs local legal and operational review before activation.

5. Emergency veterinary coordination

Decision: Active, but rename carefully

Use:

Emergency veterinary coordination

Avoid:

“Emergency veterinary treatment by PetSaathi.”

PetSaathi may:

- Display verified veterinary contacts

- Contact the owner

- Contact an emergency clinic

- Arrange transport through an approved provider

- Share authorised pet information

- Record the emergency timeline

- Assist with owner spending authorisation

- Coordinate sitter handover

PetSaathi should not:

- Diagnose a condition

- Prescribe medication

- Change medication doses

- Promise ambulance availability without a contracted provider

- Guarantee veterinary response time

- Represent support staff as veterinary professionals

The Indian Veterinary Council Act regulates veterinary practice, and the right to practise veterinary medicine is tied to registered veterinary practitioners, subject to limited statutory exceptions.

Emergency workflow

Concern detected

↓

Incident ticket created

↓

Owner contacted

↓

Registered veterinary partner contacted

↓

Transport or clinic instructions confirmed

↓

Authorisation recorded

↓

Outcome and records linked to booking

6. Grooming camps

Decision: Partner-led pilot

PetSaathi should organise and coordinate the event, while a screened grooming provider performs the service.

Required controls

- Written society permission

- Groomer identity and business verification

- Service menu and pricing

- Resident consent

- Pet health and behaviour declaration

- Hygiene and equipment plan

- Water, electricity and waste-disposal plan

- Appointment capacity

- Incident procedure

- Cancellation/refund rules

- No sedation by a groomer

- Veterinary escalation for health concerns

Recommended Phase 7 scope

Start with:

- Bathing

- Brushing

- Basic coat care

- Nail trimming where appropriate

- Ear-cleaning only within partner competence

Avoid complex or medically sensitive procedures during the initial pilot.

7. Vaccination camps

Decision: Registered-veterinarian partner only

PetSaathi should act as:

Event coordinator

+

Booking and communication platform

+

Record-delivery facilitator

The veterinary partner remains responsible for clinical decisions and vaccine administration.

Required controls

- Registered veterinary practitioner

- Veterinary registration details checked

- Owner consent

- Pet identity confirmation

- Current medical-history questions

- Vaccine name

- Batch and expiry information

- Administration date

- Next-due date

- Veterinary certificate

- Storage and handling under veterinary-partner procedures

- Adverse-event escalation

- Emergency equipment and contact plan

- Waste and sharps disposal by the appropriate partner

The Veterinary Council of India maintains the governing professional framework and code of conduct for registered veterinary practitioners.

Do not advertise:

“All pets must be vaccinated at the PetSaathi camp.”

Participation should be voluntary unless a separate lawful service requirement applies.

8. Pet training workshops

Decision: Partner-led educational programme

Initial workshops may cover:

- Basic leash handling

- Recall foundations

- Puppy socialisation

- Separation preparation

- Enrichment

- Safe introductions

- Dog-body-language education

- Responsible common-area behaviour

Partner screening

Record:

- Trainer identity

- Training experience

- Methods used

- Species and behaviour scope

- References

- Incident history

- Insurance where available

- Prohibited methods

- Escalation to veterinarian or qualified behaviour professional

Safety rules

Do not permit:

- Physical cruelty

- Fear-based public demonstrations

- Unsupervised dog-to-dog mixing

- Guaranteed behaviour “cures”

- Medical diagnosis

- Automatic breed-based judgement

- Group sessions without compatibility controls

9. Lost-pet alert

Decision: Basic controlled feature

This can provide strong society-level value, but it creates privacy and misuse risks.

Alert fields

Alert ID

Pet name

Current photograph

Species and description

Last-seen society area

Last-seen time

Safe approach instructions

Owner-approved contact method

Alert status

Expiry time

Privacy protections

Do not publish:

- Full apartment number

- Owner’s private phone number by default

- Detailed home-access information

- Pet medical records

- Permanent public location history

Use:

- Masked contact

- In-app response

- Society security contact

- Time-limited alert link

Status flow

DRAFT

ACTIVE

SIGHTING_REPORTED

OWNER_CONTACTED

FOUND

EXPIRED

CANCELLED

FALSE_REPORT_REVIEW

Critical boundary

The lost-pet feature must not be used to identify and relocate community animals. Community-animal management is governed separately under the Animal Birth Control Rules and AWBI implementation guidance.

10. Pet-parent community

Decision: Active with moderation

Recommended functions:

- Society announcements

- Pet-care events

- Sitter introductions

- Veterinary-camp announcements

- Walking-group coordination

- Responsible pet-care education

- Lost-pet alerts

- Resident referrals

Do not use it as

- An emergency-support channel

- A veterinary diagnosis group

- A place for publishing resident complaints or allegations

- A public pet-risk list

- A replacement for structured incident reporting

- A channel for sharing private resident data

Moderation categories

- Harassment

- Personal-data disclosure

- Dangerous medical advice

- Animal cruelty

- False lost-pet reports

- Commercial spam

- Resident disputes

- Discriminatory pet/breed targeting

Every emergency message should redirect to:

Call PetSaathi support

or

Open an incident ticket

11. Society pet directory

Decision: Optional and opt-in only

A pet directory should never be created automatically from resident booking data.

The DPDP Act and the final DPDP Rules establish requirements around digital personal-data processing, including clear notices, security and staged statutory obligations. PetSaathi should therefore collect directory participation separately from service registration.

Safe directory entry

A resident may choose to display:

- Pet name

- Pet photograph

- Species

- General breed description

- Pet-parent display name

- Society block, optionally

- Friendly-with-dogs status as owner-reported

- Participation in pet events

Never display publicly

- Exact apartment number

- Personal phone number

- Medical conditions

- Bite history

- Risk classification

- Veterinary records

- Vaccination documents

- Emergency contacts

- Booking history

- Home-access information

Access levels

PRIVATE

VERIFIED_SOCIETY_RESIDENTS

PET_PARENT_GROUP_ONLY

HIDDEN

Required customer controls

- Explicit opt-in

- Preview before publication

- Edit

- Hide temporarily

- Delete

- Report misuse

- Separate marketing consent

12. Partner-service architecture

Create a partner registry:

society_service_partners

- id

- partner_type

- business_name

- city

- verification_status

- professional_registration

- insurance_reference

- service_scope

- agreement_start

- agreement_end

- incident_contact

- status

Partner types:

VETERINARY_CLINIC

VETERINARY_PRACTITIONER

GROOMER

TRAINER

BOARDING_HOST

PET_TRANSPORT

EMERGENCY_PROVIDER

Partner statuses

APPLIED

UNDER_REVIEW

APPROVED

PROBATION

ACTIVE

SUSPENDED

EXPIRED

REJECTED

PetSaathi should clearly disclose when a service is supplied by a third-party partner. Pricing, refund, grievance and service information must be displayed clearly; India’s e-commerce rules require relevant consumer information and handling of accepted refunds.

13. Final service priority

P0 — Launch with every active society

- Daily dog walking

- In-home pet sitting

- Emergency veterinary coordination

- Pet-parent community

- Lost-pet alert

- Society sitter-access system

- Report Cards and incident support

P1 — Add after stable initial operations

- Controlled boarding beta

- Same-sitter walking plans

- Grooming camp

- Training workshop

P2 — Add with professional partners and stronger controls

- Vaccination camp

- Society pet directory

- Advanced community events

- Pet transport partnerships

Vaccination can occur earlier when a fully verified veterinary partner and operational plan already exist, but PetSaathi should not rush medical events merely for society promotion.

14. What would be wrong in this model

Mistake 1 — Calling coordination “veterinary support”

Problem: Customers may believe PetSaathi provides medical advice.

Correction: Use “emergency veterinary coordination through registered partners.”

Mistake 2 — Automatically creating a pet directory

Problem: Residents may not want pet identity and household information shared.

Correction: Separate, explicit opt-in with minimal data.

Mistake 3 — Treating boarding like ordinary sitting

Problem: Boarding creates compatibility, property, health and capacity risks.

Correction: Restricted beta with separate approval.

Mistake 4 — Letting camps operate without a verified partner

Problem: PetSaathi may unintentionally become responsible for activities outside its competence.

Correction: Partner-led service with written role allocation.

Mistake 5 — Sharing all service data with the society

Problem: Society approval does not justify unrestricted access to resident data.

Correction: Aggregate society reporting by default.

Mistake 6 — Using the community group for incident handling

Problem: Evidence becomes fragmented and allegations become public.

Correction: Community message → structured complaint or incident ticket.

Final approved positioning

PetSaathi provides verified pet-care support for apartment communities, including dog walking, in-home pet sitting, screened boarding, service updates, emergency veterinary coordination and pet-parent community support. We help residents access reliable care while supporting organised sitter entry, clear service records, responsive issue handling and responsible coexistence within the society.

Final operating principle

PetSaathi owns the care-service workflow; qualified partners own specialist services; residents control their personal data; and the society receives only the access and aggregate information necessary to operate the partnership.

Simple explanation for professor

“Phase 7 will provide pet-care services inside selected apartment societies. The main active services will be dog walking and home pet sitting. Boarding will remain a controlled beta because it needs more health, compatibility and property checks.

PetSaathi will provide emergency veterinary coordination, but it will not diagnose or treat animals. Medical services and vaccination camps will be conducted only through registered veterinary partners.

Grooming camps and training workshops will also be organised through verified partners. The lost-pet alert will help residents and security find an owner’s missing pet, but it will protect the owner’s private contact and apartment details.

The pet-parent community will support events, updates and referrals, but emergencies and serious complaints will always be recorded through the formal incident system.

A society pet directory will remain optional. Residents must separately choose whether their pet appears in it, and sensitive information such as medical records, bite history and exact apartment details will never be publicly displayed.

This approach gives residents convenient pet-care support without allowing the society or PetSaathi to control lawful pet ownership or expose private information.”

PetSaathi Phase 7 — Package 1: No-Fee Society Pilot 🏢🐾

Executive decision

The package is a strong entry offer for the first five societies, but the public name should be modified.

Recommended name

PetSaathi No-Fee Society Pilot

or:

Free Society Setup Pilot

Avoid advertising it simply as a “Free Society Pilot”, because the society pays no partnership fee but residents still pay for dog walking, pet sitting and other booked services. ASCI’s advertising code requires claims to be truthful and says something should not be described as “free” when the consumer must bear a direct cost other than limited delivery-type charges. The offer must therefore explain clearly what is free and what remains paid.

Correct headline

No setup or partnership fee for the society during the 15–30 day pilot. Residents pay only when they book an individual PetSaathi service.

1. Purpose of this package

The No-Fee Society Pilot is not intended to generate partnership revenue immediately.

Its purpose is to validate:

- Resident demand

- Society access procedures

- Local sitter availability

- Booking density

- Customer trust

- Repeat walking demand

- Operational complaints

- Society willingness to continue

The revenue model during the pilot is:

Society partnership fee: ₹0

Resident registration fee: ₹0

Pet Profile creation: ₹0

Individual care booking: Paid

Sitter payout: Per completed service

PetSaathi income: Margin from resident bookings

The package should be treated as a customer-acquisition and operating-validation programme, not unlimited free support.

2. Recommended package structure

| Feature | Included | Important boundary |
| --- | --- | --- |
| Society onboarding | Yes | One standard setup |
| Resident trial offer | Yes | One eligible offer per household |
| Society-approved sitter roster | Yes | Only active, relevant sitters |
| WhatsApp booking assistance | Yes | Resident-initiated or opt-in |
| Pet-care awareness poster | Yes | Standard co-branded asset |
| Pet-parent group introduction | Yes | Moderated, optional group |
| Society landing page/QR | Yes | Recommended addition |
| Basic monthly pilot summary | Yes | Aggregated data only |
| Society branding | Minimal | Logo/name only with permission |
| Dedicated on-site desk | No | Paid package later |
| Guaranteed dedicated sitter | No | Depends on availability |
| Unlimited emergency service | No | Coordination only |
| Free resident pet-care services | No | Bookings remain paid |
| Custom software development | No | Standard pilot configuration |
| Exclusivity | No | Not during first pilot |

3. What “free” includes

The society receives the following without a partnership or setup fee:

Society setup

PetSaathi will:

- Create the society account

- Record authorised committee and facility contacts

- Configure approved service hours

- Document gate-entry procedures

- Record replacement-sitter rules

- Set a pilot booking cap

- Create a society-specific booking link or QR code

Society sitter roster

PetSaathi will provide a limited list of sitters who are:

- Active on the platform

- Approved for relevant services

- Available in the society’s area

- Registered for society access where required

- Trained for their assigned service categories

Use the term:

Society access registered

Do not use:

Society guarantees this sitter

The society should receive only the information needed for gate and access administration—not full sitter identity documents, private records or unrelated platform information.

Resident awareness materials

The pilot may include:

- One digital poster

- One printable lobby poster

- One WhatsApp announcement

- One FAQ

- One safety/process overview

- One resident booking QR code

Basic pilot reporting

The committee may receive aggregated figures such as:

Residents registered

Booking requests

Completed services

On-time service rate

Average resident rating

Open society-access issues

Resolved society-level complaints

Individual Pet Profiles, medical details, private media, full GPS routes, emergency contacts and payment information should not be exposed through the society report. The DPDP Rules, 2025 were officially published with an enforcement timeline, so PetSaathi should build resident notice, purpose limitation, controlled access and retention into society onboarding.

4. Resident trial offer

Recommended offer

For dog walking:

First 30-minute dog walk at ₹99–₹149, including sitter verification details, service updates and a Pet Report Card.

Alternative pet-sitting offer:

First one-hour home pet-sitting visit at ₹199–₹299.

Do not provide every service free. A fully free care service can:

- Attract low-intent bookings

- Increase no-shows

- Reduce perceived trust

- Create sitter-compensation problems

- Make paid conversion harder to measure

Trial eligibility

Recommended conditions:

Verified society resident

One trial per household

One eligible pet

Complete Pet Profile

Service area active

Eligible sitter available

Advance payment completed

Not transferable

Subject to pilot booking cap

After-trial conversion

After a successful trial:

Report Card delivered

↓

Customer review requested

↓

Same-sitter option shown

↓

5-walk starter plan offered

↓

10-walk or monthly plan offered later

The trial should validate repeat demand, not remain an isolated discounted booking.

5. WhatsApp booking support

Approved use

WhatsApp may support:

- Resident registration link

- Booking assistance

- Payment reminders

- Sitter assignment notifications

- Service-start updates

- Report Card link

- Replacement updates

- Refund-status updates

Important controls

The society should not automatically add every resident to a PetSaathi WhatsApp group or share resident contact lists.

Use:

Society announcement

↓

Resident opens QR/link

↓

Resident receives privacy notice

↓

Resident opts in

↓

WhatsApp communication begins

The committee should not upload a resident database unless the necessary notice, authority and purpose have been properly established.

WhatsApp group boundary

The optional pet-parent group may be used for:

- Service announcements

- Pet-care events

- Sitter introductions

- Awareness content

- Lost-pet alerts

- General community coordination

It should not be used for:

- Medical diagnosis

- Public complaints against sitters

- Incident investigation

- Publishing risk classifications

- Sharing apartment access details

- Emergency response

Emergencies should move immediately into the formal support and incident workflow.

6. Pet-care awareness poster

Recommended content

The poster should explain:

Available services

- Dog walking

- In-home pet sitting

- Screened boarding beta, where available

- Emergency veterinary coordination

- Service updates and Report Cards

Trust controls

- Verified caregiver profiles

- Controlled society entry

- Pet Profile and care instructions

- Service evidence

- Support and incident escalation

Resident responsibilities

- Provide accurate behaviour and medical information

- Keep safe leash/harness equipment ready

- Inform PetSaathi of health changes

- Follow society cleanliness requirements

- Keep emergency contacts updated

Call to action

Scan to register your pet and book the society trial.

Messaging boundary

The poster must not suggest that PetSaathi:

- Controls all animals in the society

- Guarantees zero risk

- Replaces a veterinarian

- Can remove community animals

- Allows the society to prohibit lawful pet ownership

AWBI continues to publish official guidance for pet owners, caregivers, RWAs and apartment-owner associations. Society communication should support responsible coexistence rather than blanket pet-control language.

7. Pet-parent group introduction

Recommended introduction format

PetSaathi may conduct:

- A 30–45 minute online orientation

- A small society lobby session

- A sitter-introduction meeting

- A resident Q&A

- A dog-walking demonstration without unsafe group mixing

Suggested agenda

1. What PetSaathi provides

2. How sitters are reviewed

3. How residents create Pet Profiles

4. How booking and payment work

5. How service tracking works

6. What the Report Card contains

7. What happens if a sitter cancels

8. How incidents and emergencies are handled

9. Trial offer and repeat plans

10. Questions from residents

Important inclusion

The meeting should include non-pet-resident concerns where relevant:

- Entry control

- Common-area behaviour

- Waste cleanup

- Walking timings

- Complaint process

- Privacy

This helps position the pilot as a community convenience and safety programme rather than an exclusive pet-owner promotion.

8. Minimal society branding

Included

PetSaathi may provide:

PetSaathi × Green Meadows

Society Pilot

on:

- Resident poster

- Landing page

- WhatsApp announcement

- Pilot summary

- Society-specific QR page

Permission requirement

PetSaathi should obtain written approval before using:

- Society logo

- Society name in public advertising

- Committee-member testimonial

- Photographs of society premises

- Resident testimonials

- Claims that the society endorses or recommends PetSaathi

ASCI requires advertising claims and institutional references to be truthful and not misleading; references that create an unjustified advantage should have permission.

Not included

- Full custom visual identity

- Dedicated society app

- White-label platform

- Large physical banners

- Permanent on-site kiosk

- Custom campaign production

- Exclusive co-branding

These can belong to a future paid package.

9. Pilot duration

Recommended default

21 days

Allow a range of:

Minimum: 15 days

Default: 21 days

Maximum: 30 days

Why 21 days works

It provides enough time for:

- Resident announcement

- First bookings

- Report Card delivery

- Initial reviews

- Same-sitter repeat requests

- Five-walk-plan interest

- Committee feedback

A 15-day pilot may work for a high-intent society. A 30-day pilot is better where resident onboarding is slower.

Pilot phases

Days 1–3: Setup

- Society configuration

- Security briefing

- Sitter access registration

- Resident communication

- Landing page and QR launch

Days 4–14: Trial services

- First paid bookings

- Daily monitoring

- Complaint handling

- Resident feedback

- Sitter-performance tracking

Days 15–21: Conversion and review

- Repeat-plan offers

- Committee review

- Pilot metrics

- Continuation proposal

10. Society eligibility

The free pilot should not be offered to every society.

Recommended qualification requirements

A society should have:

- A recognised committee or authorised facility manager

- One operational contact

- One security contact

- A viable number of interested pet parents

- Local sitter supply

- Clear entry rules

- Willingness to distribute the resident opt-in link

- Agreement to the basic incident and access process

Suggested demand threshold

Before activation, aim for either:

10+ interested pet-parent households

or:

5+ likely paid trial bookings

A society with no resident interest should remain in the lead pipeline rather than consuming setup resources.

11. Recommended first-five rollout

Do not activate all five societies on the same day.

Safer sequence

Society 1

↓

First 5–10 services reviewed

↓

Society 2

↓

Operational corrections

↓

Societies 3–5 launched as a cluster

Select societies that are geographically close enough to share sitter capacity and backup coverage.

First-five selection mix

A useful pilot group could include:

- Two large premium societies

- Two medium family-oriented societies

- One smaller high-pet-density society

The purpose is to learn which society profile produces the best conversion and operational density.

12. Pilot economics

Example: one society

Assume:

15 paid trial dog walks

Average customer price: ₹129

Total GMV: ₹1,935

Average sitter payout: ₹90

Total sitter payouts: ₹1,350

Payment/support cost: ₹180

Pre-acquisition contribution: ₹405

Add pilot acquisition costs:

Design and poster allocation

Operations setup

Security training

Resident orientation

Discount subsidy

Support time

The first pilot may be unprofitable. That is acceptable when it generates evidence and repeat plans.

Stronger economic outcome

Suppose five residents purchase ten-walk plans at ₹1,499:

Plan GMV: ₹7,495

If the gross platform margin is approximately 30%:

Gross platform margin: roughly ₹2,249

before support and acquisition costs

The key commercial metric is:

Contribution after resident conversion and actual service delivery—not the number of people joining the WhatsApp group.

13. Pilot success metrics

Resident funnel

Society residents reached

↓

Landing-page visits

↓

Opt-in registrations

↓

Pet Profiles completed

↓

Trial booking started

↓

Payment completed

↓

Service completed

↓

Review submitted

↓

Repeat booking or plan

Recommended minimum targets per society

| Metric | Minimum target |
| --- | --- |
| Opt-in resident leads | 15–30 |
| Completed Pet Profiles | 10+ |
| Paid pilot bookings | 5–10 |
| Completed-service rate | 90%+ |
| On-time service rate | 95%+ |
| Report Card delivery | 98%+ |
| Average rating | 4.5+ |
| Repeat interest | 25%+ |
| Critical unresolved incidents | 0 |
| Security-entry failures | Below 5% |
| Committee continuation interest | Yes |

Pilot outcome classifications

Convert to paid partnership

Use when:

- Resident demand exists

- Operations are stable

- Repeat demand is visible

- Committee wants continued support

Continue no-fee testing briefly

Use when:

- Demand exists

- Sample is too small

- One fixable operational issue remains

Pause

Use when:

- No resident demand

- Society does not support access

- Local sitter supply is inadequate

- Complaints are unresolved

- Committee expectations are incompatible

14. Pilot agreement

Even a free pilot needs a short written agreement or memorandum.

Required terms

Pilot start and end date

No partnership/setup fee

Residents pay for booked services

Active services

Resident offer

Booking cap

Society responsibilities

PetSaathi responsibilities

Security-entry process

Data-sharing limits

Brand-use permission

Complaint and incident contacts

Termination rights

No automatic renewal

No exclusivity

Society responsibilities

The society should:

- Nominate authorised contacts

- Permit approved communication

- Explain gate procedures

- Support registered sitter access

- Notify PetSaathi of access-policy changes

- Avoid sharing resident data without proper process

- Route service complaints through the agreed channel

PetSaathi responsibilities

PetSaathi should:

- Maintain sitter records

- Control individual assignments

- Collect resident payments

- Provide service updates

- Handle replacements and incidents

- Protect resident data

- Provide aggregate pilot reporting

- Remain responsible for its service operations

15. What is wrong in the original package

Problem 1 — “Free” is ambiguous

Correction

Say:

No society setup or partnership fee. Resident bookings are paid.

Problem 2 — “Verified sitter list” may expose too much data

Correction

Provide an active society-access roster with minimum necessary fields.

Problem 3 — WhatsApp support could become unlimited manual booking work

Correction

Define support hours, supported requests and escalation channels.

Problem 4 — No demand threshold

Correction

Require minimum resident interest before full setup.

Problem 5 — No booking cap

Correction

Set a pilot cap based on local sitter capacity.

Problem 6 — No conversion plan

Correction

Use trial → repeat booking → five-walk plan → monthly programme.

Problem 7 — Free pilot may continue indefinitely

Correction

Use a fixed end date, one review and an explicit continuation decision.

Final approved package

PetSaathi No-Fee Society Pilot

Best for

The first five qualified societies in one city cluster.

Duration

15–30 days, with 21 days recommended.

Society price

Setup fee: ₹0

Pilot partnership fee: ₹0

Automatic renewal: No

Resident price

Residents pay only for the individual services they book.

Included

- Society onboarding

- Society access configuration

- Resident trial offer

- Society-access sitter roster

- WhatsApp booking assistance

- Society landing page and QR

- Basic awareness materials

- Pet-parent introduction

- Minimal approved co-branding

- Aggregated pilot report

Revenue

PetSaathi earns from completed resident bookings and subsequent walking or sitting plans.

Main success condition

The pilot should create paid services, high resident satisfaction and repeat demand—not merely registrations or WhatsApp-group members.

Simple explanation for professor

“The first society package will be a no-fee pilot for the first five qualified apartment societies.

The society will not pay any setup or partnership fee for approximately 15 to 30 days. However, resident pet-care services will not be completely free. Residents will pay when they book dog walking or pet sitting, usually with a discounted first-service offer.

PetSaathi will configure the society, document security-entry rules, provide an approved sitter roster, create a QR booking page, share awareness material and introduce the service to pet parents.

Residents will register voluntarily rather than the society sharing their private contact list. The society will receive only aggregate results such as the number of completed services and the on-time rate. It will not receive individual medical, payment or GPS information.

The pilot will have a fixed booking cap and end date. After the pilot, PetSaathi will review paid bookings, customer ratings, repeat demand, entry issues and complaints. Successful societies can then move to a paid or long-term partnership package.”

etSaathi Phase 7 — Package 2: Basic Society Partner 🏢🐾

Executive decision

The Basic Society Partner package is commercially sensible after a successful pilot, but two parts need correction:

- The ₹5,000–₹15,000 monthly range should be tied to society size, active pet-parent demand, support intensity and reporting needs.

- Replace the vague phrase “plus commission on bookings” with a clearly defined commercial model.

Recommended public positioning

A managed pet-care partnership for apartment communities, including a society-specific resident portal, local sitter access, priority matching, resident benefits, monthly operational reporting and dedicated support.

Recommended commercial wording

Society partnership fee: ₹5,000–₹15,000 per month, plus applicable taxes. Residents pay separately for the pet-care services they book. PetSaathi earns its standard platform margin from completed bookings.

Do not make it appear that the society pays a monthly fee and an undefined extra commission on every resident booking.

Industry providers themselves note that society-platform pricing depends on community size, modules, integrations and support requirements. Dedicated onboarding, security-team training and operational support also create real delivery costs, so a single flat price for every society would not be sustainable.

1. Who should receive this package?

The Basic Society Partner package should be offered only after a society has demonstrated:

Successful pilot

↓

Resident demand

↓

Stable sitter supply

↓

Repeat-booking interest

↓

Working gate-access process

↓

Manageable complaint volume

Minimum qualification criteria

Recommended requirements:

- At least 10 completed pilot services

- At least 10–20 registered pet-parent households

- Resident rating of approximately 4.5 or higher

- No unresolved critical incident

- Working security-entry procedure

- At least two eligible local sitters

- Committee or facility-manager approval

- Evidence of repeat-booking demand

A signed society agreement without active resident demand should not automatically qualify for a paid monthly package.

2. Correct package structure

| Feature | Final treatment |
| --- | --- |
| Society-specific landing page | Included |
| Resident benefit or discount | Included with funding limits |
| Priority sitter matching | Included, subject to eligibility and availability |
| Monthly pet-care report | Included as aggregate reporting |
| Emergency support contact | Included as coordination support |
| Dedicated WhatsApp support | Included with defined hours and SLA |
| Society access roster | Add |
| Society operations contact | Add |
| Incident escalation workflow | Add |
| Quarterly resident awareness activity | Conditional by tier |
| Custom software development | Not included |
| Guaranteed sitter availability | Not included |
| Unlimited 24/7 support | Not included |
| Individual resident data report | Not included |

3. Recommended pricing tiers

The original ₹5,000–₹15,000 range is reasonable only when divided into clear service levels.

Tier A — Basic Lite

Recommended price

₹5,000 per month plus applicable taxes

Suitable for

- Approximately 100–250 homes

- Up to 25 active pet-parent households

- One tower or a simple access process

- Limited monthly booking volume

- Standard business-hours support

Included

- Society landing page

- QR booking link

- Resident benefit code

- Local sitter-access roster

- Monthly aggregate report

- WhatsApp support during published hours

- One society operations contact

- Standard emergency escalation contact

- Standard co-branded communication material

Not included

- Dedicated on-site staff

- Custom integrations

- Large resident events

- Guaranteed backup sitter

- 24/7 non-emergency support

Tier B — Basic Standard

Recommended price

₹9,000–₹10,000 per month plus applicable taxes

Suitable for

- Approximately 251–600 homes

- 25–60 active pet-parent households

- Multiple towers

- Recurring walk plans

- Moderate support and access-management requirements

Included

Everything in Basic Lite, plus:

- Named PetSaathi operations owner

- Priority support queue

- Monthly committee review call

- Enhanced society report

- Sitter punctuality and access reporting

- Priority backup-candidate generation

- One resident awareness session per quarter

- Society-specific walking-plan campaign

- Issue and complaint dashboard summary

This should be the default recommended package for most active societies.

Tier C — Basic Plus

Recommended price

₹15,000 per month plus applicable taxes

Suitable for

- More than 600 homes

- Large multi-tower communities

- High pet-parent density

- More complex security procedures

- Higher support and reporting expectations

- Several active sitter schedules

Included

Everything in Standard, plus:

- Extended support coverage

- Multi-tower sitter-access configuration

- Enhanced continuity and backup planning

- Quarterly society performance presentation

- Two resident campaigns or events per quarter

- Custom service-window configuration

- Deeper locality and sitter-capacity reporting

- Faster P1 operational escalation

- Controlled boarding or partner-event coordination where enabled

Still excluded

- Medical treatment

- Guaranteed emergency transport

- Unlimited on-site staff

- White-labelled software

- Custom development

- Unlimited marketing campaigns

4. Society-specific landing page

Decision: Approve

The page should be more than a generic marketing page with the society name inserted.

Recommended structure

Society name and approved co-branding

↓

Available services

↓

Resident benefit

↓

Approved-access sitter profiles

↓

How booking works

↓

Trust and safety controls

↓

Emergency coordination explanation

↓

Pricing and policies

↓

Book service CTA

Suggested page sections

Hero section

Trusted pet-care support for Green Meadows residents

Book verified dog walkers and pet sitters with service updates, Report Cards and responsive support.

Society-specific information

- Active services

- Supported service hours

- Active locality

- Society entry procedure

- Resident pricing

- Trial or partner benefit

- Support contact

- Cancellation and refund summary

Trust information

- Identity verification status

- Training badges

- Society-access registration

- Service permissions

- Customer ratings

- Completed booking count

Important wording

Do not say:

“Guaranteed sitter available.”

Use:

Priority matching with eligible local sitters, subject to availability and care requirements.

Marketing claims should remain legal, honest and truthful, including across websites, SMS, emails, posters and promotional material.

5. Resident discount

Decision: Approve with limits

A resident discount should have:

- Clear funding source

- Defined validity

- Usage limit

- Eligible services

- Non-transferability rule

- Minimum booking value where applicable

- Exclusion from other offers where necessary

Recommended resident benefits

Option A — First-booking benefit

₹100 off the first eligible service

Option B — Society package pricing

5 dog walks at a society-specific rate

10 dog walks at a society-specific rate

Option C — Priority benefit

Free first meet-and-greet

or

Priority same-sitter request

A non-price benefit can protect margins better than permanent discounting.

Recommended rule

Do not provide an unlimited permanent percentage discount.

Instead:

First service offer

↓

Five-walk starter plan

↓

Ten-walk or monthly plan

↓

Loyalty benefit based on actual repeat use

Discount transparency

Resident checkout should show:

Standard service price: ₹199

Society partner benefit: −₹30

Final payable amount: ₹169

Do not inflate the displayed standard price merely to create an artificial discount.

6. Priority sitter matching

Decision: Approve with precise definition

Priority matching must mean:

PetSaathi reviews the request before ordinary non-priority requests and searches the approved local sitter pool using service eligibility, Pet Profile controls, availability, travel time and reliability.

It must not mean:

- Guaranteed sitter

- Guaranteed preferred sitter

- Automatic highest-rated sitter

- Safety checks bypassed

- Immediate booking confirmation

- Unlimited replacement

Correct priority-matching order

Service permission

↓

Pet and handling compatibility

↓

Safety status

↓

Availability

↓

Travel feasibility

↓

Society access status

↓

Workload

↓

Reliability ranking

↓

Customer preference

Suggested priority SLA

| Booking type | Initial matching target |
| --- | --- |
| Future standard request | Within 2 business hours |
| Next-day request | Within 30–60 minutes |
| Same-day request | Within 15–30 minutes |
| Active replacement | Immediate operational review |

These should be service targets, not absolute contractual guarantees unless PetSaathi has sufficient supply.

Capacity rule

Priority access should remain subject to:

Active sitter capacity

Daily booking cap

Service area

Pet risk controls

Society access approval

7. Monthly pet-care report

Decision: Approve as aggregate reporting

The society report should help the committee understand programme performance without exposing private resident information.

Recommended report sections

Programme activity

Registered pet-parent households

Booking requests

Paid bookings

Completed services

Cancelled services

Active repeat plans

Service reliability

On-time service rate

Report Card completion

Sitter replacement count

Security-entry success

Support response performance

Resident experience

Average rating

Review response rate

Repeat-booking rate

Common service requests

Aggregate complaint count

Safety and operations

Operational exceptions

Society-access issues

Resolved society-level incidents

Open society-level corrective actions

Commercial summary

Where contractually appropriate:

Resident service GMV

Society programme fee

Discount funding

Aggregate refunds

Information not to include

- Resident names

- Flat numbers

- Phone numbers

- Pet medical conditions

- Bite histories

- Individual risk classifications

- Emergency contacts

- Individual GPS routes

- Private media

- Detailed complaint allegations

- Payment credentials

The DPDP Act recognises individuals’ interest in protecting their digital personal data, and the final DPDP Rules were published in November 2025 with staged commencement provisions. Society reporting should therefore follow data minimisation, purpose limitation and controlled access.

8. Emergency support contact

Decision: Approve, but describe it as coordination

Use:

PetSaathi emergency escalation and veterinary coordination contact

Do not use:

“PetSaathi emergency vet service”

unless PetSaathi actually employs or contracts qualified veterinary professionals for the advertised service.

Included support

PetSaathi may:

- Receive an urgent service report

- Contact the pet owner

- Contact the saved emergency person

- Contact the listed veterinary clinic

- Coordinate an approved transport option

- Create an incident ticket

- Help share authorised pet information

- Keep the society security team informed where necessary

Not included

PetSaathi does not:

- Diagnose animals

- Prescribe medication

- Change medication dosage

- Guarantee clinic availability

- Guarantee ambulance availability

- Make owner financial decisions without authority

Emergency availability

Separate:

Active-service emergency support

Available during an active PetSaathi service

General resident veterinary coordination

Available during published support hours

or through approved partner arrangements

Do not imply continuous 24/7 support unless staffing and partners genuinely support it.

9. Dedicated WhatsApp support

Decision: Approve with defined boundaries

“Dedicated” should mean a society-specific support entry point or routing code—not necessarily one employee permanently assigned to one society.

Recommended model

Society WhatsApp number

↓

Resident selects society or booking

↓

Request categorised

↓

Support queue created

↓

SLA and owner assigned

Support categories

| Category | Suggested response target |
| --- | --- |
| Active-service emergency | Immediate |
| Active-service problem | Under 5–10 minutes |
| Booking question | Under 30 minutes |
| Payment question | Under 1 hour |
| Refund/cancellation | Same working day |
| General enquiry | Same working day |

WhatsApp support should handle

- Registration help

- Booking help

- Payment status

- Sitter assignment questions

- Service updates

- Replacement communication

- Report Card access

- Refund-status enquiries

It should not become

- An unstructured incident database

- A veterinary-advice service

- An unlimited committee chat

- A public sitter-complaint channel

- An unofficial payment method

- A place to share apartment access codes permanently

NoBrokerHood publicly describes society onboarding, staff training, resident-query handling and an assigned operational person as part of its support model, which illustrates why dedicated society support must be priced and capacity-managed rather than offered without limits.

10. Missing feature: society access roster

Add this to the package.

The committee or security team should have access to a limited active roster containing:

Sitter display name

Photograph

PetSaathi sitter ID

Permitted service

Access status

Validity period

Emergency PetSaathi contact

Do not provide:

- Full KYC documents

- Personal address

- Bank information

- Other customer assignments

- Private verification notes

- Detailed reliability history

Access states

PENDING_REGISTRATION

ACTIVE

TEMPORARILY_PAUSED

EXPIRED

REVOKED

When a sitter is removed or replaced, access status should update promptly.

11. Missing feature: society operations owner

Each paid society should have:

Primary PetSaathi operations contact

Backup operations contact

Society committee contact

Facility/security contact

Emergency escalation contact

This is necessary because monthly fees should purchase operational accountability—not only a landing page.

12. Correct commercial model

Recommended model: retainer plus resident booking margin

Society pays

₹5,000–₹15,000 monthly partnership fee

plus applicable taxes

Residents pay

Published dog-walking, sitting or boarding prices

less any stated society benefit

PetSaathi earns

Monthly society fee

+

Normal service contribution from resident bookings

This is clearer than saying “plus commission.”

What should “commission” mean?

There are three possible meanings.

Model 1 — PetSaathi platform margin

PetSaathi collects the customer price, pays the sitter and retains a platform margin.

Example structure:

Resident service payment

− sitter payout

− payment/support cost

= PetSaathi contribution

This should be called:

Platform service margin

not “commission charged to the society.”

Model 2 — Society receives referral share

PetSaathi pays the society a percentage or fixed amount for eligible bookings.

This creates additional complexity around:

- Committee approval

- Accounting

- Resident-price transparency

- Conflict of interest

- Refund adjustments

- GST and invoicing

- Disclosure of incentives

This model is not recommended for the Basic package.

Model 3 — Society pays transaction commission

The society pays PetSaathi an additional amount for each booking.

This should generally be avoided because the society is already paying a monthly fee while residents pay for services.

13. Recommended booking economics

Use a contribution formula:

Monthly society contribution =

Monthly partnership fee

+

Contribution from completed resident bookings

− Resident discounts funded by PetSaathi

− Dedicated support cost

− Society onboarding allocation

− Partner or campaign cost

− Refund and recovery cost

Track separately:

- Gross merchandise value

- PetSaathi service revenue

- Sitter payouts

- Payment costs

- Partnership-fee revenue

- Direct support cost

- Contribution margin

Do not call total resident booking value “PetSaathi revenue.”

14. GST and invoicing

The contract should state whether quoted prices are:

Inclusive of applicable taxes

or:

Exclusive of applicable taxes

A registered supplier’s tax invoice must include relevant supplier and recipient details, the service description, total and taxable value, applicable tax rate and tax charged.

Recommended invoice separation:

Society invoice

Basic Society Partnership Fee — July 2026

Resident invoice

Dog Walking Service — Booking BK-1001

Do not combine society subscription fees and individual resident services into an unclear invoice.

The exact GST classification, place-of-supply treatment, registration position and any withholding implications should be confirmed with a chartered accountant before launch.

15. Consumer-facing transparency

Resident checkout and the landing page should clearly display:

- Provider identity

- Service description

- Full price

- Discount

- Taxes where applicable

- Payment method

- Cancellation policy

- Refund policy

- Complaint contact

- Expected service timing

- Whether the service is delivered by PetSaathi or a partner

The Consumer Protection (E-Commerce) Rules impose duties around providing information relating to returns, refunds, exchanges, payments, grievance redressal and other transaction terms.

16. Recommended contract term

Initial paid term

Three months

This gives enough time to measure:

- Repeat plans

- Sitter performance

- Support workload

- Resident conversion

- Society complaint patterns

- Contribution margin

Renewal options

Month-to-month

or

Six-month renewal

or

Annual partnership with discount

Avoid locking the first partner societies into long annual agreements before the service model is proven.

Recommended notice

30-day termination notice

Immediate suspension should be allowed for:

- Safety obstruction

- Serious data misuse

- Non-payment

- Unauthorised branding

- Repeated access refusal

- Illegal or discriminatory service demands

17. Monthly package SLA

The package should contain a written service-level schedule.

| Area | Target |
| --- | --- |
| Landing-page availability | Reasonable production uptime target |
| Booking-support response | Under 30 minutes in support hours |
| Active-service issue | Under 5–10 minutes |
| P1 operational alert | Immediate acknowledgement |
| Monthly report | By an agreed monthly date |
| Sitter-access update | Same working day |
| Refund-status response | Same working day |
| Critical incident escalation | Immediate |

Clearly distinguish:

- Response time

- Mitigation time

- Final resolution time

A support response does not mean the underlying issue has been resolved.

18. Renewal metrics

A society should remain on the paid package when it shows meaningful utilisation.

Recommended monthly health score

| Metric | Healthy result |
| --- | --- |
| Active paying households | 10+ |
| Completed bookings | 20+ |
| On-time rate | 95%+ |
| Report Card delivery | 98%+ |
| Average rating | 4.5+ |
| Repeat customers | Increasing |
| Security-entry failures | Below 3–5% |
| Unresolved critical complaints | 0 |
| Society continuation interest | Positive |
| Contribution after support costs | Positive or improving |

Low-usage response

When a society has fewer than five monthly bookings:

Review resident awareness

↓

Review pricing and service timing

↓

Run one activation campaign

↓

Measure for another month

↓

Downgrade, pause or terminate

Do not keep delivering dedicated support indefinitely to an inactive society.

19. What is wrong in the original package?

Problem 1 — Same price range without tiers

A small 120-home building and a 1,500-home multi-tower community cannot receive the same support for the same operational cost.

Correction

Price by:

- Number of homes

- Active pet households

- Booking volume

- Towers and gates

- Support hours

- Reporting requirements

- Integrations

- On-site activity

Problem 2 — “Commission” is undefined

It is unclear whether the society, resident, sitter or PetSaathi pays it.

Correction

Use:

Monthly society fee plus PetSaathi’s standard service margin from resident bookings.

Problem 3 — Resident discount can destroy margin

Correction

Use a limited, budgeted resident benefit rather than unlimited discounting.

Problem 4 — Priority matching may sound guaranteed

Correction

State:

Priority search among eligible and available local sitters.

Problem 5 — Dedicated WhatsApp can become unlimited work

Correction

Define:

- Support hours

- Response targets

- Included scope

- Emergency channel

- Escalation

- Fair-use limits

Problem 6 — Monthly reports may expose private data

Correction

Provide aggregate reporting by default.

Problem 7 — No operational deliverable

A landing page and discount alone do not justify a ₹15,000 monthly fee.

Correction

Include:

- Operations owner

- Access roster

- SLA

- Monthly review

- Alert handling

- Society-level reporting

- Resident activation support

Final approved package

PetSaathi Basic Society Partner

Best for

Societies that have completed a successful no-fee pilot and demonstrated recurring resident demand.

Monthly pricing

| Society profile | Recommended price |
| --- | --- |
| Basic Lite | ₹5,000 + applicable taxes |
| Basic Standard | ₹9,000–₹10,000 + applicable taxes |
| Basic Plus | ₹15,000 + applicable taxes |

Resident services

Residents continue to pay for the individual dog-walking, pet-sitting or boarding services they book.

PetSaathi revenue

Monthly society partnership fee

+

Standard service contribution from completed bookings

Included

- Society-specific landing page

- Resident partner benefit

- Priority eligible-sitter matching

- Active society-access sitter roster

- Monthly aggregate pet-care report

- Emergency coordination contact

- Dedicated WhatsApp support queue

- Named PetSaathi operations owner

- Complaint and incident escalation

- Monthly programme review

- Minimal approved co-branding

Not included

- Guaranteed sitter availability

- Veterinary diagnosis or treatment

- Unlimited 24/7 support

- White-labelled platform

- Unlimited resident campaigns

- Custom software development

- Automatic society access to private resident information

Recommended minimum term

Three months after pilot conversion

Main success condition

The partnership should increase paid bookings, repeat plans and local service reliability while reducing travel, entry failures and manual society coordination.

Simple explanation for professor

“The second package is for societies that have completed the free pilot and shown real resident demand.

The society will pay a monthly partnership fee between ₹5,000 and ₹15,000 depending on the number of homes, active pet parents, support needs and reporting complexity. Residents will still pay separately for the dog walking or pet sitting services they book.

PetSaathi will create a society-specific landing page, provide a resident benefit, maintain a local approved-access sitter roster and give booking requests priority among eligible sitters. Priority does not mean guaranteed availability because safety, experience, location and schedule must still be checked.

The society will receive a monthly report showing aggregate bookings, on-time performance, ratings and access issues. It will not receive individual pet medical details, payment data, photographs or GPS routes.

A dedicated WhatsApp support queue and named operations owner will help residents and the society resolve booking, payment, replacement and service issues. Emergency support will mean coordination with the customer and veterinary contacts, not veterinary treatment by PetSaathi.

Instead of saying ‘plus commission on bookings,’ the clearer business mod

PetSaathi Phase 7 — Package 3: Premium Pet-Care Desk 🏢🐾✨

Executive decision

Approve Package 3 with modifications.

The package is appropriate for large premium gated communities, but the phrase “dedicated society pet-care coordinator” must be defined carefully.

At ₹15,000 per month, PetSaathi can realistically provide a named shared coordinator with defined support and on-site hours. It should not promise a full-time employee exclusively stationed at one society. A genuinely full-time on-site coordinator should use custom staffing-based pricing above the standard package range.

Recommended positioning

A managed pet-care desk for premium residential communities, combining resident support, scheduled dog-walking programmes, an approved caregiver pool, partner-led pet events, safety reporting and priority emergency coordination.

Society-management platforms operating in India commonly emphasise onboarding, staff and security training, ongoing support, dashboards and a named operational contact. This supports charging a management retainer only when PetSaathi delivers real operational ownership—not merely a landing page and WhatsApp number.

1. Correct commercial structure

Society pays

Monthly Premium Pet-Care Desk retainer:

₹15,000–₹50,000

+ applicable taxes

Residents pay

Residents separately pay for:

- Dog walks

- Pet-sitting visits

- Boarding

- Grooming appointments

- Training sessions

- Other individually booked services

PetSaathi earns

Monthly society management fee

+

Platform contribution from completed resident bookings

+

Clearly disclosed partner-event coordination fees, where applicable

Use “service-booking revenue” or “platform service margin”, not an undefined “commission.”

The agreement and resident checkout should clearly show service descriptions, prices, cancellation terms, refund policies and grievance contacts. India’s Consumer Protection (E-Commerce) Rules require e-commerce entities to disclose relevant transaction, payment, refund and grievance information and to process accepted refund requests.

2. Recommended package tiers

Tier A — Premium Desk Essential

Price

₹15,000–₹20,000 per month plus applicable taxes

Best for

- Approximately 300–600 homes

- 25–50 active pet-parent households

- One or two gates

- Moderate monthly booking volume

- A society that has completed the Basic Partner stage

Coordinator model

- Named shared society coordinator

- Dedicated WhatsApp routing

- Approximately 4–8 scheduled on-site hours per month

- Monthly committee review

- Backup coordinator during leave

Included

- Regular dog-walking slots

- Society-access walker roster

- Resident support queue

- One partner-led event per quarter

- Lost-pet alert system

- Monthly safety and operations report

- Priority active-service escalation

- Society-specific resident portal

- Repeat walking-plan promotion

Tier B — Premium Desk Managed

Price

₹25,000–₹35,000 per month plus applicable taxes

Best for

- Approximately 600–1,200 homes

- 50–100 active pet-parent households

- Several towers or access points

- Multiple recurring walk schedules

- Higher reporting and support requirements

Coordinator model

- Named coordinator responsible for the society

- Defined weekly availability

- Approximately 12–20 on-site hours per month

- Scheduled pet-parent help desk

- Facility and security coordination

- Monthly operations meeting

Included

Everything in Essential, plus:

- Multiple walking-slot groups

- Enhanced backup-sitter planning

- Two resident activities per quarter

- Priority grooming or veterinary-partner camps

- Society-level complaint dashboard

- Sitter punctuality and access analytics

- Higher-priority replacement workflow

- Regular pet-parent community sessions

- Quarterly safety review

Tier C — Premium Resident Concierge

Price

₹40,000–₹50,000 per month plus applicable taxes

Best for

- Large premium townships

- More than 1,200 homes

- High pet density

- Multiple gates, towers and facility teams

- High recurring booking volume

- Significant society-event programme

Coordinator model

- Named lead coordinator

- Defined extended weekly/on-site schedule

- Backup operational contact

- Multi-tower service planning

- Enhanced support SLA

- More frequent committee reporting

Included

Everything in Managed, plus:

- Multi-zone walking schedules

- Stronger peak-hour backup coverage

- Monthly pet-care activity or campaign

- Premium resident onboarding

- Enhanced monthly safety presentation

- Quarterly capacity and demand planning

- Partner-event calendar

- Faster society-level operational escalation

- Dedicated programme review with committee/facility team

Important boundary

A full-time exclusive on-site coordinator should not automatically be included at ₹50,000. It should be quoted separately based on salary, statutory employment costs, working hours, supervision, replacement coverage, travel, equipment and service scope.

3. Dedicated society pet-care coordinator

Decision: Approve with defined scope

The coordinator is the operational owner for the partnership—not a veterinarian, dog trainer, emergency responder or personal assistant for every resident.

Coordinator responsibilities

Resident support

- Explain PetSaathi services

- Help residents register

- Assist with Pet Profiles

- Explain packages and booking status

- Help residents access Report Cards

- Route refund and complaint requests

Society operations

- Coordinate sitter security registration

- Maintain the active-access roster

- Review walking-slot demand

- Monitor access failures

- Coordinate with the facility manager

- Provide aggregate programme reports

Service reliability

- Monitor high-priority bookings

- Review missing acknowledgements

- Trigger replacement workflows

- Track overdue Report Cards

- Escalate active-service problems

Partner activities

- Schedule grooming or vaccination camps

- Verify partner readiness

- Coordinate space and resident appointments

- Track event incidents and feedback

Coordinator must not

- Diagnose a pet

- Recommend unapproved medication

- Promise guaranteed veterinary availability

- Override Red-risk or safety decisions

- Approve refunds without finance authority

- Share resident information with the committee

- Assign unverified caregivers

- Accept cash outside the approved payment process

Coordinator availability

Publish clear service hours:

Regular resident support:

For example, 8:00 AM–8:00 PM

Active-service urgent escalation:

According to contracted coverage

Critical emergency:

Immediate routing to the defined emergency process

“Dedicated” should mean named responsibility and priority routing, not unlimited 24/7 access.

4. Regular dog-walking slots

Decision: Approve as a core premium feature

Regular slots should create predictable supply and repeat revenue.

Example:

| Slot | Capacity |
| --- | --- |
| 6:30–7:00 AM | 3 individual walks |
| 7:00–7:30 AM | 3 individual walks |
| 7:30–8:00 AM | 3 individual walks |
| 6:00–6:30 PM | 3 individual walks |
| 6:30–7:00 PM | 3 individual walks |

Important safety rule

These are scheduling windows—not automatic group walks.

Dogs should not be combined merely because they use the same slot. Shared walks require separate compatibility, handling and owner-consent controls.

Recurring-slot flow

Resident selects preferred days and time

↓

Pet profile and walking controls reviewed

↓

Preferred walker checked

↓

Individual future bookings created

↓

Credits reserved

↓

Reminders scheduled

↓

Backup coverage evaluated

Slot management should include

- Maximum sitter capacity

- Walking duration

- Handover buffer

- Society-entry buffer

- Sitter travel between towers

- Pet size and handling controls

- Same-sitter preference

- Substitute approval

- Public-holiday and festival rules

Customer promise

Use:

Reserved recurring time window with preferred-sitter continuity where availability permits.

Do not use:

Guaranteed same walker every day.

5. Verified walker pool

Decision: Approve

Use the term:

Society-approved-access walker pool

This represents access and platform verification—not a guarantee that risk is zero.

Walker eligibility

Each active walker should have:

- Identity verification status

- Relevant training

- Active service permission

- Society access registration

- Pet-size permissions

- Risk-control capabilities

- Availability

- Reliability status

- No active safety restriction

Society/security roster

The limited roster may show:

Walker display name

PetSaathi ID

Current photograph

Approved service

Access validity

Status

PetSaathi operations contact

Do not provide the society with:

- Full KYC documents

- Home address

- Bank details

- Raw police-verification documents

- Other customer bookings

- Detailed performance investigations

Advertising and partnership materials must use factual and substantiated verification claims. ASCI’s code requires advertising representations to be truthful and not misleading.

6. Grooming camps

Decision: Approve as partner-led events

The Premium package may include event coordination, but the groomer remains responsible for performing the grooming service.

PetSaathi responsibilities

- Screen the partner

- Publish services and prices

- Manage resident appointment slots

- Confirm society permissions

- Organise space and queue flow

- Collect feedback

- Route complaints

- Maintain event records

Grooming-partner responsibilities

- Bring trained staff and suitable equipment

- Maintain hygiene

- Follow handling instructions

- Refuse services beyond competence

- Avoid sedation

- Report safety concerns

- Dispose of waste appropriately

- Carry any locally required permissions or insurance

Recommended initial grooming scope

- Bathing

- Brushing

- Basic coat care

- Nail trimming where appropriate

- Basic hygiene services within partner competence

Do not include medical skin treatment or sedation-based grooming as ordinary camp services.

7. Vaccination camps

Decision: Approve only through registered veterinary practitioners

Vaccination is a veterinary clinical activity. PetSaathi should act as coordinator, while the registered veterinary practitioner controls assessment, consent, vaccine administration and medical records.

The Indian Veterinary Council Act regulates veterinary practice and provides for registers of veterinary practitioners. PetSaathi must verify the professional registration of the veterinary practitioner responsible for a camp.

Required controls

- Registered veterinary practitioner verified

- Clinic or veterinary-partner agreement

- Owner consent

- Pet identification

- Relevant health questions

- Vaccine name

- Batch and expiry details

- Administration date

- Next-due date

- Practitioner details

- Veterinary certificate

- Cold-chain responsibility assigned to partner

- Adverse-reaction procedure

- Sharps and medical-waste handling

- Emergency escalation

Important messaging

Use:

Vaccination camp conducted by a registered veterinary partner.

Do not use:

PetSaathi vaccination service.

Financial boundary

The monthly package may include coordination, but vaccines, clinical examinations and certificates may be billed separately by the partner or through a clearly disclosed PetSaathi marketplace transaction.

8. Lost-pet alert system

Decision: Approve as a controlled society feature

Alert flow

Owner reports pet missing

↓

Pet identity and alert verified

↓

Society security and opted-in residents notified

↓

Sightings submitted through controlled form

↓

Owner/support contacted

↓

Alert closed when pet is found

Alert information

May include:

- Pet name

- Current photograph

- Species and description

- Last-seen time

- Last-seen society area

- Safe approach guidance

- Masked contact or PetSaathi support link

Do not publish

- Exact home number

- Owner’s direct phone by default

- Medical records

- Full tracking history

- Permanent public link

- Family emergency contacts

Alert states

DRAFT

ACTIVE

SIGHTING_REPORTED

OWNER_CONTACTED

FOUND

EXPIRED

CANCELLED

FALSE_REPORT_REVIEW

The society pet directory and lost-pet alerts must remain opt-in and purpose-limited. India’s final DPDP Rules were published on November 14, 2025 with staged commencement provisions, so PetSaathi should implement clear notices, access restrictions, security and retention controls according to the provisions applicable at launch.

9. Society pet event

Decision: Approve with event limits

The package should define exactly how many events are included.

Recommended allowance

| Tier | Included event activity |
| --- | --- |
| Essential | One event per quarter |
| Managed | Two activities per quarter |
| Concierge | One activity or campaign per month |

Event options

- Pet-parent orientation

- Responsible dog-walking workshop

- Pet first-aid awareness with a veterinary partner

- Grooming camp

- Vaccination camp

- Trainer-led behaviour workshop

- Pet photography day

- Adoption-awareness event with an authorised organisation

- Lost-pet preparedness session

- Pet-parent community meet

Event safety plan

Every event should define:

- Capacity

- Registration

- Pet compatibility requirements

- Leash and equipment rules

- Separate waiting areas

- Water and shade

- Waste management

- Incident contact

- Veterinary escalation

- Partner responsibilities

- Weather fallback

Avoid unrestricted pet gatherings where unfamiliar animals are allowed to interact without controls.

10. Monthly safety report

Decision: Approve, but keep it aggregated

The report should help the committee improve society-level operations without exposing individual residents or sitters.

Recommended report

Programme summary

- Registered pet-parent households

- Active walking plans

- Completed services

- Service types

- Peak booking periods

Reliability

- On-time rate

- Median delay

- Report Card delivery

- Replacement events

- Entry success rate

- Support response performance

Safety

- Operational exceptions

- Incidents by severity

- Resolved society-access concerns

- Lost-pet alerts

- Overdue corrective actions

Community

- Events conducted

- Resident participation

- Aggregate feedback

- Common resident concerns

- Awareness material delivered

Capacity

- Active walkers

- Backup coverage

- Peak-slot utilisation

- Waitlisted requests

- Capacity recommendation

Do not include

- Resident names or flat numbers

- Detailed pet medical information

- Bite histories

- Full sitter disciplinary records

- Individual complaint allegations

- GPS routes

- Private photographs

- Emergency contacts

- Payment credentials

The monthly report should use role-based access and data minimisation. The society needs programme-level operational information, not full access to PetSaathi’s resident database.

11. Priority emergency support

Decision: Approve as priority coordination—not veterinary treatment

Included

- Priority support routing

- Immediate incident-ticket creation

- Owner and emergency-contact calls

- Veterinary-partner coordination

- Transport-partner coordination where contracted

- Society-security coordination

- Relevant Pet Profile information sharing with authorisation

- Booking and evidence timeline

- Post-event customer follow-up

Not included

- Medical diagnosis

- Medication prescription

- Guaranteed ambulance

- Guaranteed clinic admission

- Unlimited treatment cost

- Automatic spending authority

- PetSaathi staff performing clinical procedures

Suggested SLA

| Situation | Target |
| --- | --- |
| Critical active-service alert | Immediate acknowledgement |
| Owner contact attempt | Immediate |
| Veterinary-partner contact | As soon as incident is triaged |
| Society security notification | Where operationally necessary |
| Non-emergency resident query | Published support SLA |

Distinguish:

Response time

≠

Veterinary arrival time

≠

Final incident resolution

12. Pricing viability

Why ₹15,000 is not enough for full-time exclusivity

The monthly retainer must cover some combination of:

Coordinator time

Operations supervision

WhatsApp/support workload

Society setup

Security training

Monthly reporting

Events

Technology

Replacement management

Incident readiness

Travel

Administrative overhead

Therefore:

- ₹15,000–₹20,000: shared coordinator with limited on-site availability

- ₹25,000–₹35,000: named managed coordinator with regular on-site hours

- ₹40,000–₹50,000: enhanced concierge programme, but still not necessarily a full-time exclusive employee

- Full-time exclusive desk: custom commercial quotation

This pricing distinction is a business-model recommendation based on delivery scope. Society-management providers’ own descriptions show that onboarding, staff/security training, resident support and direct operational ownership are meaningful service components that need capacity and staffing.

13. Illustrative unit economics

The following model is hypothetical and should be replaced with actual Phase 7 data.

Managed package example

Society retainer:                    ₹30,000

50 monthly dog walks × ₹49 margin:   ₹2,450

20 package walks × ₹40 margin:         ₹800

10 pet-sitting services × ₹120:      ₹1,200

Partner coordination contribution:   ₹1,500

Total gross contribution:           ₹35,950

Estimated direct monthly programme costs:

Coordinator allocation:             ₹12,000

Support allocation:                  ₹4,000

On-site travel:                      ₹2,000

Reporting/admin:                     ₹2,000

Event allocation:                    ₹3,000

Technology/payment overhead:         ₹2,000

Estimated direct cost:              ₹25,000

Estimated contribution:             ₹10,950

Important conclusion

The retainer should fund baseline management. Booking volume should improve profitability—not subsidise a heavily underpriced “dedicated” desk.

14. Contract and billing rules

Recommended initial term

Three-month minimum following a successful pilot

For the highest tier, a six-month programme may be appropriate after the first review.

Contract should state

- Package tier

- Coordinator availability

- On-site hours

- Included events

- Support hours

- Active services

- Resident pricing model

- Emergency-coordination limits

- Data-sharing rules

- Branding permission

- Reporting schedule

- Termination

- Payment due date

- Additional charges

- Event cancellation

- Partner responsibilities

Invoicing

The society partnership fee and resident booking charges should be invoiced separately.

CBIC rules require tax invoices for taxable service supplies to contain prescribed information and generally require the invoice for services to be issued within 30 days of supply. The exact GST classification and tax treatment should be confirmed with a chartered accountant.

15. What is wrong in the original package?

Problem 1 — “Dedicated coordinator” is financially ambiguous

Correction

Define:

- Named coordinator

- Shared or exclusive

- Support hours

- On-site hours

- Backup coverage

- Maximum included workload

Problem 2 — Regular slots may be interpreted as guaranteed supply

Correction

Sell reserved time-window capacity, subject to pet compatibility, payment, sitter availability and operational limits.

Problem 3 — Camps are described as PetSaathi-delivered services

Correction

Grooming and vaccination camps should be partner-led, with clear professional responsibility.

Problem 4 — Emergency support sounds clinical

Correction

Use:

Priority emergency escalation and veterinary coordination.

Problem 5 — Monthly safety report could expose personal data

Correction

Deliver aggregated operational reporting with restricted access.

Problem 6 — Events have no frequency limit

Correction

Define quarterly or monthly allowances by tier.

Problem 7 — Booking revenue is unclear

Correction

State:

Residents pay for booked services; PetSaathi retains its disclosed platform service contribution.

Problem 8 — No capacity limit

Correction

Each package should define:

- Maximum active pet households

- Maximum monthly support volume

- Included events

- On-site coordinator hours

- Number of gates/towers

- Extra-work pricing

16. Recommended add-on pricing

These are proposed commercial amounts, not statutory rates.

| Add-on | Suggested treatment |
| --- | --- |
| Additional on-site coordinator block | Fixed hourly/day rate |
| Extra society event | ₹5,000–₹15,000 plus partner costs |
| Large vaccination camp | Custom partner quote |
| Additional tower/gate configuration | Monthly add-on |
| Extended support hours | Monthly add-on |
| Full-time exclusive coordinator | Custom staffing quote |
| Custom integration | Separate project fee |
| Printed campaign materials | At cost plus coordination |
| Emergency transport | Resident-paid/provider-priced |
| Dedicated hard-standby sitter | Booking-specific charge |

17. Premium package success metrics

Resident adoption

- Registered pet-parent households

- Active paying households

- First paid bookings

- Walking-plan conversion

- Plan-credit utilisation

- Same-sitter repeat rate

Service reliability

| Metric | Target |
| --- | --- |
| On-time service rate | 95%+ |
| Report Card delivery | 98%+ |
| Priority booking continuity | 90%+ |
| Security-entry success | 97%+ |
| Critical alert ownership | 100% |
| Unresolved critical incidents | 0 |

Desk performance

- Median support response

- Coordinator tickets resolved

- Repeat resident enquiries

- Event participation

- Committee satisfaction

- Monthly report delivered on time

- Admin minutes per booking

Commercial health

- Monthly society retainer

- Resident GMV

- Platform service contribution

- Coordinator cost

- Event cost

- Refund cost

- Net society contribution

- Renewal interest

18. Renewal and downgrade rules

Renew Premium Desk when

- 25+ active paying households

- Strong recurring-plan demand

- Positive programme contribution

- Society values the coordinator

- Events generate useful engagement

- Complaints are manageable

- Security-entry process works

- Committee wants continuation

Downgrade to Basic Partner when

- Booking activity is moderate

- On-site coordinator demand is low

- Events have weak participation

- Society uses mainly the portal and WhatsApp support

Pause or terminate when

- Society repeatedly blocks approved sitters

- Resident demand is absent

- Payment remains overdue

- Society requests unlawful or discriminatory pet restrictions

- Sensitive data is misused

- Safety procedures are obstructed

- The programme remains financially unsustainable

AWBI publishes guidance for pet owners, caregivers, RWAs and apartment associations. PetSaathi’s partnership should support responsible coexistence and should not be used to implement blanket pet bans or unlawful animal-control policies.

Final approved package

PetSaathi Premium Pet-Care Desk

Best for

Large, premium gated communities with demonstrated pet-parent demand, recurring booking density and complex society-access requirements.

Price

| Tier | Monthly fee |
| --- | --- |
| Premium Desk Essential | ₹15,000–₹20,000 + taxes |
| Premium Desk Managed | ₹25,000–₹35,000 + taxes |
| Premium Resident Concierge | ₹40,000–₹50,000 + taxes |
| Full-time exclusive desk | Custom quote |

Included

- Named pet-care coordinator

- Defined coordinator and support hours

- Regular walking-slot programme

- Approved-access walker pool

- Grooming and veterinary-partner camp coordination

- Lost-pet alert system

- Society pet events

- Monthly aggregate safety report

- Priority emergency escalation

- Society resident portal

- Dedicated WhatsApp routing

- Complaint and incident coordination

- Walking-plan and repeat-booking campaigns

Residents pay separately for

- Individual dog walks

- Pet-sitting visits

- Boarding

- Grooming services

- Veterinary services or vaccines

- Training appointments

- Transport and other partner services

Not included

- Guaranteed zero-risk care

- Guaranteed sitter availability

- Veterinary diagnosis or treatment by PetSaathi

- Unlimited events

- Unlimited 24/7 support

- A full-time exclusive coordinator at the standard lowest tier

- Society access to private resident records

- Automatic use of resident media for marketing

Final operating principle

The Premium Pet-Care Desk should be priced as a managed local operation—not as a collection of promotional features. The monthly retainer pays for coordination, access, support, reporting and service reliability; residents continue to pay for the care services they use.

Simple explanation for professor

“The Premium Pet-Care Desk is designed for large gated societies with many pet-owning families.

The society will pay between ₹15,000 and ₹50,000 per month depending on its size, number of pet parents, support hours, events and operational complexity. At the lower price, the coordinator will be shared and available for defined hours. A full-time coordinator working only for one society will require separate custom pricing.

The coordinator will help residents register, manage regular walking schedules, coordinate sitter access, monitor service problems and prepare the monthly society report.

Residents can book regular dog-walking slots from a verified local walker pool. These slots will improve repeat bookings, but the system will still check pet behaviour, sitter availability and safety before confirmation.

Grooming camps will be conducted through verified grooming partners. Vaccination camps will be conducted only by registered veterinary practitioners. PetSaathi will organise the camp but will not perform veterinary treatment.

The lost-pet alert will notify society security and opted-in residents while protecting the owner’s private information. Society events may include pet-care awareness, training workshops, grooming camps or veterinary-partner sessions.

The monthly safety report will show aggregate information such as completed services, punctuality, entry issues and incidents. It will not expose individual pet medical records, GPS routes or resident complaints.

Priority emergency support means that PetSaathi will quickly create an incident record, contact the owner and coordinate with veterinary or transport partners. It does not mean that PetSaathi provides veterinary diagnosis or guarantees an ambulance.”

PetSaathi Phase 7 — Package 4: Society Event & Camp Model 🎪🐾

Executive decision

Approve this package with important modifications.

The Event/Camp Model can generate many qualified pet-parent leads quickly, but PetSaathi should operate primarily as the:

Event organiser

+ booking platform

+ resident communication layer

+ partner-verification layer

+ payment and support coordinator

Specialist providers remain responsible for delivering specialist services:

- A registered veterinary practitioner controls health examinations, clinical advice and vaccination.

- A verified groomer performs grooming.

- A screened trainer conducts the training workshop.

- The sponsor funds or supports the event under a clearly disclosed commercial arrangement.

The recommended public name is:

PetSaathi Society Pet-Care Event & Camp Programme

This package may be sold independently or included as an add-on to the Basic Society Partner and Premium Pet-Care Desk packages.

1. Corrected event revenue model

| Event | Recommended commercial model |
| --- | --- |
| Pet health-check camp | Fixed coordination fee or fee per completed appointment |
| Grooming camp | Fixed partner fee or percentage of completed net service value |
| Vaccination camp | Fixed event-management fee; avoid incentives based on vaccine quantity |
| Pet-parent meet-up | Transparent sponsorship plus optional stall fees |
| Dog-training workshop | Ticket revenue split with trainer |
| Follow-up bookings | Normal PetSaathi service contribution |

Important correction

Avoid using only the word commission.

Every agreement should specify:

Who charges the resident

Who issues the invoice

Who delivers the service

What PetSaathi earns

What the partner earns

Who handles refunds

Who handles complaints

Who carries clinical or professional responsibility

Without this clarity, an event dispute can become a payment, consumer-support and liability problem.

2. Package purpose

This package has four business goals:

- Acquire opted-in pet-parent leads.

- Create trust through physical society presence.

- Generate direct event revenue.

- Convert attendees into recurring PetSaathi customers.

The real funnel is:

Society residents reached

↓

Event registrations

↓

Residents who attend

↓

Pet Profiles created

↓

Trial service booked

↓

Paid service completed

↓

Repeat walking or sitting plan

Event attendance alone is not business success.

3. Pet health-check camp

Decision: Approve only through a registered veterinary partner

A pet health-check camp may involve:

- Basic physical examination

- Weight and body-condition observation

- Dental or skin observations

- Vaccination-record review

- General preventive-care advice

- Referral for further examination

PetSaathi should not perform or market these as its own clinical services.

The Indian Veterinary Council Act regulates veterinary practice and gives registered veterinary practitioners the right to practise veterinary medicine. It also restricts veterinary practice by unregistered persons, subject to limited state-authorised minor services under registered-veterinarian supervision.

Recommended operating model

Resident registers pet

↓

Veterinary consent form completed

↓

Pet identity confirmed

↓

Registered veterinarian performs examination

↓

Veterinarian records findings

↓

Resident receives clinical summary or referral

↓

PetSaathi receives only permitted operational data

PetSaathi responsibilities

- Verify the veterinarian’s registration.

- Obtain society permission.

- Manage appointment slots.

- Provide resident notices.

- Control queues and waiting areas.

- Process bookings where contractually agreed.

- Route complaints to the correct provider.

- Maintain event and payment records.

- Offer follow-up PetSaathi services separately.

Veterinary partner responsibilities

- Clinical examination

- Clinical advice

- Medical records

- Prescription or treatment decisions

- Professional consent

- Clinical waste handling

- Emergency response relating to the examination

- Referral to a clinic where necessary

Recommended revenue model

Use one of these:

Fixed event coordination

Veterinary partner pays PetSaathi:

₹5,000–₹15,000 proposed coordination fee

Completed appointment fee

₹100–₹300 proposed fee

per completed, verified appointment

Society-sponsored camp

Society or sponsor pays event cost

Residents receive free or subsidised checks

Veterinarian remains clinically responsible

A fixed coordination fee is generally cleaner than taking a percentage of medical fees because it reduces the appearance of incentives to recommend unnecessary clinical activity.

4. Grooming camp

Decision: Approve as a partner-led commercial event

The grooming partner should provide:

- Trained groomers

- Equipment

- Cleaning materials

- Safe restraint practices

- Hygiene and disinfection

- Staff supervision

- Service-specific consent

- Incident reporting

Recommended launch services

- Bathing

- Brushing

- Basic coat care

- Nail trimming where appropriate

- Basic hygiene services

- Limited ear cleaning within partner competence

Do not include as ordinary camp services:

- Sedation

- Medical skin treatment

- Wound treatment

- Veterinary dental procedures

- Complex services outside the partner’s competence

Recommended revenue model

Percentage model

PetSaathi:

15–25% proposed share

Grooming partner:

75–85% proposed share

Calculate the split on a clearly defined amount:

Net completed service value

after approved discounts and refunds

before or after tax as specified in the agreement

Fixed appointment model

PetSaathi receives:

₹100–₹300 proposed fee

per completed grooming appointment

Fixed event-management model

Partner or society pays:

₹7,500–₹20,000 proposed event fee

The fixed-fee model is often easier when grooming prices vary significantly by pet size, coat and service.

5. Vaccination camp

Decision: Approve only through a registered veterinary practitioner

Vaccination should be clinically controlled by the veterinary partner.

The Indian Veterinary Council Act places veterinary practice with registered veterinary practitioners, while limited vaccination services by specified assistants depend on state authorisation and registered-veterinarian supervision. PetSaathi’s safest national policy is therefore to require a registered veterinary practitioner to control every vaccination camp.

Required controls

Veterinary registration verified

Owner consent

Pet identity

Relevant health questions

Vaccine name

Batch number

Expiry date

Administration date

Next due date

Veterinary clinic/practitioner

Certificate or record

Adverse-reaction workflow

The veterinary partner should remain responsible for:

- Vaccine sourcing

- Storage

- Temperature control

- Administration

- Medical suitability

- Sharps and biomedical waste

- Adverse-event response

Government animal-health programmes explicitly treat cold-chain infrastructure and vaccine logistics as required components of vaccination delivery, reinforcing the need to assign these responsibilities to the veterinary partner.

Recommended revenue model

Avoid:

PetSaathi receives commission

for every vaccine dose sold

That can create the wrong clinical incentive.

Prefer:

Fixed event-management fee

₹7,500–₹25,000 proposed

depending on size and operational scope

Fixed completed-registration fee

₹100–₹250 proposed

per completed resident appointment

Sponsor-funded camp

A pet-health brand or society may subsidise the event, but the sponsor must not control the veterinarian’s clinical decisions.

Public wording

Use:

Vaccination camp conducted by a registered veterinary partner and coordinated by PetSaathi.

Do not use:

PetSaathi vaccinates your pet.

6. Pet-parent meet-up

Decision: Approve as a community and sponsorship event

This event can include:

- Pet-parent orientation

- Sitter introductions

- Responsible pet-care awareness

- PetSaathi service demonstration

- Lost-pet preparedness

- Society access rules

- Veterinary-partner Q&A

- Sponsor booths

- Resident networking

Sponsorship revenue

Proposed sponsorship levels:

| Sponsor level | Proposed price |
| --- | --- |
| Supporting sponsor | ₹10,000–₹20,000 |
| Main sponsor | ₹25,000–₹50,000 |
| Presenting sponsor | ₹50,000+ for a major event |

These are proposed commercial bands, not statutory or universal market prices.

Sponsorship controls

A sponsor may receive:

- Approved logo placement

- Event booth

- Short educational presentation

- Product samples with resident consent

- Aggregate attendance information

- Opt-in lead referrals where clearly disclosed

A sponsor must not automatically receive:

- Resident phone numbers

- Pet medical details

- Booking histories

- Exact apartment details

- Emergency contacts

- Non-consenting attendee information

Sponsored digital posts and promotional material should clearly identify the commercial relationship. ASCI permits labels such as “Sponsored,” “Partnership,” “Ad” and “Collaboration” and requires promotional content to be identifiable as advertising.

Recommended disclosure

This event is supported by [Sponsor]. PetSaathi does not share resident contact information with sponsors unless the resident separately opts in.

7. Dog-training workshop

Decision: Approve as a humane, trainer-led educational workshop

Recommended topics:

- Leash handling

- Recall foundations

- Puppy socialisation

- Understanding body language

- Enrichment

- Separation preparation

- Safe introductions

- Common-area behaviour

- Reward-based training foundations

Trainer verification

Record:

Identity

Training background

Experience

References

Methods used

Service scope

Incident history

Insurance, where available

Prohibited techniques

Prohibited event practices

- Physical punishment

- Intimidation-based demonstrations

- Forced interactions

- Uncontrolled off-leash groups

- Guaranteed behavioural “cures”

- Breed-based conclusions

- Medical diagnosis

- Humiliating or entertainment-focused animal tricks

The Prevention of Cruelty to Animals Act is intended to prevent unnecessary pain or suffering. Its performing-animal chapter also regulates ticketed exhibitions and training for such exhibitions. An ordinary educational workshop is not necessarily the same as an animal performance, but a ticketed show built around animals performing for entertainment should receive specific legal review.

Recommended ticket structure

| Format | Proposed resident price |
| --- | --- |
| Group awareness session | Free–₹299 |
| Educational workshop | ₹299–₹799 |
| Small practical session | ₹799–₹1,499 |
| Private consultation | Partner-specific price |

Proposed revenue split

Trainer:

50–70%

PetSaathi:

20–30%

Society/venue/operations:

Remaining share where applicable

The agreement should specify whether payment-provider fees, taxes, refunds, venue cost and marketing cost are deducted before the split.

8. Recommended Event Package tiers

Event Starter

Proposed price

₹5,000–₹10,000 coordination fee

plus partner service charges

Includes

- One small event

- Standard registration page

- Society communication template

- Basic check-in

- Up to a configured attendee limit

- Partner coordination

- Basic lead and attendance report

Best for:

- Small meet-up

- Trainer talk

- Pet-parent orientation

Standard Society Camp

Proposed price

₹15,000–₹30,000 coordination fee

plus professional/partner costs

Includes

- Registration and time slots

- One professional partner

- On-site coordinator

- Society communication

- QR check-in

- Consent collection

- Payment management

- Incident workflow

- Follow-up campaign

- Event report

Best for:

- Grooming camp

- Health-check camp

- Vaccination camp

Premium Pet-Care Event

Proposed price

₹30,000–₹75,000+

depending on size and complexity

Includes

- Multiple partners or activity zones

- Lead coordinator

- Registration desk

- Sponsor management

- Event branding

- Professional sessions

- Incident and emergency plan

- Resident offers

- Post-event lead conversion

- Detailed event report

Best for:

- Pet-care weekend

- Large township activation

- Sponsored pet festival

- Multi-service event

9. End-to-end event workflow

Stage 1 — Event proposal

Define:

Event purpose

Target society

Target attendees

Services offered

Partner

Revenue model

Society fee

Resident fee

Sponsor involvement

Capacity

Date and location

Stage 2 — Partner approval

Verify:

- Identity

- Business details

- Professional registration where applicable

- Experience

- Service scope

- Equipment

- Incident process

- Insurance where available

- Commercial agreement

Stage 3 — Society approval

Confirm:

- Authorised society contact

- Venue

- Electricity and water

- Access

- Noise limits

- Cleaning

- Waste disposal

- Parking

- Security

- Emergency route

- Branding permission

Stage 4 — Resident registration

Collect only necessary information:

Resident name

Contact

Society/unit verification

Pet name and species

Selected slot

Relevant service information

Consent

Payment

Medical information should be collected only when necessary for the veterinary service and accessed only by authorised personnel.

The DPDP Rules, 2025 were published in November 2025 with staged commencement provisions. Event registration should therefore include a clear notice describing what information is collected, why it is needed, who receives it and how long it will be retained.

Stage 5 — Event-day check-in

QR or booking verification

↓

Pet identity confirmed

↓

Consent checked

↓

Queue or appointment assigned

↓

Service delivered

↓

Completion recorded

↓

Incident or follow-up routed

Stage 6 — Payment and invoicing

The system should distinguish:

- Society event fee

- Resident service fee

- Partner professional fee

- Sponsor payment

- Refund

- PetSaathi coordination fee

Registered service suppliers must issue invoices containing required service, value and tax information; CBIC’s invoice rules also specify timelines and invoice particulars for taxable services.

The final GST classification and tax treatment should be confirmed with a chartered accountant.

Stage 7 — Post-event conversion

Within 24–48 hours:

Thank attendee

↓

Send service summary or partner record

↓

Request feedback

↓

Offer PetSaathi trial

↓

Offer pet-profile completion

↓

Offer walking/sitting plan

10. Event data model

society_events

id

society_id

event_type

title

description

venue

starts_at

ends_at

capacity

registration_status

event_status

lead_coordinator_id

partner_id

sponsor_id

pricing_model

created_at

event_registrations

id

event_id

resident_id

pet_id

appointment_slot

consent_version

payment_status

attendance_status

service_status

created_at

event_partners

event_id

partner_id

partner_role

verification_snapshot

professional_registration

commercial_model

revenue_share

fixed_fee

responsibility_scope

event_transactions

event_id

registration_id

payer_type

gross_amount_paise

discount_paise

refund_paise

partner_amount_paise

petSaathi_amount_paise

tax_amount_paise

status

event_incidents

Link the normal incident system rather than storing serious safety issues only in event notes.

11. Event safety plan

Every event should have:

- Named event owner

- Partner owner

- Society contact

- Security contact

- Veterinary emergency contact

- Capacity limit

- Pet separation plan

- Entry and exit flow

- Water and shade

- Hygiene and waste management

- Incident form

- Emergency evacuation path

- Weather fallback

- Cancellation process

Animal interaction rules

- Use scheduled slots.

- Avoid overcrowding.

- Keep incompatible animals separated.

- Require leashes or secure carriers.

- Do not create uncontrolled group play.

- Allow nervous pets to wait outside the main area.

- Do not force participation.

- Stop a service when distress or danger appears.

12. Lead-generation rules

Valid event lead

Count someone as a qualified lead only when the resident:

- Registers voluntarily

- Provides a valid contact method

- Identifies a pet or service need

- Accepts the PetSaathi privacy notice

- Permits relevant follow-up

Do not count:

- Poster impressions

- Society WhatsApp-group membership

- Anonymous visitors

- Sponsor leads collected without resident consent

Lead classifications

EVENT_REGISTERED

ATTENDED

PET_PROFILE_STARTED

PET_PROFILE_COMPLETED

TRIAL_INTERESTED

TRIAL_BOOKED

PAID_CUSTOMER

REPEAT_CUSTOMER

13. Success metrics

Event operations

| Metric | Target |
| --- | --- |
| Registered attendees who attend | 60–80% |
| Services completed | 90%+ |
| Start-time adherence | 90%+ |
| Critical unresolved incidents | 0 |
| Partner complaints | Low and resolved |
| Customer rating | 4.5+ |

Lead generation

| Metric | Target |
| --- | --- |
| Attendees becoming qualified leads | 60%+ |
| Leads completing Pet Profiles | 30–50% |
| Leads booking a trial | 15–30% |
| Trial customers completing service | 90%+ |
| Trial customers repeating | 25–35%+ |

Event economics

Track:

Society fee

Sponsor revenue

Ticket revenue

Partner service GMV

PetSaathi coordination revenue

Partner payout

Event costs

Refunds

Post-event booking contribution

Total event contribution

Do not judge the event only by same-day ticket revenue. A high-quality event can create more value from subsequent dog-walking plans.

14. What is wrong in the original proposal?

Problem 1 — “Vet partner commission” is too vague

Correction

Use a fixed event fee or completed-appointment fee and keep clinical responsibility with the registered veterinarian.

Problem 2 — Vaccination commission could create a clinical incentive

Correction

Do not link PetSaathi income directly to the number or type of vaccines recommended. Use fixed coordination pricing.

Problem 3 — Grooming revenue share lacks a calculation base

Correction

Define whether the share applies to gross payment, net completed service value, or amount after refunds and taxes.

Problem 4 — Sponsorship can become hidden advertising

Correction

Disclose sponsors clearly and require separate resident consent before sponsor lead sharing.

Problem 5 — Ticketed training can become an animal show

Correction

Keep it educational and humane. Obtain legal review where the format involves ticketed animal performances.

Problem 6 — No medical, privacy or incident controls

Correction

Every event requires professional responsibility, resident notice, consent, access restrictions and incident handling.

Problem 7 — Leads are counted without consent or conversion

Correction

Track opt-in leads through paid and repeat bookings.

Final approved package

PetSaathi Society Event & Camp Programme

Best for

- New-society acquisition

- Resident lead generation

- Partnership activation

- Pet-parent trust building

- Partner-service testing

- Converting residents into recurring care customers

Approved services

- Veterinary-partner health-check camps

- Grooming-partner camps

- Registered-veterinarian vaccination camps

- Sponsored pet-parent meet-ups

- Humane trainer-led workshops

Revenue

Society coordination fee

+

Sponsor revenue

+

Event ticket revenue

+

Transparent partner fee/revenue share

+

Post-event PetSaathi booking contribution

Not permitted

- PetSaathi staff practising veterinary medicine

- Hidden sponsor promotion

- Uncontrolled animal gatherings

- Sharing resident lists without opt-in

- Vaccination incentives based on clinical recommendations

- Cruel or entertainment-based training

- Unclear partner responsibility

- Serious incidents stored only in WhatsApp

Final operating principle

The event should generate trust and qualified demand, but professional partners must remain responsible for the specialist services they deliver. PetSaathi owns coordination, booking, transparency, support and follow-up—not veterinary or specialist decisions.

Simple explanation for professor

“Package 4 is an event and camp model used to acquire many pet-parent leads inside apartment societies.

PetSaathi can organise health-check camps, grooming camps, vaccination camps, pet-parent meetings and dog-training workshops. However, PetSaathi will act mainly as the organiser and booking platform.

Health checks and vaccination will be conducted only through registered veterinary practitioners. Grooming will be performed by verified grooming partners, and training workshops will be conducted by screened trainers using humane methods.

PetSaathi can earn through event-coordination fees, sponsor payments, training tickets, grooming revenue share and future dog-walking or pet-sitting bookings. Medical-event income should normally use fixed coordination fees rather than commission based on the number of vaccines or treatments.

Residents must voluntarily register and receive a clear privacy notice. Sponsors and societies will not automatically receive resident phone numbers or pet medical data.

After the event, PetSaathi will invite attendees to complete their Pet Profiles, book a trial service and purchase repeat walking or sitting plans. Therefore, event success will be measured not only by attendance, but also by paid bookings and repeat customers.”

A monthly compliance watch for veterinary, privacy, advertising and municipal event rules would help before expanding camps into additional cities.

PetSaathi Phase 7 — Society-Specific Landing Pages 🏢🐾

Executive decision

Approve the society landing-page feature, but each page must be a real operational page—not a template where only the society name changes.

Recommended route structure:

/pet-care/societies/[city]/[society-slug]

Examples:

/pet-care/societies/ahmedabad/green-acres-bopal

/pet-care/societies/bengaluru/prestige-lakeside-whitefield

/pet-care/societies/gurugram/dlf-phase-5

This structure is clearer than placing every society directly below /society/, because it provides a logical hierarchy:

Pet Care

↓

City

↓

Society

Each page should answer four questions immediately:

- Is PetSaathi active in this society?

- Which services are currently available?

- Which trust and access controls are in place?

- How can a resident book safely?

1. Critical SEO warning

Do not automatically publish hundreds of near-identical society pages.

Google defines doorway abuse as creating many substantially similar pages targeting specific queries while providing little unique value. Google also warns that generating large numbers of pages without meaningful original value may violate its scaled-content policies.

Wrong approach

Green Acres pet-care page

Prestige Lakeside pet-care page

DLF Phase 5 pet-care page

with exactly the same text except for:

- Society name

- City name

- Area name

Correct approach

Index a society page only when it contains genuine society-specific information, such as:

- Active services

- Confirmed access process

- Actual service timings

- Available local sitter pool

- Society-specific resident offer

- Local veterinary partners

- Real operating contact

- Society-specific FAQ

- Actual booking capacity

- Genuine programme metrics

Google’s search systems are designed to prioritise useful, reliable, people-first pages rather than content produced primarily to manipulate rankings.

2. Society-page publishing states

Every society should have a publishing state.

DRAFT

IN_REVIEW

PILOT

ACTIVE

PAUSED

ENDED

ARCHIVED

Recommended indexing rules

| Society status | Public page | Search indexing |
| --- | --- | --- |
| Draft | No | No |
| In review | No | No |
| Pilot with limited information | Optional | Usually noindex |
| Active with complete content | Yes | Index |
| Temporarily paused | Yes, with notice | Case-specific |
| Partnership ended | Redirect or archived notice | Usually remove/index carefully |
| Duplicate/renamed society | Redirect | Canonical destination |

Only active and sufficiently complete pages should appear in the sitemap.

Google recommends using canonical URLs to identify the preferred version when duplicate or highly similar URLs exist.

3. Recommended page structure

Section 1 — Hero and society identity

Purpose

Create immediate local trust and confirm that the resident has reached the correct society page.

Recommended content

PetSaathi for Green Acres, Bopal

Verified pet-care support for Green Acres residents.

Book approved-access dog walkers and pet sitters with

service updates, Report Cards and responsive support.

Trust indicators

Display factual indicators such as:

Society partnership: Active

Society access process: Configured

Local sitter pool: 4 active caregivers

Services: Dog walking and pet sitting

Support: Available during published hours

Avoid

100% safe pet care

Guaranteed sitter

Risk-free services

Society-certified perfect walkers

Verification claims should describe exactly what was checked.

4. Section 2 — Services available

Do not show services that are unavailable in that society.

Recommended service cards

Dog walking

30-minute and 60-minute walks

Basic GPS walk proof

Photo or video update

Pet Report Card

Same-sitter preference

Pet sitting

In-home care

Food and water updates

Routine and medication instructions

Private service media

Entry and exit confirmation

Controlled boarding

Show only when:

- Boarding is activated

- Approved hosts exist

- Health and compatibility workflows are active

- Backup arrangements are available

Use:

Screened boarding beta

rather than implying universal availability.

Service status values

AVAILABLE

LIMITED_AVAILABILITY

WAITLIST

COMING_SOON

TEMPORARILY_PAUSED

NOT_AVAILABLE

The booking CTA should automatically disable or change when the selected service is not currently available.

5. Section 3 — Verified sitters nearby

Purpose

Show that real local supply exists.

Recommended sitter card

Riya S.

Services:

Dog walking · Pet sitting

Area:

Bopal and South Bopal

Society access:

Registered

Verification:

Identity reviewed

Pet-care training completed

Experience:

42 completed bookings

Rating:

4.8 from 31 eligible reviews

Availability:

Morning and evening

Privacy rule

Before booking confirmation, residents should see:

- Display name

- Profile photograph

- General area

- Service permissions

- Verification badges

- Experience

- Rating

- Availability category

Do not display:

- Home address

- Personal identification documents

- Personal phone number

- Bank details

- Exact current location

- Full incident or disciplinary history

Availability wording

Do not say:

“Riya is guaranteed for your booking.”

Use:

Preferred sitter availability will be checked when you submit your request.

6. Section 4 — Resident discount or society benefit

Purpose

Create a clear reason for residents to book through the society page.

Example

Green Acres Resident Benefit

₹100 off your first eligible dog walk

or

Free first meet-and-greet with an approved sitter

Required information

Show:

- Eligible services

- Discount amount

- Validity period

- One-per-household rule

- Minimum booking value

- Whether it combines with other offers

- Booking capacity

- Payment requirement

Checkout display

Standard price:              ₹199

Green Acres resident offer:  −₹50

Final payable amount:        ₹149

Do not use inflated “standard prices” to create an artificial discount.

7. Section 5 — Booking CTA

Primary CTA

Book Pet Care

Secondary CTA

Create Your Pet Profile

Optional CTA

Talk to Society Support

The society ID should be attached automatically:

society_id = SOC-GREEN-ACRES

The user should not need to reselect the society manually.

Recommended booking journey

Choose service

↓

Choose pet

↓

Choose date and time

↓

Confirm society address/unit

↓

Add instructions

↓

Review price and policy

↓

Submit request/payment

Do not turn the society page into a 10–12-step lead form.

8. Section 6 — How society booking works

A small visual timeline improves clarity.

1. Create Pet Profile

2. Choose service and schedule

3. PetSaathi reviews care requirements

4. Eligible local sitter is assigned

5. Payment is verified

6. Society access is prepared

7. Service is completed

8. Report Card is delivered

Important statement

A booking is confirmed only after sitter assignment, payment verification and required safety checks.

This prevents customers from assuming that submitting the form guarantees service.

9. Section 7 — Society trust and safety controls

Show the actual operating controls configured for that society.

Example

✓ Society-access caregiver roster

✓ Controlled gate-entry process

✓ Pet Profile and care instructions

✓ Service-specific sitter matching

✓ Booking reminders

✓ Basic GPS evidence for walks

✓ Private photo/video updates

✓ Report Card after service

✓ Backup replacement workflow

✓ Structured complaint and incident support

Society-specific access information

Show safe, non-sensitive details:

Primary entry:

Main visitor gate

Sitter registration:

Required before first service

Service hours:

6:00 AM–9:00 AM

5:00 PM–9:00 PM

Replacement sitter:

Must be approved through PetSaathi before arrival

Do not publish security phone numbers, visitor codes or entry credentials publicly.

10. Section 8 — Emergency support

Correct terminology

Use:

Emergency service escalation and veterinary coordination

Do not use:

PetSaathi emergency veterinary treatment

unless PetSaathi directly operates a properly qualified veterinary service.

Display

Active-service emergency?

Call PetSaathi Support

[Call Support]

Veterinary coordination is provided through available

registered partners. Availability and arrival time cannot

be guaranteed.

Privacy control

Use:

- A PetSaathi support number

- Masked call routing

- Secure authenticated support action

Do not publicly expose:

- Personal coordinator numbers

- Resident emergency contacts

- Veterinarian’s private personal number

- Pet medical information

11. Section 9 — Society-specific FAQ

FAQs should address real questions from that society.

Recommended questions

Is PetSaathi officially active in Green Acres?

Explain the current partnership or pilot status.

Which services are available?

Show active services and limits.

How does a sitter enter the society?

Explain the configured access process.

Is the same sitter guaranteed?

Explain same-sitter preference versus availability.

Is payment required before confirmation?

Explain prepaid confirmation.

Can I book for more than one pet?

Explain multi-pet profiles and charges.

What happens when the sitter cancels?

Explain the replacement and refund process.

Who can see my address and Pet Profile?

Explain role-based access.

Is GPS available for every service?

Explain that basic tracking applies mainly to dog walks.

What happens during a pet emergency?

Explain escalation and veterinary coordination.

Important SEO rule

Do not copy the same FAQ word for word across every society page.

Include genuine questions such as:

- Which gate should walkers use?

- Are morning slots available?

- Is boarding currently active?

- How are replacement sitters approved?

- Are multiple towers supported?

12. Section 10 — Partner veterinarian and groomer

Purpose

Show the local support ecosystem without overstating the partnership.

Recommended partner card

ABC Veterinary Clinic

Area:

Bopal

Partner type:

Veterinary coordination partner

Services:

Emergency consultation

General veterinary care

Vaccination appointments

Availability:

Subject to clinic availability

Last verified:

1 August 2026

Groomer card

Happy Paws Grooming

Service:

Society grooming camp partner

Next event:

18 August 2026

Booking:

Appointment required

Required controls

Before listing a partner:

- Verify business identity

- Verify veterinary registration where relevant

- Record service scope

- Record contact and escalation process

- Record verification date

- Record partnership status

- Obtain approval to use name/logo

Do not imply that every listed partner is available 24/7.

13. Recommended additional sections

Your proposed sections are good, but the following should also be included.

A. Live programme status

Programme status: Active

New booking capacity this week: Limited

Morning walk slots: 3 available

Evening walk slots: Waitlist

Do not expose exact sitter schedules publicly.

B. Society programme results

Display only when the sample is meaningful.

84 completed services

96% on-time service rate

4.7 average resident rating

98% Report Card delivery

Show the denominator or review count:

4.7 from 36 resident reviews

C. Report Card preview

Show a demonstration report containing fictional or consented data.

Pet: Bruno

Duration: 31 minutes

Approximate distance: 1.3 km

Mood: Happy and active

Water: Given

Concern: None reported

D. Resident testimonials

Use only with explicit permission.

Avoid exposing:

- Apartment number

- Phone number

- Pet medical information

- Booking history

E. Society contact and escalation policy

Explain who handles:

- Booking questions

- Active-service concerns

- Refunds

- Access problems

- Critical emergencies

14. Recommended URL strategy

Preferred structure

/pet-care/societies/[city]/[society]

Examples:

/pet-care/societies/ahmedabad/green-acres-bopal

/pet-care/societies/bengaluru/prestige-lakeside-whitefield

/pet-care/societies/gurugram/dlf-phase-5

City hub pages

Also create:

/pet-care/societies/ahmedabad

/pet-care/societies/bengaluru

/pet-care/societies/gurugram

A city page should list only active or publicly available society programmes.

Breadcrumb

Home

› Pet Care

› Ahmedabad

› Green Acres Bopal

Google supports BreadcrumbList structured data to help explain a page’s position in the website hierarchy.

15. Next.js implementation

Route structure

app/

└── pet-care/

└── societies/

└── [city]/

└── [societySlug]/

├── page.tsx

├── loading.tsx

├── not-found.tsx

└── opengraph-image.tsx

Next.js dynamic route segments are designed for routes whose values come from data, such as city and society slugs.

Recommended server-side page flow

Read city and society slug

↓

Load society record

↓

Confirm public status

↓

Load active services

↓

Load public sitter summaries

↓

Load resident benefit

↓

Load partner summaries

↓

Load society FAQs

↓

Render page

Static generation

Use generateStaticParams() for active society pages when the set is known and changes moderately. Next.js supports combining dynamic routes with generateStaticParams to generate specified routes at build time.

Dynamic metadata

Use generateMetadata() to create page-specific:

- Title

- Description

- Canonical URL

- Open Graph title

- Open Graph image

- Robots rules

Next.js supports route-dependent metadata through generateMetadata, including dynamic values based on route parameters.

16. Recommended metadata

Title

Pet Care in Green Acres Bopal | Dog Walking & Pet Sitting | PetSaathi

Description

PetSaathi provides verified dog walking and in-home pet sitting

for Green Acres Bopal residents, with service updates, Report Cards

and society-access caregivers.

Canonical

https://petsaathi.in/pet-care/societies/ahmedabad/green-acres-bopal

Open Graph

PetSaathi × Green Acres Bopal

Trusted pet care for your society

Google recommends descriptive, relevant page titles and may use several page signals when generating title links in search results.

17. Structured data

Recommended

BreadcrumbList

Use on each society page.

Organization

Use primarily on the PetSaathi homepage to identify PetSaathi’s organisation details and logo. Google specifically recommends organisation markup on the home page for organisational identification.

Generic WebPage and Service

These may help describe the page semantically, but not every schema.org type produces a Google rich result. Google maintains a defined gallery of structured-data features it supports for rich search appearances.

Do not misuse LocalBusiness

A residential society page is not automatically a PetSaathi business branch.

Use LocalBusiness only where PetSaathi has a genuine local business presence with accurate:

- Address

- Opening hours

- Contact

- Operational identity

Google’s LocalBusiness markup is intended to describe actual business details such as business location and operating hours.

Do not mark the society’s address as a PetSaathi office merely for local SEO.

Validation

Validate structured data with:

- Google Rich Results Test

- Schema.org validator

- Search Console URL Inspection

Google recommends testing structured data and fixing critical validation errors before broader deployment.

18. Sitemap and indexing

Generate the sitemap only from active, indexable society pages.

ACTIVE + content_complete + public = sitemap inclusion

Do not add:

- Draft pages

- Empty society templates

- Ended partnerships

- Pages with no active service

- Internal preview URLs

Google uses sitemaps to discover important pages and understand information such as update dates. Next.js supports generating dynamic sitemap files through its metadata file conventions.

19. Mobile-first design

Most society users will likely arrive from:

- WhatsApp

- QR posters

- Mobile search

- Society communication apps

The page should therefore be designed mobile-first.

Mobile layout order

Society identity

Services

Resident benefit

Book CTA

Trust controls

Available sitter summaries

How it works

Report Card preview

Emergency support

FAQs

Partners

Sticky action bar

[Book Now] [WhatsApp Support]

Avoid blocking the page immediately with a full-screen sign-up popup.

Google recommends responsive design and warns that intrusive interstitials can harm usability and make content harder for users and search engines to access.

20. Performance requirements

Avoid loading:

- Full Google Maps SDK above the fold

- Original sitter photographs

- Autoplay videos

- Every partner image immediately

- Large tracking demonstrations

- Multiple analytics systems before content

Recommended:

- Optimised responsive images

- Lazy-loaded maps

- Server-rendered primary content

- Small sitter-card images

- Deferred report preview media

- Cached public society data

Google recommends good Core Web Vitals for loading, interactivity and visual stability as part of a strong user experience.

21. Privacy and data protection

The public page must not expose private resident or booking data.

Public information

- Society name

- Area

- Active services

- General service windows

- Public sitter summaries

- Resident benefit

- Public partner details

- Aggregate metrics

- Support contact

Authenticated resident information

- Exact booking status

- Assigned sitter

- Exact address/unit

- Pet Profile

- Private Report Card

- Photos/videos

- GPS route

- Refund status

- Complaints/incidents

Society-only aggregate information

- Completed service counts

- On-time rate

- Access issues

- Aggregate complaints

- Programme status

The DPDP Act and final DPDP Rules establish the current Indian digital-personal-data framework, including published rules and enforcement timelines. Society onboarding and landing-page forms should therefore use clear notices, limited data collection, controlled access and defined retention.

22. Recommended data model

societies

id

name

slug

city_id

area

public_status

partnership_status

hero_heading

hero_description

logo_reference

support_channel

primary_service_window

created_at

updated_at

society_service_configs

society_id

service_type

status

starting_price_paise

booking_cap

service_hours

tracking_required

report_card_required

resident_offer_id

society_public_sitters

society_id

sitter_id

display_status

access_status

priority

public_bio_override

society_partners

society_id

partner_id

partner_type

public_status

service_scope

last_verified_at

society_faqs

id

society_id

question

answer

sort_order

public

society_page_metrics

society_id

completed_services

on_time_rate

average_rating

review_count

report_delivery_rate

display_approved_at

Only display metrics that have passed an internal sample-size and privacy check.

23. API structure

Public APIs

GET /api/public/societies/:city/:slug

GET /api/public/societies/:id/services

GET /api/public/societies/:id/sitters

GET /api/public/societies/:id/partners

GET /api/public/societies/:id/faqs

Resident APIs

POST /api/societies/:id/verify-resident

POST /api/societies/:id/bookings

GET  /api/societies/:id/resident-benefits

Admin APIs

POST /api/admin/societies

PUT  /api/admin/societies/:id

PUT  /api/admin/societies/:id/publish

PUT  /api/admin/societies/:id/services

PUT  /api/admin/societies/:id/sitters

PUT  /api/admin/societies/:id/partners

PUT  /api/admin/societies/:id/faqs

Public endpoints should return a restricted public response model rather than the full society database object.

24. Analytics events

Track:

view_society_page

click_book_society_service

select_society_service

start_society_booking

submit_society_booking

payment_started

payment_success

click_whatsapp_support

view_sitter_profile

view_resident_offer

create_pet_profile

view_report_card_demo

Funnel

Society page view

↓

Book CTA

↓

Service selected

↓

Pet Profile created

↓

Booking submitted

↓

Payment completed

↓

Service completed

↓

Repeat booking

Society-page success metrics

| Metric | Initial target |
| --- | --- |
| Page → booking CTA | 8–15% |
| CTA → booking start | 40%+ |
| Booking start → submit | 40–60% |
| Submit → payment completed | 60–85% |
| Completed service → repeat | 25–35%+ |
| WhatsApp support dependency | Decreasing over time |
| Unsupported service clicks | Low |
| Mobile page errors | Near zero |

These are proposed product targets and should be adjusted using pilot results.

25. What is wrong in many society landing pages?

Mistake 1 — Only the society name changes

Correct

Every indexed page must contain actual local operating information.

Mistake 2 — Fake local supply

Wrong

“20 sitters near your society”

when none are currently eligible.

Correct

Display only active and verified local capacity.

Mistake 3 — Showing unavailable services

Correct

Use explicit service statuses and waiting lists.

Mistake 4 — Emergency support is exaggerated

Correct

Describe veterinary coordination and actual support hours.

Mistake 5 — Society address is used as a fake PetSaathi branch

Correct

Do not misuse LocalBusiness structured data.

Mistake 6 — Resident discount has hidden conditions

Correct

Display eligibility and final price clearly.

Mistake 7 — The page exposes sensitive access information

Correct

Keep gate codes, unit numbers and personal contacts behind authentication.

Mistake 8 — Hundreds of thin pages are indexed

Correct

Publish only complete, active, unique pages and apply noindex to incomplete pilot pages.

Final approved page blueprint

1. Breadcrumb

2. Society hero

3. Partnership and availability status

4. Services available

5. Resident benefit

6. Booking CTA

7. How booking works

8. Trust and safety controls

9. Local sitter summaries

10. Society access information

11. Report Card demonstration

12. Programme results

13. Emergency coordination

14. Society-specific FAQs

15. Local vet/groomer partners

16. Final booking CTA

17. Privacy, cancellation and support links

Definition of done

A society landing page is ready only when:

Operational accuracy

- Society partnership status is correct.

- Services shown are genuinely active.

- Sitter summaries reflect real capacity.

- Resident benefit is valid.

- Support contact is working.

- Access procedure is verified.

Conversion

- Booking CTA is visible immediately.

- Society is preselected.

- Pricing is clear.

- Mobile booking works.

- WhatsApp is available as support, not the only workflow.

SEO

- Page has substantial unique content.

- Title and description are society-specific.

- Canonical URL is correct.

- Active page is included in sitemap.

- Incomplete pages are not indexed.

- Breadcrumb structured data validates.

Privacy

- No resident information is public.

- No private sitter document is exposed.

- No exact GPS route is public.

- Society receives only aggregate programme data.

- Forms include appropriate data-use notices.

Performance

- Hero content loads quickly.

- Images are optimised.

- Maps load only when required.

- Mobile layout is stable.

- Primary content is server-rendered and crawlable.

Final operating principle

A society landing page should be a live service interface for residents—not a mass-produced SEO page. It must accurately represent local supply, access, pricing, safety controls and booking availability.

Simple explanation for professor

“The society landing page will be a personalised web page for each active apartment society.

For example, Green Acres Bopal will have its own page showing the pet-care services available inside that society, the local sitter pool, the resident offer, booking process, support contact and society-specific rules.

The page will not simply replace one society name with another. Every page must contain real local details such as service timings, access rules, available sitters, partner veterinarians and frequently asked questions.

Residents can choose dog walking or pet sitting, create their Pet Profile and submit a booking directly from the page. The society will already be selected, so residents do not need to enter the complete location again.

Only public sitter information will appear on the page. Personal documents, addresses, phone numbers and disciplinary information will remain private.

The page will include emergency veterinary coordination, but PetSaathi will not claim to provide veterinary treatment. It will also show only active services and genuine availability.

For search visibility, only complete and active society pages will be indexed. Empty or copied pages will not be published because large numbers of similar pages can be treated as low-value doorway content.

The final goal is to make every society page a trusted local booking portal that improves resident conversion and reduces operational confusion.”

PetSaathi Phase 7 — Society Resident Verification, Sitter Pool and Pet-Care Calendar 🏢🐾

Executive decision

Approve all three features, with these corrections:

| Feature | Decision | Important correction |
| --- | --- | --- |
| Society resident verification | Approve | Use layered verification; a flat number or WhatsApp number alone is insufficient |
| Society sitter pool | Approve | Use capacity rules and service permissions, not fixed headcounts only |
| Society pet-care calendar | Approve | Separate private service slots from public society events |

The final operating structure should be:

Resident verifies society membership

↓

Resident creates Pet Profile

↓

System shows society-supported services and calendar

↓

Booking is matched to the approved local sitter pool

↓

Gate access, payment and safety checks complete

↓

Service proceeds

2. Society resident verification

Goal

Confirm that a user is genuinely connected to a society before providing:

- Society-specific resident discounts

- Private society booking slots

- Internal pet-parent community access

- Society event registration

- Lost-pet alerts

- Society-specific support

- Access to resident-only sitter information

Verification should not be used to block a resident from ordinary public PetSaathi services. It only controls access to society-specific benefits and private community features.

Recommended verification principle

Do not rely on one field.

Weak verification

Flat number entered

↓

User immediately marked verified

Anyone who knows a tower and flat number could misuse this flow.

Correct verification

User selects “I live in this society”

↓

Phone number verified

↓

Tower/block and flat entered

↓

Society-specific proof checked

↓

Verification status assigned

A WhatsApp OTP confirms control of a phone number; it does not independently prove that the person lives in the society.

Verification methods

Method A — Society invite link

Best for controlled resident onboarding.

Society sends approved invitation

↓

Resident opens signed link

↓

Link identifies society

↓

Resident verifies phone

↓

Resident enters tower/unit

↓

Membership activated

Use a signed, time-limited token containing:

society_id

invitation_id

expires_at

allowed_use_count

campaign_reference

Do not put a resident’s name, phone or apartment number directly inside the URL.

Recommended status

VERIFIED_BY_INVITE

Method B — Society resident code

The society receives a code such as:

GREENACRES-PET-2026

The resident enters:

- Code

- Phone verification

- Tower

- Flat number

This is convenient but weaker because codes may be forwarded outside the society.

Use this for:

PROVISIONAL_VERIFICATION

until additional confirmation occurs.

Method C — Admin or facility approval

Best for high-value services and unclear cases.

Resident submits details

↓

PetSaathi admin reviews request

↓

Authorised society contact confirms residency

↓

Resident becomes verified

The society contact should see only what is necessary:

- Resident display name

- Tower/block

- Unit number

- Verification request date

Do not reveal:

- Pet medical details

- Booking history

- Payment details

- Emergency contacts

- Complaints

Method D — Resident document review

Use only when genuinely necessary.

Possible proof:

- Redacted maintenance receipt

- Resident card

- Rental/occupancy confirmation

- Society application screenshot

- Approved tenant record

Collect the minimum data needed and allow unnecessary details to be hidden.

The DPDP framework requires PetSaathi to explain what personal data it collects, the purpose of collection and how the person can exercise applicable rights. The final DPDP Rules were published on November 14, 2025 with staged commencement provisions.

Do not permanently store a full document when recording a verification result and limited audit metadata is sufficient.

Recommended verification hierarchy

| Level | Verification | Access |
| --- | --- | --- |
| V0 — Unverified | Phone only | Public services |
| V1 — Provisional | Society code + phone | View resident offers |
| V2 — Verified resident | Invite link or admin confirmation | Book society services |
| V3 — Verified household | Unit ownership/tenancy confirmed | Directory/community features |
| V4 — Society representative | Committee/facility role approved | Limited society administration |

Do not give a society representative access to resident booking or medical information merely because they hold a committee role.

Verification states

NOT_STARTED

PHONE_VERIFIED

DETAILS_SUBMITTED

PROVISIONAL

ADMIN_REVIEW_REQUIRED

VERIFIED

REJECTED

EXPIRED

REVOKED

Reverification triggers

Set verification to review when:

- Resident changes society

- Tenant leaves

- Phone ownership changes

- Society reports an invalid unit

- Invite link was misused

- Verification is older than the configured period

- Committee or facility records materially change

Recommended review period:

Owners: every 12–24 months

Tenants: according to lease/occupancy period

Society representatives: every committee term

Verification data model

society_memberships

- id

- society_id

- user_id

- membership_type

- tower

- unit_number_encrypted

- verification_level

- verification_status

- verification_method

- verified_at

- expires_at

- verified_by

- rejection_reason

- revoked_at

- created_at

- updated_at

Membership types:

OWNER

TENANT

FAMILY_MEMBER

AUTHORISED_OCCUPANT

SOCIETY_COMMITTEE

FACILITY_STAFF

SECURITY_STAFF

Invite table

society_invites

- id

- society_id

- token_hash

- invite_type

- max_uses

- used_count

- expires_at

- status

- created_by

- created_at

Store the token hash—not the raw reusable token.

Resident verification API

POST /api/societies/:id/membership/start

POST /api/societies/:id/membership/verify-phone

POST /api/societies/:id/membership/redeem-invite

POST /api/societies/:id/membership/submit

GET  /api/me/society-memberships

GET  /api/admin/societies/:id/membership-requests

PUT  /api/admin/society-memberships/:id/approve

PUT  /api/admin/society-memberships/:id/reject

PUT  /api/admin/society-memberships/:id/revoke

Every API must verify that the current user can access the exact society-membership object. OWASP identifies manipulation of object IDs as a major API risk and recommends object-level authorization checks whenever an endpoint receives a user-controlled record ID.

Verification-security rules

- Rate-limit OTP and invite attempts.

- Expire OTPs quickly.

- Prevent invite-token reuse beyond its limit.

- Encrypt or strongly protect unit numbers.

- Never expose complete resident lists publicly.

- Do not reveal whether a particular person lives in a society.

- Audit approvals, rejections and revocations.

- Require elevated permission for bulk verification.

- Return generic error messages for invalid resident data.

- Never trust a client-sent verification_status.

Resident-facing message

Verify your Green Acres residency to access society-only offers, local sitter availability, community events and resident support. Your verification details are used only to confirm society access and are not shown publicly.

3. Society sitter pool

Goal

Maintain enough trained, verified and locally available caregivers to serve the society without relying on one person.

Your proposed counts are a reasonable starting hypothesis:

| Role | Proposed count |
| --- | --- |
| Primary walkers | 3–5 |
| Backup walkers | 2–3 |
| Pet sitters | 2–5 |
| Boarding hosts nearby | 1–3 |
| Emergency veterinary partners | 1–2 |

However, the final requirement must depend on booking capacity, not only headcount.

Why headcount alone is insufficient

A society may have five walkers, but:

- Three may be unavailable in the morning.

- One may not handle large dogs.

- One may be under safety review.

- Two may already have overlapping bookings.

- Only one may be registered with security.

The real metric is:

Eligible sitter capacity

for each service window

Recommended launch capacity

Small society

Approximately 10–25 active pet households:

| Role | Recommended |
| --- | --- |
| Primary walkers | 2–3 |
| Backup candidates | 1–2 |
| Pet sitters | 1–2 |
| Boarding partners | 1 controlled |
| Vet coordination partners | 1 primary + 1 fallback |

Medium society

Approximately 25–60 active pet households:

| Role | Recommended |
| --- | --- |
| Primary walkers | 3–5 |
| Backup candidates | 2–3 |
| Pet sitters | 2–4 |
| Boarding partners | 1–2 |
| Vet partners | 1–2 |

Large premium society or township

More than 60 active pet households:

| Role | Recommended |
| --- | --- |
| Primary walkers | 5–10 |
| Backup candidates | 3–5 |
| Pet sitters | 3–6 |
| Boarding partners | 2–3 |
| Vet partners | 2+ |
| Operations coordinator | 1 named owner |

These are initial planning ranges. Actual staffing should be recalculated from demand and sitter utilisation.

Society sitter roles

Primary walker

A primary walker is eligible to receive ordinary confirmed walking assignments.

Requirements:

Identity verification

Dog-walking training

Society access active

Pet-size permission

Required handling skills

Active availability

Acceptable reliability

No safety restriction

Backup walker

A backup walker is not simply “another sitter.”

They must be able to:

- Reach the society within the required time

- Handle the same pet controls

- Work during the same slot

- Pass society entry requirements

- Avoid schedule conflicts

A candidate list should be refreshed close to service time. An old list does not constitute active backup coverage.

Pet sitter

Home sitting requires additional authorization:

- Home-entry training

- Key/access procedure

- Privacy expectations

- Food and medication task permissions

- Entry/exit confirmation

- Emergency handling

Boarding host

A boarding host must pass a separate process:

- Property approval

- Capacity limit

- Resident-animal information

- Safe separation space

- Escape prevention

- Vaccination/health policy

- Compatibility controls

- Emergency plan

- Society or property permission where required

Veterinary coordination partner

A listed partner may provide:

- Clinic contact

- Emergency coordination

- Vaccination camp

- Health-check camp

PetSaathi should label veterinary services as partner-delivered and should not represent itself as the clinical provider.

Society pool states

PENDING_ACCESS

ACTIVE

TEMPORARILY_UNAVAILABLE

CAPACITY_FULL

TRAINING_EXPIRED

VERIFICATION_EXPIRED

SAFETY_REVIEW

SUSPENDED

REVOKED

Only ACTIVE sitters should be considered for automatic candidate generation.

Capacity formula

Calculate available walking capacity by slot:

Available walk capacity =

Eligible active walkers

× safe walks per slot

− existing assigned walks

− reserved backup capacity

Example:

Morning active walkers: 4

Safe bookings per walker: 2

Total capacity: 8

Existing bookings: 6

Reserved backup capacity: 1

New capacity available: 1

Do not continue accepting bookings simply because the society package advertises priority matching.

Dependency protection

No society should depend entirely on one sitter.

Set alerts when:

One sitter handles more than 50% of society bookings

No eligible backup exists

Only one sitter can handle a required pet control

Peak-slot utilisation exceeds 85%

Suggested action:

- Recruit another local sitter

- Reduce booking cap

- Open a waitlist

- Alter service windows

- Add a paid standby option

- Stop promoting the affected slot

Society sitter-pool dashboard

Show administrators:

Active walkers

Active sitters

Backup candidates

Upcoming verification expiry

Upcoming training expiry

Morning capacity

Evening capacity

Current utilisation

Unavailable sitters

Open safety reviews

Single-sitter dependency

The society/security view should be limited to access-relevant fields:

Display name

Photograph

PetSaathi sitter ID

Approved service

Access status

Validity period

PetSaathi support contact

4. Society pet-care calendar

Goal

Create one calendar that helps residents understand:

- Available recurring care slots

- Society pet events

- Booking deadlines

- Seasonal pet-safety planning

- Package schedules

- Partner activities

Do not mix public society events with private individual bookings in the same public view.

Calendar layers

Layer A — Public society events

Visible to residents and, where approved, publicly on the society landing page:

- Grooming camp

- Vaccination camp

- Pet-parent meet-up

- Training workshop

- Pet first-aid awareness session

- Lost-pet preparedness session

Layer B — Verified-resident opportunities

Visible only after resident verification:

- Available dog-walking windows

- Pet-sitting availability

- Society plan enrolment deadlines

- Festival care registration

- Boarding request deadlines

- Resident-exclusive workshops

Layer C — Personal booking calendar

Visible only to the customer:

- Confirmed walks

- Pet-sitting visits

- Boarding check-in/out

- Payment deadline

- Sitter assignment

- Report Card status

Layer D — Operations calendar

Visible to authorised admins:

- Sitter shifts

- Backup coverage

- Event staffing

- Capacity blocks

- Verification expiries

- Partner availability

- Incident follow-ups

Dog-walking slots

The calendar may show:

Monday–Friday

6:30–7:00 AM — Limited availability

7:00–7:30 AM — Available

7:30–8:00 AM — Waitlist

5:30–6:00 PM — Available

6:00–6:30 PM — Full

Do not publicly show:

- Which resident booked

- Pet name

- Unit number

- Assigned sitter’s full schedule

- Exact handover location

A slot means a booking opportunity—not a guaranteed group walk.

Event calendar data

Each public event should include:

Event name

Event type

Society

Date

Start and end time

Venue

Capacity

Registration deadline

Partner

Price

Resident eligibility

Pet requirements

Cancellation status

Google’s Event structured-data documentation recommends providing dedicated event information such as location, start date and event details. Event markup may help qualifying public event pages become eligible for richer search presentation.

Use Event structured data only for genuine public or discoverable event pages—not for private resident bookings.

Calendar event states

DRAFT

SCHEDULED

REGISTRATION_OPEN

ALMOST_FULL

FULL

WAITLIST

REGISTRATION_CLOSED

IN_PROGRESS

COMPLETED

POSTPONED

CANCELLED

When an event is postponed, preserve the original schedule in history and notify registered residents.

Holiday and festival planning

Holiday boarding deadlines

Show clear operational deadlines:

Diwali boarding requests

Early registration opens: configured date

Standard deadline: configured date

Late requests: manual review

Final health confirmation: 24–48 hours before check-in

Do not use the same hard-coded date every year. Festival dates and operational capacity must be configured annually.

Diwali pet-safety planning

Recommended calendar content:

- Fireworks anxiety preparation session

- Pet Profile update deadline

- Medication/veterinary-plan reminder

- Quiet-room preparation guide

- Boarding/pet-sitting booking deadline

- Emergency contact confirmation

- Sitter availability notice

- Lost-pet prevention reminder

- Collar, tag and microchip information reminder

AWBI guidance supports responsible handling of pet dogs in common areas, and its public-parks guidance recognises reasonable walking timings rather than complete exclusion. Society calendar rules should support safe scheduling, not become a tool for blanket pet restrictions.

Recommended calendar views

Resident view

Month

Agenda

Upcoming events

Available walk slots

My bookings

Registration deadlines

Admin view

Capacity

Sitter shifts

Events

Partners

Booking deadlines

Coverage gaps

Verification expiries

Society management view

Only aggregate operational information:

Upcoming approved events

General service windows

Security preparation

Expected registered attendance

Approved partner/sitter access

Calendar reminders

Recommended reminder sequence:

Event

Registration confirmation

7 days before

24 hours before

2 hours before

Event completed / feedback

Dog-walking plan

Plan confirmed

Previous evening

30 minutes before

Service started

Report Card ready

Holiday boarding

Registration deadline approaching

Pet Profile incomplete

Vaccination information incomplete

Final health confirmation

Check-in reminder

A reminder should be cancelled when the event or booking is cancelled, rescheduled or already completed.

Calendar data model

society_calendar_events

- id

- society_id

- event_type

- visibility

- title

- description

- starts_at

- ends_at

- timezone

- venue

- capacity

- registration_count

- registration_deadline

- price_paise

- partner_id

- status

- recurrence_rule

- created_by

- created_at

- updated_at

Visibility:

PUBLIC

VERIFIED_RESIDENTS

REGISTERED_ATTENDEES

CUSTOMER_PRIVATE

ADMIN_ONLY

SOCIETY_OPERATIONS

Service slots

society_service_slots

- id

- society_id

- service_type

- day_of_week

- starts_at_local

- ends_at_local

- capacity

- reserved_capacity

- status

- effective_from

- effective_until

Registrations

society_event_registrations

- id

- event_id

- user_id

- pet_id

- registration_status

- payment_status

- consent_version

- registered_at

Calendar API

GET  /api/public/societies/:id/events

GET  /api/societies/:id/calendar

GET  /api/societies/:id/service-slots

POST /api/societies/:id/events/:eventId/register

POST /api/societies/:id/service-slots/:slotId/request

POST /api/admin/societies/:id/events

PUT  /api/admin/society-events/:id

PUT  /api/admin/society-events/:id/cancel

PUT  /api/admin/society-events/:id/postpone

A public event endpoint should not accidentally return private attendee or resident fields. OWASP warns that APIs may expose sensitive object properties even when a user is authorized to access the underlying object, so public and internal response models should remain separate.

End-to-end resident journey

Resident visits society page

↓

Selects “I live in this society”

↓

Phone and residency verification

↓

Society membership activated

↓

Resident sees local sitter pool and calendar

↓

Selects walking slot or event

↓

Creates/chooses Pet Profile

↓

System checks capacity and eligibility

↓

Payment or registration completed

↓

Confirmation and reminders sent

What is wrong in the original proposal?

Problem 1 — Flat number is treated as proof

Correction: Use phone verification plus invite, admin approval or another trusted method.

Problem 2 — WhatsApp number is treated as residency proof

Correction: It proves phone control, not physical residence.

Problem 3 — Fixed sitter counts ignore actual capacity

Correction: Measure eligible service capacity by slot, skill and risk controls.

Problem 4 — Backup walkers may also be busy

Correction: Revalidate availability, distance and eligibility when backup is required.

Problem 5 — Calendar could expose private bookings

Correction: Separate public, resident, personal and administrative layers.

Problem 6 — Society calendar may become a restriction tool

Correction: Use it for service availability and reasonable coordination, not blanket pet bans.

Problem 7 — Festival dates may be hard-coded

Correction: Configure exact dates, deadlines and capacity annually.

Definition of done

Resident verification

- Phone ownership is verified.

- Residency uses a second reliable method.

- Membership has an expiry/review process.

- Unit details remain protected.

- Society representatives receive limited information.

- Revoked residents lose private society access.

Sitter pool

- Every sitter has active service permission.

- Peak-slot capacity is measured.

- Backup candidates are genuinely usable.

- No society depends entirely on one sitter.

- Boarding and veterinary partners have separate approval.

- Expiring credentials produce alerts.

Calendar

- Public and private calendars are separated.

- Capacity and waitlists work.

- Rescheduling and cancellation work.

- Reminder workflows stop when obsolete.

- Festival deadlines are configurable.

- Event registration includes appropriate privacy and consent handling.

- Private attendee data is not returned through public APIs.

Final operating principle

Verify residents with layered evidence, manage sitters by real service capacity, and use the society calendar to coordinate care and events without exposing private bookings or creating unlawful pet restrictions.

Simple explanation for professor

“The resident-verification feature will confirm that a person genuinely belongs to a society before giving access to resident offers and private society services.

A flat number or WhatsApp number alone is not enough. The user will first verify the phone number and then use a society invite link, resident code or admin approval. Verification can expire or be revoked when the resident moves.

Each society will also have a local sitter pool. A medium society may begin with three to five primary walkers, two or three backup walkers, two to four pet sitters, nearby boarding partners and veterinary contacts. However, the system will measure actual availability and skills instead of relying only on the number of sitters.

The society calendar will show walking windows, grooming and vaccination camps, pet-parent meetings, training workshops and holiday booking deadlines. Public events, private resident opportunities, personal bookings and admin schedules will remain separate.

For Diwali, the calendar may include boarding deadlines, anxiety-preparation reminders, emergency-contact updates and lost-pet-prevention guidance. Dates will be configured for each year rather than hard-coded.

Together, these features ensure that society benefits are protected from misuse, local sitter supply is reliable and residents can easily plan recurring care and pet events.”

PetSaathi Phase 7 — Lost-Pet Alert and Society Pet-Parent Community 🐾🚨🏢

Executive decision

Approve both features with strict boundaries:

| Feature | Decision | Main rule |
| --- | --- | --- |
| Lost-pet alert | Approve as a controlled emergency feature | Time-limited, verified and privacy-safe |
| Society pet-parent community | Approve with WhatsApp for MVP | Voluntary, moderated and not used for incident management |

The two systems should work together but remain separate:

Lost pet reported

↓

PetSaathi verifies the alert

↓

Structured alert record created

↓

Society security notified

↓

Opted-in residents receive alert

↓

Sightings submitted privately

↓

Pet found or alert expires

The WhatsApp group distributes approved community information. The PetSaathi database remains the authoritative record for alerts, sightings, incidents and resolutions.

5. Lost-pet alert system

Goal

Help reunite an owned pet with its family quickly while protecting:

- The owner’s personal information

- The resident’s apartment details

- The pet from unsafe handling

- Society residents from false or excessive notifications

- Community animals from being incorrectly labelled as lost pets

Current pet photographs and up-to-date identification are important for recovering missing animals. AVMA recommends keeping identification and microchip information current, while lost-pet guidance from the ASPCA recommends using a recent photograph, physical description, last-seen information and contact details in search materials.

Recommended lost-pet alert information

Public or resident-visible fields

Pet photograph

Pet name

Species

Breed/general description

Colour and distinguishing marks

Sex

Approximate size

Last-seen society area

Last-seen date and time

Safe approach instructions

Alert ID

PetSaathi/admin contact

Optional information

- Collar colour

- Harness colour

- Microchip status: YES / NO / UNKNOWN

- Whether the pet is anxious

- Whether the pet should be approached

- Reward information, after owner confirmation

Do not display publicly

Exact apartment number

Owner’s full private phone number

Pet medical records

Bite-history details

Internal risk classification

Full GPS history

Door-access instructions

Owner emergency contacts

Identity documents

The DPDP Act and final DPDP Rules establish India’s framework for handling digital personal data. The final rules were published on November 14, 2025 with staged commencement provisions, so the alert must collect only necessary information, explain its purpose and restrict who can access sensitive fields.

Important contact correction

The proposal includes:

Owner contact

For safety, do not publish the owner’s direct number by default.

Use one of these:

Call PetSaathi Support

Send a private sighting report

Call society security

Masked owner-contact relay

The owner may explicitly choose to display a contact number, but PetSaathi should explain that residents may forward or screenshot the alert.

Recommended alert contact block

Seen Bruno?
Do not chase him. Submit a sighting through PetSaathi or call society security.
Alert: LPA-1024

Lost-pet alert activation flow

Step 1 — Owner reports the pet missing

The owner selects:

Report Missing Pet

The system asks:

- Which registered pet is missing?

- When was the pet last seen?

- Where was the pet last seen?

- Who last saw the pet?

- Is the pet wearing a collar or harness?

- Is the pet injured or medically vulnerable?

- Is the pet friendly, fearful or likely to run?

- Can residents approach the pet?

- Should society security be contacted?

- Which contact method may PetSaathi use?

Step 2 — Immediate safety instructions

Before alert publication, show:

Search the home and immediate common areas.

Inform society security.

Check stairs, parking areas, gardens and utility spaces.

Keep gates informed.

Do not ask untrained residents to chase a frightened pet.

Contact local shelters, veterinary clinics or appropriate authorities

when the pet may have left the society.

The alert should complement—not replace—local searches, veterinary clinics, shelters or municipal reporting. ASPCA lost-pet guidance recommends checking the immediate area, contacting shelters, veterinary hospitals and local agencies, and sharing consistent recent photographs and descriptions.

Step 3 — Alert verification

Do not instantly broadcast every submitted alert.

Verify:

Reporter owns or is authorised for the pet

Pet Profile exists

Pet photograph is current

Last-seen information is plausible

Society membership is verified

Owner consents to selected information being shared

Alert is not a duplicate

Emergency exception

For an active PetSaathi service where the sitter reports an escape:

Alert status = ACTIVE_EMERGENCY

Incident ticket = created immediately

Society security = notified immediately

Owner = contacted immediately

The normal approval step may happen in parallel.

Step 4 — Create alert

Recommended alert states:

DRAFT

VERIFICATION_REQUIRED

ACTIVE_URGENT

ACTIVE

SIGHTING_REPORTED

SEARCH_AREA_UPDATED

OWNER_CONTACTED

PET_FOUND

EXPIRED

CANCELLED

FALSE_REPORT_REVIEW

ARCHIVED

Priority levels

| Priority | Example |
| --- | --- |
| Critical | Pet in traffic, injured, medically vulnerable or escaped during service |
| High | Pet recently missing inside society |
| Standard | Pet missing for longer period with no immediate hazard |
| Informational | Pet found and owner being located |

Step 5 — Alert distribution

Notify only relevant audiences.

Primary audience

- Society security

- PetSaathi operations

- Verified society residents who opted into alerts

- Pet-parent community members

- Assigned sitter or active search team

Optional expanded audience

- Nearby partner veterinarian

- Adjacent PetSaathi societies

- Local shelters or animal-support organisations

- Nearby opted-in PetSaathi users

Do not send an Ahmedabad alert to all PetSaathi customers across the city.

Geographic notification levels

Level 1 — Same society

Level 2 — Nearby society cluster

Level 3 — Selected locality

Level 4 — Wider city circulation after admin review

Escalation should depend on:

- Time missing

- Reliable sightings

- Whether the pet may have exited the society

- Pet mobility

- Safety concerns

- Owner consent

Sighting-report workflow

Residents should not reply with sightings only in a busy WhatsApp group.

Provide:

Report a Sighting

Ask:

- Where did you see the pet?

- When?

- Was the pet moving in a particular direction?

- Did you approach it?

- Do you have a photograph?

- Can PetSaathi contact you?

- Is the pet currently in immediate danger?

Sighting privacy

A sighting should be visible to:

- Owner

- PetSaathi incident/search administrator

- Society security where necessary

Do not publish the reporting resident’s identity to the whole community.

Sighting states

SUBMITTED

UNDER_REVIEW

LIKELY_MATCH

CONFIRMED

NOT_A_MATCH

DUPLICATE

FALSE_REPORT

A single unverified sighting should not automatically change the public last-seen location.

Safe approach instructions

Every alert should contain one of these:

APPROACH_CALMLY

DO_NOT_CHASE

DO_NOT_APPROACH

OFFER_FOOD_AND_NOTIFY

KEEP_VISUAL_CONTACT

CONTACT_SECURITY_IMMEDIATELY

Example:

Bruno may run when frightened. Please do not chase or surround him. Keep him in sight from a safe distance and contact PetSaathi immediately.

Pet found workflow

Possible match located

↓

Owner/pet identity confirmed

↓

Pet condition checked

↓

Veterinary review recommended where necessary

↓

Active alert closed

↓

All alert channels updated

↓

Post-incident review created

Closing notification

Bruno has been found safely. Thank you to Green Acres residents and security for helping. This alert is now closed.

Remove or expire public alert links after closure. Retain only the internal records required for safety, audit and incident review.

Anti-spam rules

Notification limits

Use:

Initial alert

One meaningful search-area update

One confirmed sighting update where useful

Found/closed notification

Do not broadcast:

- Every unverified sighting

- Repeated “still missing” messages every hour

- Emotional speculation

- Unverified accusations

- Graphic media

- Personal disputes

Quiet hours

Critical missing-pet alerts may override quiet hours.

Routine community announcements should follow configured hours.

Lost-pet alert data model

lost_pet_alerts

id

public_code

pet_id

owner_id

society_id

incident_id

status

priority

last_seen_at

last_seen_area

last_seen_lat

last_seen_lng

public_description

approach_instruction

public_contact_mode

owner_contact_private

admin_owner_id

activated_at

expires_at

found_at

closed_at

created_at

updated_at

lost_pet_sightings

id

alert_id

reported_by

reported_at

sighting_time

area_description

lat

lng

media_reference

description

status

reviewed_by

created_at

lost_pet_notifications

id

alert_id

audience_type

channel

recipient_reference

message_version

status

sent_at

delivered_at

Recommended lost-pet APIs

POST /api/pets/:id/lost-alert

GET  /api/lost-pet-alerts/:code

POST /api/lost-pet-alerts/:code/sightings

PUT  /api/lost-pet-alerts/:id/found

PUT  /api/lost-pet-alerts/:id/cancel

GET  /api/admin/lost-pet-alerts

PUT  /api/admin/lost-pet-alerts/:id/activate

PUT  /api/admin/lost-pet-alerts/:id/escalate

PUT  /api/admin/lost-pet-alerts/:id/close

Public APIs should return only the approved alert fields, not the complete pet or owner database record.

Prevention feature

The lost-pet system should also encourage prevention:

Current pet photo

Updated phone details

Collar and identification tag

Microchip status

Harness/collar escape history

PetSaathi emergency contact

Safe approach instructions

AVMA recommends keeping identification and microchip information current, and emergency guidance recommends maintaining current pet photographs for identification.

6. Society pet-parent community

Goal

Create a trusted resident communication channel for:

- Pet-care announcements

- Society events

- Local service updates

- Sitter introductions

- Responsible pet-care education

- Lost-pet alerts

- Pet-parent networking

- Resident feedback

For the Phase 7 MVP, WhatsApp is sufficient, but it should not become PetSaathi’s operational database.

Recommended MVP structure

Instead of one noisy group, use:

A. Announcement group or community

Admins publish:

- Service launches

- Grooming/vaccination camps

- Workshop dates

- Walking-plan enrolment

- Holiday-care deadlines

- Verified lost-pet alerts

- Important service updates

Residents do not need to reply to every announcement.

B. Pet-parent discussion group

Residents may discuss:

- Pet-friendly local resources

- General experiences

- Event questions

- Walking-plan interest

- Community recommendations

This group needs moderation.

C. Private support chat

Use 1:1 PetSaathi WhatsApp support for:

- Booking problems

- Payments

- Refunds

- Complaints

- Pet Profile questions

- Individual sitter issues

- Emergencies

D. Formal incident system

Use the PetSaathi platform for:

- Injuries

- Bites

- Missing pets

- Unsafe handling

- Privacy complaints

- Serious service failures

WhatsApp message

↓

Support recognises safety issue

↓

Incident ticket created

↓

Incident ID shared privately

WhatsApp consent

Residents should join voluntarily through:

- QR code

- Invite link

- Resident onboarding form

- Community opt-in checkbox

Meta’s WhatsApp Business guidance requires businesses to obtain opt-in before sending business messages to users. PetSaathi should record when, where and for what type of communication the resident opted in.

Suggested consent text

I agree to receive PetSaathi society service updates, event announcements and urgent lost-pet alerts on WhatsApp. I can leave the group or change my communication preferences at any time.

Keep separate preferences for:

Service notifications

Community announcements

Events and offers

Lost-pet emergency alerts

Marketing

Joining an operational alert channel should not automatically create marketing consent.

Important WhatsApp product decision

Meta now documents WhatsApp group capabilities for its Business Platform, but its group functionality has account and onboarding requirements and is not identical to ordinary WhatsApp Business app groups. For the MVP, PetSaathi should use a manually administered WhatsApp group or Community unless there is a clear need and eligibility for API-driven group automation.

Do not delay Phase 7 by building a complex group-management integration.

Community membership rules

Only allow:

Verified society residents

Authorised society contacts

Approved PetSaathi moderators

Selected partner experts during defined events

Do not automatically add:

- All society phone numbers

- Former residents

- Sitters who do not need community access

- Sponsors

- Groomers or vendors permanently

- Unverified outside users

Recommended group name

Green Acres Pet Parents × PetSaathi

Description:

Verified resident community for PetSaathi service updates, pet-care events, responsible pet-parent coordination and approved lost-pet alerts. For booking or emergency support, contact PetSaathi privately.

Community rules

Pin these rules:

- Respect all residents and animals.

- Do not share apartment numbers, access codes or private contact details.

- Do not provide veterinary diagnoses or medication instructions.

- Do not publicly accuse a sitter, resident or pet.

- Report safety concerns privately to PetSaathi.

- Do not post commercial promotions without admin permission.

- Use lost-pet alerts only through the verified process.

- Do not share graphic or distressing content.

- Do not target pets by breed.

- Repeated violations may result in removal.

Allowed content

PetSaathi service announcements

Event calendar

Walking-plan availability

Sitter introductions

Pet-care education

Verified lost-pet alerts

Found-pet updates

General pet-parent questions

Society-approved partner events

Restricted content

Home access details

Resident telephone lists

Pet medical records

Unverified sitter complaints

Payment screenshots

Full GPS routes

Risk classifications

Private incident media

Personal conflicts

Unapproved advertising

Moderation roles

PetSaathi moderator

- Publishes verified service updates

- Handles lost-pet alerts

- Removes unsafe content

- Redirects complaints

- Records significant violations

- Escalates incidents

Society representative

- Confirms society operational announcements

- Helps manage access/event information

- Does not access private bookings or Pet Profiles

Veterinary/partner guest

- Added only for a scheduled session

- Restricted to the relevant topic

- Removed after the event when no longer needed

Community escalation model

Normal question

→ Community response

Booking issue

→ Private PetSaathi support

Complaint

→ Complaint ticket

Safety concern

→ Incident ticket

Missing pet

→ Lost-pet alert workflow

Medical emergency

→ Owner + registered veterinarian + incident workflow

Verified service updates

Only post confirmed information.

Examples:

Morning walking slots: Two 7:00–7:30 AM slots are available next week.

Grooming camp: Registration is open for Sunday, August 16. Appointment required.

Service update: Evening walks are temporarily paused due to severe weather. Affected customers are being contacted privately.

Do not share:

Riya has cancelled again because she is unreliable.

Use:

Affected bookings are being reassigned. Customers will receive private updates.

WhatsApp retention and official records

Important operational information should be copied into PetSaathi’s structured system.

| WhatsApp content | Authoritative PetSaathi record |
| --- | --- |
| Booking request | Booking |
| Refund question | Support/refund ticket |
| Sitter complaint | Complaint |
| Injury report | Incident |
| Missing pet | Lost-pet alert |
| Event registration | Event registration |
| Sighting | Lost-pet sighting |

WhatsApp chat history must not be the only evidence for a serious safety or financial matter.

Future in-app society group

Build the in-app community later when WhatsApp creates problems such as:

- Too much spam

- Difficult moderation

- Resident phone-number exposure

- Lost history

- Limited role control

- Poor event organization

- Safety reports mixed with casual chat

Future in-app features

Society announcements

Event registration

Verified-resident profiles

Topic channels

Lost-pet alerts

Private sighting reports

Moderation tools

Report post

Block user

Role permissions

Searchable history

Notification preferences

Do not add direct peer-to-peer chat until moderation, abuse reporting and privacy controls are ready.

Community data model

society_communities

id

society_id

name

platform

external_group_reference

status

join_policy

created_at

society_community_memberships

id

community_id

user_id

role

membership_status

opt_in_version

joined_at

left_at

removed_reason

society_announcements

id

society_id

announcement_type

title

body

visibility

related_event_id

related_alert_id

published_by

published_at

expires_at

Metrics

Lost-pet alert metrics

| Metric | Target |
| --- | --- |
| Verified alerts before standard broadcast | 100% |
| Critical alerts activated quickly | Immediate |
| Alerts with current photo | 95%+ |
| Alerts with safe-approach guidance | 100% |
| Unauthorised owner-contact exposure | 0 |
| Duplicate alerts | Near zero |
| Closed alerts updated across channels | 100% |
| False or malicious alert review | 100% |

Community metrics

| Metric | Desired result |
| --- | --- |
| Verified resident membership | 100% |
| Opt-in recorded | 100% |
| Emergency reports converted to tickets | 100% |
| Spam complaints | Low |
| Community-to-paid-booking conversion | Increasing |
| Event registration conversion | Increasing |
| Serious privacy breaches | 0 |
| Messages requiring admin moderation | Track and reduce |

What is wrong in the original proposal?

Problem 1 — Publishing the owner’s direct contact

Correction: Use PetSaathi, society security or masked contact by default.

Problem 2 — Every resident can broadcast an alert

Correction: Alerts should be verified before standard distribution.

Problem 3 — A sighting in WhatsApp changes the search area

Correction: Sightings require structured submission and review.

Problem 4 — One group handles everything

Correction: Separate announcements, community discussion, private support and incidents.

Problem 5 — Adding residents without consent

Correction: Residents must voluntarily opt in; business messaging requires prior opt-in.

Problem 6 — WhatsApp becomes the incident database

Correction: Every safety or financial issue must have a structured PetSaathi record.

Problem 7 — Lost-pet alerts could target community animals

Correction: The feature is for verified owned pets. Community-animal matters use separate lawful coordination processes.

Definition of done

Lost-pet alert

- Reporter and pet ownership are verified.

- A current photograph is available.

- Owner contact is protected by default.

- Alert contains safe-approach instructions.

- Society security is included in the workflow.

- Sightings are submitted privately.

- Alerts expire or close correctly.

- Incident records are created for service-related escapes.

- Community animals cannot be falsely processed as owned missing pets.

Society community

- Membership is opt-in.

- Residents are verified.

- Community rules are pinned.

- Moderators are assigned.

- Announcements and discussion are separated where possible.

- Emergencies move to private support.

- Complaints and incidents become structured records.

- Marketing consent remains separate.

- Residents can leave or change notification preferences.

Final operating principle

Use the community to distribute verified information and build trust, but use PetSaathi’s structured systems to manage bookings, sightings, incidents, refunds and private resident data.

Simple explanation for professor

“The lost-pet alert feature will help society residents and security find an owned pet that has gone missing.

The owner will report the pet through PetSaathi and provide a current photograph, the pet’s name, description, last-seen location and safe approach instructions. PetSaathi will verify the report before sending it to residents.

The owner’s apartment number and personal phone number will not be publicly displayed by default. Residents will contact PetSaathi or society security, or submit a private sighting report. When the pet is found, the alert will be closed across all channels.

For the pet-parent community, WhatsApp is sufficient for the MVP. Residents must voluntarily join the community. It can be used for PetSaathi announcements, event information, walking-plan availability, pet-care awareness and verified lost-pet alerts.

However, WhatsApp will not be used as the official incident or booking system. A complaint, injury, refund issue or missing-pet report will always create a structured record inside PetSaathi.

This design allows the community to remain useful and friendly while protecting residents from spam, privacy exposure and unverified information.”

PetSaathi Society Partnership Pitch Deck

Recommended 10-slide structure 🐾🏢

The proposed structure is strong. The deck should tell one simple story:

Society-level pet-care problems

↓

PetSaathi’s organised service model

↓

Benefits for every stakeholder

↓

Safety and operating controls

↓

Low-risk pilot

↓

Evidence and commercial partnership

The deck should not present PetSaathi as a system for controlling pets or enforcing blanket pet restrictions. AWBI publishes specific guidance for pet owners, caregivers, RWAs and apartment-owner associations, so the positioning should focus on responsible coexistence, verified care and organised access.

Slide 1 — The problem

Objective

Show that apartment pet care is not only a pet-parent problem. It also affects security teams, society managers and other residents.

Recommended headline

Pet care inside apartment communities is still fragmented, informal and difficult to manage.

Slide content

Pet parents struggle with

- Reliable daily dog walking

- Pet care during office hours and travel

- Finding screened caregivers

- Last-minute cancellations

- Receiving trustworthy service updates

- Emergency coordination

Societies struggle with

- Unknown helpers entering the premises

- Unstructured gate approvals

- Resident complaints and misunderstandings

- No formal escalation process

- No reliable list of service providers

- Pet-care issues being managed through scattered WhatsApp messages

Better visual

Use a two-column layout:

PET PARENTS                  SOCIETY OPERATIONS

No reliable walker          Unknown service providers

Travel-care stress          Gate-access confusion

No service proof            Unstructured complaints

Last-minute cancellations stress          Gate-access confusion

No service   No escalation process

Presenter explanation

“Pet parents need reliable support, but the society also needs controlled access, clear operating rules and a proper complaint process. Today, these needs are usually handled informally.”

Avoid

Do not write:

- “Pets create problems in societies.”

- “We solve pet menace.”

- “We control society pets.”

- “We eliminate pet and non-pet conflict.”

Use:

We reduce unmanaged pet-care and access issues through a structured service process.

Slide 2 — The solution

Objective

Explain PetSaathi in one sentence and show the complete resident experience.

Recommended headline

A verified pet-care network designed for apartment communities.

Main statement

PetSaathi connects society residents with approved-access dog walkers, pet sitters and screened boarding partners, supported by service updates, Report Cards and responsive operations.

Core solution blocks

Verified care

- Dog walkers

- Home pet sitters

- Screened boarding beta

- Approved specialist partners

Transparent service

- Sitter profile and verification indicators

- Arrival and service updates

- Basic GPS proof for dog walks

- Photos and videos

- Automated Pet Report Cards

Operational support

- Sitter replacement workflow

- Structured complaints and incidents

- Emergency veterinary coordination

- Cancellation and refund support

Suggested process visual

Resident books

↓

Pet Profile reviewed

↓

Eligible local sitter assigned

↓

Payment confirmed

↓

Society entry prepared

↓

Service completed

↓

Report Card delivered

Presenter explanation

“PetSaathi manages the complete workflow—from resident booking and sitter matching to society access, service evidence, Report Cards and issue resolution.”

Important wording

Use:

Emergency veterinary coordination through registered partners

Do not use:

PetSaathi emergency veterinary treatment

Veterinary practice in India is regulated through the Indian Veterinary Council Acterinary practitioners. citeturn393327search12

Slide 3 — Benefits for the entire society

Objective

Demonstrate that the partnership benefits more than pet owners.

Recommended headline

One programme. Benefits for every society stakeholder.

| Stakeholder | Benefit |
| --- | --- |
| Pet parents | Convenient, reliable and documented care |
| RWA/facility manager | Organised service process and fewer unmanaged issues |
| Security team | Approved sitter roster and clear access workflow |
| Non-pet residents | Better service timings, cleanliness expectations and complaint routing |
| Sitters | Verified access and dense local bookings |
| Veterinary/grooming partners | Qualified local demand |
| Society | Stronger resident amenity and community trust |

Stronger benefit line

PetSaathi supports responsible coexistence—not pet control.

Additional operating benefits

- Reduced sitter travel time

- Faster replacements

- Better same-sitter continuity

- More recurring walking plans

- Lower resident-acquisition cost

- Society-level performance visibility

Presenter explanation

“The main advantage is density. When several residents use the service in the same society, sitters travel less, arrive more reliably and can provide repeat care more efficiently.”

Slide 4 — Safety and verification

Objective

Answer the society committee’s most important question:

“How do you protect residents, pets and the society?”

Recommended headline

Trust is built through layered controls—not one badge.

Suggested six-part safety system

1. Sitter review

- Identity verification

- Interview

- Service-specific training

- Experience and reference review

- Service permissions

2. Society access

- Active sitter roster

- Photo and PetSaathi ID

- Access validity

- Replacement-sitter approval

- Entry and exit procedure

3. Pet Profile

- Behaviour and handling information

- Medical and food instructions

- Emergency contacts

- Service-specific care controls

4. Service proof

- Arrival confirmation

- Start and end time

- Basic GPS evidence for walks

- Photo/video updates

- Pet Report Card

5. Reliability system

- Punctuality

- Completion rate

- Customer ratings

- Report quality

- Cancellation/no-show history

6. Incident support

- Structured incident ticket

- Severity and escalation

- Customer communication

- Corrective action

- Refund and payout review

Suggested visual

Use a shield in the centre with six surrounding controls:

Verification

Pet Profile

Society access

Service proof

Incident workflow

Emergency coordination

Presenter explanation

“We do not claim zero risk. We reduce operational risk through verification, Pet Profiles, controlled matching, service evidence and a documented escalation process.”

Claims to avoid

- “100% safe”

- “Completely risk-free”

- “Guaranteed trusted”

- “Zero incidents”

- “Police-approved platform”

Advertising and pitch claims should be factual, honest and supportable; ASCI’s code specifically emphasises truthful represenainst misleading claims. citeturn393327search6

Slide 5 — Society services

Objective

Show the service menu without making the MVP look unfocused.

Recommended headline

Everyday care, travel support and community pet services.

Organise services into three groups

Core resident services

| Service | Status |
| --- | --- |
| Daily dog walking | Active |
| Home pet sitting | Active |
| Walking packages | Active |
| Same-sitter repeat requests | Active |
| Controlled boarding | Beta |

Trust and support services

| Service | Status |
| --- | --- |
| Pet Report Cards | Active |
| Basic GPS walk proof | Active |
| Lost-pet alert | Active |
| Emergency veterinary coordination | Basic/partner-led |
| Pet-parent community | Active |

Partner-led society activities

| Activity | Status |
| --- | --- |
| Grooming camp | Partner-led |
| Vaccination camp | Registered-veterinarian partner |
| Pet health-check camp | Veterinary partner |
| Dog-training workshop | Screened trainer |
| Pet-parent meet-up | Society event |

Important slide rule

Do not give every service equal visual importance.

Highlight:

- Dog walking

- Pet sitting

- Report Cards

- Society access

- Emergency coordination

Keep camps and events as secondary benefits.

Presenter explanation

“Daily walking and home sitting are our core recurring services. Boarding remains controlled, while grooming, vaccination and training activities are delivered through appropriate verified partners.”

Slide 6 — The pilot offer

Objective

Make the first decision easy and low risk for the society.

Recommended headline

Start with a controlled 30-day society pilot.

Better package name

No-Fee Society Setup Pilot

This is clearer than calling the whole offer “free,” because residents still pay for the individual services they book.

Included

- No society setup fee

- No society partnership fee during the pilot

- Society-specific resident booking page

- Resident trial pricing

- Approved-access sitter roster

- WhatsApp booking assistance

- Pet-care awareness poster

- Pet-parent introduction session

- Basic society access setup

- Aggregate pilot summary

Residents pay for

- Dog-walking bookings

- Pet-sitting bookings

- Boarding or partner services

- Packages purchased after the trial

Recommended pilot boundaries

Duration: 21–30 days

Booking cap: Based on local sitter capacity

Services: Dog walking + pet sitting

Societies: Selected qualified pilots

Automatic renewal: No

Pilot success measurements

- Registered pet parents

- Paid services

- On-time rate

- Report Card delivery

- Resident rating

- Repeat interest

- Security-entry failures

- Society complaints

- Committee continuation interest

Presenter explanation

“The society does not need to commit to a long contract immediately. We first test resident demand, sitter access, service quality and repeat interest through a controlled pilot.”

Slide 7 — Partnership packages

Objective

Show the long-term commercial path without overwhelming the committee.

Recommended headline

Choose the partnership level that matches your community.

| Package | Society fee | Best for | Key inclusions |
| --- | --- | --- | --- |
| No-Fee Pilot | ₹0 for 15–30 days | First validation | Trial offer, sitter roster, support and summary |
| Basic Society Partner | ₹5,000–₹15,000/month | Active medium societies | Landing page, resident benefits, priority matching, reporting |
| Premium Pet-Care Desk | ₹15,000–₹50,000/month | Premium gated communities | Named coordinator, recurring slots, events, enhanced support |
| Event/Camp Model | Event-specific | Lead generation | Health, grooming, vaccination, workshops and meet-ups |

Add:

Residents continue to pay separately for the individual care services they book.

Pricing clarification

The price should depend on:

- Number of homes

- Active pet households

- Towers and gates

- Support hours

- Booking volume

- Coordinator time

- Event frequency

- Reporting needs

Avoid

Do not use:

“Plus commission”

unless the contract defines:

- Who pays it

- Who receives it

- The calculation basis

- Treatment of taxes, refunds and discounts

Use:

Society retainer plus PetSaathi’s standard contribution from completed resident service bookings.

Presenter explanation

“The pilot helps us find the right long-term model. Smaller societies may need only a digital partnership, while larger communities may need regular walking slots, a named coordinator and partner events.”

Slide 8 — Launch process

Objective

Show that implementation is controlled and uncomplicated.

Recommended headline

From society approval to live resident services in six steps.

Recommended flow

1. Society approval

↓

2. Access and operating rules configured

↓

3. Resident announcement and opt-in

↓

4. Local sitter pool mapped

↓

5. Trial bookings launched

↓

6. Monthly performance review

Expanded explanation

Step 1 — Society approval

- Authorised committee/facility contact

- Pilot scope

- Services and timings

- Data-sharing boundaries

Step 2 — Society setup

- Gate process

- Approved sitter roster

- Support contacts

- Emergency workflow

Step 3 — Resident onboarding

- Society landing page

- QR code

- Voluntary registration

- Pet Profile creation

Step 4 — Sitter readiness

- Society access

- Local availability

- Backup candidates

- Service permissions

Step 5 — Controlled bookings

- Limited booking cap

- Active monitoring

- Report Cards

- Reviews

Step 6 — Review

- Bookings

- Ratings

- Repeat demand

- Access failures

- Complaints

- Partnership recommendation

Privacy note

Residents should register through an opt-in form. The society should not simply give PetSaathi its complete resident contact list.

India’s DPDP Act recognises the protection of digital personal data, and the final DPDP Rules were published on November 14, 2025 with staged commencement. The deck should therefore promise voluntary registration, purpose-liting. citeturn393327search2turn393327search11

Slide 9 — Case study or pilot evidence

Objective

Prove that PetSaathi can deliver—not just present an idea.

Recommended headline

Early evidence from controlled PetSaathi operations

Only use actual verified data

Do not invent:

- Number of bookings

- Customer ratings

- Repeat percentages

- Testimonials

- Society partnerships

- Sitter counts

- GPS success rates

Recommended case-study format

Pilot overview

City:

Active area:

Pilot duration:

Active services:

Verified sitters:

Key results

Paid bookings:

Completed bookings:

On-time service rate:

Report Cards delivered:

Average rating:

Repeat customers:

Refund/dispute rate:

Operational result

“PetSaathi reduced the average administrative follow-up required per booking from ___ minutes to ___ minutes.”

Resident testimonial

“____________________________”

Include only with permission.

Learning

“The highest repeat demand came from __________, while the main operating challenge was __________.”

When Phase 5 data is not ready

Rename the slide:

Pilot success metrics

Show what the society pilot will measure:

- Paid resident bookings

- Service completion

- On-time arrival

- Report Card delivery

- Repeat plans

- Resident rating

- Entry failures

- Complaints

- Committee satisfaction

This is more trustworthy than presenting fictional data.

Suggested visual

Use four large metric cards and one short testimonial.

Avoid dense charts unless the data sample is meaningful.

Slide 10 — Call to action

Objective

Ask the committee for one clear next step.

Recommended headline

Start a controlled PetSaathi pilot in your society.

Primary CTA

Approve a 30-day verified pet-care pilot.

What happens next

15-minute society discovery call

↓

Resident-demand survey

↓

Access and service review

↓

Pilot proposal

↓

Launch date

Information required from the society

- Authorised committee/facility contact

- Approximate occupied homes

- Estimated pet households

- Security-entry process

- Preferred service timings

- Resident communication channel

- Pilot approval process

Closing line

Safer pet-care access. Better society coordination. Happier pet parents.

Contact area

Include:

- PetSaathi contact person

- Phone/WhatsApp

- Email

- Website

- QR code

- City/operating area

Strong presenter close

“We are not asking the society to commit to a complex long-term programme today. We are asking for approval to test a controlled, measurable 30-day service with verified local sitters and transparent reporting.”

Recommended deck narrative

The deck should flow emotionally and logically:

Slide 1:

There is an unmanaged operational problem.

Slide 2:

PetSaathi has an organised solution.

Slide 3:

Every stakeholder benefits.

Slide 4:

Safety and verification are built into the process.

Slide 5:

The society receives useful recurring services.

Slide 6:

The first step is low risk.

Slide 7:

There is a clear long-term partnership model.

Slide 8:

Implementation is simple.

Slide 9:

Results are measurable.

Slide 10:

Approve the pilot.

Recommended design direction

Visual style

- Premium

- Warm

- Trustworthy

- Spacious

- Mobile-app inspired

- Community-focused

Colour system

- Cream or warm white background

- Soft blue for trust

- Pet-friendly green for safety/status

- Warm orange for calls to action

- Dark charcoal for readable text

Typography

Use a modern rounded sans-serif such as:

- Manrope

- Plus Jakarta Sans

- Inter

- DM Sans

Visual assets

Use:

- Real Indian apartment-community settings

- Genuine pet-parent and sitter interactions

- Service Report Card previews

- Society access visuals

- Simple process diagrams

- Minimal icons

Avoid:

- Excessive generic stock photos

- Aggressive pet imagery

- Security-guard stereotypes

- Fake dashboard screenshots

- Too many paw icons

- Long paragraphs

Slide text limits

Recommended:

One main idea per slide

One headline

Three to six key points

No paragraph longer than three lines

Essential legal and credibility footer

Add a small footer on relevant slides:

Services are subject to Pet Profile review, sitter eligibility, availability and applicable society procedures. Veterinary services are delivered through qualified partners. PetSaathi does not guarantee zero risk.

On pricing slides:

Prices are indicative and subject to final scope, applicable taxes and local operating requirements.

On case-study slides:

Results reflect the specified pilot period and sample.

Pitch delivery length

Five-minute society pitch

| Section | Time |
| --- | --- |
| Problem | 35 seconds |
| Solution | 40 seconds |
| Stakeholder benefits | 35 seconds |
| Safety | 50 seconds |
| Services | 35 seconds |
| Pilot | 45 seconds |
| Packages | 30 seconds |
| Launch process | 30 seconds |
| Evidence | 30 seconds |
| CTA | 20 seconds |

Two-minute summary

“PetSaathi provides verified pet-care support for apartment communities. Residents can book dog walkers and home pet sitters through a structured platform with Pet Profiles, approved-access caregivers, payment verification, service updates and Pet Report Cards.

The society benefits from a controlled sitter roster, clearer entry procedures, a formal complaint process and better coordination between pet parents, security and management. We can also coordinate screened boarding, partner-led grooming or vaccination camps and emergency veterinary contacts.

We recommend beginning with a controlled 30-day pilot. There is no society setup fee during the pilot; residents pay for only the services they book. PetSaathi manages onboarding, sitter access, WhatsApp support, trial bookings and an aggregate performance report.

At the end of the pilot, we review paid bookings, punctuality, resident ratings, repeat demand, entry issues and complaints. The society can then decide whether to continue with a Bsic Partner or Premium Pet-Care Desk programme.”

PetSaathi Phase 7 — Society Outreach System 🏢🐾

Executive decision

Your channel list is strong, but the outreach system should not treat every channel equally.

The most effective sequence is:

Existing pet parent or local partner introduction

↓

RWA/facility-manager conversation

↓

Resident-demand validation

↓

15-minute discovery meeting

↓

Society pilot proposal

↓

Security and access discussion

↓

Resident opt-in campaign

↓

Controlled pilot launch

WhatsApp should be the primary follow-up and conversion channel, not the default cold-prospecting channel. Meta requires businesses to obtain opt-in before messaging people on WhatsApp. For SMS and commercial calls, TRAI’s framework similarly centres commercial communications on customer consent and registered sender processes.

1. Society outreach channel priorities

Priority 1 — Warm introductions and resident-led access

These should generate the highest-quality conversations.

Pet-parent groups

Purpose: Prove resident demand before approaching the committee.

A society committee is more likely to consider the proposal when several residents already want:

- Daily walking support

- Travel-time sitting

- Same-sitter plans

- Festival care

- Grooming or veterinary-partner camps

Recommended process

Existing resident expresses interest

↓

Resident introduces PetSaathi to pet-parent group admin

↓

Admin approves one information post

↓

Interested residents opt in

↓

PetSaathi measures demand

↓

Resident champion introduces RWA/facility manager

Do not add residents to a group or contact them individually from a society list without an appropriate opt-in. Under India’s current data-protection framework, PetSaathi should explain what information is collected, why it is needed and how it will be used.

Best lead indicator

10+ residents interested

or

5+ residents ready for a paid trial

A WhatsApp group with 200 members but only one potential customer is not meaningful demand.

Priority 2 — Direct B2B decision-makers

RWA or managing committee

Role: Commercial and policy approval.

Discuss:

- Resident benefit

- Approved sitter access

- Pilot duration

- Data-sharing limits

- Complaint escalation

- Society reporting

- Commercial package after pilot

The committee pitch should focus on organised pet-care access and coexistence, not controlling or restricting pets.

Best first contact

- Warm resident introduction

- Email or LinkedIn introduction

- Short phone call

- Permission-based WhatsApp follow-up

- Formal meeting

Desired outcome

Not an immediate contract. The first outcome should be:

A 15-minute society discovery meeting.

Facility manager

Role: Operational champion.

Facility managers usually understand:

- Visitor access

- Security procedures

- Tower and gate complexity

- Existing resident complaints

- Event permissions

- Common-area limitations

- Committee approval processes

The facility manager may not have authority to sign the partnership, but can determine whether the programme is operationally possible.

Questions to ask

- How are external service providers currently registered?

- Does security require advance approval?

- Are there permitted service hours?

- Is there an active pet-parent group?

- How many towers and gates are involved?

- Who can formally approve a pilot?

- Are resident events permitted?

- What complaints commonly occur?

Security office

Role: Access-design stakeholder, not initial sales target.

Security should be engaged after the society or facility manager shows interest.

Discuss:

- Sitter photo and PetSaathi ID

- Access validity

- Booking confirmation

- Entry and exit procedures

- Replacement sitter approval

- Emergency escalation

- Revoked sitter access

Do not expect the security team to approve the commercial pilot.

2. Local trust and referral channels

Local veterinarians

Purpose

Veterinary clinics can:

- Introduce PetSaathi to pet-heavy societies

- Participate in health or vaccination camps

- Provide emergency-coordination contacts

- Refer busy pet parents

- Strengthen local credibility

Recommended partnership request

Do not begin by asking:

“Can you promote PetSaathi to all customers?”

Use:

“We are building verified society-level pet-care support. We would like to explore resident education, referral and veterinary-partner coordination in nearby apartment communities.”

Referral tracking

Record:

Partner

Society referred

Introduction date

Meeting completed

Pilot signed

Paid residents acquired

Referral fee or commercial terms

Medical recommendations must remain under the control of qualified veterinary professionals; PetSaathi should describe veterinary services as partner-delivered coordination rather than its own clinical care.

Pet shops and groomers

Purpose

Pet shops often know:

- High-pet-density societies

- Active pet-parent groups

- Frequently travelling customers

- Local grooming demand

- Communities interested in events

Partnership options

- Society introduction

- QR referral cards

- Grooming camp

- Co-hosted awareness event

- Resident offer

- Fixed converted-customer referral fee

Avoid exchanging full customer lists. Use resident-controlled QR forms or referral links.

Dog parks and walking areas

Purpose

Use them for market observation and voluntary conversations, not aggressive selling.

Learn:

- Which societies have many dog owners

- Popular walking times

- Common pet-care problems

- Existing walker networks

- Society clusters with high demand

Good field approach

“We are researching verified pet-care support for nearby apartment communities. Which societies in this area have active pet-parent groups?”

Do not photograph, record or collect resident information without permission.

3. Digital outreach channels

LinkedIn

Best targets

- Facility managers

- Property managers

- Community managers

- RWA office bearers with public professional profiles

- Real-estate developer experience teams

- Premium property-management companies

Correct method

Use highly personalised outreach:

Name

Society/property

Area

Relevant operational problem

One-sentence PetSaathi solution

15-minute meeting request

Do not use automated mass connection requests. LinkedIn states that excessive invitations, ignored invitations, spam reports or suspected automation can lead to account restrictions; it recommends relevant, thoughtful invitations.

Suggested cadence

Day 1: Personalised connection request

Day 3–4: Short value message after acceptance

Day 7: Share one-page pilot summary

Day 12: Final polite follow-up

Then stop

Facebook groups

Best groups

- Local apartment-community groups

- Area pet-parent groups

- City dog-owner groups

- Resident community groups

- Local lost-and-found pet groups

Correct approach

Ask the administrator before promotional posting.

Post useful content first:

- Society pet-care checklist

- Festival pet-safety guide

- How to verify a dog walker

- Travel-care preparation

- Lost-pet prevention

Meta allows Pages to participate in or create groups, but group administrators and members can moderate or report spam.

Avoid

- Posting identical advertisements in dozens of groups

- Repeatedly commenting “DM us”

- Messaging group members privately without invitation

- Claiming unverified society partnerships

- Using resident posts to build hidden contact lists

WhatsApp

Best use

WhatsApp is ideal for:

- Warm introductions

- Permission-based follow-up

- Resident interest collection

- Meeting confirmation

- Pilot updates

- Booking assistance

- Event registration

- Service notifications

Meta requires an opt-in before a business initiates WhatsApp communication. Marketing messages and utility messages also serve different purposes: marketing templates promote offers, while utility templates generally follow a user action or request.

Correct acquisition flow

Poster / resident group / referral

↓

Resident clicks WhatsApp link

↓

Resident sends “PET”

↓

Opt-in and interest recorded

↓

PetSaathi shares details

↓

Resident books or joins waitlist

Incorrect flow

Society shares 300 resident phone numbers

↓

PetSaathi sends bulk promotional messages

TRAI treats unwanted commercial messages and calls as unsolicited commercial communications and provides complaint/reporting mechanisms.

4. Recommended channel allocation

| Channel | Primary purpose | Priority |
| --- | --- | --- |
| Existing pet parents | Warm society introductions | P0 |
| RWA/committee | Partnership approval | P0 |
| Facility manager | Operational qualification | P0 |
| Pet-parent groups | Demand validation | P0 |
| Local vets | Trust and society introductions | P1 |
| Pet shops/groomers | Referrals and events | P1 |
| LinkedIn | Professional decision-maker outreach | P1 |
| WhatsApp | Opt-in follow-up and conversion | P1 |
| Security office | Access design after interest | P1 |
| Dog parks | Market discovery | P2 |
| Facebook groups | Awareness and community leads | P2 |

5. End-to-end outreach workflow

Step 1 — Build a qualified society list

For each society, record:

Society name

Area

Approximate homes

Estimated pet-parent density

Facility manager

RWA/committee contact

Existing resident champion

Security complexity

Nearby sitter capacity

Nearby veterinary partner

Lead source

Do not purchase or scrape private resident contact lists.

Step 2 — Score every society

Recommended score:

| Factor | Weight |
| --- | --- |
| Resident pet demand | 25% |
| Local sitter supply | 20% |
| Geographic fit | 15% |
| Committee accessibility | 15% |
| Security feasibility | 10% |
| Society size | 10% |
| Nearby partner ecosystem | 5% |

Priority classification:

80–100: Priority target

60–79: Qualified target

40–59: Nurture

Below 40: Do not actively pursue

Step 3 — Identify three contacts

For every target society, find:

- Resident champion

- Operational contact

- Decision-maker

Example:

Resident champion: Pet-parent group administrator

Operational contact: Facility manager

Decision-maker: RWA secretary

This is stronger than relying on one person.

Step 4 — Send the first message

The first message should:

- Identify the sender

- Explain the local relevance

- Present one clear benefit

- Request only 15 minutes

- Avoid sending large attachments

- Avoid unsupported claims

ASCI’s current code requires objectively verifiable advertising claims to be capable of substantiation. Therefore, use “screened,” “identity reviewed” or “trained” only where PetSaathi actually performs and records those checks.

Step 5 — Follow-up cadence

B2B prospect

Day 1: First introduction

Day 3: Short follow-up

Day 7: Send one-page pilot summary

Day 12: Final follow-up

Day 30: Re-engage only with meaningful new information

Stop following up when:

- The person declines

- They request no further messages

- The society is not interested

- Contact details appear incorrect

- Multiple messages receive no response

Step 6 — Conduct a discovery call

15-minute agenda

Minutes 0–3:

Society overview and current pet-care situation

Minutes 3–7:

Resident demand and common problems

Minutes 7–10:

Security and access process

Minutes 10–13:

PetSaathi pilot model

Minutes 13–15:

Decision process and next step

Discovery questions

- How many homes are occupied?

- Is there an active pet-parent group?

- What are the most common pet-care needs?

- How are outside walkers currently admitted?

- Are there common security or cleanliness issues?

- Which service timings are most useful?

- Who must approve a pilot?

- Would the society distribute an opt-in resident survey?

Step 7 — Validate resident demand

Use a short opt-in survey:

Name

Society/tower

Phone

Pet type

Interested service

Preferred time

Trial interest

Consent to receive PetSaathi information

Do not ask for medical or behavioural information during lead collection. Collect that later through the private Pet Profile.

Step 8 — Present the pilot

Recommended pilot:

Duration: 21–30 days

Society setup fee: ₹0

Partnership fee: ₹0

Residents pay for booked services

Initial services: Walking + sitting

Booking cap: Based on sitter capacity

Monthly aggregate summary: Included

Automatic renewal: No

Step 9 — Configure and launch

Pilot approved

↓

Society record created

↓

Gate procedures documented

↓

Local sitter roster approved

↓

Resident announcement released

↓

Registrations opened

↓

First bookings monitored

↓

Pilot review

6. CRM pipeline

Use these stages:

IDENTIFIED

QUALIFIED

INTRODUCTION_REQUESTED

CONTACTED

REPLIED

DISCOVERY_SCHEDULED

DISCOVERY_COMPLETED

RESIDENT_SURVEY

PROPOSAL_SENT

COMMITTEE_REVIEW

PILOT_APPROVED

SETUP_IN_PROGRESS

ACTIVE_PILOT

CONVERTED

NURTURE

LOST

Required loss reasons

NO_RESIDENT_DEMAND

NO_COMMITTEE_APPROVAL

NO_LOCAL_SITTER_SUPPLY

SECURITY_NOT_FEASIBLE

PRICE_OBJECTION

EXISTING_PROVIDER

FOLLOW_UP_LATER

NO_RESPONSE

LEGAL_OR_POLICY_CONCERN

7. Outreach KPIs

Activity metrics

| Metric | Weekly target during outreach |
| --- | --- |
| Qualified societies researched | 10–15 |
| Warm introductions requested | 5–10 |
| Personalised B2B messages | 15–25 |
| Follow-ups completed | 15–25 |
| Partner conversations | 3–5 |

Conversion metrics

| Funnel | Initial target |
| --- | --- |
| Contacted → response | 20–40% |
| Response → discovery call | 40–60% |
| Discovery → resident survey | 40–60% |
| Survey → proposal | 40–60% |
| Proposal → pilot | 25–50% |
| Pilot → paid partnership | 30–60% |

These are planning targets, not guaranteed benchmarks. Actual results should be segmented by lead source.

Lead-source quality

Track:

Meetings

Pilots

Paid resident bookings

Repeat plans

Revenue

Acquisition cost

A channel producing many contacts but no paid bookings should be deprioritised.

8. Corrected society outreach message

Your original message is useful, but it makes three claims too broadly:

- “safe boarding” should be screened or controlled boarding beta

- Not every service necessarily contains video updates

- Veterinary care should be described as coordination through qualified partners

Here is the stronger version:

Hi [Name],

I’m [Your Name] from PetSaathi. We are launching a structured pet-care support programme for apartment communities in [Area].

PetSaathi helps residents book:

• screened dog walkers
• in-home pet sitters
• controlled boarding, where available
• emergency veterinary coordination through registered partners
• partner-led grooming and vaccination camps

Our service workflow includes sitter screening, society-access coordination, booking updates and a Pet Report Card after completed services. Dog walks may also include basic GPS and photo proof.

We would like to offer [Society Name] a controlled 30-day pilot with no society setup fee. Residents would pay only for the services they choose to book.

Would you be available for a 15-minute discussion on [Option 1] or [Option 2]?

Regards,
[Your Name]
PetSaathi
[Phone / WhatsApp]
[Website]

9. Corrected pet-parent group message

The group message should be posted by the group administrator or with their permission. “Reply PET” creates a clear expression of interest, after which PetSaathi can respond privately.

Hi everyone 🐾

PetSaathi is planning a verified pet-care pilot for residents of [Society/Area].

Available services may include:

• 30-minute and 60-minute dog walks
• in-home pet sitting
• screened boarding beta
• emergency veterinary coordination through registered partners

Residents receive booking updates and a Pet Report Card after completed services. Dog walks may also include basic GPS and photo proof.

🎉 Launch offer: First eligible 30-minute dog walk from ₹99, subject to sitter availability, Pet Profile review and pilot capacity.

Reply PET or use this link to receive the service details privately: [Opt-in Link]

Your contact information will be used only to share PetSaathi pilot and booking information. You may opt out at any time.

10. Short first-contact version

Use this for LinkedIn or a warm WhatsApp introduction:

Hi [Name], I’m [Your Name] from PetSaathi.

We help apartment communities organise verified dog-walking and pet-sitting support with approved sitter access, service updates, Pet Report Cards and a structured issue-escalation process.

We are selecting a small number of societies in [Area] for a 30-day pilot with no society setup fee.

Would a 15-minute introductory discussion be possible this week?

These messages can be shortened further for specific surfaces, but the legal and operational qualifications should remain intact.

11. Recommended outreach assets

Prepare these before contacting societies:

- Ten-slide society pitch deck

- One-page pilot summary

- Society FAQ

- Resident interest form

- Sitter verification explainer

- Sample Pet Report Card

- Society access workflow

- Pilot pricing sheet

- Privacy and data-sharing summary

- Calendar-booking link

Do not send all ten assets in the first message. Use:

First message:

Short introduction

After interest:

One-page summary

Before meeting:

Pitch deck

After meeting:

Custom pilot proposal

12. Common outreach mistakes

Mistake 1 — Cold WhatsApp blasting

Problem: Low trust, spam reports and weak consent.

Correction: Use introductions, public opt-in links and permission-based follow-up. Meta requires business messaging opt-in, while TRAI provides mechanisms to report unwanted commercial communications.

Mistake 2 — Selling to security first

Problem: Security rarely has commercial authority.

Correction: Get society or facility approval first, then design the access process with security.

Mistake 3 — Starting with every service

Problem: The pitch becomes complex.

Correction: Lead with dog walking and pet sitting. Present boarding and partner camps as controlled secondary offerings.

Mistake 4 — Promising “verified” without defining it

Correction: Explain whether verification includes identity review, interview, training, society access or other checks.

Mistake 5 — Asking the society for its resident database

Correction: Ask the society to distribute a resident-controlled opt-in form.

Mistake 6 — No clear CTA

Correction: Request a 15-minute discovery call, not a vague “let us know.”

Mistake 7 — Repeated follow-ups

Correction: Use a limited cadence and respect decline or silence.

Mistake 8 — Measuring only replies

Correction: Measure pilot approvals, paid bookings, repeat services and contribution margin.

Final operating principle

Use residents and trusted local partners to open doors, use committees and facility managers to approve the programme, use security to operationalise access, and use permission-based WhatsApp communication to convert interested residents into bookings.

Simple explanation for professor

“PetSaathi will use different outreach channels for different purposes.

Pet parents and local veterinary or pet-shop partners can introduce us to societies where real demand already exists. The RWA or committee will make the partnership decision, while the facility manager will help us understand service timings, security procedures and common resident concerns. The security office will be involved after the society shows interest so that sitter entry and replacement rules can be configured.

LinkedIn will be used for personalised contact with facility and property managers. Facebook groups and dog parks will mainly help us identify pet-parent communities and society clusters. WhatsApp will be the main follow-up and resident-conversion channel, but residents must voluntarily request information or opt in.

The first outreach message will briefly explain PetSaathi and request a 15-minute meeting. After a society responds, we will conduct a discovery call, run a resident-interest survey and present a controlled 30-day pilot.

The society should not give PetSaathi its full resident contact list. Residents will register themselves through a QR code or opt-in form.

The success of outreach will not be measured only by messages or meetings. We will track signed pilots, paid resident bookings, repeat walking plans, customer ratings and the contribution generated by each society.”

A monthly compliance watch for WhatsApp, TRAI, privacy and advertising changes would help keep these outreach templates current.

PetSaathi Phase 7 — Week 1: Society Partnership Preparation 🏢🐾

Week 1 objective

By the end of Day 7, PetSaathi should possess a complete society-sales and pilot-launch kit that allows the team to:

Identify a suitable society

↓

Contact the decision-maker

↓

Explain the business model

↓

Validate resident demand

↓

Send a formal pilot proposal

↓

Sign a pilot agreement

↓

Configure the society page

↓

Begin resident onboarding

Week 1 is not for approaching hundreds of societies immediately. It is for creating one consistent system so that pricing, safety claims, resident privacy, operations and contract terms do not change from one sales conversation to another.

Recommended Week 1 sequence

| Day | Task | Primary output |
| --- | --- | --- |
| Day 1 | Finalise society offer | Approved packages and commercial rules |
| Day 2 | Create pitch deck | 7–10 slide presentation and PDF |
| Day 3 | Build landing-page template | Reusable society page |
| Day 4 | Prepare outreach scripts | WhatsApp, email, call and follow-up templates |
| Day 5 | Configure society CRM | Lead pipeline and reporting sheet |
| Day 6 | Draft pilot agreement | Legal and operational pilot document |
| Day 7 | Review all launch material | Outreach-ready partnership kit |

Day 1 — Finalise the society offer

Goal

Create one approved commercial and operational framework that tells the team:

- Which packages exist

- Who each package is for

- What is included

- What remains excluded

- Who pays

- What residents pay separately

- What PetSaathi promises

- What PetSaathi does not promise

Step 1: Approve the four-package ladder

Package 1 — No-Fee Society Pilot

Best for: first-time society testing.

Society setup fee: ₹0

Pilot partnership fee: ₹0

Duration: 15–30 days

Recommended default: 21–30 days

Resident care services: Paid

Automatic renewal: No

Included:

- Society onboarding

- Resident trial offer

- Approved-access sitter roster

- WhatsApp booking assistance

- Awareness poster

- Society landing page

- Aggregate pilot report

Package 2 — Basic Society Partner

Best for: societies that have demonstrated real resident demand.

Price:

₹5,000–₹15,000 per month

+ applicable taxes

Included:

- Society-specific landing page

- Resident benefits

- Priority matching among eligible sitters

- Monthly aggregate report

- Dedicated WhatsApp routing

- Named operations owner

- Society access roster

Package 3 — Premium Pet-Care Desk

Best for: larger premium societies and townships.

Price:

₹15,000–₹50,000 per month

+ applicable taxes

Included:

- Named coordinator

- Regular walking windows

- Enhanced sitter and backup pool

- Partner-led camps

- Society events

- Lost-pet alert system

- Safety reporting

- Priority escalation

A full-time exclusive on-site coordinator should remain a separately priced staffing arrangement.

Package 4 — Event and Camp Programme

Best for: lead generation and resident activation.

Possible events:

- Veterinary-partner health-check camp

- Registered-veterinarian vaccination camp

- Grooming camp

- Pet-parent meetup

- Humane training workshop

Revenue may come from:

Event coordination fee

+

Transparent ticket income

+

Sponsor contribution

+

Defined partner revenue share

+

Future care bookings

Step 2: Approve the positioning

Official positioning

PetSaathi helps apartment communities organise verified pet-care support through approved-access dog walkers, in-home pet sitters, screened boarding partners, service updates, Report Cards and structured issue escalation.

Avoid

- “We manage all pets in your society.”

- “We solve the pet menace.”

- “Completely safe pet care.”

- “Guaranteed trusted sitters.”

- “Zero-risk care.”

AWBI’s published guidance addresses pet owners, caregivers, RWAs and apartment-owner associations and states that RWAs and AOAs should not impose blanket bans on keeping pet dogs. PetSaathi should therefore sell responsible service coordination and coexistence—not pet control.

ASCI’s advertising code requires claims to be truthful, supportable and not misleading through wording or omission. Terms such as “verified,” “safe,” “free” and “guaranteed” must therefore be precisely defined.

Step 3: Define package boundaries

Create an inclusion matrix:

| Capability | Pilot | Basic | Premium | Event |
| --- | --- | --- | --- | --- |
| Society landing page | Yes | Yes | Yes | Event page |
| Resident booking support | Basic | Priority | Enhanced | Event-specific |
| Approved sitter roster | Yes | Yes | Enhanced | As needed |
| Monthly report | Pilot summary | Yes | Detailed | Event report |
| Coordinator | Shared operations | Named owner | Named coordinator | Event lead |
| Resident events | No/optional | Limited | Included by tier | Core |
| Veterinary services | Coordination | Coordination | Partner-led | Partner-led |
| Guaranteed sitter | No | No | No | No |
| Resident care included in fee | No | No | No | Only if contract states |
| Private resident data for society | No | No | No | No |

Step 4: Finalise pricing rules

Every package should state:

Society fee

Applicable taxes

Resident booking charges

Discount funding

Partner charges

Event charges

Refund responsibility

Renewal terms

Termination notice

Digital service pages and checkouts should clearly communicate service identity, prices, payment terms, refund terms and grievance mechanisms. India’s Consumer Protection (E-Commerce) Rules apply to services sold digitally and contain disclosure and grievance-related obligations.

Day 1 output

Create a document named:

PetSaathi_Society_Package_Matrix_v1

It should contain:

- Positioning statement

- Package comparison

- Pricing

- Included and excluded features

- Support hours

- Resident charges

- Commercial assumptions

- Safety disclaimers

- Data-sharing restrictions

- Approval owner

Day 1 definition of done

- All packages have exact names.

- “Free” clearly means no society partnership fee—not free resident care.

- “Priority” does not mean guaranteed availability.

- Veterinary services are described as partner-led coordination.

- Pricing and taxes are clearly stated.

- Package limits are measurable.

- The founder, operations lead and finance owner approve the final matrix.

Day 2 — Create the society pitch deck

Goal

Produce a persuasive presentation that a committee or facility manager can understand within five to ten minutes.

Recommended 10-slide structure

Slide 1 — Society problem

Cover:

- Unverified helpers

- Inconsistent dog walking

- Travel-related pet-care needs

- Gate-entry confusion

- Scattered complaints

- Last-minute cancellations

Slide 2 — PetSaathi solution

Show:

Resident booking

→ Pet Profile

→ Eligible sitter

→ Payment

→ Society access

→ Service

→ Report Card

Slide 3 — Stakeholder benefits

Include:

- Pet parents

- RWA or manager

- Security

- Non-pet residents

- Sitters

- Veterinary and grooming partners

Slide 4 — Safety and verification

Show:

- Identity review

- Interview

- Service training

- Pet Profile

- Society-access controls

- Service proof

- Incident workflow

Slide 5 — Services

Prioritise:

- Dog walking

- In-home sitting

- Walking packages

- Report Cards

- Emergency veterinary coordination

Show boarding and camps as secondary or controlled services.

Slide 6 — Pilot offer

Explain:

30-day controlled pilot

No society setup fee

Residents pay for booked services

Approved sitter roster

Resident support

Aggregate report

Slide 7 — Packages

Show all four packages without excessive detail.

Slide 8 — Launch process

Approval

→ Access setup

→ Resident announcement

→ Registrations

→ Sitter mapping

→ Trial bookings

→ Pilot report

Slide 9 — Evidence

Use only verified PetSaathi data.

Include:

- Completed bookings

- On-time rate

- Report Card delivery

- Ratings

- Repeat customers

- Testimonials with permission

When actual data is unavailable, label the slide:

Pilot Success Measures

Never fabricate traction.

Slide 10 — Call to action

Approve a controlled 30-day PetSaathi pilot for your society.

Pitch-deck quality rules

- One idea per slide

- Maximum five or six short points

- Large, readable typography

- Real or licensed imagery

- No invented customer metrics

- No unsupported “100% safe” claims

- Pricing marked indicative when not final

- Strong CTA and contact details

Day 2 output

Create:

PetSaathi_Society_Pitch_Deck_v1.pptx

PetSaathi_Society_Pitch_Deck_v1.pdf

Also create:

PetSaathi_5_Minute_Pitch_Notes

Day 2 definition of done

- Deck can be delivered in under seven minutes.

- Claims match actual product functionality.

- Pricing matches Day 1.

- Pilot terms match the agreement draft.

- No fake metrics or endorsements appear.

- The PDF is readable on mobile.

- The final slide contains one clear action.

Day 3 — Create the reusable society landing-page template

Goal

Build one technical template that can generate accurate society pages without manually redesigning each page.

Recommended route

/pet-care/societies/[city]/[societySlug]

Example:

/pet-care/societies/ahmedabad/green-acres-bopal

Next.js App Router supports dynamic route segments such as [city] and [societySlug]. Dynamic metadata can also be generated from route-specific data using generateMetadata.

Recommended page sections

- Society identity

- Active partnership status

- Available services

- Resident offer

- Booking CTA

- Local sitter summaries

- How booking works

- Safety controls

- Society access information

- Report Card preview

- Emergency coordination

- FAQs

- Partner veterinarian/groomer

- Privacy and policy links

Data-driven architecture

society

services

resident offer

active sitter summaries

access rules

partners

FAQs

programme metrics

support information

Do not hard-code society names and details inside the React components.

Public-page restrictions

Do not expose:

- Resident names

- Flat numbers

- Private phone numbers

- Gate codes

- Pet medical information

- Full GPS routes

- KYC documents

- Internal complaint data

The DPDP Rules, 2025 were published on November 14, 2025 with staggered commencement dates. Landing-page registration and lead forms should therefore be designed with clear notices, defined purposes, restricted access and controlled retention from the beginning.

SEO publication rules

Use page states:

DRAFT

PILOT

ACTIVE

PAUSED

ENDED

ARCHIVED

Only complete and genuinely active society pages should normally be indexable.

Google treats large numbers of substantially similar location pages created mainly to rank for related searches as potential doorway or scaled-content abuse. Every indexed society page should contain authentic local services, availability, access rules, FAQs and operating information.

Day 3 output

Create:

SocietyLandingPage

SocietyServiceCard

SocietySitterCard

ResidentOfferCard

SocietyTrustSection

SocietyFAQ

SocietyPartnerCard

SocietyBookingCTA

And a sample page for one fictional or approved pilot society.

Day 3 definition of done

- Society data is loaded dynamically.

- Inactive services cannot be booked.

- The society ID is attached to the booking.

- Private data never enters the public response.

- Draft pages use noindex.

- Metadata is society-specific.

- The page is responsive and mobile-first.

- The CTA works from page to booking flow.

Day 4 — Create outreach scripts

Goal

Give every team member approved language for contacting societies and residents.

Required script library

1. RWA/committee message

Purpose:

- Explain the local problem

- Introduce PetSaathi

- Offer a pilot

- Request a 15-minute call

2. Facility-manager message

Focus on:

- Service-provider access

- Gate procedures

- Walking timings

- Resident support

- Operational reporting

3. Resident champion message

Ask for:

- Pet-parent demand

- Introduction to the group admin

- Introduction to committee/facility contact

4. Veterinarian/pet-shop message

Focus on:

- Society introductions

- Partner-led events

- Referral arrangements

- Local pet-care ecosystem

5. Pet-parent group announcement

Include:

- Available services

- Trial offer

- Opt-in link

- Privacy notice

- Capacity limits

6. Email introduction

Use a more formal version with:

- Problem

- Solution

- Pilot summary

- Meeting request

- One-page attachment

7. Follow-up messages

Prepare:

Day 3 follow-up

Day 7 value follow-up

Day 12 final polite follow-up

WhatsApp compliance rule

Businesses must obtain user opt-in before sending WhatsApp business messages, and messages should be relevant to the permission provided. Society residents should therefore join through an invite, QR link or resident-initiated conversation rather than being imported into a promotional list.

Script claims checklist

Every script should answer:

- What does “verified” mean?

- Is boarding active or beta?

- Are veterinary services partner-led?

- Are residents paying?

- Is sitter availability guaranteed?

- Is the offer limited?

- How can recipients opt out?

Day 4 output

Create:

PetSaathi_Society_Outreach_Script_Library_v1

Containing:

- Four WhatsApp scripts

- Two email templates

- One phone-call opener

- One discovery-call agenda

- Three follow-up messages

- One resident group announcement

- One opt-out response

- One rejection/nurture response

Day 4 definition of done

- Messages are personalised, not spam-like.

- Resident outreach requires opt-in.

- No unsupported safety promises appear.

- The CTA asks for one clear next step.

- Boarding and veterinary claims are accurate.

- Follow-up stops after rejection or opt-out.

- All team members use the same approved wording.

Day 5 — Create the society CRM

Goal

Build one source of truth for every society opportunity.

A spreadsheet can be sufficient for the first 50–100 prospects. The important requirement is a consistent pipeline—not sophisticated software.

CRM pipeline stages

IDENTIFIED

QUALIFIED

INTRODUCTION_REQUESTED

CONTACTED

REPLIED

DISCOVERY_SCHEDULED

DISCOVERY_COMPLETED

RESIDENT_SURVEY

PROPOSAL_SENT

COMMITTEE_REVIEW

PILOT_APPROVED

SETUP_IN_PROGRESS

ACTIVE_PILOT

CONVERTED

NURTURE

LOST

Required CRM fields

Society details

- Society name

- City

- Area

- Approximate homes

- Number of towers

- Number of gates

- Estimated pet households

- Walking environment

- Existing pet-parent group

Contacts

- Resident champion

- RWA contact

- Facility manager

- Security contact

- Contact channel

- Contact permission

- Last interaction

Commercial information

- Proposed package

- Estimated monthly potential

- Price objection

- Existing provider

- Decision timeline

- Proposal value

Operational information

- Nearby sitter count

- Morning capacity

- Evening capacity

- Backup availability

- Gate complexity

- Local vet partner

- Pilot feasibility

Pipeline data

- Current stage

- Next action

- Next action date

- Owner

- Lead source

- Probability

- Lost reason

Qualification score

| Factor | Weight |
| --- | --- |
| Resident demand | 25% |
| Local sitter supply | 20% |
| Geographic cluster fit | 15% |
| Decision-maker access | 15% |
| Security feasibility | 10% |
| Society size | 10% |
| Local partner ecosystem | 5% |

CRM dashboards

Track:

- Prospects by stage

- Meetings scheduled

- Proposals open

- Pilot conversion

- Lead source

- Next actions overdue

- Estimated residents

- Active society pipeline value

- Lost reasons

Day 5 output

Create:

PetSaathi_Society_CRM_v1

Recommended tabs:

- Society pipeline

- Contacts

- Activity log

- Resident-survey results

- Proposal tracker

- Pilot tracker

- Dashboard

- Dropdown/reference data

Day 5 definition of done

- Every prospect has an owner.

- Every active opportunity has a next action.

- Duplicate societies are identified.

- Contact consent/source is recorded.

- Lost reasons are standardised.

- Society qualification is measurable.

- The dashboard updates from CRM data.

Day 6 — Create the pilot agreement draft

Goal

Prepare a short but operationally complete agreement for legal review and society negotiation.

This is not merely a sales proposal. It must clearly allocate obligations between:

PetSaathi

Society/RWA/AOA

Residents

Sitters

Professional partners

Under the Indian Contract Act, agreements become contracts when legal requirements such as competent parties, free consent, lawful consideration and lawful object are satisfied. The draft should be reviewed by a qualified Indian lawyer before use across different society and state structures.

Recommended agreement sections

1. Parties

- PetSaathi legal entity

- Society/RWA/AOA legal name

- Registered address

- Authorised representative

- Effective date

2. Purpose

Controlled resident pet-care pilot within the named society.

3. Duration

Start date

End date

No automatic renewal

Extension process

4. Pilot services

Specify exactly:

- Dog walking

- In-home sitting

- Controlled boarding, if applicable

- Resident support

- Partner events, if applicable

5. Commercial terms

- Society fee

- Resident service pricing

- Taxes

- Discounts

- Payment responsibility

- Refund responsibility

- Partner charges

6. PetSaathi responsibilities

- Maintain sitter approval records

- Control assignment

- Process bookings/payment

- Provide service updates

- Manage complaints/incidents

- Protect resident information

- Provide aggregate report

7. Society responsibilities

- Nominate authorised contacts

- Share approved resident announcement

- Define gate procedure

- Support approved sitter access

- Notify changes

- Avoid unauthorised resident-data sharing

- Route complaints through the agreed channel

8. Resident relationship

State that:

- Residents register voluntarily.

- Residents provide accurate Pet Profiles.

- Individual service contracts/payments remain separate unless expressly agreed.

- The society does not guarantee individual services.

9. Sitter access

Define:

- Registration

- Photo/ID display

- Validity

- Replacement access

- Revocation

- Emergency entry

10. Safety and incidents

Include:

- Incident reporting

- Emergency contacts

- Cooperation

- Evidence preservation

- No guarantee of zero risk

- Authority to pause services

11. Veterinary and specialist partners

State that clinical or specialist services are delivered by appropriately qualified partners and not by ordinary PetSaathi support staff.

12. Data protection

Cover:

- Data collected

- Purpose

- Who can access it

- Society reporting

- Retention

- Security

- Incident notification

- Resident requests

13. Brand usage

- Society-name/logo permission

- PetSaathi branding

- Testimonials

- Photography

- Public announcements

14. Liability and indemnity

This section requires lawyer-led drafting based on the legal entity, insurance and state-specific society structure.

15. Termination

Include:

- Notice period

- Immediate suspension reasons

- Safety obstruction

- Non-payment

- Data misuse

- Illegal demands

- Unauthorised branding

- Repeated sitter-access refusal

16. Disputes and governing law

Require legal advice for:

- Jurisdiction

- Arbitration

- Notice

- Escalation

- Governing law

Day 6 output

Create:

PetSaathi_Society_Pilot_Agreement_Draft_v1

Also prepare:

Schedule A — Active Services

Schedule B — Pricing

Schedule C — Access SOP

Schedule D — Data Sharing

Schedule E — Support and Escalation

Day 6 definition of done

- Parties and authorised signatories are clear.

- Resident payments are separated from society fees.

- Services and exclusions are explicit.

- Data sharing is minimal.

- Brand permission is documented.

- Emergency responsibilities are realistic.

- No party is promised zero risk.

- Legal-review notes are clearly marked.

- Agreement terms match the pitch deck and package list.

Day 7 — Review all launch materials

Goal

Perform a cross-functional consistency review before society outreach begins.

Review team

Include:

- Founder/product owner

- Operations lead

- Engineering lead

- Finance owner

- Safety owner

- Marketing/sales owner

- Legal adviser

- Privacy/security reviewer

Review 1 — Commercial consistency

Confirm that the same prices appear in:

- Package list

- Pitch deck

- Landing page

- Outreach scripts

- Proposal

- Agreement

- CRM

Review 2 — Claims consistency

Check words such as:

Verified

Safe

Free

Guaranteed

Emergency

Veterinary

Approved

Certified

Dedicated

Priority

Each word must have a defined meaning.

Review 3 — Product consistency

Confirm that advertised functionality actually exists:

- Booking

- Payment

- Sitter assignment

- Report Card

- Incident handling

- Resident verification

- Landing page

- Support channel

Review 4 — Privacy consistency

Confirm:

- Resident registration is opt-in.

- Society does not receive private Pet Profiles.

- Contact lists are not uploaded casually.

- Public pages expose only public fields.

- CRM stores only necessary business-contact data.

- Lead forms include notices.

Review 5 — Operational consistency

Run a tabletop test:

Society approves pilot

↓

Resident registers

↓

First booking is created

↓

Sitter reaches gate

↓

Service completes

↓

Report Card is sent

↓

Complaint occurs

↓

Pilot report is generated

Every step must have an owner and SOP.

Review 6 — Technical test

Test:

- Landing-page mobile layout

- Society-specific metadata

- CTA

- CRM form

- WhatsApp link

- Resident lead form

- PDF download

- Email attachments

- Analytics events

- Error states

Review 7 — Legal and consumer review

Check:

- Prices

- Taxes

- Refund terms

- Grievance contact

- Service-provider identity

- Veterinary-partner wording

- Safety disclaimers

- Contract authority

- Data notices

Week 1 final deliverables

1. Pitch deck

10-slide editable presentation

PDF export

Presenter notes

2. Society package list

Pilot

Basic

Premium

Event/Camp

Pricing

Limits

Exclusions

3. Landing-page template

Reusable route

CMS/database fields

Mobile layout

Booking integration

SEO and privacy controls

4. Outreach scripts

WhatsApp

Email

LinkedIn

Phone opener

Resident group announcement

Follow-ups

Opt-out handling

5. Society CRM

Pipeline

Contacts

Activities

Qualification score

Dashboard

Lost reasons

6. Pilot agreement

Main agreement

Commercial schedule

Access SOP

Data-sharing schedule

Support schedule

7. FAQ

Prepare separate sections for:

Society committee

- Is PetSaathi responsible for sitters?

- What data does the society receive?

- What does the pilot cost?

- What happens after the pilot?

- How are complaints handled?

Security team

- How do we verify a sitter?

- What happens with a replacement?

- How is access revoked?

- Whom do we call?

Residents

- How do I book?

- Is payment prepaid?

- Is the same sitter guaranteed?

- What information can a sitter see?

- What happens during cancellation?

- How do I report an emergency?

Week 1 folder structure

Phase-7-Society-Partnership/

│

├── 01-Packages/

│   └── Society-Package-Matrix-v1

│

├── 02-Pitch-Deck/

│   ├── Society-Pitch-Deck-v1.pptx

│   ├── Society-Pitch-Deck-v1.pdf

│   └── Presenter-Notes

│

├── 03-Landing-Page/

│   ├── Page-Wireframe

│   ├── Content-Schema

│   └── Technical-Specification

│

├── 04-Outreach/

│   ├── WhatsApp-Scripts

│   ├── Email-Scripts

│   ├── Follow-Ups

│   └── Discovery-Call-Script

│

├── 05-CRM/

│   ├── Society-CRM

│   └── CRM-Data-Dictionary

│

├── 06-Agreement/

│   ├── Pilot-Agreement-Draft

│   └── Agreement-Schedules

│

└── 07-FAQ-and-SOP/

├── Society-FAQ

├── Security-FAQ

└── Resident-FAQ

Week 1 readiness scorecard

| Requirement | Pass condition |
| --- | --- |
| Society packages | Approved and priced |
| Pitch deck | Mobile-readable and factually accurate |
| Landing page | Working reusable template |
| Outreach scripts | Approved and opt-in compliant |
| CRM | Pipeline and next actions functional |
| Pilot agreement | Complete draft sent for legal review |
| FAQ | Covers society, security and resident concerns |
| Claims | Supported and consistently worded |
| Privacy | Notices and access rules defined |
| Pilot operations | End-to-end tabletop test passed |

Common Week 1 mistakes

Mistake 1 — Designing the deck before finalising the offer

This creates inconsistent pricing and promises.

Correct order:

Offer

→ Deck

→ Page

→ Scripts

→ Agreement

Mistake 2 — Treating the landing page as only a design task

It must represent real services, capacity, privacy and booking states.

Mistake 3 — Building CRM with no next-action field

A contact list is not a CRM.

Every opportunity needs:

Owner

Stage

Next action

Next date

Mistake 4 — Copying outreach scripts for every society

Personalise:

- Society name

- Area

- Likely resident need

- Relevant service

- Lead source

Mistake 5 — Launching before the agreement and SOP agree

The sales deck must not promise anything operations cannot deliver.

Mistake 6 — Calling the pilot entirely free

Correct wording:

No society setup or partnership fee; residents pay for booked services.

Mistake 7 — Treating the agreement as a downloaded generic template

The agreement must reflect PetSaathi’s real booking, access, payment, privacy, incident and partner workflows.

Final Week 1 operating principle

Every society should receive the same accurate commercial offer, safety explanation, privacy standard and pilot process—even when the pitch and landing page are personalised to that society.

Simple explanation for professor

“During the first week of Phase 7, we will prepare everything required before approaching apartment societies.

On Day 1, we will finalise our four society packages, prices, included features and limitations.

On Day 2, we will create a professional pitch deck explaining the society problem, PetSaathi’s solution, safety process, services, pilot offer, packages and launch process.

On Day 3, we will create a reusable society landing-page template. Each active society can have a personalised page showing available services, local sitters, resident offers, booking options, FAQs and support information.

On Day 4, we will prepare approved WhatsApp, email, phone and follow-up scripts. Residents will receive messages only after voluntarily requesting information or opting in.

On Day 5, we will create a CRM to track every society, contact, meeting, proposal, next action and pilot result.

On Day 6, we will prepare a pilot agreement covering services, payment, sitter access, society responsibilities, resident privacy, incidents, branding and termination. A legal professional should review it before use.

On Day 7, the product, operations, sales, finance, safety and legal teams will review all materials together. We will test one complete example from society approval to resident booking and final Report Card.

At the end of Week 1, PetSaathi will have a complete, consistent and outreach-ready society partnership kit.”

A monthly compliance watch for DPDP, WhatsApp, AWBI and consumer-rule changes would keep these materials current as Phase 7 expands.

PetSaathi Phase 7 — Week 2: Build the Society Target List 🏢🐾

Week 2 objective

Create a verified, prioritised and outreach-ready list of 50 apartment societies in one city—not a random spreadsheet of society names.

By Day 14, every priority society should have:

Society profile

+ demand estimate

+ operational fit

+ contact source

+ decision-maker path

+ priority score

+ personalised message

+ next action

The final outcome should be:

50 researched societies, 15–20 high-priority targets, 10–15 personalised first contacts and a clean CRM for follow-up.

1. Correct structure for the 50-society list

Do not treat all 50 societies equally.

Recommended segmentation

| Segment | Count | Purpose |
| --- | --- | --- |
| Tier A — Priority launch targets | 15 | Contact during Week 2–3 |
| Tier B — Qualified prospects | 20 | Contact after testing first messages |
| Tier C — Nurture prospects | 10 | Require more research or introductions |
| Tier D — Strategic experiments | 5 | Large township, premium project or unusual opportunity |

Geographic rule

The 50 societies should come from only two or three nearby micro-markets.

For an Ahmedabad pilot, an example could be:

Cluster 1: Bopal

Cluster 2: South Bopal

Cluster 3: Satellite / Prahlad Nagar

Avoid building a list spread across the entire city. Society density is valuable because the same sitter pool, emergency contacts and operations team can support several nearby communities.

2. Improved Society CRM columns

Your proposed columns are a good beginning, but the CRM needs separate fields for research, qualification, contacts, operations and next actions.

A. Society identity

| Column | Example |
| --- | --- |
| Society ID | SOC-AHD-001 |
| Society name | Green Acres |
| City | Ahmedabad |
| Area | Bopal |
| Complete locality | South Bopal Extension |
| Address | Publicly listed address |
| Map reference | Google Maps listing |
| Society type | Premium gated apartment |
| Project status | Occupied / partly occupied / unknown |
| Number of towers | 8 |
| Estimated flats | 500 |
| Estimated occupied flats | 425 |
| Research confidence | High / Medium / Low |

Important

Do not enter 500 flats merely because someone guessed it.

Store:

Flats estimate

Source

Date checked

Confidence

Possible sources include the society’s official website, public property information, RERA records, mapping data or confirmation from management.

For Ahmedabad, the official GujRERA portal can help identify registered residential projects and promoter information. However, a RERA entry is a discovery and verification source—it does not by itself prove current occupancy, active management or pet-parent demand.

B. Pet-demand information

| Column | Example |
| --- | --- |
| Estimated pet families — low | 25 |
| Estimated pet families — likely | 45 |
| Estimated pet families — high | 60 |
| Estimate confidence | Medium |
| Evidence source | Vet referral + resident group |
| Active pet-parent group | Yes |
| Existing dog walkers visible | Yes |
| Pet events previously held | Unknown |
| Most likely service | Daily dog walking |
| Secondary service | Pet sitting |
| Peak expected time | 6:30–9:00 AM |

Do not use one unexplained exact number such as:

Estimated pet families: 50

Use a range:

Low estimate: 30

Likely estimate: 45

High estimate: 60

Confidence: Medium

C. Decision-maker contacts

| Column | Example |
| --- | --- |
| Resident champion | Priya S. |
| RWA/committee contact | Secretary |
| Facility manager | Rahul M. |
| Property-management company | ABC Facility Services |
| Security supervisor | Collected after interest |
| Public phone | Business contact |
| Public email | manager@... |
| LinkedIn profile | Public professional profile |
| Contact source | Society website |
| Permission status | Public B2B contact |
| Preferred channel | Email / call |
| Last verified | 18 July 2026 |

Privacy rule

Names, phone numbers and email addresses are personal data. Record:

- Where the information came from

- Why PetSaathi needs it

- Who can access it

- Whether the person asked not to be contacted

- When it should be deleted

India’s Digital Personal Data Protection Rules, 2025 were published on November 14, 2025, with staged commencement provisions. The CRM should therefore be built with purpose limitation, controlled access and retention rules from the beginning.

D. Operational fit

| Column | Example |
| --- | --- |
| Nearby active walkers | 4 |
| Nearby backup walkers | 2 |
| Nearby pet sitters | 3 |
| Boarding partner nearby | 1 |
| Veterinary partner nearby | 2 |
| Distance from launch hub | 2.4 km |
| Estimated travel time | 12 minutes |
| Gate complexity | Medium |
| Sitter registration needed | Yes |
| Resident event possible | Yes |
| Morning capacity | Strong |
| Evening capacity | Limited |
| Operational fit score | 82/100 |

Google Places can help discover and verify publicly listed societies, clinics, pet shops and other points of interest, but important operational data must still be confirmed directly. The Places API provides structured location information about establishments and geographic places.

E. Commercial opportunity

| Column | Example |
| --- | --- |
| Recommended first offer | No-Fee Society Pilot |
| Estimated trial bookings | 10–20 |
| Potential monthly walks | 80 |
| Potential sitting bookings | 10 |
| Likely package | Basic Society Partner |
| Price sensitivity | Medium |
| Event interest | Grooming camp |
| Key value proposition | Same-sitter daily walks |
| Revenue potential | High |
| Commercial score | 78/100 |

These are internal estimates—not promises for the society pitch.

F. CRM activity

| Column | Example |
| --- | --- |
| CRM stage | CONTACTED |
| Lead source | Vet introduction |
| Lead owner | Prince |
| First-contact date | 21 July 2026 |
| Last interaction | WhatsApp introduction |
| Response | Requested deck |
| Next action | Send pilot summary |
| Next follow-up | 23 July 2026 |
| Days without action | 2 |
| Main objection | Wants resident survey first |
| Lost reason | Blank |
| Notes | Interested in grooming camp |

3. Recommended CRM stages

Replace the broad status:

Contacted / Interested / Signed

with a controlled pipeline:

IDENTIFIED

QUALIFIED

INTRODUCTION_REQUESTED

CONTACTED

REPLIED

DISCOVERY_SCHEDULED

DISCOVERY_COMPLETED

RESIDENT_SURVEY

PROPOSAL_SENT

COMMITTEE_REVIEW

PILOT_APPROVED

SETUP_IN_PROGRESS

ACTIVE_PILOT

CONVERTED

NURTURE

LOST

Every active society must have:

Owner

Current stage

Next action

Next-action date

A society without a next action is not being actively managed.

4. Sources for building the list

Use a layered research process.

Source 1 — Existing PetSaathi contacts

Start with:

- Existing pet parents

- Internship or college network

- Friends and family

- Local pet owners

- Previous enquiries

- Existing sitter contacts

Ask:

“Which apartment societies in Bopal or South Bopal have active pet-parent communities?”

Warm introductions generally provide better access to committee members than cold outreach.

Source 2 — Official and public property data

Use:

- State RERA portal

- Society or developer website

- Public property-management information

- Publicly listed project documents

- Mapping platforms

For Gujarat, GujRERA is the official project and agent registration portal.

Use RERA information to identify:

- Project name

- Developer

- Area

- Approximate project scale

- Registration details

Do not treat it as proof that:

- All homes are occupied

- An RWA is active

- The listed promoter manages the property

- The society contains many pet families

Source 3 — Google Maps and locality research

Search terms:

premium apartment society Bopal

gated community South Bopal

residential township Satellite Ahmedabad

apartment society near pet clinic Bopal

Record:

- Correct spelling

- Area

- Public website

- Public phone

- Approximate scale

- Nearby parks

- Nearby veterinary clinics

- Nearby pet shops

Do not copy all map listings blindly. Confirm that the location is residential and currently relevant.

Source 4 — Veterinarians and pet shops

Ask partners:

- Which societies send many customers?

- Which localities have daily walking demand?

- Which societies organise pet events?

- Which societies have active pet-parent groups?

- Which managers are open to pet initiatives?

Correct referral method

Ask the partner to:

- Introduce PetSaathi

- Forward a QR code

- Share the pilot information

- Invite PetSaathi to a joint meeting

Do not ask the clinic or shop to hand over its customer database.

Source 5 — Dog parks and walking locations

Observe:

- Which society gates dog owners come from

- Busy walking periods

- Existing independent walkers

- Common complaints

- Nearby clusters

Use voluntary conversations. Do not secretly photograph residents or collect contact information without permission.

Source 6 — LinkedIn

Search for:

Facility Manager + Bopal

Community Manager + Ahmedabad

Property Manager + apartment

RWA Secretary + society name

LinkedIn limits invitations to prevent misuse and may restrict accounts that send too many or use prohibited automation. It recommends sending relevant and thoughtful invitations rather than high-volume requests.

Source 7 — Resident groups

Use:

- Society Facebook groups

- Pet-parent groups

- Local community pages

- Resident referrals

- WhatsApp introductions

Do not enter or scrape closed community groups using false identities.

5. How to identify a “pet-heavy” society

Do not rely on one signal.

Strong signals

- Active resident pet-parent group

- Previous vaccination or grooming camp

- Multiple pet-related businesses nearby

- Several visible dog walkers during peak hours

- Resident champion confirms demand

- Facility manager reports recurring pet-care requests

- Society has a pet-related notice or process

- Existing PetSaathi lead resides there

Medium signals

- Large occupied premium project

- Suitable walking environment

- Nearby veterinary clinic

- Multiple towers and family households

- Society organises resident events

- Security already manages external service providers

Weak signals

- Expensive property

- Many flats

- Attractive website

- Good online reviews

A premium society is not automatically pet-heavy.

6. Society priority scoring model

Use a 100-point score.

| Factor | Weight |
| --- | --- |
| Verified or likely resident demand | 25 |
| Local sitter and backup capacity | 20 |
| Geographic cluster fit | 15 |
| Access to decision-maker | 15 |
| Security and operational feasibility | 10 |
| Society size and occupancy | 10 |
| Vet/pet-shop partner ecosystem | 5 |

Score interpretation

| Score | Segment | Action |
| --- | --- | --- |
| 80–100 | Tier A | Contact immediately |
| 65–79 | Tier B | Qualified outreach |
| 50–64 | Tier C | Research/nurture |
| Below 50 | Hold | Do not spend active sales time |

Automatic hold conditions

Even a high score should be paused when:

- No local sitter supply exists

- Travel time is unreasonable

- Society requests unlawful pet-control activity

- No authorised contact can be identified

- The project is not occupied

- Contact data came from a questionable source

- The society is outside the launch cluster

Day 8 — List the top 20 premium societies

Goal

Create an initial longlist of 20 societies with enough scale, demand potential and geographic fit.

Tasks

1. Choose the launch clusters

Example:

Bopal

South Bopal

Satellite

2. Identify 30–40 candidates

Use:

- GujRERA

- Google Maps

- Public developer websites

- Existing resident contacts

- Vet/pet-shop referrals

3. Reduce to the best 20

Remove:

- Unoccupied projects

- Commercial developments

- Properties outside the service radius

- Societies without local sitter coverage

- Duplicate project names

- Projects with unclear identity

4. Assign initial confidence

High confidence:

Multiple reliable sources

Medium:

One reliable source plus supporting evidence

Low:

Unconfirmed directory or word-of-mouth entry

Day 8 output

20 premium or strategically valuable societies

with identity, location, scale and source fields completed

Day 9 — Collect manager and RWA contacts

Goal

Find the right contact path—not merely any resident’s phone number.

Contact priority

1. Warm resident introduction

2. Facility manager

3. RWA/AOA secretary or president

4. Property-management company

5. Public society email

6. LinkedIn professional contact

Security staff should not be treated as the commercial decision-maker.

Contact research checklist

For each society, try to identify:

- Resident champion

- Operational contact

- Authorised decision-maker

Example:

Resident champion: Pet-parent group admin

Operational contact: Facility manager

Decision-maker: RWA secretary

Data-quality rules

Store:

Contact name

Role

Source

Date verified

Public or referred

Preferred communication method

Do-not-contact status

Day 9 output

- 20 societies with at least one contact path

- 10 societies with two contact paths

- 5 societies with all three stakeholders identified

Day 10 — Identify pet-heavy societies

Goal

Separate genuinely promising societies from projects that only appear premium.

Research actions

- Speak with nearby vets

- Speak with pet shops

- Review public society posts

- Ask resident champions

- Visit selected local walking areas

- Check for prior camps or pet events

- Check existing PetSaathi enquiries

- Observe peak walking activity respectfully

Create demand ratings

CONFIRMED:

Resident or manager confirms meaningful demand

LIKELY:

Several supporting signals

POSSIBLE:

Large society but little direct evidence

UNKNOWN:

No useful demand evidence

Day 10 output

At least 10 confirmed/likely pet-heavy societies

and demand-confidence labels for all 20 premium targets

Day 11 — Contact veterinarians and pet shops for referrals

Goal

Use trusted local businesses to discover additional societies and obtain warm introductions.

Partner list

Build:

- 5–10 veterinary clinics

- 5–10 pet shops

- 3–5 groomers or trainers

Questions

Ask:

- Which societies have the largest pet-parent customer base?

- Which societies request vaccination or grooming camps?

- Which areas have recurring dog-walking demand?

- Can the partner introduce PetSaathi to a resident or manager?

- Would the partner participate in a society event?

Referral recording

| Field | Example |
| --- | --- |
| Partner | ABC Veterinary Clinic |
| Society referred | Green Acres |
| Introduction status | Requested |
| Partner interest | Vaccination camp |
| Commercial expectation | Fixed event fee |
| Next action | Send one-page summary |

Day 11 output

- 10+ partner conversations

- 10–20 additional society names

- 3–5 warm introduction opportunities

- Updated 50-society longlist

Day 12 — Segment societies by priority

Goal

Convert the list into a sales plan.

Steps

1. Remove invalid records

Remove or hold:

- Duplicate societies

- Unoccupied projects

- Far-away communities

- No sitter coverage

- No reliable contact source

- No likely resident demand

2. Score all 50 societies

Apply the 100-point model.

3. Assign tiers

Tier A: 15 societies

Tier B: 20 societies

Tier C: 10 societies

Strategic: 5 societies

4. Assign a package hypothesis

Examples:

Green Acres:

No-Fee Pilot → Basic Partner

Premium Township:

No-Fee Pilot → Premium Pet-Care Desk

Low-demand society:

Event/Camp Model first

5. Assign an owner

Each Tier A target must have one PetSaathi team owner.

Day 12 output

Final 50-society CRM

with segments, scores, owners and recommended first offers

Day 13 — Prepare personalised messages

Goal

Create one relevant message for every Tier A society.

Do not use exactly the same message 15 times.

Personalisation fields

Each message should reference one or two genuine points:

- Society name

- Area

- Existing resident introduction

- Society size

- Likely service need

- Nearby sitter availability

- Local partner referral

- Relevant event interest

Message structure

1. Who you are

2. Why you selected this society

3. The relevant society problem

4. PetSaathi’s solution

5. Pilot offer

6. One clear CTA

Example logic

Society with daily walking interest

“Several residents in Bopal have asked about reliable morning dog-walking support…”

Society referred by veterinarian

“ABC Veterinary Clinic suggested that your community has an active pet-parent group…”

Premium township

“Your multi-tower access structure makes an approved sitter roster and central pet-care desk especially useful…”

Do not mention pet-family numbers unless they have been reliably sourced.

Channel preparation

For every Tier A society, prepare:

- Email version

- WhatsApp version

- LinkedIn version

- Phone-call opener

- Relevant attachment

- Preferred send time

- Follow-up dates

For WhatsApp Business outreach, Meta requires user opt-in before message templates are sent; opt-in should identify the business and messaging purpose. Messages should be personalised and useful.

Day 13 output

15 personalised outreach packs

Each pack contains:

- Primary message

- Secondary channel

- Contact name

- Personalisation reason

- CTA

- Follow-up schedule

Day 14 — Outreach batch 1

Goal

Test outreach quality before contacting all 50 societies.

Recommended batch size

Contact 10–15 societies, not all 50.

Recommended composition

| Target type | Count |
| --- | --- |
| Warm resident introductions | 4–5 |
| Vet/pet-shop referrals | 3–4 |
| High-priority facility managers | 3–4 |
| Cold strategic experiment | 1–2 |

This mixture helps compare lead sources.

Outreach sequence

Warm introduction requested

↓

Initial personalised message

↓

CRM activity logged

↓

Response monitored

↓

Follow-up task scheduled

↓

Discovery meeting booked

Do not send

- Ten-page deck without context

- Full agreement

- Several attachments

- Long technical explanation

- Repeated messages on the same day

First-contact attachment

Use only one:

One-page society pilot summary

Send the full pitch deck after interest or before the meeting.

Day 14 output

- 10–15 societies contacted

- 100% outreach logged

- Follow-up dates scheduled

- Initial response data available

- Messaging improvements identified

7. Week 2 outreach dashboard

Track daily:

| Metric | Week 2 target |
| --- | --- |
| Societies identified | 50 |
| Societies with verified area/address | 50 |
| Societies with scale estimate | 40+ |
| Societies with contact path | 35+ |
| Societies with decision-maker | 20+ |
| Confirmed/likely pet-heavy societies | 15+ |
| Warm introductions | 5–10 |
| Tier A societies | 15 |
| Personalised outreach packs | 15 |
| Batch 1 societies contacted | 10–15 |
| CRM records with next action | 100% |

Early response targets

These are planning benchmarks, not guarantees:

| Funnel | Initial target |
| --- | --- |
| Contact delivered | 90%+ |
| Contact → reply | 20–40% |
| Reply → discovery call | 40–60% |
| Warm intro → discovery call | 50%+ |

Evaluate performance by lead source—not only total replies.

8. Week 2 final deliverables

1. Master society CRM

50 researched societies

2. Priority list

15 Tier A

20 Tier B

10 Tier C

5 strategic

3. Contact database

Includes:

- Source

- Role

- Permission status

- Preferred channel

- Last verified

- Do-not-contact status

4. Pet-demand map

Shows:

- Confirmed pet-heavy societies

- Likely societies

- Uncertain societies

- Local sitter capacity

- Vet/pet-shop ecosystem

5. Personalised outreach packs

15 society-specific messages

6. Batch 1 outreach report

Includes:

- Messages sent

- Delivery

- Replies

- Meetings requested

- Objections

- Message improvements

9. Common Week 2 mistakes

Mistake 1 — Filling the CRM with unverified estimates

Correction: Store source, date and confidence.

Mistake 2 — Selecting societies only because they are premium

Correction: Demand and local sitter supply matter more than property price.

Mistake 3 — Building a city-wide list

Correction: Concentrate on two or three nearby clusters.

Mistake 4 — Treating every contact as a decision-maker

Correction: Separate resident champion, operational contact and authorised approver.

Mistake 5 — Buying or scraping private contact lists

Correction: Use public business contacts, professional profiles, warm introductions and opt-in forms.

Mistake 6 — Asking clinics for customer data

Correction: Request an introduction or ask the clinic to share PetSaathi’s QR link.

Mistake 7 — Sending the same message to all 50 societies

Correction: Personalise the reason for approaching each Tier A society.

Mistake 8 — Contacting all 50 on the first day

Correction: Test 10–15 contacts, analyse results and improve the message.

Mistake 9 — No next-action date

Correction: Every active CRM record must have an owner and next follow-up.

Week 2 definition of done

Week 2 is complete only when:

Research

- 50 valid societies are recorded.

- Duplicates and unoccupied projects are removed.

- Every record has a research source.

- Estimates include confidence levels.

Demand

- At least 15 societies have confirmed or likely pet demand.

- Pet-heavy status is supported by evidence.

- Local service needs are identified.

Contacts

- At least 35 societies have a valid contact path.

- At least 20 have a decision-maker or operational contact.

- Contact sources and permissions are recorded.

- Do-not-contact requests can be enforced.

Operations

- Tier A societies have local sitter capacity.

- Travel and backup feasibility are checked.

- No priority society depends on one unavailable sitter.

Outreach

- Fifteen personalised message packs are ready.

- Ten to fifteen societies receive Batch 1 outreach.

- Every contact is logged.

- Every active opportunity has a follow-up date.

Simple explanation for professor

“During Week 2, PetSaathi will create a researched list of 50 apartment societies in one city.

We will not select societies only because they are large or premium. We will check resident pet demand, nearby sitter availability, society access, decision-maker contacts and geographic distance.

On Day 8, we will identify the first 20 premium or strategically useful societies. On Day 9, we will find facility managers, RWA members and resident contacts. On Day 10, we will identify which societies have genuine pet-parent demand.

On Day 11, we will speak with local veterinary clinics, pet shops, groomers and trainers for society referrals. We will request introductions instead of asking them to share private customer lists.

On Day 12, all 50 societies will be scored and divided into priority groups. On Day 13, personalised WhatsApp, email and LinkedIn messages will be prepared for the highest-priority societies.

On Day 14, PetSaathi will contact only the first 10 to 15 societies. We will measure replies, meeting requests and objections before contacting the remaining list.

The final CRM will show the society name, location, estimated size, pet demand, contacts, operational fit, priority score, current sales stage and next follow-up date. This creates a focused sales pipeline instead of an unorganised contact list.”

PetSaathi Phase 7 — Week 3: Society Outreach and Meetings 🏢🐾

Week 3 objective

Convert the Week 2 target list into real partnership discussions.

By the end of Week 3, PetSaathi should achieve:

| Result | Target |
| --- | --- |
| Qualified societies contacted | 30 |
| Positive responses | 8–12 |
| Meetings scheduled or completed | 5–8 |
| Resident-demand surveys approved | 3–5 |
| Pilot proposals requested | 2–4 |
| CRM records with a next action | 100% |

The main objective is not to send 30 messages. It is to create 5–8 serious conversations with authorised or influential society stakeholders.

1. Define what “contacted” means

A society should count as contacted only when:

✓ A relevant contact has been identified

✓ The contact source has been recorded

✓ The message is personalised

✓ The message has been delivered through an appropriate channel

✓ The activity is recorded in the CRM

✓ A follow-up date is assigned

Do not count:

- Generic messages sent to an unverified number

- Instagram or Facebook comments

- Messages sent only to security guards

- Unanswered calls without a follow-up message

- Bulk WhatsApp broadcasts to unknown contacts

- LinkedIn connection requests without context

Required contact roles

Try to identify at least two of these for every Tier A society:

| Role | Purpose |
| --- | --- |
| Resident champion | Proves pet-parent demand |
| Facility manager | Explains daily operations |
| RWA/AOA representative | Approves partnership |
| Property manager | Coordinates large communities |
| Pet-parent group administrator | Enables resident survey |
| Security supervisor | Designs access after approval |

Security should normally be involved after the committee or facility manager expresses interest.

2. Recommended Week 3 operating flow

Review priority CRM

↓

Research contact before outreach

↓

Send personalised introduction

↓

Follow up through a second channel

↓

Schedule discovery meeting

↓

Conduct 30-minute meeting

↓

Send meeting summary

↓

Launch resident-demand survey

↓

Prepare pilot proposal

Each step should have a clear CRM stage, owner and deadline.

3. Improved daily schedule

Your proposed schedule is good. The following version adds preparation, meeting documentation and proposal work.

| Time | Task | Expected output |
| --- | --- | --- |
| 09:00–09:30 | Dashboard review | Priority tasks and overdue follow-ups |
| 09:30–10:00 | Contact research | Personalisation details |
| 10:00–12:00 | Calls, email, LinkedIn and approved WhatsApp outreach | New contacts and follow-ups |
| 12:00–12:45 | CRM updates | Every interaction recorded |
| 12:45–13:00 | Meeting preparation | Notes and documents ready |
| 14:00–16:00 | Society discovery meetings | Needs and next actions confirmed |
| 16:00–17:00 | Send deck, summary or survey | Formal follow-up completed |
| 17:00–18:00 | Pet-parent and partner outreach | Resident-demand validation |
| 18:00–18:15 | Daily review | Tomorrow’s priority list |

Important operating rule

Do not postpone CRM updates until the end of the week.

Update the CRM immediately after:

- Calls

- Replies

- Meetings

- Objections

- Introductions

- Follow-up promises

- Proposal requests

This prevents lost context and duplicate outreach.

4. Suggested Day 15–21 execution plan

Day 15 — Prepare the outreach batch

Goal

Select the first 10–12 societies to contact.

Recommended mix

| Lead type | Count |
| --- | --- |
| Warm resident introductions | 3–4 |
| Vet or pet-shop referrals | 2–3 |
| Facility-manager contacts | 3–4 |
| Cold strategic targets | 1–2 |

Tasks

- Verify contact names and roles.

- Review society size and likely demand.

- Check nearby sitter capacity.

- Identify the best starting service.

- Prepare a personalised message.

- Set follow-up dates before sending.

Output

10–12 complete outreach packs

Day 16 — First outreach batch

Goal

Contact the first batch using the strongest available channel.

Channel order

Warm introduction

→ Email or call

→ Permission-based WhatsApp

→ LinkedIn

First-contact objective

Request a 15-minute introductory call.

Do not ask the society to approve the full partnership in the first message.

Output

- 10–12 initial contacts

- Delivery and response status

- Follow-up tasks scheduled

- Message objections recorded

Day 17 — Follow-ups and first meetings

Goal

Convert responses into discovery calls.

Follow-up message structure

Reference earlier message

↓

Restate one relevant benefit

↓

Offer two specific meeting times

↓

Keep message under 100 words

Example:

“Hi Mr. Shah, following up on the PetSaathi society pilot shared on Monday. The programme may be particularly useful for organising approved dog walkers and recurring morning slots in Green Acres. Would Wednesday at 3:00 PM or Thursday at 11:30 AM work for a 15-minute discussion?”

Output

- First meetings conducted

- New discovery meetings scheduled

- Resident survey opportunities identified

Day 18 — Second outreach batch

Goal

Contact another 8–10 societies using lessons from the first batch.

Improve:

- Subject line

- Opening sentence

- Pilot explanation

- Call-to-action

- Attachment length

- Channel selection

Output

18–22 cumulative societies contacted

Day 19 — Society meetings and demand validation

Goal

Conduct meetings and secure permission to test resident interest.

The preferred next step after a positive meeting is usually:

A short resident opt-in survey

This is less risky for the society than immediately signing a full agreement.

Survey questions

- Pet type

- Interested service

- Preferred days

- Preferred time

- Current care arrangement

- Interest in first paid trial

- Consent to receive PetSaathi information

Do not collect medical details at this stage.

Output

- Resident survey approvals

- Pet-parent group introductions

- Operational requirements recorded

Day 20 — Final outreach batch and proposals

Goal

Reach the 30-society contact target and prepare customised pilot summaries.

Proposal-ready societies should have

Confirmed society contact

+

Likely resident demand

+

Local sitter capacity

+

Feasible gate process

+

Clear pilot scope

Output

- 30 societies contacted

- Two to four customised pilot summaries

- Meetings scheduled for unresolved opportunities

Day 21 — Weekly review

Goal

Analyse quality, not only outreach volume.

Review:

- Which channel produced the most replies?

- Which message produced meetings?

- Which objections appeared repeatedly?

- Which societies lack local sitter supply?

- Which opportunities need resident demand first?

- Which targets should be removed?

- Which societies are ready for a pilot proposal?

Output

Week 3 Outreach Performance Report

5. Meeting preparation

Every meeting should have a one-page internal briefing.

Society briefing

Society:

Area:

Estimated homes:

Likely pet families:

Contact:

Contact role:

Lead source:

Nearby active sitters:

Likely hero service:

Known access process:

Known concerns:

Recommended pilot:

Desired meeting outcome:

Materials to prepare

Bring or send only the necessary material:

- Society pitch deck

- One-page pilot summary

- Sample Pet Report Card

- Sitter-verification explanation

- Resident survey link

- Pilot pricing summary

Do not begin the meeting by reading the entire pitch deck.

The meeting should be a discovery conversation, not a lecture.

6. Detailed 30-minute meeting agenda

Minutes 0–3 — Introduction

Objective

Establish credibility and explain why PetSaathi selected the society.

Recommended introduction

“Thank you for meeting with us. PetSaathi is developing a structured pet-care programme for apartment communities. We help residents access screened dog walkers and pet sitters while supporting sitter access, service monitoring, Report Cards and formal issue escalation.”

Confirm attendees

Identify:

- Decision-maker

- Operational stakeholder

- Resident representative

- Person responsible for the next step

Avoid

Do not spend three minutes describing every future PetSaathi feature.

Minutes 3–7 — Understand the society’s current situation

Ask first; do not pitch immediately

Recommended questions:

- Approximately how many homes are occupied?

- Is there an active pet-parent group?

- How do residents currently find dog walkers or sitters?

- How are external helpers registered with security?

- Are there recurring pet-care complaints?

- Which service timings create the most difficulty?

- Do residents frequently request travel-time care?

- Has the society previously conducted pet events?

Goal

Identify the real problem.

The society may care more about:

- Security access

- Dog-walking reliability

- Cleanliness

- Last-minute replacements

- Resident communication

- Event coordination

Do not assume every society has the same priority.

Minutes 7–12 — Present the PetSaathi solution

Connect the solution directly to the problems they mentioned.

Example

When the problem is unknown helpers:

“PetSaathi maintains an approved-access sitter roster with a current photo, PetSaathi ID, service permission and access status.”

When the problem is recurring dog walks:

“We can configure regular walking windows with preferred-sitter continuity and backup options.”

When the problem is complaints:

“Every material complaint or safety issue becomes a structured record with an owner, status and resolution.”

Show the operating flow

Resident registers

→ Creates Pet Profile

→ Requests service

→ Eligible sitter assigned

→ Payment verified

→ Gate access prepared

→ Service completed

→ Report Card delivered

Minutes 12–17 — Explain the pilot

Recommended pilot

Duration: 21–30 days

Society setup fee: ₹0

Society partnership fee: ₹0

Residents pay for services booked

Initial services: Dog walking and pet sitting

Booking cap: Based on capacity

Automatic renewal: No

Included

- Society landing page

- Resident trial offer

- Sitter access roster

- WhatsApp booking assistance

- Pet-parent announcement

- Basic awareness material

- Aggregate pilot report

Pilot success metrics

- Registered pet parents

- Paid bookings

- Service completion

- Punctuality

- Report Card delivery

- Ratings

- Repeat interest

- Access problems

- Complaints

Important clarity

“No-fee pilot” means there is no society partnership fee. It does not mean all resident pet-care services are free.

Claims about pricing, verification and service capability should remain accurate and supportable. ASCI’s self-regulatory code requires advertising to be legal, honest and truthful.

Minutes 17–22 — Safety and trust process

Explain layered controls

Sitter controls

- Identity review

- Interview

- Service-specific training

- Society-access registration

- Reliability history

- Active safety restrictions

Pet controls

- Pet identity

- Handling behaviour

- Medical and food instructions

- Bite or escape history

- Emergency contacts

- Service-specific controls

Service controls

- Arrival update

- Start and end evidence

- Basic GPS proof for walks

- Photo/video updates where required

- Pet Report Card

- Incident escalation

Recommended safety statement

“PetSaathi does not claim zero risk. We reduce risk through structured information, sitter eligibility, controlled matching, service evidence and documented escalation.”

Veterinary boundary

“Emergency support means coordination with the owner, registered veterinary partners and available transport support. PetSaathi does not diagnose or provide veterinary treatment.”

Minutes 22–27 — Pricing and partnership path

Do not show every detailed pricing variation unless the society asks.

Present the progression

| Stage | Fee |
| --- | --- |
| No-Fee Pilot | ₹0 society fee |
| Basic Society Partner | ₹5,000–₹15,000/month |
| Premium Pet-Care Desk | ₹15,000–₹50,000/month |
| Event/Camp Model | Event-specific pricing |

Explain that pricing depends on:

- Number of homes

- Active pet families

- Towers and gates

- Support hours

- Coordinator requirements

- Booking volume

- Event frequency

- Reporting needs

Correct commercial statement

“Residents pay separately for the services they book. The society fee covers programme setup, coordination, support and reporting according to the selected package.”

Minutes 27–30 — Decision and next step

Do not end with:

“Please let us know.”

Agree on one specific next action.

Preferred next actions

- Society approves resident-interest survey

- PetSaathi sends pilot proposal

- Security-access review is scheduled

- Committee presentation is arranged

- Pet-parent introduction is provided

- Follow-up date is confirmed

Close with a commitment

“We will send the one-page pilot summary and resident survey by 5:00 PM today. Could we review the survey response together next Tuesday at 3:00 PM?”

Record the agreed date before ending the meeting.

7. Meeting qualification questions

Resident demand

- How many residents have asked for pet-care services?

- Is there an active pet-parent group?

- Is dog walking the main need?

- Are travel and festival care common problems?

- Would residents pay for a discounted first trial?

Operations

- How are external service providers approved?

- Which gate should sitters use?

- Is advance visitor approval required?

- Are replacement sitters allowed?

- Are there service-hour restrictions?

- Who coordinates security changes?

Decision process

- Who approves the pilot?

- Is a committee vote required?

- Does the facility manager have implementation authority?

- What documentation is required?

- When is the next committee meeting?

Commercial fit

- Does the society prefer no-fee resident-paid services?

- Is the society considering a managed amenity?

- Is there interest in grooming or vaccination camps?

- Would the society sponsor resident benefits?

8. Meeting outcome classifications

After every meeting, choose one outcome.

A — Pilot ready

Requirements:

- Decision-maker supportive

- Demand likely

- Access feasible

- Sitter capacity available

Next step:

Send customised pilot proposal

B — Resident demand required

Society is interested but needs evidence.

Next step:

Launch resident opt-in survey

C — Committee review required

The contact supports the proposal but lacks authority.

Next step:

Schedule formal committee presentation

D — Operational review required

Demand exists, but access or sitter capacity is unclear.

Next step:

Facility/security workshop

E — Nurture

Timing is not suitable.

Next step:

Record future review date

F — Disqualified

Examples:

- No local sitter supply

- No resident demand

- Unoccupied property

- Outside operating area

- Society demands unlawful or unsafe practices

- No valid decision path

9. Post-meeting process

Within two hours

Update the CRM:

- Attendees

- Problems identified

- Demand estimate

- Current provider

- Pilot interest

- Access requirements

- Objections

- Decision process

- Agreed next action

- Follow-up date

Same working day

Send:

- Thank-you message

- Meeting summary

- Relevant deck or one-page summary

- Resident survey or proposal

- Agreed next date

Follow-up summary structure

Current challenges

PetSaathi proposal

Pilot scope

Society responsibilities

PetSaathi responsibilities

Information required

Agreed next step

Target date

Do not send the generic agreement unless the society has reached the proposal or committee-review stage.

10. Pet-parent group follow-up

Pet-parent groups are used to validate demand, not to bypass the society committee.

Correct process

Society/group admin gives permission

↓

One approved group announcement

↓

Interested residents reply or open opt-in link

↓

PetSaathi contacts only opted-in residents

↓

Demand summary shared with society

Meta requires businesses to obtain opt-in before sending proactive WhatsApp messages. The opt-in should identify the business and the messaging purpose, and user opt-out requests must be respected.

Do not:

- Add residents to WhatsApp groups automatically

- Import society contact lists

- Message every group member privately

- Combine service notifications with unrelated marketing consent

- Continue contacting residents after they opt out

11. Outreach channel rules

WhatsApp

Use for:

- Warm introductions

- Resident-initiated conversations

- Meeting confirmation

- Approved follow-ups

- Survey and pilot links

For WhatsApp Business Platform outreach, proactive conversations require appropriate opt-in and approved message templates.

LinkedIn

Use personalised messages and limit invitations to relevant professional contacts. LinkedIn states that high invitation volume or prohibited automation can result in temporary account restrictions.

Email

Use business email when publicly listed or provided through an introduction.

Include:

- Sender identity

- Reason for contact

- Society relevance

- One clear CTA

- Easy opt-out instruction

Personal-data handling

CRM records should contain only the information necessary for outreach and partnership management. The final DPDP Rules, 2025 were published on November 14, 2025, with staged implementation provisions; PetSaathi should record the purpose and source of personal contact information, restrict access and honour applicable correction or deletion processes.

12. Common society objections

“We already have local dog walkers.”

Response

“PetSaathi does not need to replace every existing arrangement. The pilot can focus on residents who need verified backup, travel-time sitting, structured updates or recurring plans.”

“Residents will not pay.”

Response

“We recommend validating that through an opt-in resident survey before launching. The society does not need to pay during the initial pilot.”

“We do not want responsibility for incidents.”

Response

“PetSaathi manages individual bookings, sitter assignments, service records and incident workflows. The pilot agreement clearly separates society access coordination from individual pet-care responsibility.”

“How can you guarantee safety?”

Response

“We do not promise zero risk. We use identity review, training, Pet Profiles, controlled matching, service evidence and incident escalation to reduce and manage risk.”

“We cannot share resident data.”

Response

“That is correct. The society can share a QR code or announcement. Interested residents register voluntarily with PetSaathi.”

“Can you guarantee the same sitter?”

Response

“We support preferred-sitter continuity, but confirmation depends on availability, eligibility and service conditions. A replacement process is available when required.”

“The price is too high.”

Response

“The initial pilot has no society partnership fee. After the pilot, the package is selected according to actual resident demand and support requirements.”

13. Week 3 CRM fields

After each contact or meeting, record:

Current stage

Contacted person

Role

Channel

Response

Meeting date

Meeting attendees

Problems identified

Estimated resident demand

Existing service arrangement

Access complexity

Preferred pilot service

Commercial interest

Main objection

Decision process

Next action

Next action date

Opportunity owner

Recommended meeting stages

DISCOVERY_SCHEDULED

DISCOVERY_COMPLETED

RESIDENT_SURVEY_APPROVED

PILOT_REQUESTED

PROPOSAL_IN_PREPARATION

PROPOSAL_SENT

COMMITTEE_REVIEW

14. Week 3 scorecard

| Metric | Target |
| --- | --- |
| Qualified societies contacted | 30 |
| Tier A societies contacted | 15 |
| Warm introductions used | 5–10 |
| Replies received | 8–12 |
| Meetings scheduled/completed | 5–8 |
| Resident surveys approved | 3–5 |
| Pilot summaries requested | 2–4 |
| Invalid contact records corrected | 100% |
| Meetings with defined next action | 100% |
| CRM updated same day | 100% |

Meeting-quality metrics

Do not measure only meeting count.

Track:

- Decision-maker attendance

- Resident-demand evidence

- Operational feasibility

- Clear approval process

- Next meeting date

- Survey or proposal approval

- Time from meeting to next action

15. Common Week 3 mistakes

Mistake 1 — Sending 30 generic messages

Correction: Contact fewer societies with stronger personalisation and channel selection.

Mistake 2 — Pitching before understanding the problem

Correction: Spend the first seven minutes asking questions.

Mistake 3 — Using all 10 slides in every meeting

Correction: Show only the slides relevant to that society’s concerns.

Mistake 4 — Leaving without a scheduled next action

Correction: Agree on a survey, proposal, committee meeting or review date.

Mistake 5 — Sending the pilot agreement too early

Correction: Send a one-page summary first; provide the agreement after genuine interest.

Mistake 6 — Treating verbal interest as a qualified opportunity

Correction: Record the approval process, decision-maker and timeline.

Mistake 7 — Promising safety or sitter availability

Correction: Explain controls, eligibility and capacity honestly.

Mistake 8 — Ignoring pet-parent demand

Correction: Validate whether residents will actually book and pay.

Mistake 9 — Failing to follow up quickly

Correction: Send a written summary and next step on the same working day.

Week 3 definition of done

Week 3 is complete only when:

Outreach

- Thirty qualified societies have received personalised contact.

- Outreach sources and permissions are recorded.

- Warm introductions are prioritised.

- WhatsApp outreach follows opt-in requirements.

- Declines and opt-outs are respected.

Meetings

- Five to eight discovery meetings are scheduled or completed.

- Every meeting follows a structured agenda.

- Society problems are documented before pitching.

- Decision-makers and approval processes are identified.

- Every meeting ends with one specific next action.

Qualification

- Resident demand is estimated.

- Sitter capacity is checked.

- Gate and security feasibility are understood.

- The correct pilot service is selected.

- Weak or unsuitable societies are moved to nurture or lost.

CRM

- Every interaction is logged.

- Every active opportunity has an owner.

- Every active opportunity has a next-action date.

- Objections and decision timelines are recorded.

- Duplicate contact attempts are prevented.

Commercial progress

- Three to five societies approve a resident survey.

- Two to four societies request a pilot summary or proposal.

- No unsupported promise is made to secure a meeting.

- Sales materials remain consistent with actual operations.

Simple explanation for professor

“During Week 3, PetSaathi will contact 30 qualified apartment societies and aim to schedule five to eight meetings.

Every morning, we will review the CRM and identify important follow-ups. From 10:00 AM to 12:00 PM, we will contact society managers, RWA members and resident representatives using personalised calls, emails, LinkedIn messages or permission-based WhatsApp messages.

Each society meeting will last approximately 30 minutes. First, we will introduce PetSaathi and ask about the society’s current pet-care and security problems. We will then explain our solution, including verified sitter access, Pet Profiles, service updates, Report Cards and incident handling.

After understanding the society’s needs, we will present the no-fee pilot. The society will not pay a setup fee during the pilot, while residents will pay only for the services they book.

We will also explain the safety system, pricing and long-term packages. Every meeting must finish with one specific next step, such as a resident survey, pilot proposal, committee presentation or access review.

After the meeting, the team will update the CRM and send a written summary on the same day. Week 3 will be successful when PetSaathi has five to eight serious society discussions, three to five resident-demand surveys and two to four potential pilot opportunities.”

PetSaathi Phase 7 — Week 4: First Society Pilots 🏢🐾🚀

Week 4 objective

Convert the strongest Week 3 opportunities into 2–3 operational society pilots that produce real paid services—not only signed agreements or resident registrations.

The complete Week 4 outcome should be:

2–3 signed pilot societies

↓

Society access and support configured

↓

50–100 residents opt in

↓

20–50 paid services completed or scheduled

↓

Report Cards and reviews collected

↓

Repeat demand measured

↓

Society continuation decision prepared

The strongest approach is to activate societies in the same geographic cluster so they can share sitter capacity, backup caregivers, veterinary partners and operational support.

1. Correct interpretation of the Week 4 targets

| Metric | Proposed target | Final definition |
| --- | --- | --- |
| Pilot societies | 2–3 | Agreement signed and operational setup completed |
| Pet-parent leads | 50–100 | Residents who voluntarily opt in and identify a service need |
| Paid bookings | 20–50 | Payment verified and booking accepted into the service workflow |
| Repeat interest | 10+ | Residents requesting another service or package details |
| Society feedback | Collected | Structured committee, security and resident feedback |

Important distinction

A society should not count as an active pilot merely because its committee verbally agrees.

An active pilot requires:

Signed pilot document

+ authorised contacts

+ gate-access process

+ resident communication approval

+ usable sitter capacity

+ active booking page

Similarly, a WhatsApp-group member or poster viewer is not automatically a qualified lead. Residents should register voluntarily through an opt-in page or resident-initiated WhatsApp interaction. Meta requires businesses to obtain opt-in before proactively messaging people on WhatsApp.

2. Week 4 readiness gate

Before launching any society, verify six areas.

Society readiness

- Pilot agreement signed

- Authorised committee or facility contact

- Security contact confirmed

- Approved communication channel

- Service timings confirmed

- Access and replacement procedures documented

Product readiness

- Society landing page works

- Resident verification works

- Pet Profile form works

- Booking and payment work

- Report Card workflow works

- Support and incident actions work

Supply readiness

- Primary walkers available

- Pet sitters available

- Backup candidates available

- Access registration completed

- Peak-slot capacity calculated

- No sitter has an active safety restriction

Commercial readiness

- Trial price approved

- Resident discount configured

- Sitter payouts defined

- Cancellation/refund policy published

- Taxes and invoices configured where applicable

- Daily booking cap defined

Privacy readiness

- Resident notice is visible

- Society receives only aggregate reporting

- Unit numbers and Pet Profiles are restricted

- WhatsApp communication is opt-in

- Media and Report Cards are private

India’s final Digital Personal Data Protection Rules were published on November 14, 2025, with different provisions commencing on staged timelines. The pilot should therefore use clear notices, limited collection and controlled access from the beginning.

Operational readiness

- Named PetSaathi pilot owner

- Backup operations owner

- Emergency escalation contact

- Daily dashboard

- Society-specific FAQ

- Stop/pause procedure

3. End-to-end pilot launch process

Stage 1 — Society agrees

The verbal agreement from Week 3 should become a documented pilot approval.

Confirm the parties

Record:

Society legal/operating name

Authorised representative

PetSaathi legal entity

Pilot start and end dates

Active services

Resident pricing

Society responsibilities

PetSaathi responsibilities

Recommended pilot period

21–30 days

Week 4 launches the pilot; the pilot itself may continue into subsequent weeks.

The agreement should state

- No society setup or partnership fee during the pilot

- Residents pay for individual services

- No automatic renewal

- No guarantee of sitter availability

- PetSaathi controls assignments

- Society coordinates approved access

- Veterinary services are partner-delivered

- Resident data is not freely shared with the society

- Either party may pause the pilot for safety or operational reasons

Completion condition

Pilot status = SIGNED

This is not yet ACTIVE.

Stage 2 — Create the society landing page

The page becomes the main resident entry point.

Recommended URL

/pet-care/societies/[city]/[society-slug]

Example:

/pet-care/societies/ahmedabad/green-acres-bopal

Page content

- Society name

- Pilot status

- Services available

- Trial offer

- Society-supported service hours

- Public caregiver summaries

- Booking process

- Trust and safety controls

- Emergency coordination contact

- Society-specific FAQ

- Privacy, cancellation and refund links

Pilot-page indexing rule

A newly created pilot page with limited unique information can initially use:

noindex, follow

Make it indexable only when the partnership is active and the page has meaningful, accurate local content. Google classifies mass-produced pages with little unique user value as potential scaled-content or doorway abuse.

Technical checks

- Society ID automatically attached

- Unsupported services disabled

- Prices loaded from server configuration

- Mobile CTA visible

- Resident verification link works

- Analytics events fire correctly

- Public API excludes private fields

Completion condition

Landing page = PUBLISHED_FOR_PILOT

Stage 3 — Share the resident announcement

The society should distribute the announcement through an approved channel.

Use:

- Society WhatsApp announcement

- Resident application

- Email circular

- Lobby poster

- QR code

- Pet-parent group

- Facility-manager notice

Correct data flow

Society shares announcement

↓

Interested resident opens link

↓

Resident sees privacy notice

↓

Resident registers voluntarily

↓

PetSaathi records interest

Wrong data flow

Society sends PetSaathi its complete resident phone list

↓

PetSaathi sends bulk promotional messages

Announcement content

Include:

- What PetSaathi provides

- Pilot dates

- Services

- Trial price

- Capacity limitation

- Resident eligibility

- Booking link

- Support contact

- Opt-out information

Example offer

First eligible 30-minute dog walk from ₹99, subject to Pet Profile review, sitter availability and pilot capacity.

Completion condition

Resident campaign = LIVE

4. Collect pet-parent registrations

Goal

Obtain 50–100 qualified, opt-in leads across the pilot societies.

Recommended registration form

Collect only:

Resident name

Verified phone

Society

Tower/block

Unit — protected

Pet type

Interested service

Preferred time

Trial interest

Communication consent

Do not collect full medical or behavioural history in the lead form. That belongs in the private Pet Profile after the resident decides to proceed.

Lead statuses

REGISTERED

RESIDENCY_PENDING

RESIDENCY_VERIFIED

PET_PROFILE_STARTED

PET_PROFILE_COMPLETED

TRIAL_REQUESTED

PAID_CUSTOMER

Qualified lead definition

Count a resident as qualified when they have:

- Voluntarily registered

- Provided a usable contact

- Identified a pet-care need

- Accepted the relevant notice

- Belong to the pilot society

- Not opted out

Lead target distribution

For three societies:

| Society | Lead target |
| --- | --- |
| Society A | 20–40 |
| Society B | 15–30 |
| Society C | 15–30 |

Do not force equal targets. A smaller high-pet-density society may outperform a large premium society.

5. Map and activate the local sitter pool

Goal

Confirm real service capacity before accepting resident payments.

Sitter-pool requirements per pilot cluster

| Role | Suggested starting level |
| --- | --- |
| Primary dog walkers | 3–5 |
| Backup walker candidates | 2–3 |
| Pet sitters | 2–4 |
| Operations owner | 1 |
| Backup operations owner | 1 |
| Emergency veterinary contacts | 1–2 |

These are planning ranges. The real requirement is eligible capacity for each time window.

Sitter mapping workflow

Resident demand collected

↓

Morning/evening demand calculated

↓

Eligible sitters filtered

↓

Travel time checked

↓

Society access registered

↓

Pet-size and handling permissions checked

↓

Primary and backup capacity published

Required checks

- Service permission

- Active verification

- Society-access status

- Availability

- Travel feasibility

- Pet-size permission

- Reliability status

- No conflicting assignment

- No safety hold

Capacity example

Four eligible morning walkers

× two safe walks each

= eight potential services

Existing commitments: five

Backup capacity reserved: one

New morning capacity: two

The landing page should display:

Available

Limited availability

Waitlist

It should not continue accepting unlimited requests.

6. Launch the trial offer

Recommended core offer

Dog walking

First 30-minute dog walk:

₹99–₹149

Includes:

- Eligible sitter matching

- Arrival/start update

- Basic walk evidence

- Photo update where operationally appropriate

- Pet Report Card

- Same-sitter repeat option

Pet sitting

First one-hour home sitting:

₹199–₹299

Eligibility rules

Verified society resident

One introductory offer per household

Pet Profile completed

Service supported in society

Eligible sitter available

Prepayment completed

Subject to booking cap

Commercial guardrails

- Sitter still receives an approved payout.

- Discount funding is tracked.

- Offer has a start and end date.

- Slots cannot be transferred.

- Refund/cancellation rules are visible.

- “From ₹99” is used only when a genuine ₹99 slot exists.

Digital service pages should clearly disclose service information, pricing, payment, refunds and grievance mechanisms. The Consumer Protection (E-Commerce) Rules apply to goods and services transacted through digital platforms.

7. Create and confirm the first bookings

Booking workflow

Resident chooses service

↓

Selects or creates Pet Profile

↓

Chooses date/time

↓

Confirms society/unit

↓

Server calculates price

↓

Booking request created

↓

PetSaathi reviews requirements

↓

Eligible sitter assigned

↓

Resident pays

↓

Payment verified

↓

Booking confirmed

Payment rule

Do not confirm a prepaid pilot booking based only on the frontend success screen.

Razorpay describes server-side payment-signature verification as mandatory and recommends webhooks or API verification to handle callback failures and confirm payment state.

Required confirmation guard

Payment signature verified

+ payment captured/confirmed

+ active sitter assignment

+ no unresolved safety block

= CONFIRMED

Razorpay webhooks should also have their signatures validated before processing.

8. Deliver the first services

The first 5–10 bookings per society should receive enhanced operational monitoring.

Pre-service checklist

Customer

- Pet Profile complete

- Current-health confirmation

- Equipment ready

- Correct address/unit

- Emergency contact current

- Handover instructions ready

Sitter

- Booking acknowledged

- Access status active

- Pet instructions reviewed

- Travel started on time

- Phone charged

- Backup escalation understood

Operations

- Booking visible on live dashboard

- Backup options identified

- Payment verified

- Support contact ready

- Society security prepared

Service execution

Sitter arrives

↓

Security/access check

↓

Customer handover

↓

Service starts

↓

Updates/tracking captured

↓

Service completes

↓

Pet safely returned

↓

Report Card submitted

Evidence requirements

At minimum:

- Arrival or check-in confirmation

- Actual start time

- Actual end time

- Photo/video according to service policy

- Care observations

- Concern flag

- Completion confirmation

- Report Card

Incident rule

Any injury, escape, bite, major delay, unsafe handling or serious service failure should create a structured incident—not remain only in WhatsApp.

9. Generate and deliver the Report Card

Every completed service should produce a Report Card.

Dog-walking report

- Pet

- Sitter

- Start and end time

- Duration

- Approximate distance

- Water

- Pee/poop

- Mood

- Behaviour

- Media

- Concern

- Sitter note

Pet-sitting report

- Entry and exit times

- Food

- Water

- Toilet

- Play/activity

- Mood

- Medication task if authorised

- Media

- Concern

- Note

Report target

Report Cards delivered:

98%+

A serious concern may place the report into admin review before normal delivery.

10. Collect customer reviews

A review should be allowed only after the service is completed.

Review items

- Sitter punctuality

- Pet handling

- Communication

- Report quality

- Overall experience

- Would book again?

- Same sitter requested?

- Private complaint?

Review flow

Report Card delivered

↓

Review request sent

↓

Resident rates service

↓

Low rating routed to support

↓

Positive customer shown repeat option

Review target

For 20–50 paid bookings:

10–25 completed reviews

Important distinction

A review is not the correct place for urgent safety reporting.

Use:

- Review for service feedback

- Complaint ticket for formal dissatisfaction

- Incident ticket for safety events

11. Convert trials into repeat services

The target of 10+ repeat interest is useful but should be separated into stronger funnel stages.

Repeat funnel

REPEAT_INTERESTED

REPEAT_REQUESTED

PACKAGE_VIEWED

PACKAGE_PURCHASED

SECOND_BOOKING_PAID

SECOND_SERVICE_COMPLETED

The strongest validation is:

Second paid service completed

Recommended offers

After first dog walk

- Book same sitter again

- Five-walk starter pack

- Select weekly slot

After third service

- Ten-walk plan

- Preferred sitter schedule

- Society morning/evening plan

After pet sitting

- Weekly sitting plan

- Travel-care waitlist

- Festival-care priority registration

Week 4 target

10+ repeat-interest signals

5+ second booking requests

3–8 package or second-booking payments

The actual target should be adjusted according to how early in the week first services are completed.

12. Collect society feedback

Do not ask only:

“Did you like the pilot?”

Collect structured feedback from three groups.

Committee or facility manager

Ask:

- Was the setup process clear?

- Did residents understand the offer?

- Were sitter-access records useful?

- Were complaints handled properly?

- Was PetSaathi responsive?

- Should the pilot continue?

- Which package appears suitable?

Security team

Ask:

- Was sitter identification clear?

- Did replacements cause confusion?

- Were entry details available on time?

- Were any sitters denied access?

- What should be simplified?

Pet-parent residents

Ask:

- Was booking easy?

- Did you trust the sitter information?

- Was the service on time?

- Was the Report Card useful?

- Would you book again?

- What prevented you from booking?

Feedback record

Stakeholder

Rating

Positive feedback

Operational problem

Requested improvement

Severity

Owner

Due date

Resolution

13. Day-by-day Week 4 plan

Day 22 — Final pilot approvals

Tasks

- Select 2–3 strongest societies.

- Finalise pilot scope.

- Confirm authorised signatories.

- Sign pilot agreement.

- Confirm contacts and dates.

- Establish booking cap.

Output

2–3 pilots signed

Day 23 — Configure societies

Tasks

- Create society records.

- Publish pilot landing pages.

- Configure services and prices.

- Add access rules.

- Configure resident benefits.

- Create support routing.

- Set analytics events.

Output

Societies technically launch-ready

Day 24 — Resident announcement and registration

Tasks

- Release approved announcement.

- Publish QR codes.

- Open resident verification.

- Begin Pet Profile onboarding.

- Monitor form and support issues.

- Answer society FAQs.

Output

First 25–50 opt-in leads

Day 25 — Sitter mapping and first booking requests

Tasks

- Match demand to sitter availability.

- Register sitters with security.

- Identify backup candidates.

- Open limited trial slots.

- Review initial Pet Profiles.

- Send payment links/orders.

Output

First 5–15 paid bookings

Day 26 — First services

Tasks

- Monitor all services live.

- Confirm entry and handover.

- Verify tracking/update flows.

- Ensure Report Cards are delivered.

- Contact residents after service.

- Resolve issues immediately.

Output

First complete request-to-report journey

Day 27 — Expand bookings and repeat conversion

Tasks

- Open additional capacity.

- Run second service batch.

- Ask for reviews.

- Offer same-sitter repeat.

- Present five-walk starter pack.

- Gather security feedback.

Output

20–50 cumulative paid bookings or confirmed pipeline

10+ repeat-interest signals

Day 28 — Pilot health review

Tasks

- Analyse each society separately.

- Calculate funnel performance.

- Review sitter reliability.

- Review incidents and complaints.

- Gather committee feedback.

- Decide next-week improvements.

Output

Week 4 Society Pilot Health Report

14. Week 4 pilot dashboard

Track by society—not only as one combined total.

Acquisition

| Metric | Target |
| --- | --- |
| Announcement reach | Track |
| Landing-page visits | Track |
| Opt-in leads | 50–100 |
| Verified residents | 60%+ of leads |
| Pet Profiles completed | 30–60 |
| Trial requests | 25–60 |

Conversion

| Metric | Target |
| --- | --- |
| Booking requests → payment started | 50%+ |
| Payment started → successful | 70–85% |
| Paid bookings | 20–50 |
| Paid → completed service | 90%+ |

Service quality

| Metric | Target |
| --- | --- |
| On-time services | 95%+ |
| Report Cards delivered | 98%+ |
| Security-entry success | 97%+ |
| Sitter no-shows | Below 5% |
| Critical unresolved incidents | 0 |
| Customer rating | 4.5–4.6+ |

Retention

| Metric | Initial Week 4 target |
| --- | --- |
| Repeat interest | 10+ |
| Second booking requests | 5+ |
| Second paid bookings/packages | 3–8 |
| Same-sitter requests | Track |

Society health

| Metric | Target |
| --- | --- |
| Society feedback completed | 100% pilots |
| Security feedback completed | 100% pilots |
| Access issues recorded | 100% |
| Continuation interest | 2+ societies |
| Unresolved critical complaints | 0 |

15. Pilot funnel

Resident announcement seen

↓

Society landing page visited

↓

Resident opted in

↓

Residency verified

↓

Pet Profile completed

↓

Trial booking requested

↓

Payment started

↓

Payment verified

↓

Sitter assigned

↓

Service completed

↓

Report Card delivered

↓

Review submitted

↓

Repeat booking

Suggested analytics events

view_society_page

start_resident_verification

verify_society_resident

start_pet_profile

complete_pet_profile

click_trial_offer

start_booking

submit_booking

payment_started

payment_success

service_completed

report_delivered

submit_review

click_book_again

purchase_walk_pack

Google Analytics supports recommended and custom event measurement for user interactions, and server-side events can supplement browser measurement where required.

16. Pilot booking caps

Do not open unlimited capacity.

Recommended initial cap

| Stage | Maximum |
| --- | --- |
| First service day | 3–5 bookings |
| After first review | 5–10/day |
| Stable operation | Increase based on sitter capacity |

Pause new bookings when

- No backup coverage exists

- Entry failures repeat

- Report Cards are overdue

- Sitter utilisation is unsafe

- Active incident is unresolved

- Payment reconciliation fails

- Support queue exceeds capacity

Use:

AVAILABLE

LIMITED_AVAILABILITY

WAITLIST

PAUSED

on the society page.

17. Pilot decision states

At the end of the initial launch period, classify each society.

CONTINUE_PILOT

Use when:

- Demand exists

- Sample is still small

- Operations are improving

- No critical blocker exists

CONVERT_TO_BASIC_PARTNER

Use when:

- Consistent paid demand

- Stable sitter access

- Repeat interest

- Society wants ongoing reporting/support

OFFER_PREMIUM_DESK

Use when:

- High resident density

- Many recurring slots

- Complex access needs

- Coordinator demand exists

EVENT_FIRST_STRATEGY

Use when:

- Resident awareness is low

- Society wants a grooming, veterinary or training event first

- Recurring service demand is uncertain

PAUSE_AND_FIX

Use when:

- Entry process fails

- Sitter supply is insufficient

- Support load is too high

- Product defects affect bookings

TERMINATE_PILOT

Use when:

- Society obstructs safety processes

- Resident demand is absent

- Data is misused

- Unlawful pet-control expectations persist

- Economics are structurally unsustainable

18. Common Week 4 mistakes

Mistake 1 — Calling a signed agreement a successful pilot

Correction: A successful pilot requires registrations, paid services and operational evidence.

Mistake 2 — Activating all societies on the same day

Correction: Stagger launches by 24–48 hours where possible.

Mistake 3 — Promoting before sitter supply is ready

Correction: Confirm slot-level capacity before announcements.

Mistake 4 — Collecting leads without consent

Correction: Use resident opt-in forms and resident-initiated WhatsApp conversations.

Mistake 5 — Counting unpaid booking requests as paid bookings

Correction: Count only payments verified by the backend.

Mistake 6 — Offering unlimited ₹99 bookings

Correction: Limit the offer by household, dates and capacity.

Mistake 7 — Sending the society private resident data

Correction: Provide aggregate performance only.

Mistake 8 — Measuring “repeat interest” only by survey answers

Correction: Track second requests, payments and completed services separately.

Mistake 9 — Waiting until the end to ask for feedback

Correction: Gather feedback after the first 5–10 services.

Mistake 10 — Continuing despite operational warning signs

Correction: Use booking caps, waitlists and pause controls.

19. Week 4 deliverables

1. Signed pilot agreements

2–3 signed and configured pilots

2. Live society pages

- Correct services

- Resident trial

- Booking CTA

- Support contact

- Accurate availability

3. Resident lead database

50–100 opted-in residents

4. Society sitter-roster documents

- Primary caregivers

- Backup candidates

- Access status

- Service permissions

- Capacity

5. Paid booking records

20–50 paid pilot bookings

6. Report Cards and reviews

- Every completed service has a report

- Reviews requested

- Low ratings routed to support

7. Society feedback records

- Committee

- Facility manager

- Security

- Residents

8. Pilot health report

For each society:

Leads

Pet Profiles

Bookings

Payments

Completed services

On-time rate

Report delivery

Rating

Repeat interest

Complaints

Incidents

Access failures

Recommendation

Week 4 definition of done

Week 4 is complete only when:

Partnership

- Two or three authorised pilot agreements are signed.

- Pilot dates and scope are clear.

- Each society has operational contacts.

- Society responsibilities are documented.

Residents

- Registration is voluntary.

- Verification works.

- Leads are qualified.

- Pet Profiles are private.

- Opt-outs are respected.

Sitter operations

- Local sitter capacity exists.

- Security access is active.

- Backup candidates are identified.

- Booking caps reflect actual capacity.

- No single sitter creates unsafe dependency.

Payments and bookings

- Pricing is server-controlled.

- Payments are verified.

- Failed payments do not confirm bookings.

- Cancellations and refunds are traceable.

- Every status transition is audited.

Services

- First services complete successfully.

- Entry/start/end events are recorded.

- Report Cards are delivered.

- Reviews and concerns are routed correctly.

- Critical incidents have immediate ownership.

Business validation

- 20–50 paid bookings are generated or firmly confirmed.

- At least ten residents show repeat intent.

- Stronger repeat signals are tracked separately.

- Society and security feedback is collected.

- Each society receives a continuation recommendation.

Simple explanation for professor

“During Week 4, PetSaathi will launch its first two or three apartment-society pilots.

First, each society will sign a pilot agreement explaining the services, dates, payment model, sitter-access process, resident privacy and responsibilities of both parties.

PetSaathi will then create a society-specific landing page showing the trial offer, available services, local sitter information, booking steps and support contact.

The society will share an approved announcement and QR code with residents. Interested pet parents will register voluntarily rather than the society giving PetSaathi its full contact database.

After registration, residents will create their Pet Profiles. PetSaathi will analyse demand and map nearby walkers, pet sitters and backup caregivers. Only the number of booking slots that can be safely supported will be opened.

Residents can then book the introductory service. Payment will be verified through the backend before the booking becomes confirmed. The assigned sitter will complete the service and submit a Pet Report Card containing timings, care updates, media and any concerns.

After every service, the resident can submit a review and request the same sitter or a walking package. PetSaathi will separately track repeat interest, second booking requests and actual second paid services.

At the end of the week, PetSaathi will collect feedback from residents, society management and security. Each society will then be classified as ready to continue, ready for a paid partnership, needing operational improvements or unsuitable for further launch.

The Week 4 success condition is not only signing two or three societies. It is completing real paid services safely and proving that residents want to book again.”

PetSaathi Phase 7 — Week 5: Scale Pilots and Run Society Events 🏢🐾

Week 5 objective

Week 5 moves PetSaathi from a small pilot experiment into a controlled society cluster.

The goal is to:

Stabilise the first 2–3 pilots

↓

Add 3–5 nearby societies

↓

Run 1–3 carefully controlled events

↓

Convert residents into paid services

↓

Build a verified local partner network

↓

Collect credible testimonials

↓

Identify the strongest societies and services

By the end of Week 5, PetSaathi should have 5–8 total pilot societies, but they should ideally remain within the same two or three nearby localities.

Do not spread eight societies across an entire city. Density is still more valuable than geographic reach.

1. Correct Week 5 targets

| Metric | Proposed target | Correct measurement |
| --- | --- | --- |
| Total pilot societies | 5–8 | Signed, configured and operational |
| Society bookings | 75–150 | Paid bookings, tracked separately from completed services |
| Events or camps | 1–3 | Properly approved and operationally completed |
| Veterinary/grooming partners | 3–5 | Verified, contracted or pilot-approved partners |
| Testimonials | 5–10 | Real, consented and attributable feedback |

Add these quality targets

| Metric | Recommended target |
| --- | --- |
| Completed booking rate | 90%+ |
| On-time service rate | 95%+ |
| Report Card delivery | 98%+ |
| Security-entry success | 97%+ |
| Customer rating | 4.6+ |
| Repeat-interest rate | 25%+ |
| Critical unresolved incidents | 0 |
| Event attendee satisfaction | 4.5+ |
| Partner complaints unresolved | 0 |

2. Important distinction: signed versus active societies

A society should count as an active pilot only when:

Pilot approval signed

+

Society landing page live

+

Resident communication published

+

Local sitter capacity confirmed

+

Security/access workflow working

+

At least one resident registration or booking

Use these statuses:

PROSPECT

PILOT_APPROVED

SETUP_IN_PROGRESS

RESIDENT_REGISTRATION_OPEN

ACTIVE_PILOT

PAUSED

COMPLETED

CONVERTED

A society with a signed agreement but no residents, sitters or bookings should remain SETUP_IN_PROGRESS.

3. Society expansion strategy

Do not add all 3–5 societies at once

Recommended activation sequence:

Review first pilot performance

↓

Select next 2 strongest societies

↓

Launch and monitor

↓

Fix common problems

↓

Activate remaining 1–3 societies

Recommended cluster model

For example, in Ahmedabad:

Cluster A:

Bopal + South Bopal

Cluster B:

Satellite + Prahlad Nagar

Each cluster should ideally share:

- Dog walkers

- Backup sitters

- Operations owner

- Emergency veterinary contacts

- Grooming partners

- Event equipment

- Support procedures

4. Society selection criteria for expansion

Choose the next 3–5 societies based on:

| Factor | Weight |
| --- | --- |
| Confirmed resident demand | 25% |
| Local sitter capacity | 20% |
| Geographic proximity | 15% |
| Committee readiness | 15% |
| Security/access feasibility | 10% |
| Society size and occupancy | 10% |
| Partner-event potential | 5% |

Do not activate a society when

- No eligible local sitter is available.

- All peak slots are already full.

- Security access remains unresolved.

- The society expects illegal or discriminatory pet controls.

- Resident demand is only assumed.

- Existing pilots have unresolved safety failures.

- Support staff cannot monitor additional bookings.

5. Week 5 operating model

Week 5 contains two parallel workstreams.

Workstream A — Scale recurring care services

Resident announcement

→ Pet Profile

→ Trial booking

→ Completed service

→ Report Card

→ Review

→ Repeat plan

Workstream B — Run society events

Society and partner approval

→ Resident registration

→ Event delivery

→ Feedback

→ Pet Profile creation

→ Trial service conversion

Events should support the main marketplace. They should not distract the team from dog walking, sitting and repeat service quality.

6. Society event strategy

Each event should have one primary purpose.

| Event | Primary purpose |
| --- | --- |
| Pet health-check camp | Trust and veterinary-partner credibility |
| Grooming day | Direct event revenue and resident activation |
| Dog-walking trial day | Convert residents into recurring services |
| Pet-parent meetup | Community trust and demand discovery |
| Diwali safety session | Seasonal education and early-care bookings |
| Puppy-care workshop | Education and long-term customer acquisition |

Do not run an event merely to produce social-media photographs.

Every event should have:

Target audience

Capacity

Partner

Revenue model

Registration process

Consent

Safety plan

Conversion goal

Success metrics

7. Event 1 — Pet health-check camp

Purpose

Build resident trust and introduce PetSaathi through a useful professional service.

Correct responsibility model

PetSaathi acts as:

- Event coordinator

- Registration platform

- Resident communication layer

- Queue and payment coordinator

- Follow-up service platform

A registered veterinary practitioner remains responsible for:

- Clinical examination

- Medical advice

- Diagnosis

- Prescription

- Referral

- Clinical records

The Indian Veterinary Council Act regulates veterinary practice and provides for registered veterinary practitioners and veterinary councils. Therefore, PetSaathi should not present ordinary staff or event coordinators as veterinary professionals.

Possible services

- General physical check

- Weight assessment

- Skin or coat observation

- Dental observation

- Vaccination-record review

- Preventive-care guidance

- Clinic referral

Recommended workflow

Resident registers

↓

Pet and appointment verified

↓

Owner consent confirmed

↓

Veterinarian examines pet

↓

Clinical summary provided

↓

Follow-up recommendation recorded

↓

PetSaathi offers relevant care services separately

Revenue model

Prefer:

- Fixed coordination fee

- Fixed fee per completed appointment

- Society-sponsored event

Avoid commission linked directly to how many treatments or vaccines are recommended.

Conversion offer

After the appointment:

Complete your PetSaathi Pet Profile and receive a first dog-walking or pet-sitting offer.

8. Event 2 — Grooming day

Purpose

Generate event revenue and attract residents who may later use recurring care services.

Partner requirements

The grooming partner should provide:

- Experienced staff

- Safe equipment

- Hygiene process

- Pet-handling process

- Service menu

- Capacity limits

- Incident procedure

- Cleaning and waste disposal

Recommended services

- Bathing

- Brushing

- Basic coat care

- Nail trimming when appropriate

- Basic hygiene services

Do not include as routine grooming services

- Sedation

- Medical skin treatment

- Wound treatment

- Veterinary dental procedures

- Any service beyond partner competence

Revenue models

Revenue share

Resident pays service price

↓

Refunds/discounts adjusted

↓

Partner share calculated

↓

PetSaathi coordination share calculated

Fixed partner fee

PetSaathi receives an agreed amount per completed appointment.

Society event fee

The society pays PetSaathi to coordinate the event.

Required transparency

Residents should clearly see:

- Service provider

- Service description

- Price

- Cancellation policy

- Refund policy

- Complaint channel

India’s Consumer Protection (E-Commerce) Rules apply to digital transactions for goods and services and require clear consumer-facing information and grievance arrangements.

9. Event 3 — Dog-walking trial day

Purpose

This should be the highest-priority Week 5 event because it directly converts residents into PetSaathi’s strongest recurring service.

Recommended format

Do not gather many unknown dogs for a group walk.

Use individual scheduled trial appointments:

09:00–09:30 — Resident 1

09:45–10:15 — Resident 2

10:30–11:00 — Resident 3

Each trial includes:

- Pet Profile review

- Owner handover

- Equipment check

- Individual walk

- Basic GPS evidence

- Photo update

- Pet Report Card

- Repeat offer

Safety rule

Two dogs should not be combined merely because they booked the same event.

Shared walking requires:

- Compatibility review

- Owner consent

- Sitter capability

- Appropriate equipment

- Separate service policy

Recommended offer

30-minute trial walk:

₹99–₹149

Trial-day conversion flow

Trial completed

↓

Report Card delivered

↓

Customer review requested

↓

Same walker shown

↓

Five-walk pack offered

↓

Regular society time slot selected

Success metrics

- Trials completed

- On-time rate

- Customer rating

- Same-sitter requests

- Five-walk plan purchases

- Second completed services

10. Event 4 — Pet-parent meetup

Purpose

Build community trust, understand resident needs and create warm leads.

Suggested agenda

1. Introduction to PetSaathi

2. Responsible society pet-care process

3. How sitter verification works

4. Pet Profile demonstration

5. Report Card demonstration

6. Lost-pet alert explanation

7. Upcoming care services and events

8. Resident questions

Useful discussion topics

- Daily walking needs

- Holiday care

- Boarding concerns

- Society access

- Emergency contacts

- Common-area coordination

- Same-sitter preferences

Commercial use

The meetup can promote:

- Trial dog walks

- Five-walk plans

- Pet-sitting bookings

- Upcoming camps

- Society pet-parent community

Privacy rule

Do not automatically add every attendee to PetSaathi marketing lists or WhatsApp groups.

Residents should opt in for:

- Service information

- Event reminders

- Lost-pet alerts

- Marketing offers

Meta requires businesses to obtain opt-in before sending people WhatsApp business messages, and the opt-in should make the business and messaging purpose clear.

11. Event 5 — Diwali pet-safety session

Purpose

Build seasonal trust and generate early bookings for walking, sitting and controlled boarding.

Timing

Run the session before peak Diwali travel and fireworks activity, not after booking capacity is already full.

Suggested topics

- Fireworks anxiety preparation

- Safe indoor space

- Identification tag and current pet photo

- Walk timing adjustments

- Door and gate safety

- Pet Profile health update

- Emergency veterinarian details

- Lost-pet prevention

- Travel and boarding deadlines

- Medication discussions with the pet’s veterinarian

Presenter model

Use:

- Registered veterinarian for medical guidance

- Screened trainer or behaviour professional for behaviour preparation

- PetSaathi operations team for booking and safety workflows

PetSaathi staff should not diagnose anxiety or recommend medication.

Conversion opportunities

- Diwali pet-sitting bookings

- Individual walking slots

- Boarding beta waitlist

- Same-sitter festival continuity

- Emergency-contact verification

- Lost-pet alert preparation

12. Event 6 — Puppy-care workshop

Purpose

Acquire long-term customers early in the pet-parent journey.

Suggested topics

- Puppy routine

- Toilet schedule

- Safe socialisation

- Leash foundations

- Bite inhibition education

- Food and water routine

- Veterinary schedule awareness

- Home safety

- Separation preparation

- Pet Profile creation

Partner model

Use:

- Registered veterinarian for health topics

- Humane trainer for training topics

- PetSaathi for care-service planning

Safety controls

- Avoid uncontrolled puppy mixing.

- Use limited capacity.

- Require secure carriers or leashes.

- Keep nervous puppies separated.

- Do not force interactions.

- Do not diagnose medical or behavioural conditions publicly.

The Prevention of Cruelty to Animals Act is India’s primary central legislation against unnecessary animal pain or suffering; event design and handling should remain humane and controlled.

13. Event approval workflow

Every event should follow the same controlled process.

Event concept created

↓

Society approves venue and date

↓

Partner verified

↓

Commercial agreement signed

↓

Capacity and safety plan approved

↓

Registration page published

↓

Resident communication sent

↓

Event delivered

↓

Payments and partner payout reconciled

↓

Feedback and conversion campaign

Event status values

DRAFT

PARTNER_REVIEW

SOCIETY_APPROVAL

REGISTRATION_OPEN

ALMOST_FULL

FULL

IN_PROGRESS

COMPLETED

POSTPONED

CANCELLED

14. Event registration data

Collect only what is required.

General event fields

- Resident name

- Verified phone

- Society

- Pet name

- Pet species

- Appointment slot

- Consent

- Payment status

Clinical events

The veterinary partner may require additional health information, but access should remain limited to authorised personnel.

The DPDP Rules, 2025 were officially published on November 14, 2025 with staged commencement timelines. PetSaathi should provide a clear notice explaining what data is collected, why it is required, which partner receives it and how long it will be retained.

Do not collect unnecessarily

- Full resident family details

- Unrelated medical records

- Government identification for ordinary event registration

- Emergency contacts when not needed

- Permanent marketing consent hidden inside event consent

15. Build the local partner network

Week 5 target

Create 3–5 usable partners, for example:

| Partner type | Suggested count |
| --- | --- |
| Veterinary clinics/practitioners | 1–2 |
| Grooming partners | 1–2 |
| Dog trainer/educator | 1 |
| Emergency transport or additional clinic | Optional |

Partner verification checklist

Business verification

- Legal/business name

- Public contact

- Service area

- Pricing

- References

- Agreement status

Professional verification

For veterinary partners:

- Practitioner name

- Registration information

- Clinic

- Service scope

Operational verification

- Staff capacity

- Equipment

- Event capacity

- Cancellation policy

- Incident process

- Insurance where available

- Availability

Commercial verification

- Fixed fee or revenue share

- Tax treatment

- Invoice responsibility

- Refund responsibility

- Payment timeline

- Marketing permissions

Partner statuses

IDENTIFIED

CONTACTED

UNDER_REVIEW

APPROVED_FOR_PILOT

ACTIVE

PAUSED

SUSPENDED

EXPIRED

16. Add 3–5 more societies

Expansion workflow

Select qualified society

↓

Confirm demand

↓

Check sitter capacity

↓

Sign pilot approval

↓

Configure landing page

↓

Register security access

↓

Open resident registration

↓

Launch limited booking slots

Recommended launch order

First expansion batch

Add two societies with:

- Strong resident interest

- Existing local sitter capacity

- Simple security process

Second expansion batch

Add one to three societies after reviewing the first expansion results.

Booking-cap model

| Society stage | Recommended daily cap |
| --- | --- |
| First two service days | 3–5 |
| Stable after review | 5–10 |
| Mature pilot | Based on verified slot capacity |

17. Week 5 day-by-day execution plan

Day 29 — Review Week 4 pilots

Tasks

- Compare all active societies.

- Review booking completion.

- Review security-entry failures.

- Review sitter capacity.

- Review support workload.

- Identify reusable fixes.

Output

Pilot scaling readiness report

Day 30 — Select new societies and events

Tasks

- Select 3–5 expansion societies.

- Choose 1–3 event concepts.

- Confirm society interest.

- Confirm partner availability.

- Assign operations owners.

Output

Expansion and event calendar

Day 31 — Partner verification and agreements

Tasks

- Verify veterinary and grooming partners.

- Define service responsibilities.

- Finalise event pricing.

- Confirm invoicing and refunds.

- Review incident procedures.

Output

3–5 approved pilot partners

Day 32 — Configure new society pilots

Tasks

- Sign pilot approvals.

- Create landing pages.

- Configure resident offers.

- Configure service capacity.

- Register sitters with security.

- Publish FAQs and support contacts.

Output

3–5 societies ready for resident launch

Day 33 — Open event and society registrations

Tasks

- Publish resident announcements.

- Open QR registration.

- Launch event slots.

- Start Pet Profile onboarding.

- Monitor demand by time slot.

- Create waitlists where needed.

Output

New resident leads and event registrations

Day 34 — Deliver first event and expanded services

Tasks

- Monitor check-in.

- Manage queues and capacity.

- Verify service delivery.

- Record incidents.

- Deliver reports or partner records.

- Collect same-day feedback.

Output

First completed event

+

expanded booking volume

Day 35 — Conversion and performance review

Tasks

- Send attendee follow-ups.

- Offer trial dog walks or sitting.

- Request reviews and testimonials.

- Review partner performance.

- Calculate event economics.

- Decide which societies can grow further.

Output

Week 5 expansion and event report

18. Testimonials

Week 5 target

Collect 5–10 credible testimonials.

Possible sources:

- Pet parents

- Facility manager

- RWA representative

- Security supervisor

- Veterinary partner

- Grooming partner

Testimonial consent

Before publishing, record:

- Exact approved wording

- Name display preference

- Society display permission

- Pet photo permission

- Channel permission

- Expiry or withdrawal process

Display options

Full first name + pet name

First name + initial

Anonymous society resident

Facility manager, society name

Never fabricate or rewrite beyond approval

A real customer statement should not be exaggerated into a guarantee.

For example:

Original:

“The walker was on time and the report was useful.”

Do not transform it into:

“PetSaathi is the safest and best pet-care company in India.”

Advertising claims and endorsements should remain truthful and not misleading.

Testimonial types

Service testimonial

“The sitter arrived on time and Bruno’s Report Card made the service very transparent.”

Society testimonial

“The approved sitter list made the security process easier during the pilot.”

Partner testimonial

“The society registration process helped us organise appointments efficiently.”

19. Event-to-booking conversion

Every event needs a follow-up campaign.

Within two hours

- Thank attendees.

- Share partner record or service confirmation.

- Provide support contact.

Within 24 hours

- Request event feedback.

- Invite residents to complete Pet Profiles.

- Offer trial dog walking or pet sitting.

Within 48–72 hours

- Remind interested residents.

- Offer same-society service slots.

- Promote walking packages.

Conversion funnel

Event registered

↓

Attended

↓

Pet Profile started

↓

Pet Profile completed

↓

Trial booking requested

↓

Payment completed

↓

Service completed

↓

Repeat booking

Recommended targets

| Funnel stage | Initial target |
| --- | --- |
| Registered → attended | 60–80% |
| Attended → qualified lead | 60%+ |
| Lead → Pet Profile completed | 30–50% |
| Lead → trial booking | 15–30% |
| Trial → completed service | 90%+ |
| Completed service → repeat | 25–35% |

These are internal planning targets and should be updated from actual pilot data.

20. Booking target breakdown

The target of 75–150 society bookings should be divided into clear categories.

| Booking category | Example target |
| --- | --- |
| Dog-walking trials | 25–50 |
| Repeat dog walks | 25–60 |
| Pet-sitting bookings | 10–20 |
| Boarding beta | 0–5 |
| Event-linked service bookings | 10–20 |

Track separately

BOOKING_REQUESTED

PAYMENT_STARTED

PAID

CONFIRMED

COMPLETED

CANCELLED

REFUNDED

Do not report unpaid requests as paid bookings or paid bookings as completed services.

21. Week 5 dashboard

Society expansion

| Metric | Target |
| --- | --- |
| Total active pilot societies | 5–8 |
| New societies configured | 3–5 |
| Society landing pages live | 100% |
| New resident registrations | Track |
| Security-access success | 97%+ |

Booking performance

| Metric | Target |
| --- | --- |
| Paid society bookings | 75–150 |
| Completed services | 90%+ of due bookings |
| On-time rate | 95%+ |
| Report Cards delivered | 98%+ |
| Repeat requests | 25%+ |
| Refund/dispute rate | Below 5% |

Events

| Metric | Target |
| --- | --- |
| Events completed | 1–3 |
| Registration attendance | 60–80% |
| Event rating | 4.5+ |
| Event safety incidents | Zero preferred |
| Event-to-trial conversion | 15–30% |
| Partner payments reconciled | 100% |

Partners

| Metric | Target |
| --- | --- |
| Active approved partners | 3–5 |
| Written commercial scope | 100% |
| Veterinary registration checked | 100% relevant partners |
| Unresolved partner complaints | 0 |

Social proof

| Metric | Target |
| --- | --- |
| Approved testimonials | 5–10 |
| Permission records | 100% |
| Fake or unverified testimonials | 0 |

22. Event financial report

For every event, calculate:

Society coordination fee

+

Resident ticket/service revenue

+

Sponsor revenue

+

Post-event booking contribution

−

Partner payout

−

Venue/setup cost

−

Staff and travel

−

Discounts

−

Refunds

−

Marketing cost

=

Net event contribution

Separate these values

- Event GMV

- PetSaathi revenue

- Partner payout

- Tax

- Refunds

- Net contribution

Do not call the total resident payment value PetSaathi revenue.

GST invoice rules require prescribed information on invoices for taxable services and generally provide a 30-day period for issuing service invoices, subject to applicable exceptions. Final tax treatment should be confirmed with a chartered accountant.

23. Major risks during Week 5

Risk 1 — Scaling before Week 4 is stable

Control

Do not add new societies when:

- Report Cards are missing.

- Payments are unreconciled.

- Existing incidents remain unresolved.

- No backup sitters exist.

- Support response is deteriorating.

Risk 2 — Events consume all operations capacity

Control

Assign separate owners for:

- Normal bookings

- Event operations

- Partner coordination

Do not cancel regular care services to run promotional events.

Risk 3 — Overcrowded events

Control

Use:

- Appointment slots

- Capacity limit

- Waitlist

- Separate pet waiting areas

- Secure leashes/carriers

- No forced interaction

Risk 4 — Unverified professional partner

Control

Verify identity, credentials, service scope and responsibility before promotion.

Risk 5 — Resident data shared with partners

Control

Partners receive only the data needed to deliver the booked service. Marketing access requires separate resident permission.

Risk 6 — Discount-driven low-quality bookings

Control

Keep services prepaid and limit introductory offers by household and capacity.

Risk 7 — Testimonials without consent

Control

Use a formal testimonial approval process.

24. Common Week 5 mistakes

Mistake 1 — Adding five societies without sitter capacity

Correction: Calculate slot-level capacity before announcements.

Mistake 2 — Running three events on one weekend

Correction: Run one event first, review operations and then expand.

Mistake 3 — Calling every veterinary clinic a partner

Correction: A partner must be reviewed and have an agreed operating scope.

Mistake 4 — Counting event attendees as customers

Correction: Track attendees, leads, paid bookings and repeat customers separately.

Mistake 5 — Using camps only for branding

Correction: Every event needs a conversion path into Pet Profiles and bookings.

Mistake 6 — Combining unfamiliar dogs for convenience

Correction: Use individual appointments unless compatibility is separately approved.

Mistake 7 — Publishing private attendee information

Correction: Society and sponsors receive aggregate results unless residents separately opt in.

Mistake 8 — Collecting generic testimonials

Correction: Collect specific feedback about punctuality, transparency, service quality or society operations.

25. Week 5 deliverables

1. Expanded society portfolio

5–8 total active pilot societies

2. Society cluster map

Shows:

- Active societies

- Sitter locations

- Peak service windows

- Backup coverage

- Veterinary partners

- Event partners

3. Event operating kit

Includes:

- Event proposal

- Registration page

- Consent language

- Partner agreement

- Appointment schedule

- Safety checklist

- Incident procedure

- Feedback form

4. Partner registry

3–5 reviewed and approved partners

5. Society booking report

75–150 paid bookings

with payment and completion status separated

6. Event performance report

For each event:

- Registrations

- Attendance

- Services delivered

- Revenue

- Partner payout

- Feedback

- Incidents

- Converted bookings

7. Testimonial library

5–10 approved testimonials

with consent records

8. Week 6 recommendations

Classify:

- Societies ready to convert

- Societies needing more time

- High-performing events

- Weak events

- Strong partners

- Partners to pause

- Areas with insufficient capacity

Week 5 definition of done

Week 5 is complete only when:

Societies

- Five to eight pilots are operational.

- New societies have real resident demand.

- Each has active sitter capacity.

- Security workflows function.

- Booking caps are enforced.

Bookings

- Paid and completed bookings are reported separately.

- Payments are verified.

- Services are monitored.

- Report Cards are delivered.

- Repeat demand is tracked.

Events

- At least one event is completed safely.

- Partner responsibility is documented.

- Registration and consent are controlled.

- Event attendees are offered a relevant next step.

- Financial reconciliation is complete.

Partners

- Veterinary partners have appropriate professional verification.

- Grooming and training partners have defined service scopes.

- Refund and complaint responsibility is clear.

- Partner performance is recorded.

Testimonials

- Every published testimonial is genuine.

- The customer or partner approved the wording.

- Personal data and images are used only with permission.

- No statement is converted into an unsupported safety claim.

Operations

- Existing pilot quality has not fallen.

- No critical incident remains unresolved.

- Support workload remains manageable.

- The team can explain which societies, events and services deserve further investment.

Final Week 5 operating principle

Scale only the society services that are already reliable, and use events to create qualified demand—not to hide weak recurring booking performance.

The most important Week 5 result is not the number of events or society logos.

It is:

More nearby residents

+

More completed paid services

+

Reliable local sitters

+

Useful partners

+

Strong repeat intent

+

No decline in safety or service quality

Simple explanation for professor

“During Week 5, PetSaathi will expand from the first two or three societies to a total of five to eight active pilot societies.

We will add only societies located near the existing pilot areas so that walkers, backup sitters, veterinary partners and the operations team can serve them efficiently.

PetSaathi will also conduct one to three events. A pet health-check camp will be organised through a registered veterinary partner. A grooming day will be delivered through a verified grooming provider. A dog-walking trial day will allow residents to experience an individual paid trial walk and receive a Pet Report Card.

Other event options include pet-parent meetings, Diwali safety sessions and puppy-care workshops. PetSaathi will coordinate registrations and operations, while qualified partners remain responsible for veterinary, grooming or training services.

After every event, residents will be invited to complete their Pet Profiles and book a trial dog walk or pet-sitting service. This means the event is used to create real customers instead of only social-media visibility.

By the end of Week 5, the goal is to have five to eight active pilot societies, 75 to 150 paid society bookings, three to five approved partners and five to ten genuine testimonials.

PetSaathi will continue scaling only if service completion, punctuality, Report Cards, security access and customer satisfaction remain strong.”

PetSaathi Phase 7 — Weeks 6–8: Convert Pilots into Paid Society Partnerships 🏢🐾💼

Executive decision

The conversion model is approved, but a society should not become a paid partner based only on registrations, booking requests or positive verbal feedback.

A successful conversion must prove four things:

Resident demand

+

Reliable service delivery

+

Positive operating economics

+

Society willingness to continue

The recommended Weeks 6–8 sequence is:

Week 6 — Audit pilot performance

↓

Week 7 — Present and negotiate paid proposal

↓

Week 8 — Sign, invoice and activate paid partnership

1. Correct paid-conversion criteria

Your original criteria are a useful minimum:

| Metric | Original target |
| --- | --- |
| Pet-parent leads | 30+ |
| Paid bookings | 15+ |
| Repeat customers | 5+ |
| Average rating | 4.5+ |
| RWA feedback | Positive |
| Complaints | Manageable |

However, several terms need exact definitions.

A. Pet-parent leads: 30+

Approved with modification

Count only qualified opt-in residents who:

- Live in or are authorised occupants of the society

- Voluntarily registered

- Identified a genuine pet-care requirement

- Provided valid contact information

- Accepted the relevant communication and privacy notice

- Have not opted out

Do not count:

- WhatsApp-group members

- Poster views

- Event visitors who did not register

- Unverified phone numbers

- Residents imported from a society list without a valid process

The DPDP Rules, 2025 were officially published on November 14, 2025 with staged commencement provisions. PetSaathi should therefore maintain clear notices, defined data purposes, limited access and appropriate retention for pilot and partnership data.

Stronger target

Minimum: 30 qualified leads

Strong: 50+

Excellent: 75+

Also report:

Qualified leads

→ Pet Profiles completed

→ First paid booking

B. Paid bookings: 15+

Modify to completed paid bookings

A booking should count toward conversion only when:

Payment verified

+

Sitter assigned

+

Service completed

+

Report Card delivered

A booking request, payment attempt or future confirmed booking is useful pipeline data, but it does not prove service delivery.

Recommended threshold

| Level | Completed paid services |
| --- | --- |
| Minimum conversion evidence | 15 |
| Strong Basic Partner evidence | 25–40 |
| Premium Desk consideration | 50+ with recurring demand |

Also report:

- Paid bookings created

- Completed bookings

- Cancelled bookings

- Refunded bookings

- No-shows

- Services still scheduled

Digital service transactions should clearly present service information, prices, payment terms, cancellation/refund terms and grievance channels. The Consumer Protection (E-Commerce) Rules apply to goods and services transacted over digital or electronic networks.

C. Repeat customers: 5+

Important correction

Do not define repeat customer as:

“The resident said they are interested in booking again.”

Use:

A resident who completed at least one additional paid service after the introductory booking.

Track the stages separately:

REPEAT_INTERESTED

REPEAT_REQUESTED

SECOND_BOOKING_PAID

SECOND_SERVICE_COMPLETED

PACKAGE_PURCHASED

PACKAGE_CREDITS_USED

Recommended threshold

Minimum:

5 second paid bookings or package purchases

Stronger:

25%+ of eligible first-time customers repeat

Best evidence:

Second service completed successfully

Example:

28 first paid customers

7 completed second services

Repeat completion rate:

25%

A package purchase is useful, but PetSaathi should also monitor whether the customer actually consumes the package credits.

D. Rating: 4.5+

Approve with sample-size protection

A 4.8 rating from three residents is not sufficient evidence.

Report:

Average rating

+

Number of submitted reviews

+

Review response rate

+

Rating distribution

Recommended threshold

Average rating: 4.5+

Minimum completed reviews: 10

Review response rate: 40–50%+

No unresolved 1-star safety complaint

Example:

Average rating: 4.7/5

Reviews submitted: 18

Review response rate: 64%

1–2 star reviews: 1

Critical unresolved reviews: 0

Any public conversion claim such as “4.7-rated service” must match the real data and sample. ASCI’s code requires advertising and promotional representations to be legal, honest, truthful and capable of substantiation.

E. RWA feedback: positive

Replace vague feedback with a scorecard

Collect feedback from:

- RWA/AOA representative

- Facility manager

- Security supervisor

- Pet-parent residents

- Non-pet resident complaints, where relevant

Society scorecard

| Question | Rating |
| --- | --- |
| Was pilot setup clear? | 1–5 |
| Was the sitter-access roster useful? | 1–5 |
| Was PetSaathi responsive? | 1–5 |
| Were complaints handled properly? | 1–5 |
| Did the service provide resident value? | 1–5 |
| Should the society continue? | Yes/No |
| Preferred partnership package | Pilot/Basic/Premium/Event |

Paid-conversion requirement

Authorised society representative supports continuation

+

Security/facility process is workable

+

No major unresolved operational objection

A few residents liking the service does not replace formal society approval.

F. Complaints: manageable

Replace with measurable limits

Recommended thresholds:

| Metric | Target |
| --- | --- |
| Critical unresolved complaints | 0 |
| Total society complaints | Below 5 per 100 completed services |
| Security-entry failures | Below 3–5% |
| Complaint acknowledgement | Same working day |
| Active-service issue response | Under 5–10 minutes |
| Complaints with assigned owner | 100% |
| Repeated unresolved complaint pattern | 0 |

Complaint categories should include:

Sitter access

Punctuality

Sitter conduct

Pet handling

Cleanliness

Common-area use

Payment/refund

Privacy

Service quality

Safety incident

“Manageable” should never be used to hide one serious unresolved safety incident.

2. Additional mandatory conversion criteria

The original criteria should be expanded with operational and financial gates.

Service reliability

| Metric | Target |
| --- | --- |
| Paid → completed service | 90%+ |
| On-time arrival | 95%+ |
| Report Card delivery | 98%+ |
| Sitter no-show rate | Below 3–5% |
| Security-entry success | 97%+ |
| Payment reconciliation | 100% |
| Unresolved critical incidents | 0 |

Sitter capacity

The society should have:

- At least two usable primary caregivers

- Genuine backup coverage for priority services

- No unsafe dependency on one sitter

- Enough capacity for peak walking windows

- No unresolved verification or training expiry

Customer retention

Second completed booking rate: 20–25%+

or

5+ recurring/package customers

Operational workload

Measure:

Support minutes per booking

Admin interventions per booking

Replacement frequency

Manual payment corrections

Access failures

Report Card follow-ups

A society generating 20 bookings but requiring three hours of manual support per booking may not be ready for a standard paid package.

3. Unit economics gate

A society should not be converted solely because it has demand. It should have a credible path to positive contribution.

Track four separate financial values

1. Resident booking GMV

2. PetSaathi service revenue

3. Society partnership-fee revenue

4. Net contribution after direct costs

Do not describe total resident booking value as PetSaathi revenue.

Contribution formula

Society contribution =

Society monthly fee

+

PetSaathi margin from resident services

− Resident discounts funded by PetSaathi

− Sitter payments

− Payment-provider costs

− Society coordinator allocation

− Support cost

− Refund/recovery cost

− Event allocation

Example pilot economics

Resident service GMV:              ₹22,000

PetSaathi service contribution:     ₹6,500

Direct pilot support cost:          ₹5,000

Discount subsidy:                   ₹1,200

Pilot contribution before fee:        ₹300

Recommended paid plan:

Basic Society Partner:

₹9,999/month + applicable taxes

Expected post-conversion contribution:

Monthly fee:                       ₹9,999

Service contribution:             ₹6,500

Estimated direct costs:           ₹7,500

Estimated society contribution:   ₹8,999

These values are examples only. Use real pilot data in every proposal.

Where PetSaathi is required to issue a tax invoice for a taxable service, CBIC’s invoice rules generally require a service invoice within 30 days of the supply of service. Final GST registration, classification and invoicing treatment should be confirmed with a chartered accountant.

4. Conversion-readiness decision model

Use these outcomes instead of a simple yes/no decision.

BASIC_PARTNER_READY

Use when:

- 30+ qualified resident leads

- 15+ completed paid bookings

- 5+ repeat customers

- 4.5+ rating with sufficient reviews

- Operations stable

- Society wants continued support

- Moderate reporting and support needs

Recommended package:

Basic Society Partner

₹5,000–₹15,000/month

PREMIUM_DESK_READY

Use when:

- 50+ active or qualified pet households

- Strong recurring walking demand

- Multiple walking windows

- Complex gates or towers

- 40–50+ completed monthly services

- Coordinator demand exists

- Events and local partnerships are valuable

Recommended package:

Premium Pet-Care Desk

₹15,000–₹50,000/month

EVENT_MODEL_READY

Use when:

- Society engagement is high

- Recurring-care bookings remain limited

- Camps or workshops receive stronger demand

- The society does not need ongoing management

Recommended package:

Event/Camp Model

Event-specific pricing

EXTEND_PILOT

Use when:

- Resident demand appears promising

- Sample is too small

- Repeat customers have not matured

- One fixable operational issue remains

- No critical safety blocker exists

Recommended extension:

14–30 additional days

with defined targets

Do not extend free pilots indefinitely.

PAUSE_AND_FIX

Use when:

- Access failures are frequent

- Report Cards are missing

- Sitter supply is weak

- Support workload is excessive

- Payment/refund workflow is unstable

DO_NOT_CONVERT

Use when:

- No meaningful resident demand

- No usable local sitter supply

- Critical incidents remain unresolved

- Society obstructs safety controls

- Society expects unlawful pet-control practices

- Data-access expectations are unacceptable

- Economics are structurally negative

5. Week 6 — Pilot audit and conversion preparation

Goal

Determine which societies are ready for a paid proposal.

Day 36 — Freeze the pilot dataset

Create a defined reporting period:

Pilot start date

Pilot end date

Data cutoff time

Reconcile:

- Resident registrations

- Pet Profiles

- Booking requests

- Payments

- Completed services

- Cancellations

- Refunds

- Reviews

- Repeat bookings

- Complaints

- Incidents

Do not update the presentation manually from scattered spreadsheets after the data is frozen.

Day 37 — Analyse the resident funnel

For each society:

Announcement reach

↓

Landing-page visits

↓

Qualified leads

↓

Pet Profiles completed

↓

Paid bookings

↓

Completed services

↓

Reviews

↓

Second bookings

Identify the largest drop-off.

Example:

62 qualified leads

45 Pet Profiles

31 booking requests

28 payments

26 completed services

18 reviews

7 second completed bookings

Day 38 — Analyse operational quality

Review:

- On-time rate

- Sitter acceptance

- Sitter cancellations

- Security-entry failures

- Replacement use

- Report Card completion

- Support workload

- Complaints

- Incidents

Prepare one operational summary for the society and a more detailed internal report.

The society report should remain aggregated. It should not include individual Pet Profiles, medical details, private media, emergency contacts or complaint narratives.

Day 39 — Calculate economics

Calculate:

- Resident GMV

- PetSaathi margin

- Sitter payouts

- Discounts

- Payment costs

- Support cost

- Refund cost

- Net pilot contribution

- Expected paid-plan contribution

Determine the minimum society fee needed to support the agreed service level.

Day 40 — Collect society and resident feedback

Conduct a 20–30 minute review with:

- Committee representative

- Facility manager

- Security representative

Collect resident feedback separately.

Ask:

- What worked?

- What caused operational friction?

- Which services were most valuable?

- Does the society want continued service?

- Does it need basic support or a managed desk?

- What reporting frequency is expected?

- What pricing concerns exist?

Day 41 — Classify every society

Assign:

BASIC_PARTNER_READY

PREMIUM_DESK_READY

EVENT_MODEL_READY

EXTEND_PILOT

PAUSE_AND_FIX

DO_NOT_CONVERT

Document the reasons.

Day 42 — Prepare the renewal proposal

Create:

Society Pilot Results & Partnership Recommendation

Include:

- Pilot overview

- Resident funnel

- Completed-service results

- Reliability metrics

- Resident ratings

- Repeat demand

- Society feedback

- Issues resolved

- Commercial recommendation

- Next steps

6. Week 7 — Present and negotiate the paid partnership

Goal

Secure commercial agreement from qualified societies.

Day 43 — Send executive summary

Do not begin by sending a long legal agreement.

Send:

- One-page result summary

- Recommended package

- Proposed price

- Meeting request

The results must be accurate and verifiable. Public or promotional claims should remain truthful and substantiated.

Day 44 — Conduct the conversion meeting

Recommended 30-minute agenda

| Time | Topic |
| --- | --- |
| 0–5 min | Review pilot objective |
| 5–12 min | Resident and booking results |
| 12–17 min | Quality, safety and feedback |
| 17–22 min | Recommended paid package |
| 22–27 min | Pricing, scope and questions |
| 27–30 min | Decision and next action |

Presenter principle

Do not only say:

“We completed 28 bookings.”

Explain the business value:

“Twenty-eight residents paid for services, 93% of due bookings were completed, seven residents completed a second service, and the access process succeeded on 97% of visits.”

Day 45 — Confirm paid scope

Agree on:

- Package

- Monthly fee

- Applicable taxes

- Active services

- Support hours

- Coordinator model

- Included campaigns or events

- Monthly reporting

- Resident benefit

- Sitter-access process

- Escalation SLA

- Data-sharing limits

Day 46 — Resolve commercial objections

“Why should the society pay when residents already pay?”

Response:

“Resident charges pay for individual care services. The society retainer covers programme management, approved-access coordination, resident support, reporting, complaint escalation and society-level operations.”

“Can we continue the pilot for free?”

Response:

“The no-fee period was designed to validate demand. Continued support, reporting and access management require a defined paid scope. We can also offer a smaller Basic Lite plan or time-limited extension tied to specific targets.”

“Can you reduce the price?”

Consider:

- Lower support hours

- Fewer resident campaigns

- Quarterly rather than monthly event

- Basic reporting

- Lower active-household cap

Do not reduce price without reducing scope.

Day 47 — Issue the commercial proposal

The proposal should contain:

Package

Monthly fee

Taxes

Included scope

Resident pricing model

Service limits

Support SLA

Initial term

Renewal

Termination

Payment terms

Data-sharing schedule

Recommended initial term:

Three months

This is a commercial recommendation, not a statutory requirement.

Day 48 — Contract review

Update the original pilot agreement into a paid partnership agreement or addendum.

Include:

- Effective date

- Monthly billing

- Payment due date

- Service scope

- Support coverage

- Brand use

- Data responsibilities

- Partner services

- Safety suspension

- Termination

- Renewal

Day 49 — Decision follow-up

Record one of:

APPROVED

APPROVED_WITH_CHANGES

COMMITTEE_REVIEW

PRICE_NEGOTIATION

PILOT_EXTENSION

DECLINED

Set an exact decision date.

Do not leave the proposal in an indefinite “interested” stage.

7. Week 8 — Sign and activate the paid partnership

Goal

Transition the society without interrupting resident services.

Day 50 — Sign agreement

Confirm:

- Authorised signatories

- Final package

- Service start date

- Initial term

- Notice period

- Monthly fee

- Taxes

- Payment method

Day 51 — Invoice and payment setup

Create separate billing flows:

Society invoice

Basic Society Partnership Fee

August 2026

Resident service invoice

Dog Walking Service

Booking BK-1001

Do not combine the monthly RWA partnership fee and individual resident service charges into one unclear invoice.

CBIC rules prescribe information and timing requirements for tax invoices for taxable services.

Day 52 — Activate paid package configuration

Update:

- Society status

- Support priority

- Monthly reporting

- Resident discounts

- Sitter matching priority

- Coordinator assignment

- Event allowances

- Booking caps

- SLA timers

Example:

society.package = BASIC_STANDARD

society.partnership_status = ACTIVE_PAID

society.monthly_fee = 999900 paise

society.term_start = 2026-08-01

society.term_end = 2026-10-31

Day 53 — Communicate the transition

Send residents a factual update:

- Pilot completed

- Partnership continuing

- Active services

- Resident benefits

- Support contact

- Existing booking status

- Privacy choices

Only opted-in residents should receive proactive WhatsApp messages. Meta requires businesses to obtain WhatsApp opt-in, and the opt-in should make the business identity and messaging purpose clear.

Day 54 — Train society operations

Review with facility and security teams:

- Active sitter roster

- Replacement procedure

- Access revocation

- Support escalation

- Lost-pet alert

- Event access

- Monthly reporting

Day 55 — Establish paid baseline

Freeze the first paid-month baseline:

Active pet households

Monthly booking volume

Repeat customers

Sitter capacity

Support workload

Complaint rate

Revenue

Contribution

This lets PetSaathi compare paid performance with pilot performance.

Day 56 — First paid-partnership review

Confirm:

- Invoice received/paid

- Package features active

- Residents informed

- Support routing works

- No access interruption

- Monthly review date scheduled

8. Recommended paid-conversion proposal

Pilot evidence example

Your example is persuasive:

42 pet-parent registrations

28 paid bookings

4.7 average rating

12 repeat requests

However, it should include operational and sample context:

42 qualified resident registrations

28 paid bookings

26 completed services

18 verified reviews

4.7 average rating

7 second paid services

98% Report Card delivery

96% on-time arrival

0 unresolved critical incidents

A proposal based only on “12 repeat requests” is weaker than one showing completed repeat services.

Recommended package offer

For this performance level:

Basic Society Partner — Standard

Monthly fee:

₹9,999 + applicable taxes

Initial term:

3 months

Resident care services:

Paid separately

Include

- Society-specific resident page

- Resident partner benefits

- Priority eligible-sitter matching

- Society-access roster

- Dedicated WhatsApp support routing

- Named operations owner

- Monthly aggregate report

- Complaint and incident escalation

- Monthly programme review

Exclude

- Guaranteed sitter availability

- Unlimited 24/7 support

- Full-time on-site coordinator

- Veterinary treatment by PetSaathi

- Unlimited events

- Society access to private resident data

9. Finished conversion message

Here is a professional proposal message for the society:

Send

Recipients

PetSaathi Pilot Results and Partnership RecommendationPetSaathi Pilot Results and Partnership Recommendation

Dear [Name/Committee Members],

Thank you for supporting the PetSaathi pilot at [Society Name].

During the pilot, we achieved the following results:

• 42 qualified pet-parent registrations
• 28 paid bookings
• 26 completed services
• 18 customer reviews
• 4.7/5 average customer rating
• 7 completed repeat services
• 98% Pet Report Card delivery
• 96% on-time service rate
• No unresolved critical incidents

The pilot demonstrated meaningful resident demand for organised dog walking and pet-sitting support. It also helped establish a working sitter-access process, resident-support channel and service-reporting system for the society.

Based on these results, we recommend continuing with the PetSaathi Basic Society Partner — Standard Plan.

Monthly partnership fee: ₹9,999 plus applicable taxes
Recommended initial term: 3 months

The plan includes:

• A society-specific resident booking page
• Resident partner benefits
• Priority matching among eligible local sitters
• An active society-access sitter roster
• Dedicated WhatsApp support routing
• A named PetSaathi operations owner
• Monthly aggregate service and safety reporting
• Complaint, replacement and incident escalation
• A monthly programme review with the society team

Residents will continue to pay separately for the individual pet-care services they choose to book.

The partnership fee covers society-level programme management, access coordination, resident support, reporting and operational oversight.

We propose a 30-minute review meeting on [Date/Time] to confirm the scope, commercial terms and transition date.

Regards,
[Your Name]
PetSaathi
[Phone / WhatsApp]
[Email]
[Website]

The figures must be replaced with the actual society pilot data before sending.

10. Paid conversion meeting dashboard

Show five sections only.

Resident demand

Qualified leads

Pet Profiles

Paid customers

Active repeat customers

Service delivery

Paid bookings

Completed services

On-time rate

Report Card completion

Customer experience

Average rating

Review count

Repeat rate

Top feedback

Society operations

Security-entry success

Complaints

Incidents

Support response

Commercial recommendation

Recommended package

Monthly fee

Scope

Initial term

Expected outcomes

11. Common conversion mistakes

Mistake 1 — Converting based on registrations

Correction: Require completed paid services and repeat behaviour.

Mistake 2 — Calling repeat requests repeat customers

Correction: Track second paid and completed services.

Mistake 3 — Presenting ratings without review count

Correction: Always show rating, sample size and response rate.

Mistake 4 — Hiding operational problems

Correction: Show issues, corrective actions and current status.

Mistake 5 — Pricing without cost analysis

Correction: Calculate coordinator, support, event and reporting costs.

Mistake 6 — Reducing price but keeping all features

Correction: Reduce scope when reducing price.

Mistake 7 — Continuing free support indefinitely

Correction: Set an extension deadline and measurable targets.

Mistake 8 — Ambiguous billing

Correction: Separate society-retainer invoices from resident service transactions.

Mistake 9 — Sending private resident details in the conversion report

Correction: Use aggregated data and anonymised feedback.

Mistake 10 — Publishing inflated pilot claims

Correction: Every conversion claim must match the underlying records and remain supportable.

12. Weeks 6–8 dashboard

| Metric | Conversion target |
| --- | --- |
| Qualified pet-parent leads | 30+ |
| Completed paid bookings | 15+ |
| Second paid/completed services | 5+ |
| Repeat rate | 20–25%+ |
| Average rating | 4.5+ |
| Minimum reviews | 10+ |
| On-time services | 95%+ |
| Report Cards | 98%+ |
| Security-entry success | 97%+ |
| Critical unresolved incidents | 0 |
| RWA continuation support | Yes |
| Positive economic path | Yes |

Commercial pipeline

Track:

CONVERSION_AUDIT

PROPOSAL_READY

PROPOSAL_SENT

MEETING_COMPLETED

NEGOTIATION

CONTRACT_REVIEW

APPROVED

SIGNED

INVOICED

ACTIVE_PAID

DECLINED

EXTENDED_PILOT

13. Weeks 6–8 deliverables

Pilot conversion report

For every society:

- Pilot dates

- Leads

- Pet Profiles

- Paid bookings

- Completed bookings

- Repeat customers

- Ratings and review count

- Reliability metrics

- Complaints and incidents

- Financial results

- Society feedback

- Recommended decision

Paid proposal

- Recommended package

- Scope

- Monthly fee

- Taxes

- Initial term

- Support SLA

- Reporting

- Resident benefits

- Exclusions

Paid agreement

- Commercial terms

- Responsibilities

- Data-sharing schedule

- Sitter-access procedure

- Incident process

- Branding permission

- Billing

- Renewal and termination

Activation plan

- Package configuration

- Resident communication

- Support routing

- Society training

- Invoice setup

- Monthly review schedule

Final conversion rule

A society should pay because PetSaathi has demonstrated ongoing operational value—not merely because the free-pilot period has ended.

The strongest conversion proof is:

Residents registered

+

Residents paid

+

Services completed reliably

+

Customers booked again

+

Society operations improved

+

Economics support continued delivery

Simple explanation for professor

“During Weeks 6 to 8, PetSaathi will convert successful free society pilots into paid partnerships.

In Week 6, we will audit each society’s results. We will examine qualified resident leads, completed paid bookings, second bookings, ratings, punctuality, Report Card delivery, complaints, sitter capacity and financial performance.

A society should normally have at least 30 qualified pet-parent leads, 15 completed paid services, five repeat customers, a 4.5 or higher rating and positive society feedback. It should also have no unresolved critical incident and a workable sitter-access process.

In Week 7, PetSaathi will present the pilot results to the RWA or facility team. We will recommend the correct package based on the society’s actual demand and operational requirements.

For example, a society with 42 resident registrations, 28 paid bookings, a 4.7 rating and seven completed repeat services may be recommended the Basic Society Partner plan at ₹9,999 per month plus applicable taxes.

The monthly fee will cover society-level coordination, support, reporting and sitter-access management. Residents will continue paying separately for the care services they book.

In Week 8, the society and PetSaathi will sign the paid agreement, configure billing, activate the selected package and notify residents. The team will then establish a baseline for the first paid month and schedule regular performance reviews.

The final goal is not simply to end the free pilot. It is to prove that PetSaathi provides enough measurable value for the society to continue paying for the partnership.”

A monthly compliance review covering DPDP, consumer disclosures, GST invoicing and WhatsApp messaging would be prudent before each renewal cycle.

PetSaathi Phase 7 — Paid Conversion and City-Specific Strategy 🏢🐾

Executive decision

The overall strategy is sound, with two important corrections:

- The ₹9,999 Basic Society Partner package should be a recommended standard conversion offer—not an automatic price for every society.

- Claims such as “Bengaluru users adopt digitally faster” or “Surat users are slower digitally” should be treated as pilot hypotheses, not established facts. India had roughly one billion internet subscribers by mid-2025, while the Internet in India 2025 study reported approximately 958 million active internet users. All six cities can therefore support a mobile-first PWA and digital payments; the real difference is likely to be trust, acquisition channel, society access and support expectations.

Part A — Weeks 6–8: Convert Pilots into Paid Partnerships

Core goal

Convert successful no-fee pilots into recurring society partnerships without extending free operational support indefinitely.

The conversion lifecycle should be:

Pilot completed

↓

Results verified

↓

Society health score calculated

↓

Committee review meeting

↓

Recommended package presented

↓

Commercial negotiation

↓

Paid agreement signed

↓

Invoice/payment completed

↓

Paid partnership activated

A society should not convert merely because the committee says it liked the pilot. It must show evidence of:

- Resident demand

- Paid usage

- Repeat behaviour

- Reliable sitter operations

- Positive customer experience

- Manageable support workload

- Acceptable economics

1. Correct paid-conversion criteria

Your proposed criteria are a useful minimum:

| Metric | Minimum |
| --- | --- |
| Pet-parent leads | 30+ |
| Paid bookings | 15+ |
| Repeat customers | 5+ |
| Average rating | 4.5+ |
| RWA/facility feedback | Positive |
| Complaints | Manageable |

However, add operational and financial criteria.

Recommended complete scorecard

Demand

| Metric | Minimum conversion requirement |
| --- | --- |
| Opted-in pet-parent leads | 30+ |
| Completed Pet Profiles | 15+ |
| Paid bookings | 15+ |
| Residents completing a second service | 5+ |
| Repeat or package requests | 25%+ preferred |

Quality

| Metric | Target |
| --- | --- |
| Completed-service rate | 90%+ |
| On-time service rate | 95%+ |
| Report Cards delivered | 98%+ |
| Average rating | 4.5+ |
| Critical unresolved incidents | 0 |
| Refund/dispute rate | Below 5% |

Operations

- At least two usable primary sitters

- At least one practical backup option

- Security-entry success above 95%

- No unresolved access-policy problem

- Support workload sustainable

- Society has an authorised operational contact

Economics

- Resident booking contribution is positive or improving.

- Society support cost is known.

- Discounts are not hiding weak demand.

- The proposed monthly retainer covers ongoing society-level operations.

- The society is not dependent on one heavily subsidised service.

A society with 40 leads and poor service quality should not convert. A smaller society with 22 leads, 18 completed bookings and strong repeat behaviour may still deserve conversion.

2. Society conversion score

Use a 100-point score:

| Category | Weight |
| --- | --- |
| Resident demand | 25 |
| Repeat behaviour | 20 |
| Service quality | 20 |
| Operational stability | 15 |
| Society relationship | 10 |
| Unit economics | 10 |

Decision levels

| Score | Decision |
| --- | --- |
| 80–100 | Convert immediately |
| 65–79 | Convert with conditions |
| 50–64 | Extend pilot for 14–21 days |
| Below 50 | Pause, downgrade or discontinue |

Automatic conversion blockers:

- Unresolved serious safety incident

- No usable sitter backup

- Repeated security-entry failures

- Society demands unrestricted resident information

- Residents are not paying

- Society refuses agreed operational processes

- Negative contribution with no realistic improvement path

Week 6 — Analyse and prepare conversion

Day 36 — Validate pilot data

Reconcile:

- Leads

- Verified residents

- Pet Profiles

- Booking requests

- Paid bookings

- Completed bookings

- Refunds

- Reviews

- Repeat services

- Complaints

- Incidents

Do not present booking requests as paid bookings or paid bookings as completed services.

Day 37 — Calculate society health

Prepare a scorecard for each pilot:

Society: Green Acres

Pilot duration: 30 days

Opt-in residents: 42

Pet Profiles completed: 31

Paid bookings: 28

Completed services: 27

Repeat completed customers: 7

Repeat requests: 12

Average rating: 4.7

On-time rate: 96%

Report Cards delivered: 100%

Access failures: 1

Refunds: 1

Critical incidents: 0

Day 38 — Calculate commercial viability

Track separately:

Resident service GMV

− sitter payouts

− payment fees

− discounts

− refunds

− direct support costs

= service contribution

Then add the proposed partnership fee.

The ₹9,999 retainer should pay for society-level services such as:

- Society landing page

- Resident partner benefit

- Society-access roster

- Priority support routing

- Named operations owner

- Monthly report

- Committee review

- Access and complaint coordination

It should not include unlimited resident care or a full-time coordinator.

Day 39 — Collect stakeholder feedback

Collect structured feedback from:

- RWA or committee

- Facility manager

- Security supervisor

- Pet parents

- Sitters

- Local partners

Ask:

- Which services were most valuable?

- What created the most manual work?

- Were sitter details sufficient for security?

- Did residents understand pricing?

- Which issues occurred repeatedly?

- Would the society continue?

- Which level of support is required?

Day 40 — Select the recommended package

Possible recommendations:

Basic Society Partner

Premium Pet-Care Desk

Event/Camp Partnership

Extended pilot

Pause partnership

Day 41–42 — Prepare the conversion presentation

Create a five-slide society-specific renewal presentation:

- Pilot objective

- Verified results

- Resident and society feedback

- Recommended package

- Commercial terms and next steps

Week 7 — Present and negotiate

Conversion meeting structure

Minutes 0–5 — Pilot recap

Explain what was launched and what was measured.

Minutes 5–12 — Results

Show:

- Registrations

- Paid bookings

- Completion

- Ratings

- Repeat behaviour

- Entry reliability

- Complaint outcomes

Minutes 12–18 — What the society receives next

Explain the paid package deliverables.

Minutes 18–24 — Pricing

Present one recommended plan and one alternative—not four confusing options.

Minutes 24–30 — Decision process

Confirm:

- Committee approval

- Contract review

- Budget owner

- Invoice contact

- Start date

- Next meeting

Recommended paid-conversion offer

Your Green Acres pilot produced:

- 42 opted-in pet-parent registrations

- 28 paid bookings

- 27 completed services

- 4.7 average rating

- 12 repeat requests

- 96% on-time service performance

- No unresolved critical incidents

Based on the resident demand and operating results, we recommend continuing with the PetSaathi Basic Society Partner plan at ₹9,999 per month plus applicable taxes, initially for three months.

Residents will continue paying separately for the pet-care services they book.

Included at ₹9,999

- Society-specific resident portal

- Resident partner benefit

- Priority search among eligible local sitters

- Active society-access sitter roster

- Dedicated WhatsApp support queue

- Named PetSaathi operations owner

- Monthly aggregate performance report

- Access, replacement and complaint coordination

- One monthly committee review

- Basic resident awareness material

Excluded

- Full-time on-site coordinator

- Guaranteed sitter availability

- Unlimited events

- Veterinary treatment

- Unlimited 24-hour non-emergency support

- Custom software development

- Society access to private Pet Profiles

- Resident service charges

3. Recommended term

Use an initial:

3-month paid term

This is long enough to measure repeat demand but short enough to reduce committee resistance.

Suggested terms:

- ₹9,999/month plus applicable taxes

- Three-month initial period

- Monthly payment in advance

- Thirty-day termination notice after initial term

- No automatic price increase

- Extra events and custom support priced separately

- Resident service prices remain separately displayed

Do not continue the pilot free while the committee delays indefinitely.

Possible bridge:

Maximum 14-day conversion extension

Use this only when the decision process is genuine and a meeting or vote date is confirmed.

4. Negotiation rules

When the society asks for a lower price

Do not immediately discount.

Reduce scope:

| Full ₹9,999 plan | Lower-cost alternative |
| --- | --- |
| Monthly committee review | Quarterly review |
| Named operations owner | Shared operations queue |
| Resident discount funded by PetSaathi | Society-funded benefit |
| Enhanced reporting | Standard report |
| Awareness campaign | Digital-only materials |

When discounting is justified

Require something in return:

- Six-month commitment

- Advance payment

- Minimum resident participation

- Society-funded resident benefit

- Permission for an approved case study

- Cluster partnership involving nearby societies

Never discount by weakening safety

Do not remove:

- Sitter eligibility checks

- Incident reporting

- Payment verification

- Pet Profile requirements

- Data-protection controls

- Security-access procedures

Week 8 — Activate paid partnerships

Paid activation flow

Committee approves

↓

Agreement signed

↓

Invoice issued

↓

Payment received

↓

Package configuration updated

↓

Resident communication released

↓

Monthly reporting cycle begins

Paid partnership onboarding

Confirm:

- Package tier

- Start and end date

- Society contact

- Support hours

- Monthly reporting date

- Active resident offer

- Sitter pool

- Booking caps

- Events included

- Escalation contacts

- Invoice recipient

CRM status

CONVERTED_BASIC

CONVERTED_PREMIUM

EVENT_ONLY

EXTENDED_PILOT

PAUSED

LOST

Part B — City-Specific Phase 7 Strategy

Important market interpretation

The listed neighbourhoods are sensible candidate micro-markets, but premium property activity does not automatically prove pet-parent demand.

Every city still requires:

Society research

+ resident opt-in survey

+ sitter supply validation

+ security feasibility

+ paid trial demand

Current property and office-market data support targeting technology, employment and premium residential corridors in Bengaluru, Pune, Mumbai, Gurugram and Ahmedabad. They do not provide reliable society-level pet ownership figures.

1. Bengaluru

Bengaluru’s current office-market activity remains strongly concentrated around Outer Ring Road and Peripheral East, supported by technology, GCC and IT-BPM demand. That supports the working-professional positioning around Whitefield, Bellandur and nearby eastern corridors.

Recommended micro-clusters

Cluster A — Whitefield

Hero service: Daily dog walking
Audience: Working professionals in large gated communities
Best message:

Verified society-access dog walkers with live service status and Pet Report Cards.

Cluster B — Bellandur and Sarjapur Road

Sarjapur Road has continued to develop as a major residential micro-market, with substantial housing supply across mid-market and premium segments.

Hero service: Walking plus travel-time sitting
Risk: Traffic can make large service radiuses unreliable.

Cluster C — HSR Layout

Hero service: Pet-parent community and premium sitting
Channel: Resident groups, local vets and dog parks

Cluster D — Electronic City

Hero service: Value-oriented five- and ten-walk plans
Positioning: Reliable office-hour support rather than luxury concierge

Operating rules

- Use a 2–4 km effective sitter radius.

- Do not treat Whitefield, HSR, Bellandur and Electronic City as one operational cluster.

- Show real-time service status.

- Make mobile booking and payment extremely smooth.

- Offer same-sitter repeat plans quickly.

Recommended package

- Basic Partner: ₹9,999–₹15,000

- Premium Desk for large townships: ₹25,000+

- Trial-to-pack conversion should be central

2. Pune

Pune continues to show strong office activity, with eastern and western business districts driving demand. Kharadi, Hinjewadi and Viman Nagar are major contributors to the city’s office inventory, supporting a working-professional and recurring-service strategy.

Recommended clusters

Cluster A — Baner, Wakad and Hinjewadi

Hero service: Monthly dog-walking plans
Best message:

Reliable daily walking with preferred-sitter continuity.

Cluster B — Kharadi and Viman Nagar

Hero service: Office-hour dog walking and premium sitting
Audience: IT, GCC and professional households

Operating rules

- Track remaining package credits.

- Offer regular weekly schedules.

- Build backup coverage for morning and evening peaks.

- Student sitters may expand supply, but “student” should never replace identity, training and reliability checks.

- Position packages around value and continuity, not only discounts.

Recommended package

- Basic Partner at ₹7,999–₹9,999 for early conversion

- ₹9,999–₹15,000 for larger multi-tower societies

- Premium Desk only after recurring volume is demonstrated

3. Mumbai

Mumbai requires the strictest hyperlocal approach.

Recent residential data show strong activity across the wider Mumbai Metropolitan Region, with Thane and other peripheral submarkets contributing significant new supply. Core Mumbai remains premium and operationally complex.

Do not create one Mumbai cluster

These should operate separately:

Powai

Bandra/Andheri West

Lower Parel

Thane

Area strategies

Powai

Hero service: Premium society walking and sitting
Strength: Large residential communities
Rule: Tight local radius

Bandra and Andheri West

Hero service: High-value home pet sitting
Risk: Travel unpredictability and access complexity

Lower Parel

Hero service: Premium office-hour care
Model: Fewer, higher-value clients

Thane

Hero service: Large-society walking plans
Potential: Better society density and broader recurring demand

Operating rules

- Use same-locality sitters.

- Add substantial travel buffers.

- Do not promise cross-city replacements.

- Limit initial radius to approximately 1–3 km where possible.

- Treat boarding as a restricted partner service.

- Price support and replacement complexity into the society fee.

Recommended package

- Limited Basic digital partnership: ₹9,999–₹15,000

- Operationally managed societies: ₹15,000–₹35,000

- Premium Desk for complex sites

4. Gurugram

Gurugram’s Golf Course, Southern Peripheral and Sohna-related corridors continue to attract premium residential and commercial activity. Recent reporting highlights continued growth around the greater Southern Peripheral Road and Sohna corridor.

Recommended clusters

Cluster A — DLF Phases 1–5 and Golf Course Road

Hero service: Premium safety-first pet care
Best message:

Approved-access caregivers, documented service proof and priority emergency coordination.

Cluster B — Sectors 56/57

Hero service: Family walking and sitting plans

Cluster C — Sohna Road

Hero service: Gated-community pilots
Risk: Avoid overextending into widely separated developments.

Operating rules

- Strong factual KYC badges

- Society-access registration

- Premium support SLA

- Emergency veterinary coordination

- Gate and visitor procedures configured before launch

- Never use “society-certified safe sitter”

Recommended package

- Basic Partner: ₹9,999–₹15,000

- Premium Desk: ₹25,000–₹50,000

- Society-subsidised resident benefit may work better than deep platform discounts

5. Ahmedabad

Ahmedabad’s 2025 residential market remained stable, with growing interest in higher-value housing particularly around SG Highway and SP Ring Road. This supports targeting western and south-western residential corridors.

Recommended cluster order

Cluster 1 — Bopal and South Bopal

Hero services: Dog walking and home pet sitting
Best message:

Trusted local pet caretakers for busy Ahmedabad families.

Cluster 2 — Satellite and Prahlad Nagar

Hero service: Premium family sitting and travel care

Cluster 3 — SG Highway

Hero service: Multi-society partnerships and events

Operating rules

- Use veterinary and pet-shop introductions.

- Conduct resident orientations.

- Keep WhatsApp support visible.

- Explain the service workflow in simple language.

- Use family-trust positioning.

- Offer grooming or veterinary-partner events to create initial credibility.

- Keep price accessible but do not underpay sitters.

Recommended conversion

For a society producing results such as:

42 registrations

28 paid bookings

4.7 rating

12 repeat requests

The ₹9,999 Basic Society Partner plan is a reasonable recommended offer.

For lower-volume societies:

₹6,999–₹7,999 limited plan

should reduce support scope rather than safety or operational controls.

6. Surat

Vesu, Pal and Adajan are established or developing residential areas, and Surat Municipal Corporation planning records show extensive town-planning schemes across Vesu, Adajan and Pal. However, this does not prove pet-service demand, so resident and partner validation is especially important.

Recommended clusters

Cluster A — Vesu, Citylight and Ghod Dod Road

Hero strategy: Event-led trust and premium family care
First offer: Grooming camp or pet-parent meetup followed by sitting/walking trials

Cluster B — Adajan and Pal

Hero strategy: Accessible walking and family sitting plans

Operating rules

- Begin with vet, pet-shop and resident referrals.

- Use admin-assisted WhatsApp booking.

- Keep the digital flow available but provide human support.

- Run one event before committing to a paid monthly partnership where demand is uncertain.

- Keep boarding controlled and capacity-limited.

- Use family and travel-care positioning.

Recommended package path

Event/Camp

↓

No-Fee Pilot

↓

Basic Partner only after recurring bookings

The claim that Surat is inherently “less digital” should not be used in the pitch. Nationwide digital adoption is already very high; the pilot should measure whether Surat residents prefer WhatsApp assistance, calls, self-service booking or a combination.

Recommended city launch priorities

Best for app-led validation

- Bengaluru

- Pune

Best for premium society monetisation

- Gurugram

- Mumbai

Best for controlled founder-led operations

- Ahmedabad

- Pune

Best for event- and referral-led market entry

- Surat

- Ahmedabad

Recommended PetSaathi rollout

For the current PetSaathi plan, the most operationally sensible path is:

Ahmedabad

Bopal + South Bopal

↓

Satellite + Prahlad Nagar

↓

One additional city after paid conversion succeeds

Do not launch all six cities simultaneously.

Move to another city only after the first city has:

- Three or more paid society partnerships

- Stable sitter backup coverage

- Positive contribution

- 95%+ punctuality

- Automated Report Cards

- Consistent monthly reporting

- Repeat resident demand

- A documented city-launch playbook

Final paid-conversion wording

Your society pilot has demonstrated genuine resident demand and stable operations.

During the pilot, 42 residents registered, 28 paid bookings were created, the service achieved a 4.7 average rating and 12 residents requested repeat care.

We recommend continuing with the PetSaathi Basic Society Partner plan at ₹9,999 per month plus applicable taxes for an initial three-month term.

The plan includes a society-specific resident portal, partner benefits, priority eligible-sitter matching, an active sitter-access roster, dedicated WhatsApp support, a named operations owner and monthly aggregate reporting.

Residents will continue to pay separately for the care services they book.

Final operating principle

Convert a society because it has demonstrated recurring demand, service reliability and sustainable economics—not merely because the pilot period has ended.

Simple explanation for professor

“During Weeks 6 to 8, PetSaathi will analyse every society pilot and decide whether it should become a paid partnership.

A society will be considered ready when it has enough resident leads, paid bookings, repeat customers, positive ratings, stable sitter access and manageable complaints. We will also check punctuality, Report Card delivery, security-entry performance and financial sustainability.

PetSaathi will prepare a pilot-results report and present it to the society committee. For example, if a society has 42 registrations, 28 paid bookings, a 4.7 rating and 12 repeat requests, we can recommend the Basic Society Partner plan at ₹9,999 per month.

The society fee will pay for programme management, reporting, support, sitter-access coordination and the resident portal. Residents will continue paying separately for dog walking, pet sitting and other services.

The city strategy will also differ. Bengaluru and Pune should focus on smooth digital booking and recurring walking plans. Mumbai must remain highly local because travel is difficult. Gurugram should emphasise verification and premium support. Ahmedabad should use family trust and local veterinary partnerships. Surat should begin with events, referrals and assisted WhatsApp booking.

PetSaathi should first prove the model in one city and a few nearby areas before expanding to another city.”

PetSaathi Society Unit Economics — Corrected End-to-End Model 📊🐾

Executive assessment

Your model is directionally correct, but four financial definitions must be fixed:

- Resident booking value is GMV, not automatically PetSaathi revenue.

- Track orders, service units and paying households separately.

- The estimate of 40–70 pet families in 500 flats is a planning hypothesis, not a confirmed fact.

- ₹1 lakh from only 50–150 monthly services requires a high-value mix of sitting, boarding or packages; it is unlikely from ordinary walking alone.

Current marketplace listings show substantial pricing variation. ThePetNest states that dog walks in India can range around ₹200–₹600, while individual Ahmedabad listings currently show approximately ₹140–₹210 per walk. Its boarding pages show starting prices from roughly ₹500 nationally and around ₹1,000 per night in Ahmedabad, while home sitting may begin near ₹100 per hour. These should be treated as market observations, not guaranteed city averages.

1. Start with the correct society funnel

For a 500-flat society, use this as an initial hypothesis:

500 total flats

↓

425–475 occupied flats

↓

40–70 pet-owning households

↓

20–30 interested leads

↓

10–20 first-time paying households

↓

5–10 repeat households

↓

50–150 monthly service units

The 40–70 pet-family estimate represents 8–14% of total flats. It is reasonable as an internal planning range, but it must be validated using:

- Resident survey

- Society pet-parent group

- Facility-manager estimate

- Veterinary or pet-shop referrals

- Previous society events

- Actual PetSaathi registrations

Do not present it to investors or society committees as a verified number until the survey confirms it.

2. Do not use “booking” as one universal unit

The word booking becomes misleading because these are economically different:

- One 30-minute dog walk

- One 2-hour pet-sitting visit

- One five-night boarding reservation

- One ten-walk package purchase

Use four separate metrics:

| Metric | Meaning |
| --- | --- |
| Orders | Customer transactions or booking records |
| Service units | Walks, sitting visits or boarding nights delivered |
| Paying households | Unique resident customers |
| Package credits | Walks or visits purchased but not yet consumed |

Example

A resident purchasing a ten-walk package creates:

1 order

10 service credits

10 future service units

1 paying household

Without this separation, revenue, workload and repeat usage become inaccurate.

3. Correct financial terminology

Resident GMV

The total value paid by residents:

Resident GMV =

Dog-walking payments

+ sitting payments

+ boarding payments

+ other resident service payments

Sitter or partner payout

The amount paid to:

- Dog walkers

- Pet sitters

- Boarding hosts

- Groomers

- Veterinary or training partners

Platform service margin

An internal planning formula:

Platform service margin =

Resident GMV − sitter/partner payouts

Net service contribution

A more useful metric:

Net service contribution =

Platform service margin

− payment-processing cost

− funded discounts

− refunds

− booking-specific support cost

− incident/recovery reserve

Total society contribution

Total society contribution =

Net service contribution

+ society subscription

+ event coordination contribution

− society coordinator cost

− society marketing cost

− onboarding allocation

− other society-specific costs

This is the number that shows whether one society is economically useful.

4. Payment-processing cost

Razorpay’s standard pricing currently states 2% plus GST per successful transaction, which creates an effective cost of approximately 2.36% when 18% GST is applied to the 2% gateway fee.

Therefore:

| Resident GMV | Approximate gateway cost |
| --- | --- |
| ₹25,000 | ₹590 |
| ₹50,000 | ₹1,180 |
| ₹1,00,000 | ₹2,360 |

Payment-gateway cost should be deducted before calling the service margin contribution.

5. Corrected 500-flat society model

The following scenarios use an illustrative 30% platform service margin. This is not an industry standard; replace it with PetSaathi’s actual sitter-payout rules.

Scenario A — Conservative walking-heavy society

Assumptions

Pet families: 40

Interested leads: 20

Paying households: 10

Monthly service units: 60

Service mix:

| Service | Units | Price | GMV |
| --- | --- | --- | --- |
| Dog walks | 55 | ₹180 | ₹9,900 |
| Pet-sitting visits | 5 | ₹400 | ₹2,000 |
| Resident GMV |  |  | ₹11,900 |

Economics:

| Item | Amount |
| --- | --- |
| Resident GMV | ₹11,900 |
| Illustrative 30% platform margin | ₹3,570 |
| Gateway cost | −₹281 |
| Service contribution before support | ₹3,289 |
| Basic society subscription | +₹5,000 |
| Contribution before coordinator/overhead | ₹8,289 |

Interpretation

This society may be operationally useful because of density, but resident bookings alone do not produce strong profit yet.

Scenario B — Base mixed-service society

Assumptions

Pet families: 55–60

Interested leads: 30

Paying households: 15–18

Monthly service units: 120

Service mix:

| Service | Units | Price | GMV |
| --- | --- | --- | --- |
| Dog walks | 100 | ₹220 | ₹22,000 |
| Pet-sitting visits | 15 | ₹500 | ₹7,500 |
| Boarding nights | 5 | ₹1,000 | ₹5,000 |
| Resident GMV |  |  | ₹34,500 |

Economics:

| Item | Amount |
| --- | --- |
| Resident GMV | ₹34,500 |
| Illustrative 30% platform margin | ₹10,350 |
| Gateway cost | −₹814 |
| Service contribution before support | ₹9,536 |
| Basic Society Partner fee | +₹9,999 |
| Event contribution | +₹8,000 |
| Contribution before coordinator/overhead | ₹27,535 |

Interpretation

This is a stronger target for a functioning Basic Society Partner account.

However, the ₹8,000 event amount must be PetSaathi’s actual event contribution, not the total money residents paid for grooming or veterinary services.

Scenario C — Strong mixed-service society

Assumptions

Pet families: 70+

Interested leads: 40

Paying households: 20–25

Monthly service units: 150

Service mix:

| Service | Units | Price | GMV |
| --- | --- | --- | --- |
| Dog walks | 110 | ₹250 | ₹27,500 |
| Pet-sitting visits | 25 | ₹700 | ₹17,500 |
| Boarding nights | 15 | ₹1,200 | ₹18,000 |
| Resident GMV |  |  | ₹63,000 |

Economics:

| Item | Amount |
| --- | --- |
| Resident GMV | ₹63,000 |
| Illustrative 30% platform margin | ₹18,900 |
| Gateway cost | −₹1,487 |
| Service contribution before support | ₹17,413 |
| Society subscription | +₹15,000 |
| Event contribution | +₹15,000 |
| Contribution before coordinator/overhead | ₹47,413 |

Interpretation

A society can reach strong economics when it combines:

- High-frequency walks

- Higher-value sitting

- Controlled boarding

- A paid society plan

- Profitable events

But the full ₹63,000 resident GMV is not PetSaathi’s margin.

6. Is ₹25,000–₹1 lakh monthly resident GMV realistic?

₹25,000 monthly GMV

This is realistic with a mixed model.

Examples:

100 walks × ₹200 = ₹20,000

10 sitting visits × ₹500 = ₹5,000

Total = ₹25,000

Or:

50 service units × average ₹500

= ₹25,000

₹1 lakh monthly GMV

At 150 services, ₹1 lakh requires:

₹1,00,000 ÷ 150

= approximately ₹667 average GMV per service

That is high for a walking-heavy society.

At ₹250 per walk, PetSaathi would need:

400 dog-walk service units

to generate ₹1 lakh in walking GMV.

Therefore, ₹1 lakh with 150 services generally requires:

- Multi-night boarding orders

- Premium sitting

- Package purchases

- Event revenue

- Larger service durations

- Multiple-pet bookings

Corrected recommendation

Use:

| Society stage | Likely monthly resident GMV |
| --- | --- |
| Early pilot | ₹10,000–₹25,000 |
| Stable Basic society | ₹25,000–₹50,000 |
| Strong mixed-service society | ₹50,000–₹75,000 |
| Premium/high-density upside | ₹75,000–₹1 lakh+ |

The upper range should be treated as an upside target, not a default assumption.

7. Correct the “total potential revenue” table

Your original table adds:

Resident bookings

+ society subscription

+ camp revenue

This combines three different accounting categories.

Correct structure

| Revenue layer | Correct measurement |
| --- | --- |
| Resident care bookings | GMV |
| PetSaathi care margin | Platform service margin/contribution |
| Society subscription | PetSaathi subscription revenue |
| Events | PetSaathi coordination revenue or net event contribution |
| Partner payouts | Cost/pass-through |
| Sitter payouts | Cost/pass-through |

Better monthly model

| Source | Low | Strong |
| --- | --- | --- |
| Resident service GMV | ₹25,000 | ₹1,00,000 |
| PetSaathi service margin at 30% | ₹7,500 | ₹30,000 |
| Society subscription | ₹5,000 | ₹25,000 |
| Event contribution | ₹5,000 | ₹20,000 |
| Gross PetSaathi contribution before support | ₹17,500 | ₹75,000 |

This is more accurate than calling ₹35,000–₹1.75 lakh all “revenue.”

Whether PetSaathi legally reports gross resident GMV or only its net commission as accounting revenue depends on whether it acts as principal or marketplace agent. Confirm the revenue-recognition structure with a chartered accountant.

8. Society-specific cost allocation

A society can appear profitable until its hidden operating costs are included.

Track:

| Cost | Example |
| --- | --- |
| Coordinator allocation | Time spent on society support |
| Customer support | Calls, WhatsApp and complaints |
| Sitter recruitment | Verification and training |
| Society onboarding | Meetings, access and setup |
| Resident discount | ₹99 launch subsidy |
| Payment gateway | Transaction cost |
| Replacement cost | Backup sitter incentives |
| Incident reserve | Refunds, recovery and support |
| Event staffing | Coordinator and travel |
| Technology | Notifications, media and maps |

True society contribution

True society contribution =

Service contribution

+ subscription

+ event contribution

− all society-specific variable costs

Do not scale a society that produces good GMV but negative true contribution.

9. Society conversion funnel

Your funnel is correct, but add qualification and activation stages:

Societies listed

↓

Societies qualified

↓

Decision-makers contacted

↓

Meetings completed

↓

Resident survey approved

↓

Pilot signed

↓

Pilot activated

↓

Resident announcement sent

↓

Qualified pet-parent leads

↓

First paying households

↓

Completed services

↓

Repeat completed services

↓

Paid society partnership

The difference between pilot signed and pilot activated is important. A signed society with no landing page, sitter capacity or resident campaign is not operational.

10. Funnel target analysis

Contacted → meeting: 20–30%

If PetSaathi contacts 30 qualified societies:

30 contacts

→ 6–9 meetings

If it contacts 50:

50 contacts

→ 10–15 meetings

This target is reasonable for carefully selected and personalised outreach.

Meeting → pilot: 30–50%

From 6–9 meetings:

Approximately 2–5 pilots

From 10–15 meetings:

Approximately 3–8 pilots

The upper range will normally require warm introductions, confirmed resident demand and local sitter availability.

Pilot → resident leads: 30+ leads

This should mean:

30 qualified, opted-in resident leads per activated society.

Do not count:

- Society WhatsApp members

- Poster views

- Anonymous website traffic

- Residents who never expressed pet-care interest

Leads → first paying households: 20–40%

For 30 qualified leads:

6–12 first paying households

Track first paying households, not simply bookings. One customer may create several bookings and distort acquisition conversion.

First paying households → repeat: 25–40%

For 6–12 first customers:

Approximately 2–5 repeat customers

The strongest repeat metric is:

The customer completed a second paid service.

Not merely:

- Clicked “book again”

- Asked about prices

- Viewed a package

- Said they were interested

Pilot → paid society plan: 20–30%

This is a reasonable early-stage target, but it produces slow B2B conversion.

If PetSaathi launches 3–8 pilots:

Expected paid partnerships:

approximately 1–2

To secure five paid society partners at a 25% pilot conversion rate, PetSaathi would need roughly:

20 pilots

If 40% of meetings become pilots:

50 completed meetings

If 25% of contacted societies become meetings:

200 qualified society contacts

This shows why the paid-society model needs a long and repeatable acquisition pipeline.

11. Correct funnel KPIs

| Funnel stage | Target |
| --- | --- |
| Qualified society → contact | 80%+ |
| Contact → response | 20–40% |
| Response → meeting | 40–60% |
| Contact → meeting | 20–30% |
| Meeting → resident survey | 40–60% |
| Meeting → pilot | 30–50% |
| Signed pilot → activated pilot | 80%+ |
| Lead → first paying household | 20–40% |
| First paying household → second completed service | 25–40% |
| Pilot → paid society plan | 20–30% initially |
| Paid society → renewal | 70%+ target after proven fit |

The renewal rate becomes more important than the initial pilot conversion once the model matures.

12. Paid-partnership readiness criteria

A society should not convert to paid merely because the free period has ended.

Minimum commercial criteria

| Metric | Minimum |
| --- | --- |
| Qualified pet-parent leads | 30+ |
| Unique paying households | 8–15 |
| Paid booking orders | 15+ |
| Completed services | 90%+ of due bookings |
| Repeat customers | 5+ |
| Average rating | 4.5+ |
| Rating sample | Preferably 10+ reviews |
| Report Cards delivered | 98%+ |
| Security-entry success | 97%+ |
| Critical unresolved incidents | 0 |
| RWA/facility feedback | Positive |
| Society contribution | Positive or clearly improving |

Additional recommendation

Do not use only total booking count.

For example:

15 bookings from 2 households

is weaker than:

15 bookings from 10 households

The second case proves broader resident value.

13. Recommended paid conversion offer

For a society with:

42 resident registrations

28 paid bookings

4.7 average rating

12 repeat requests

first confirm:

- How many unique paying households?

- How many services were completed?

- How many repeat services were actually paid?

- What was the society’s monthly GMV?

- What was PetSaathi’s contribution?

- How much support did the society require?

If the numbers are healthy, the offer can be:

Basic Society Partner — ₹9,999/month plus applicable taxes

Include:

- Society landing page

- Resident partner benefits

- Priority eligible-sitter matching

- Approved-access sitter roster

- Dedicated WhatsApp routing

- Monthly aggregate report

- Named operations owner

- Incident and complaint escalation

- Monthly programme review

The ₹9,999 recommendation is appropriate only when expected subscription and service contribution can cover the society’s support and coordination workload.

14. Society profitability dashboard

Track monthly:

Demand

- Pet-parent leads

- Verified residents

- Pet Profiles

- Paying households

- Repeat households

Volume

- Orders

- Service units

- Walks

- Sitting visits

- Boarding nights

- Package credits used

Financials

- Resident GMV

- Discounts

- Refunds

- Sitter payouts

- Partner payouts

- Gateway cost

- Service contribution

- Subscription revenue

- Event contribution

- Coordinator cost

- Net society contribution

Quality

- Completion rate

- On-time rate

- Report Card delivery

- Average rating

- Complaints

- Incidents

- Entry failures

15. Final corrected society economics

For a 500-flat society, the following is a more defensible target:

40–70 possible pet households

↓

20–30 qualified leads

↓

10–20 paying households

↓

50–150 monthly service units

↓

₹12,000–₹63,000 typical resident GMV

↓

₹3,000–₹19,000 service contribution

↓

+ ₹5,000–₹25,000 society retainer

↓

+ ₹0–₹15,000 event contribution

↓

− coordinator, support and acquisition costs

↓

Net society contribution

₹1 lakh+ resident GMV remains possible, but generally requires:

- More than 150 low-value walks

- Multi-night boarding

- Premium sitting

- Package purchases

- Multiple pets

- Paid events

- A larger number of active households

Final operating principle

Do not scale societies based on bookings or GMV alone. Scale the societies that produce repeat customers, reliable service delivery and positive contribution after sitter payouts, discounts, payment fees and support costs.

Simple explanation for professor

“A 500-flat society may have approximately 40 to 70 pet-owning families, but this is only an initial estimate. PetSaathi must confirm the actual number using resident surveys and registrations.

Out of these families, around 20 to 30 may initially show interest, and 10 to 20 may become paying customers. These customers may generate 50 to 150 monthly service units such as dog walks, sitting visits or boarding nights.

The total money paid by residents is called GMV. It is not all PetSaathi revenue because a major portion must be paid to walkers, sitters and boarding partners. PetSaathi’s actual contribution is calculated after sitter payouts, payment-gateway fees, discounts, refunds and support costs.

The society can also pay a monthly subscription, and PetSaathi can earn coordination revenue from events. These amounts should be added to PetSaathi’s service contribution—not to the full resident GMV.

The society funnel begins with identifying societies, contacting decision-makers, conducting meetings, launching pilots, collecting resident leads, generating paid bookings and converting repeat demand into a paid society partnership.

A society should move to a paid package only when it has enough leads, paying households, repeat customers, strong ratings, successful security access and positive economics.”

PetSaathi Phase 7 — Society Dashboard and Partnership Agreement 🏢🐾

Executive decision

Approve both components, with one clear separation:

- The society dashboard measures demand, service quality, supply health, safety and commercial value.

- The partnership agreement defines what PetSaathi and the society may—and may not—do.

The operating principle should be:

PetSaathi provides pet-care services and coordinates caregiver access. It is not a pet-rule enforcement agency, animal-control authority or substitute for municipal and veterinary authorities.

AWBI maintains specific guidance for pet owners, caregivers, RWAs and apartment-owner associations. Its 2015 guidance states that RWAs and AOAs cannot introduce blanket bans on keeping pet dogs. The partnership should therefore support responsible coexistence and organised services, not pet prohibition or removal.

Part A — Society Dashboard

1. Dashboard purpose

The dashboard should answer seven questions:

- Is there real resident demand?

- Are residents actually booking and paying?

- Are services being completed reliably?

- Are customers returning?

- Is the sitter pool healthy?

- Are complaints and incidents controlled?

- Is the society commercially valuable?

The dashboard should not be a decorative analytics page. Every metric should lead to a decision.

2. Dashboard access levels

Do not show the same dashboard to everyone.

PetSaathi admin dashboard

PetSaathi operations may view:

- Resident registrations

- Individual bookings

- Payment status

- Sitter assignments

- Pet-care controls

- Complaints and incidents

- Refunds

- Revenue and payout information

Society management dashboard

The RWA, facility manager or authorised society representative should generally see only aggregate programme information:

- Total resident leads

- Active customers

- Completed services

- On-time rate

- Aggregate complaint count

- Security-entry issues

- Event participation

- Monthly society performance

They should not automatically receive:

- Individual Pet Profiles

- Medical information

- Bite history

- Personal emergency contacts

- Full resident phone numbers

- Private Report Cards

- GPS routes

- Individual complaint narratives

- Payment credentials

The final DPDP Rules were published on November 14, 2025 with staged commencement provisions. PetSaathi should therefore use purpose-limited access, clear notices, reasonable security controls and a published contact for data-related questions or grievances.

3. Core dashboard metrics

A. Society identity

| Metric | Example | Purpose |
| --- | --- | --- |
| Society name | Green Acres | Account identification |
| City and area | Ahmedabad, Bopal | Geographic reporting |
| Society status | Active pilot | Partnership lifecycle |
| Package | Basic Partner | Commercial tracking |
| Pilot start/end | 1–30 August | Contract control |
| Operations owner | Prince | Internal accountability |
| Society contact | Facility manager | Operational escalation |

Recommended society statuses:

PROSPECT

PILOT_APPROVED

SETUP_IN_PROGRESS

ACTIVE_PILOT

PAID_PARTNER

PAUSED

ENDED

B. Resident demand

Resident leads

A valid lead is a resident who:

- Registered voluntarily

- Provided a usable contact

- Identified a pet-care need

- Accepted the relevant privacy notice

- Belongs to the society

Do not count poster impressions or all WhatsApp-group members as leads.

Dashboard fields

| Metric | Example |
| --- | --- |
| Resident leads | 42 |
| Verified residents | 35 |
| Pet Profiles started | 31 |
| Pet Profiles completed | 26 |
| Lead-to-profile conversion | 61.9% |
| Trial requests | 22 |

Formula

Lead-to-profile conversion =

Completed Pet Profiles ÷ Resident leads × 100

This tells you whether residents are genuinely interested enough to complete onboarding.

C. Active customers

An active customer should normally mean a resident who has completed at least one paid service within the selected reporting period.

Track separately:

REGISTERED_RESIDENT

PAID_CUSTOMER

ACTIVE_CUSTOMER

REPEAT_CUSTOMER

INACTIVE_CUSTOMER

| Metric | Example |
| --- | --- |
| Paid customers | 18 |
| Active this month | 14 |
| First-time customers | 8 |
| Repeat customers | 6 |
| Reactivated customers | 2 |

Do not classify someone as an active customer only because they joined a society group.

D. Bookings and usage

| Metric | Purpose |
| --- | --- |
| Booking requests | Demand before payment |
| Paid bookings | Real commercial conversion |
| Confirmed bookings | Operational commitments |
| Completed bookings | Successfully delivered services |
| Cancelled bookings | Service loss |
| Refunded bookings | Financial recovery |
| Bookings per active resident | Usage depth |
| Bookings per society per week | Marketplace density |

Important formulas

Booking conversion =

Paid bookings ÷ Qualified resident leads × 100

Completion rate =

Completed due bookings ÷ Total due bookings × 100

Booking density =

Completed bookings ÷ Active society weeks

Keep these booking states separate:

REQUESTED

PAID

CONFIRMED

COMPLETED

CANCELLED

REFUNDED

Do not report 50 booking requests as 50 completed bookings.

E. Repeat customers and retention

Repeat demand is the strongest proof that the society partnership is useful.

Track:

| Metric | Meaning |
| --- | --- |
| Repeat interest | Customer asks about booking again |
| Repeat request | Second booking request created |
| Second paid booking | Customer pays again |
| Second completed service | Strongest early retention signal |
| Package purchased | Resident buys walking plan |
| Package utilisation | Resident actually uses credits |
| Same-sitter request | Trust and continuity signal |

Recommended repeat-rate formula

Repeat customer rate =

Customers with a second completed service

÷

Customers whose repeat window has matured

× 100

Do not divide by customers who completed their first booking yesterday and have not had enough time to return.

F. Top service

Track bookings and contribution by service:

| Service | Paid bookings | Completed | Repeat rate | Rating |
| --- | --- | --- | --- | --- |
| Dog walking | 72 | 69 | 38% | 4.7 |
| Pet sitting | 18 | 17 | 24% | 4.6 |
| Boarding beta | 3 | 3 | — | 4.5 |
| Grooming camp | 21 appointments | 20 | — | 4.4 |

The top service should not be chosen using booking volume alone.

Evaluate:

Demand

+ completion rate

+ repeat rate

+ contribution

+ complaint rate

+ operational difficulty

Dog walking may have the highest volume, while sitting may generate higher contribution per booking.

G. Sitter-pool health

The dashboard should measure service capacity—not merely sitter headcount.

| Metric | Purpose |
| --- | --- |
| Active walkers | Available supply |
| Active pet sitters | Sitting capacity |
| Backup candidates | Recovery capability |
| Morning slot capacity | Peak demand control |
| Evening slot capacity | Peak demand control |
| Average sitter utilisation | Workload balance |
| Single-sitter dependency | Continuity risk |
| Verification expiry | Compliance risk |
| Training expiry | Capability risk |
| Low reliability sitters | Quality warning |

Useful alerts

NO_BACKUP_AVAILABLE

PEAK_SLOT_ABOVE_85_PERCENT

ONE_SITTER_HANDLES_ABOVE_50_PERCENT

VERIFICATION_EXPIRING

TRAINING_EXPIRED

HIGH_CANCELLATION_RATE

A society with five registered walkers can still have weak supply if only one is available during the required morning period.

H. Complaints and incidents

Do not combine ordinary complaints and safety incidents.

Complaint examples

- Delayed response

- Billing question

- Sitter communication problem

- Resident dissatisfaction

- Entry confusion

Incident examples

- Pet injury

- Bite

- Escape

- Unsafe handling

- Medical emergency

- Serious property issue

- Sitter no-show during a critical service

Track:

| Metric | Target |
| --- | --- |
| Complaints per 100 completed bookings | Below 5 |
| Critical unresolved incidents | 0 |
| Active-service response time | Under 5–10 minutes |
| Complaints acknowledged same day | 100% |
| Incidents with assigned owner | 100% |
| Corrective actions completed | 100% by due date |

Complaint-rate formula

Complaint rate =

Formal complaints ÷ Completed bookings × 100

A society with two complaints from ten services has a more serious pattern than one with two complaints from two hundred services.

I. Monthly financial value

Do not show one ambiguous figure called “revenue.”

Track separately:

| Metric | Meaning |
| --- | --- |
| Resident booking GMV | Total value paid by residents |
| Society subscription fee | Monthly society package charge |
| Event GMV | Total event service value |
| Sitter/partner payouts | Amount owed to providers |
| Refunds | Amount returned |
| Payment and support costs | Direct service costs |
| Platform service contribution | Value retained before broader overhead |
| Net society contribution | Value after direct society operating costs |

Recommended model

Monthly society contribution =

Society subscription fee

+ platform contribution from resident bookings

+ event coordination contribution

− resident discounts funded by PetSaathi

− direct coordinator/support allocation

− society-specific marketing cost

− refunds and recovery cost

Accounting recognition and GST treatment should be confirmed with a chartered accountant; the operating dashboard should still keep each component separate.

J. Event participation

Track each event through a funnel:

Residents reached

↓

Registered

↓

Attended

↓

Service completed

↓

Pet Profile created

↓

Trial booked

↓

Repeat customer

| Metric | Example |
| --- | --- |
| Event registrations | 40 |
| Attendance | 30 |
| Attendance rate | 75% |
| Qualified leads | 22 |
| Pet Profiles completed | 12 |
| Trial bookings | 7 |
| Event rating | 4.6 |
| Event contribution | ₹8,500 |

A successful event is not merely one with many photographs or attendees. It should create trust, leads, bookings or commercial value.

4. Recommended dashboard sections

Overview

Show:

- Active societies

- Today’s society bookings

- Services in progress

- Late-service alerts

- Open incidents

- Pending Report Cards

- Revenue today

- New resident leads

Demand and conversion

Show:

- Leads

- Verified residents

- Pet Profile completion

- Paid bookings

- Conversion rates

- Top booking source

Service quality

Show:

- Completion rate

- On-time rate

- Average rating

- Report Card delivery

- Refund rate

- Complaint rate

Supply

Show:

- Active sitter pool

- Peak-slot capacity

- Backup coverage

- Low-reliability sitters

- Credential expiries

Finance

Show:

- Resident GMV

- Society fee

- Sitter payouts

- Refunds

- Platform contribution

- Net society contribution

Events

Show:

- Upcoming event

- Registration

- Capacity

- Attendance

- Partner

- Event conversion

Risk and issues

Show:

- Open complaints

- Critical incidents

- Access failures

- Overdue corrective actions

- Privacy or data issues

5. Dashboard health score

Use a simple Red–Amber–Green status.

Green

- 15+ monthly paid bookings

- 90%+ completion

- 4.5+ rating

- Repeat customers present

- No critical unresolved incident

- Local backup coverage

- Positive or improving contribution

Amber

- Demand exists but repeat rate is weak

- Rating between 4.0 and 4.49

- Entry failures are increasing

- Sitter capacity is near limit

- Contribution remains negative

- Society engagement is declining

Red

- Critical unresolved incident

- Repeated security-access failures

- No backup sitter

- Low resident demand

- High refund/dispute rate

- Society requests unsafe or unlawful practices

- Significant privacy misuse

Red should trigger a formal review rather than automatic expansion.

6. Manual MVP dashboard

For the first 5–10 societies, a spreadsheet is acceptable.

Recommended tabs

1. Society Accounts

2. Resident Funnel

3. Bookings

4. Sitter Capacity

5. Complaints and Incidents

6. Finance

7. Events

8. Monthly Scorecard

9. Reference Lists

Society row example

| Society | Leads | Paid customers | Completed bookings | Repeat customers | Rating | Complaints | Monthly GMV | Health |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Green Acres | 42 | 18 | 28 | 7 | 4.7 | 1 | ₹36,800 | Green |

Move to an automated dashboard when

- More than 10–15 societies are active

- Manual updates become inconsistent

- Multiple operations users edit the sheet

- Real-time alerts are needed

- Finance reconciliation becomes complex

- Society users need controlled login access

Part B — Society Partnership Agreement

7. Agreement structure

A proper partnership agreement should clearly separate:

PetSaathi’s society-management obligations

Resident-to-PetSaathi service transactions

Sitter/provider responsibilities

Professional partner responsibilities

Society access responsibilities

Under Section 10 of the Indian Contract Act, an agreement becomes a contract where the parties have free consent, are competent to contract, and the agreement has lawful consideration and a lawful object. The final document should be reviewed by an Indian lawyer authorised to advise on the relevant state, entity type and society structure.

8. Parties and authority

The document should identify:

- PetSaathi’s legal entity

- Registered/business address

- Authorised PetSaathi signatory

- Society/RWA/AOA legal or operating name

- Society address

- Authorised society signatory

- Signatory’s authority

- Effective date

Do not sign only with an informal resident volunteer unless that person has authority to bind the society.

9. Service scope

Specify exactly which services are included.

Example:

Daily dog walking

In-home pet sitting

Controlled boarding beta

Resident booking assistance

Society sitter-access coordination

Report Card delivery

Complaint and incident support

Partner-event coordination

Also specify unavailable or excluded services:

Veterinary diagnosis or treatment by PetSaathi

Animal-control enforcement

Removal of community animals

Guaranteed sitter availability

Unlimited 24/7 support

Unlimited events

Automatic boarding approval

10. Resident booking process

Define the complete resident flow:

Resident registers voluntarily

↓

Residency is verified

↓

Pet Profile is completed

↓

Service request is submitted

↓

PetSaathi reviews eligibility

↓

Sitter is assigned

↓

Resident pays

↓

Payment is verified

↓

Booking is confirmed

The agreement should clarify:

- The society is not purchasing each resident service unless expressly agreed.

- Residents pay PetSaathi directly for their bookings.

- Individual resident terms and policies apply separately.

- The society does not guarantee service availability.

- PetSaathi controls final caregiver assignment.

11. Sitter access process

Define:

- Information provided to security

- Advance-registration period

- Approved entrance

- Permitted service windows

- Photo and PetSaathi ID

- Access validity

- Replacement-sitter procedure

- Entry denial escalation

- Access revocation

Security should see only operationally necessary fields:

Display name

Photograph

PetSaathi sitter ID

Approved service

Access validity

PetSaathi support contact

The society should not receive raw KYC files, bank information or unrelated sitter records.

12. Security-gate coordination

The agreement should assign responsibilities clearly.

PetSaathi

- Provide accurate active-roster information

- Notify replacements

- Revoke removed sitter access

- Maintain operations support

- Inform the society of material booking-access changes

Society

- Communicate gate requirements

- Train relevant security staff

- Allow properly approved sitters to enter

- Notify PetSaathi of rule changes

- Provide a route for urgent access escalation

Important protection

PetSaathi should not guarantee entry where:

- The resident did not provide required approval

- The society changed rules without notice

- Security systems are unavailable

- A government or emergency restriction applies

13. Payment model

State separately:

Society payments

- Setup fee

- Monthly subscription

- Event coordination fees

- Taxes

- Payment due date

- Late-payment consequences

Resident payments

- Service pricing

- Payment provider

- Prepayment requirement

- Discounts

- Cancellation fees

- Refund process

Partner payments

- Groomer/veterinarian/trainer payout

- Calculation basis

- Tax and invoicing responsibility

- Settlement period

- Refund adjustments

Do not use undefined language such as:

“Commission will be charged.”

Specify the payer, recipient, amount or percentage, and calculation basis.

14. Refund and cancellation policy

Define separately:

- Resident cancellation

- Sitter cancellation

- PetSaathi cancellation

- Society access failure

- Event cancellation

- Weather or force-majeure situations

- Partial service

- Full or partial refund

- Credit option

- Replacement option

The Consumer Protection (E-Commerce) Rules apply to goods and services sold through electronic systems and include consumer-information and grievance obligations. PetSaathi should clearly disclose pricing, payment, refund, cancellation and grievance arrangements.

Consumers can also escalate grievances through the Department of Consumer Affairs’ National Consumer Helpline, which currently operates through its portal, telephone number 1915 and multiple digital channels.

15. Complaint escalation

The agreement should define three levels.

Level 1 — Routine issue

Examples:

- Booking question

- Minor delay

- Report Card correction

- Billing clarification

Target:

Same-day acknowledgement

Level 2 — Material service complaint

Examples:

- Repeated lateness

- Sitter communication failure

- Access problem

- Customer alleges poor handling

Target:

Immediate case owner

Formal investigation

Written resolution

Level 3 — Critical safety incident

Examples:

- Injury

- Bite

- Escape

- Medical emergency

- Serious misconduct

Target:

Immediate escalation

Owner contacted

Emergency/veterinary coordination

Incident preservation

Senior safety review

The agreement should distinguish response time from final resolution time.

16. Emergency protocol

Define:

- Who may report an emergency

- PetSaathi emergency contact

- Society/security contact

- Owner and emergency-contact process

- Veterinary coordination

- Transport coordination

- Spending authorisation

- Evidence and incident records

- Post-incident review

Important wording:

PetSaathi coordinates with owners, society contacts and registered veterinary partners. PetSaathi does not provide veterinary diagnosis or treatment unless such services are separately delivered by qualified professionals.

17. Data privacy and confidentiality

The agreement should define:

Data PetSaathi collects

- Resident contact details

- Society membership information

- Pet Profiles

- Booking information

- Service media

- Payment status

- Complaints and incidents

Data the society receives

- Aggregate bookings

- Programme usage

- On-time rate

- Entry failures

- Aggregate complaints

- Approved sitter-access roster

Data the society does not automatically receive

- Pet medical information

- Emergency contacts

- Individual payment details

- Full GPS routes

- Private media

- Internal risk assessments

- Individual complaint narratives

Include:

- Permitted purposes

- Access restrictions

- Retention

- deletion/return after agreement termination

- Security expectations

- Data-breach communication

- Resident-request handling

- Subprocessors or service providers where applicable

The DPDP framework requires reasonable security safeguards and provides for notification relating to personal-data breaches. The 2025 Rules also contemplate clear notices and published grievance/contact mechanisms.

18. No pet-ban and no enforcement positioning

This should be a dedicated contract clause.

Recommended clause

PetSaathi is engaged solely as a pet-care service and operational coordination provider. Nothing in this Agreement authorises PetSaathi to formulate, enforce or assist in enforcing blanket prohibitions on lawful pet ownership, compel residents to surrender or remove owned pets, remove community animals, impose breed-based prohibitions, or act as an animal-control, municipal, policing or adjudicatory authority. Any society rules or actions concerning animals remain subject to applicable law, official animal-welfare guidance and competent governmental or judicial authority.

Add operational clarification

PetSaathi may reasonably:

- Refuse an individual service that cannot be delivered safely

- Require complete Pet Profile information

- Require suitable equipment

- Pause matching after an incident

- Restrict a sitter’s access

- Apply service-specific safety controls

This is different from banning a resident from owning a pet.

AWBI’s official guidance includes a dedicated RWA/AOA circular and states that blanket bans on keeping pet dogs are not legally permissible.

19. Pilot duration and review

Define:

Pilot start date

Pilot end date

Booking cap

Active services

Pilot success metrics

Review meeting date

No automatic renewal

Recommended pilot duration:

21–30 days

Success measures should include:

- Leads

- Paid bookings

- Completed services

- Rating

- Repeat customers

- Security-entry success

- Complaints

- Sitter capacity

- Society feedback

20. Renewal and conversion

At the end of the pilot, the society should move to one of these states:

CONVERT_TO_BASIC

CONVERT_TO_PREMIUM

CONTINUE_PILOT

EVENT_ONLY

PAUSE_AND_FIX

END_PARTNERSHIP

The agreement should state:

- Renewal fee

- New term

- Renewal notice

- Price-review process

- Package changes

- Additional-service pricing

- Termination notice

Do not automatically charge the society after a free pilot unless it has expressly accepted the paid plan.

21. Branding and communication permission

Define whether PetSaathi may use:

- Society name

- Society logo

- Photographs of premises

- Event photographs

- Committee testimonials

- Resident testimonials

- Partnership announcement

Require separate permission for resident names, pet photographs and testimonials.

The society should not use PetSaathi branding in a way that implies:

- Government approval

- Veterinary certification

- Guaranteed safety

- PetSaathi enforcement authority

- Exclusivity unless contracted

22. Termination and immediate suspension

Ordinary termination

Example:

30 days’ written notice

Immediate pause or termination

Possible reasons:

- Critical safety obstruction

- Unauthorised resident-data disclosure

- Repeated denial of approved sitter access

- Non-payment

- Fraud

- Misuse of brand

- Illegal or discriminatory demands

- Interference with incident investigation

- Repeated operational non-cooperation

On termination:

- Stop accepting new society-specific bookings

- Complete or cancel existing bookings appropriately

- Revoke access rosters

- Remove public partnership claims

- Reconcile payments

- Handle retained data according to policy and law

23. Agreement schedules

Keep the main contract readable by moving operational detail into schedules.

Schedule A — Active Services

Schedule B — Pricing and Payment

Schedule C — Sitter Access SOP

Schedule D — Data Sharing and Privacy

Schedule E — Support and Escalation

Schedule F — Pilot Metrics

Schedule G — Branding Permissions

This allows PetSaathi to update prices or service windows without rewriting the entire legal document, subject to the agreed amendment process.

24. End-to-end society operating cycle

Agreement signed

↓

Society configured

↓

Resident announcement approved

↓

Residents register voluntarily

↓

Services begin

↓

Dashboard updates daily

↓

Issues and incidents tracked

↓

Monthly society report generated

↓

Performance review held

↓

Renew, upgrade, fix or end

The dashboard provides evidence. The agreement provides authority and boundaries.

25. Definition of done

Dashboard

The dashboard is ready when:

- Every metric has a precise definition.

- Paid, confirmed and completed bookings are separate.

- Repeat interest and actual repeat services are separate.

- GMV, subscription fees and contribution are separate.

- Complaints and incidents are separate.

- Society management sees aggregate data only.

- Every red alert has an owner and due date.

- Monthly data can be audited back to source records.

Agreement

The agreement is ready when:

- Signatory authority is confirmed.

- Service scope and exclusions are clear.

- Resident bookings are separate from society fees.

- Sitter access responsibilities are defined.

- Refund and complaint processes are documented.

- Emergency responsibilities are realistic.

- Privacy and data-sharing boundaries are explicit.

- No-pet-ban/no-enforcement language is included.

- Renewal and termination are clear.

- An Indian lawyer has reviewed the final version.

Final operating principle

The dashboard should prove whether the partnership is creating demand, reliable services, repeat usage and positive value. The agreement should prevent operational confusion, privacy misuse and any attempt to turn PetSaathi into a society pet-control authority.

Simple explanation for professor

“The society dashboard will track the performance of every PetSaathi society partnership.

It will show resident leads, active customers, monthly bookings, repeat customers, customer ratings, complaints, sitter availability, revenue and event participation. Paid booking requests and completed services will be reported separately so that the dashboard does not exaggerate performance.

The society management will see only aggregate information. Individual pet medical details, private Report Cards, payment data and emergency contacts will remain restricted to authorised PetSaathi users.

The partnership agreement will explain which services PetSaathi provides, how residents book, how sitters enter the society, how payments and refunds work, and how complaints or emergencies are handled.

The agreement will also contain an important boundary: PetSaathi is a pet-care service provider. It is not an animal-control authority and will not create or enforce blanket pet bans.

At the end of every month, PetSaathi will use the dashboard to review demand, service quality, complaints, sitter supply and financial value. Based on this information, the society can continue, upgrade, pause or end the partnership.”

A monthly AWBI, DPDP and consumer-rule compliance watch would help keep the dashboard controls and agreement clauses current.

PetSaathi Phase 7 — Correct Society Partnership Strategy and Gate Protocol 🏢🐾

Executive decision

The corrected society model is not:

PetSaathi → RWA approval → launch

It is:

Pet-parent demand

+

RWA/facility approval

+

Security access workflow

+

Local sitter capacity

+

Veterinary/partner ecosystem

↓

Operational society partnership

PetSaathi should be positioned as a pet-care service provider and coordination platform, not an animal-control or society-rule enforcement agency. AWBI guidance states that RWAs and apartment-owner associations cannot introduce blanket bans on residents keeping pet dogs, and it promotes reasonable arrangements for responsible community living.

Mistake 1 — Pitching only to the RWA

Wrong approach

Convince RWA secretary

↓

Sign agreement

↓

Assume residents will book

An RWA can permit communication and help establish access procedures, but it does not create resident demand by itself.

Correct stakeholder model

1. Pet parents create demand

Pet parents determine whether there is a real need for:

- Daily dog walking

- Office-hour pet sitting

- Travel care

- Same-sitter plans

- Festival support

- Grooming or veterinary-partner camps

Before launching, obtain evidence such as:

10+ interested pet-parent households

or

5+ residents ready for a paid trial

2. RWA or committee provides programme approval

The committee should approve:

- Resident communication

- Pilot scope

- Partnership duration

- Society branding

- Aggregate reporting

- Commercial terms

It should not receive unrestricted access to Pet Profiles, medical data or individual payment details.

3. Facility manager makes the system operational

The facility manager helps define:

- Visitor-entry procedure

- Gates and towers

- Approved service times

- Lift or common-area procedures

- Event permissions

- Security escalation

- Replacement-sitter access

4. Security executes access

Security confirms that the arriving person matches the booking-specific access record.

Security should not decide:

- Whether the sitter is suitable for the pet

- Pet risk classification

- Refund eligibility

- Customer pricing

- Whether the booking should proceed medically

5. Local partners strengthen credibility

Veterinarians, groomers, pet shops and trainers may help with:

- Warm society introductions

- Professional events

- Emergency coordination

- Resident education

- Partner referrals

Correct sequence

Validate pet-parent interest

↓

Meet RWA/facility manager

↓

Confirm operational feasibility

↓

Design security access

↓

Launch limited pilot

Mistake 2 — Asking for a paid contract too early

Wrong approach

“Pay ₹25,000 per month before your residents have used the service.”

This creates excessive decision risk for the society.

Correct conversion model

No-fee setup pilot

↓

Resident opt-in

↓

Paid individual bookings

↓

Report Cards and ratings

↓

Repeat bookings

↓

Pilot performance report

↓

Paid society partnership

Recommended pilot

| Item | Pilot rule |
| --- | --- |
| Duration | 21–30 days |
| Society setup fee | ₹0 |
| Society partnership fee | ₹0 |
| Resident services | Paid |
| Primary services | Dog walking and home sitting |
| Capacity | Limited by available sitters |
| Renewal | Not automatic |

The phrase “free pilot” must be explained carefully: the society pays no programme fee, while residents continue paying for the individual care services they book.

Paid-conversion evidence

Before proposing a paid package, show:

- Opted-in residents

- Completed Pet Profiles

- Paid bookings

- Completed services

- On-time rate

- Report Card delivery

- Average rating

- Repeat bookings

- Entry failures

- Complaints and resolutions

A society should pay for demonstrated operational value—not a theoretical feature list.

Mistake 3 — Using a generic website link

Wrong approach

petsaathi.in

The resident then has to discover:

- Whether PetSaathi serves their society

- Which services are available

- Whether sitters can enter

- Which offer applies

- How support works

This creates unnecessary friction.

Correct approach

Create a society-specific page:

/pet-care/societies/ahmedabad/green-acres-bopal

The page should show

- Society name and programme status

- Active services

- Resident offer

- Local sitter summaries

- Society access process

- Supported service windows

- Booking CTA

- Support contact

- Report Card example

- Society-specific FAQs

- Partner veterinarian or groomer

- Current availability

Booking improvement

When the resident clicks Book Now, automatically attach:

society_id

society_service_config

resident_offer_id

access_rule_version

The resident should not have to search for the society or type the complete address again.

Privacy boundary

The public page may display:

- Society name

- General area

- Public sitter summaries

- Service windows

- Resident offer

- Support channel

It must not display:

- Resident lists

- Flat numbers

- Access codes

- Personal sitter phone numbers

- Pet medical details

- Full GPS routes

The final DPDP Rules require clear notices describing the personal data being processed and its purpose, while also specifying safeguards such as access controls, masking, logging and security measures. The rules were published in November 2025 with staged commencement provisions.

Mistake 4 — Treating pets as a society conflict

Wrong positioning

“We solve pet complaints for societies.”

This implies that pets or pet owners are the problem and risks turning PetSaathi into an enforcement mechanism.

Correct positioning

PetSaathi helps residents access reliable pet care while improving service-provider access, cleanliness coordination, service evidence and issue escalation within the community.

Balanced stakeholder message

For pet parents

- Reliable care

- Verified sitter information

- Service proof

- Repeat options

- Emergency coordination

For non-pet residents

- Clear service times

- Responsible common-area procedures

- Waste-cleanup expectations

- Complaint route

- Less unmanaged service-provider movement

For society management

- Approved-access roster

- Booking verification

- Aggregate reporting

- Formal incident process

- Clear operations contact

For security

- Booking-specific entry proof

- Current sitter photograph

- Access validity

- Clear replacement procedure

AWBI guidance says blanket pet bans are not permissible, while also advising responsible practices such as leashing in common areas, cleanliness and mutually acceptable arrangements. PetSaathi should support that balanced operating model.

Recommended agreement clause

PetSaathi is engaged solely as a pet-care service provider and operational coordination platform. PetSaathi shall not act as an animal-control authority, pet-rule enforcement agency, municipal authority or adjudicator of disputes concerning lawful pet ownership.

The Society shall not use the PetSaathi programme to impose blanket pet bans, breed-based restrictions, unlawful removal requirements or discriminatory conditions against pet-owning residents.

PetSaathi may support reasonable service-access, cleanliness, safety, communication and incident-escalation procedures consistent with applicable law, animal-welfare guidance and the terms of this Agreement.

Mistake 5 — No sitter-access planning

Wrong approach

Booking confirmed

↓

Sitter reaches gate

↓

Security has no information

↓

Sitter is refused entry

↓

Customer, sitter and security begin calling everyone

This creates delays, cancellations and safety confusion.

Correct operating principle

A booking is not operationally ready until the society access record is also ready.

The access workflow must link:

Society

+ booking

+ resident

+ assigned sitter

+ scheduled service window

End-to-end gate and security protocol

Stage 1 — Society access configuration

Before the pilot launches, create a society_access_rules record containing:

- Approved gate

- Visitor-registration requirement

- Sitter-ID format

- Advance-notice period

- Service hours

- Tower or block process

- Entry/exit logging

- Replacement-sitter procedure

- Emergency-entry process

- Security escalation contact

Stage 2 — Maintain the active sitter roster

Security receives a restricted roster with:

- Sitter display name

- Current photograph

- PetSaathi sitter ID

- Approved service category

- Access status

- Valid-from date

- Expiry date

- PetSaathi operations contact

Security should not receive:

- Full KYC document copies

- Bank information

- Home address

- Internal incident history

- Ratings investigation

- Other customers’ bookings

Stage 3 — Booking-specific access record

When the booking is confirmed, create:

access_record_id

booking_id

society_id

resident_unit_reference

assigned_sitter_id

service_type

scheduled_start

scheduled_end

access_status

Recommended access statuses:

NOT_REQUIRED

PENDING

PRE_APPROVED

ARRIVED

ENTRY_APPROVED

ENTRY_DENIED

SERVICE_IN_PROGRESS

EXIT_RECORDED

CANCELLED

EXPIRED

Stage 4 — Pre-arrival notification

Send the security desk a booking-specific notification before the service.

PetSaathi Access Notice

Booking: [Booking ID]
Society: [Society Name]
Service: [Dog Walking / Pet Sitting]
Date: [Date]
Service window: [Start Time]–[End Time]

Assigned caregiver:
Name: [Sitter Name]
PetSaathi ID: [Sitter ID]
Photo: [Secure Photo Link / App Record]
Access status: Pre-approved

Resident:
Tower/Block: [Tower]
Flat: [Flat Number]

Please verify the sitter’s PetSaathi ID and photograph at entry.

For changes, replacement confirmation or support, contact:
[PetSaathi Operations Number]

This notice is valid only for the stated booking and service window.

Stage 5 — Sitter arrival

The sitter opens the booking in the PetSaathi app and shows:

- Current photograph

- PetSaathi ID

- Booking ID

- Society name

- Resident tower and flat

- Service type

- Valid service window

- Dynamic verification code or QR, where available

The gate should not depend only on a text message that could be forwarded or edited.

Corrected sitter gate message

Your original message is directionally correct, but the sitter’s personal phone number should not be the main verification method.

Hello, I’m [Sitter Name], PetSaathi ID [Sitter ID].

I am here for confirmed booking [Booking ID].

Society: [Society Name]
Resident: [Resident First Name]
Tower/Block: [Tower]
Flat: [Flat Number]
Service: [Dog Walking / Pet Sitting]
Approved service window: [Start Time]–[End Time]

Please verify my photograph and booking in the PetSaathi access record.

For confirmation or any mismatch, contact PetSaathi Operations:
[Operations Number]

Stage 6 — Gate verification

Security checks:

Photo matches sitter

PetSaathi ID matches

Booking ID exists

Date and time are valid

Society and unit match

Access status is PRE_APPROVED

Booking has not been cancelled

If everything matches:

access_status = ENTRY_APPROVED

actual_entry_at = timestamp

Stage 7 — Resident confirmation

For first-time services or high-risk access:

- Send the resident an arrival notification.

- Let the resident approve through the app or existing visitor-management process.

- Record the approval timestamp.

Do not require the resident to share OTPs in public groups.

Stage 8 — Service start

Gate entry does not automatically start the pet-care service.

The sitter must separately confirm:

- Pet handover completed

- Correct pet identified

- Equipment checked

- Instructions reviewed

- Service started

This preserves the distinction between:

Building entry

and

Pet-care service start

Stage 9 — Exit

At completion:

- Sitter checks out of the booking.

- Security records departure where required.

- PetSaathi closes the temporary access record.

- The resident receives the Report Card.

- Access expires automatically.

Recommended rule:

access validity =

scheduled window

+ approved arrival buffer

+ approved completion buffer

Do not leave indefinite access active after the booking.

Replacement-sitter protocol

A replacement should never arrive using the original sitter’s access approval.

Correct flow

Primary sitter removed

↓

Original access record revoked

↓

Replacement verified

↓

Customer notified

↓

New booking assignment recorded

↓

New access record issued

↓

Security notified

Security message

The original caregiver is no longer authorised for booking [Booking ID]. Do not permit entry using the previous notice. A new access notice will be issued for the approved replacement.

Cancellation protocol

When a booking is cancelled:

booking_status = CANCELLED

access_status = CANCELLED

security notified

sitter notified

resident notified

A cancelled booking must not remain valid at the gate.

Emergency-entry protocol

During a genuine active-service emergency, the operations team may need to:

- Contact security

- Request expedited exit or entry

- Coordinate pet transport

- Contact the owner

- Contact a veterinary partner

- Preserve an incident timeline

Emergency access must still identify:

- Incident ID

- Booking ID

- Authorised responder

- Purpose

- Operations contact

Do not use “emergency” to bypass ordinary verification for routine delays.

Gate data-visibility matrix

| Information | Security | Assigned sitter | Society committee |
| --- | --- | --- | --- |
| Sitter name/photo | Yes | Self | Limited roster |
| PetSaathi sitter ID | Yes | Yes | Limited roster |
| Booking ID | Yes | Yes | Aggregate only |
| Resident tower/flat | Yes, booking-specific | Yes, after assignment | No default access |
| Resident phone | Prefer masked/operations relay | Masked or required contact | No |
| Service time | Yes | Yes | Aggregate |
| Payment amount | No | No need | No |
| Pet medical details | No | Relevant care only | No |
| Pet handling risks | No, unless entry safety is affected | Relevant controls | No |
| GPS route | No | During assignment | No |
| Emergency contact | PetSaathi operations | Relevant authorised contacts | No default access |
| Complaint details | No | Only when relevant | Aggregate only |

The safest design is purpose-based access: each role receives only the information required for its specific function. DPDP rules require clear processing purposes and contemplate security controls such as masking, restricted access and logging.

Important correction to your gate-data list

Sitter name

Yes. Required for identity matching.

Phone number

Store it internally, but do not rely on the sitter’s phone number as gate proof.

Prefer:

- PetSaathi ID

- Current photograph

- Booking record

- Secure operations contact

ID status

Yes, but show a simple operational status:

ACTIVE

EXPIRED

REVOKED

Do not send full KYC documents.

Booking ID

Yes. This is the main booking-specific proof.

Customer flat/tower

Yes, only to authorised security and the assigned sitter.

Do not post it in society groups.

Service time

Yes. It limits the access window.

Emergency contact

Use the PetSaathi operations or incident contact, not the resident’s private emergency-family contact.

Required gate dashboard

Security or the operations team should be able to view:

Today

- Expected sitter arrivals

- Booking windows

- Approved caregiver

- Tower and flat

- Current access status

- Replacement notices

- Cancelled bookings

Alerts

- Sitter arrived too early

- Sitter arrived after expiry

- Photo mismatch

- Booking cancelled

- Replacement not approved

- Access denied

- Sitter did not exit within expected window

Audit history

Record:

who created access

who approved it

when it became valid

when entry occurred

who denied access

why it was denied

when exit occurred

Access exception handling

Sitter not on roster

Deny temporary entry

↓

Contact PetSaathi Operations

↓

Verify assignment

↓

Issue corrected access record

Wrong booking ID

Do not permit entry until operations resolves the mismatch.

Resident does not answer

- Wait according to policy.

- Contact operations.

- Record attempted contact.

- Do not disclose private information to unrelated residents.

Security refuses a correctly approved sitter

- Record denial reason.

- Contact facility manager.

- Notify customer.

- Adjust start time or replacement.

- Preserve evidence for society review.

Sitter arrives with another person

Do not permit the unregistered person unless separately approved.

Sitter attempts entry after cancellation

Deny access and create an operational alert.

Society-partnership success model

The corrected funnel is:

Pet-parent demand confirmed

↓

RWA/facility approval

↓

Security protocol configured

↓

Society-specific page launched

↓

Residents opt in

↓

Pet Profiles completed

↓

Paid bookings confirmed

↓

Sitter entry succeeds

↓

Service completed

↓

Report Card delivered

↓

Repeat booking

↓

Paid society partnership

Key metrics

Stakeholder health

| Metric | Target |
| --- | --- |
| Residents opting in | Increasing |
| RWA response | Positive |
| Security-entry success | 97%+ |
| Sitter access mismatches | Below 2–3% |
| Access records issued on time | 98%+ |
| Unauthorised entries | 0 |
| Resident-data exposure | 0 |

Service quality

| Metric | Target |
| --- | --- |
| On-time services | 95%+ |
| Completed bookings | 90%+ |
| Report Cards | 98%+ |
| Customer rating | 4.5–4.6+ |
| Repeat customers | 25%+ |
| Critical unresolved incidents | 0 |

Definition of done

The society partnership is operationally ready only when:

- Resident demand has been validated.

- An authorised society contact has approved the pilot.

- The facility manager has reviewed the workflow.

- Security has a current sitter roster.

- Booking-specific access notices work.

- Replacement access revokes the original approval.

- Cancelled bookings automatically lose access.

- Private resident data is restricted.

- The society-specific landing page is active.

- Residents can register voluntarily.

- Every service produces a Report Card.

- PetSaathi is not used as a pet-rule enforcement agency.

Simple explanation for professor

“Many society partnership strategies fail because founders speak only to the RWA manager.

A successful society partnership needs several stakeholders. Pet parents create real service demand. The RWA gives programme approval. The facility manager explains operational requirements. Security controls sitter entry, and local veterinarians or pet shops improve trust and referrals.

PetSaathi should begin with a 21-to-30-day pilot instead of immediately asking for a large paid contract. The pilot should produce real registrations, paid bookings, ratings and repeat services. After demonstrating results, PetSaathi can offer the society a monthly paid package.

Each society should have a personalised booking page rather than a generic website link. It will show the available services, local sitters, resident offer, booking process and support contact.

PetSaathi should not describe pets as a society problem. It should explain that it helps pet parents access reliable care while improving service-provider entry, cleanliness coordination and complaint escalation.

The most important operational feature is the gate protocol. Before a service, security receives the sitter’s name, photograph, PetSaathi ID, booking ID, resident tower and flat, service type and valid time window. Security checks this information before entry.

If the sitter changes, the original access permission is cancelled and a new approval is issued. If the booking is cancelled, the gate approval is also cancelled.

Security receives only the information needed for access. It does not receive the pet’s medical history, customer payment details or private emergency contacts.

This makes the society partnership safe, organised and scalable while keeping PetSaathi clearly positioned as a pet-care provider—not an animal-control authority.”

PetSaathi Phase 7 — Society Marketing Assets and Technical Product Architecture 🏢🐾

Executive decision

Your proposed marketing and technical structure is directionally correct, but it needs four production-level improvements:

- Marketing claims must be precise. Avoid presenting “verified,” “safe,” “emergency support,” or “from ₹99” without explaining the actual checks, limitations and eligibility.

- Society membership must be separate from customer identity. One customer may move societies, belong to multiple communities or have verification revoked.

- Pricing, reports and contacts need versioned relational tables. They should not be embedded as loosely maintained columns inside the main societies table.

- Public, resident and admin APIs must return different data shapes. A public society endpoint must never expose resident, contact, pricing-rule or internal operational fields.

ASCI’s advertising code requires promotional representations to be truthful and not misleading. Therefore, every poster, brochure and landing-page claim should match the actual verification, availability and service workflow.

Part A — Society marketing assets

1. Marketing objective

The marketing system should move a resident through this funnel:

Poster or society announcement

↓

Resident scans society QR code

↓

Society landing page opens

↓

Resident verifies membership

↓

Resident creates/selects Pet Profile

↓

Resident views society offer

↓

Booking request submitted

↓

Payment verified

↓

Service completed

↓

Report Card delivered

↓

Repeat plan offered

Every marketing asset should therefore have:

- One clear society identity

- One main service promise

- One trust explanation

- One offer

- One QR-based action

- One support contact

- Visible conditions

2. Poster headline strategy

Your original headline ideas are good, but “safe” and “verified” should be used carefully.

Recommended dog-walking headline

Screened dog walkers now available for your society 🐾

Supporting line:

Book 30- or 60-minute walks with approved-access caregivers, service updates and a Pet Report Card.

CTA:

Scan to view available walking slots

This is stronger than implying that every walker is permanently available or that the service is risk-free.

Recommended pet-sitting headline

Going out? Arrange trusted in-home pet sitting.

Supporting line:

Receive food, water, routine and photo updates from an eligible PetSaathi sitter.

CTA:

Scan to book society pet care

Avoid:

“Leave your pet completely worry-free.”

That is an absolute emotional promise that cannot realistically be guaranteed.

Recommended busy-morning headline

Busy morning? Keep your dog’s routine on track.

Supporting line:

Request a local dog walker with society-access registration and a service Report Card.

CTA:

Check morning availability

Recommended trial-offer headline

Your first eligible 30-minute dog walk from ₹99

Conditions should appear immediately beneath it:

One introductory offer per verified household. Subject to Pet Profile review, sitter availability, selected time slot and pilot capacity.

Use “from ₹99” only when a genuine ₹99 booking option is actually available. Promotional claims and price representations should be accurate and supportable.

3. QR poster structure

A good society poster should contain only the information necessary to create action.

Recommended layout

Top section

PetSaathi × Green Acres Bopal

Main headline

Screened dog walking and pet sitting

for Green Acres residents

Trust points

✓ Society-access caregiver roster

✓ Booking and service updates

✓ Photo updates where applicable

✓ Pet Report Card after service

✓ Structured support and escalation

Offer

First eligible dog walk from ₹99

CTA

Scan to verify residency and book

[QR CODE]

Footer

Services are subject to Pet Profile review,

caregiver eligibility, payment and availability.

Emergency support means escalation and

veterinary coordination through available partners.

4. QR-code implementation

The QR code should not point to the generic homepage.

Use a society-specific URL:

https://petsaathi.in/societies/ahmedabad/green-acres-bopal

?utm_source=society_poster

&utm_medium=qr

&utm_campaign=green_acres_pilot

Store:

society_id

campaign_id

asset_type

placement

created_at

expires_at

This lets you distinguish:

- Lobby-poster traffic

- WhatsApp traffic

- Vet-referral traffic

- Event-poster traffic

- Security-desk referrals

5. Brochure structure

The brochure should be short—ideally two or four pages.

Page 1 — Society-specific introduction

Headline:

Reliable pet care, right inside your community

Include:

- Society name

- Active services

- Resident offer

- Booking QR code

- PetSaathi support

Page 2 — Available services

Dog walking

- 30- or 60-minute options

- Individual care

- Walk start/end record

- Basic GPS evidence where enabled

- Pet Report Card

Pet sitting

- Food and water care

- Routine support

- Home entry/exit confirmation

- Private photo updates

- Care notes

Controlled boarding

- Screening and compatibility review

- Host availability

- Health-policy requirements

- Daily updates

Label boarding clearly as:

Controlled beta—available only for eligible pets and approved hosts

Page 3 — How verification works

Explain verification in layers:

Identity reviewed

↓

Interview completed

↓

Service permissions assigned

↓

Training reviewed

↓

Society access registered

↓

Performance monitored

Do not suggest that one identity document guarantees service safety.

Recommended wording:

PetSaathi uses multiple screening and operational controls. No service can be guaranteed to be risk-free.

Page 4 — Booking, pricing and support

Include:

- Create Pet Profile

- Select service and schedule

- PetSaathi reviews care requirements

- Eligible sitter is assigned

- Payment is verified

- Society access is prepared

- Service is completed

- Report Card is delivered

Also display:

- Starting prices

- Offer conditions

- Cancellation policy link

- Refund-policy link

- WhatsApp support

- Emergency escalation explanation

6. Report Card example

Use a fictional or expressly consented example.

PET REPORT CARD 🐾

Pet: Bruno

Service: 30-minute dog walk

Sitter: Riya

Time: 7:30 AM–8:02 AM

Approximate distance: 1.4 km

Water: Given

Pee/poop: Yes

Mood: Happy and energetic

Leash behaviour: Calm after first five minutes

Concern: None reported

Sitter note:

Bruno enjoyed the walk and returned home comfortably.

Do not expose a real resident’s pet or booking information in a public brochure without permission.

7. Emergency-support wording

Replace:

Emergency support

with:

Priority service escalation and veterinary coordination

PetSaathi may:

- Contact the pet owner

- Contact saved emergency contacts

- Contact an available registered veterinary partner

- Coordinate transport where available

- Create an incident record

- Inform society security where operationally necessary

PetSaathi should not imply that ordinary support staff diagnose, prescribe medication or provide veterinary treatment.

8. Society asset checklist

Prepare these assets for every active society:

| Asset | Purpose |
| --- | --- |
| A3 lobby poster | Resident awareness |
| WhatsApp image | Group announcement |
| QR card | Security desk or event |
| Two-page brochure | Detailed explanation |
| Landing page | Conversion |
| Trial-offer card | First booking |
| Report Card demo | Trust |
| Sitter-introduction card | Local supply |
| Society FAQ | Objection handling |
| Event poster | Camp registration |

Part B — Correct technical architecture

9. Your original schema: what needs correction

The original tables are useful as a concept, but they combine unrelated responsibilities.

Original problem

societies

- contact_person

- contact_phone

A society can have:

- Multiple RWA contacts

- Facility manager

- Security supervisor

- Emergency contact

- Finance contact

- Historical contacts

Therefore, contacts should be separate records.

Original problem

society_residents

- flat_number

- verification_status

This lacks:

- Membership type

- Verification method

- Expiry

- Approval history

- Revocation

- Multiple occupants

- Tenant/owner distinction

Original problem

society_pricing

- resident_price

- normal_price

This lacks:

- Currency

- Effective dates

- Duration

- Extra-pet fee

- Peak pricing

- Tax treatment

- Offer limits

- Version history

Original problem

society_reports

- revenue

- complaints

This is ambiguous:

- Is revenue GMV or PetSaathi revenue?

- Is complaints a count or text?

- Were cancellations included?

- What reporting period was used?

- Can the calculation be reproduced?

10. Recommended core entities

societies

society_contacts

society_memberships

society_access_rules

society_service_configs

society_pricing_rules

society_offers

society_sitter_access

society_partners

society_events

society_report_snapshots

society_status_history

Use database foreign keys and unique constraints to protect relationships and prevent duplicates. PostgreSQL foreign keys maintain referential integrity between related records, while primary-key and unique constraints enforce identity and uniqueness at the database level.

11. Corrected societies table

societies

- id UUID PRIMARY KEY

- public_code VARCHAR UNIQUE

- name VARCHAR

- slug VARCHAR

- city_id UUID

- area VARCHAR

- address_line TEXT

- postal_code VARCHAR

- latitude DECIMAL

- longitude DECIMAL

- total_flats INTEGER

- estimated_occupied_flats INTEGER

- estimated_pet_families_low INTEGER

- estimated_pet_families_high INTEGER

- partnership_status ENUM

- plan_type ENUM

- public_page_status ENUM

- pilot_start_at TIMESTAMPTZ

- pilot_end_at TIMESTAMPTZ

- timezone VARCHAR

- created_at TIMESTAMPTZ

- updated_at TIMESTAMPTZ

- version INTEGER

Recommended constraints

UNIQUE(city_id, slug)

total_flats > 0

estimated_occupied_flats >= 0

estimated_occupied_flats <= total_flats

pilot_end_at > pilot_start_at

Partnership statuses

PROSPECT

QUALIFIED

PILOT_APPROVED

SETUP_IN_PROGRESS

ACTIVE_PILOT

BASIC_PARTNER

PREMIUM_PARTNER

PAUSED

ENDED

Public-page statuses

DRAFT

PRIVATE_PREVIEW

PILOT_NOINDEX

PUBLIC

PAUSED

ARCHIVED

12. Society contacts

society_contacts

- id

- society_id

- contact_type

- name

- role_title

- phone_encrypted

- email_encrypted

- preferred_channel

- source

- contact_permission_status

- is_primary

- active_from

- active_until

- created_at

- updated_at

Contact types

RWA_PRESIDENT

RWA_SECRETARY

COMMITTEE_MEMBER

FACILITY_MANAGER

SECURITY_SUPERVISOR

FINANCE_CONTACT

EMERGENCY_CONTACT

RESIDENT_CHAMPION

Do not expose this table through public APIs.

13. Replace society_residents with society_memberships

society_memberships

- id

- society_id

- customer_id

- membership_type

- tower

- unit_number_encrypted

- verification_status

- verification_method

- verified_at

- expires_at

- verified_by_user_id

- rejection_reason

- revoked_at

- created_at

- updated_at

Membership types

OWNER

TENANT

FAMILY_MEMBER

AUTHORISED_OCCUPANT

COMMITTEE_MEMBER

FACILITY_STAFF

SECURITY_STAFF

Verification statuses

NOT_STARTED

PHONE_VERIFIED

PROVISIONAL

ADMIN_REVIEW_REQUIRED

VERIFIED

REJECTED

EXPIRED

REVOKED

Verification methods

SIGNED_INVITE_LINK

SOCIETY_CODE

SOCIETY_ADMIN_APPROVAL

DOCUMENT_REVIEW

MANUAL_OPERATIONS_REVIEW

Recommended unique rule:

UNIQUE(society_id, customer_id)

A phone OTP confirms control of a phone number; it does not independently prove residence.

The membership workflow collects personal data such as phone, tower and flat information. PetSaathi should provide a clear notice, limit access and define retention. India’s final DPDP Rules were published on November 14, 2025, with staged commencement dates.

14. Society access rules

society_access_rules

- id

- society_id

- visitor_approval_required

- sitter_registration_required

- allowed_start_time

- allowed_end_time

- approved_gate

- replacement_requires_approval

- emergency_entry_process

- access_notes_private

- effective_from

- effective_until

- verified_at

- verified_by

The public landing page may display:

- General service windows

- Whether pre-registration is required

- Which general gate category is used

It must not publish:

- Entry codes

- Security personal numbers

- Unit-specific instructions

- Access credentials

15. Society service configuration

society_service_configs

- id

- society_id

- service_type_id

- service_status

- booking_cap_per_day

- minimum_notice_minutes

- tracking_required

- report_card_required

- manual_review_required

- effective_from

- effective_until

- created_at

- updated_at

Service statuses

AVAILABLE

LIMITED_AVAILABILITY

WAITLIST

COMING_SOON

TEMPORARILY_PAUSED

NOT_AVAILABLE

This prevents the public page from displaying services that operations cannot currently deliver.

16. Correct pricing architecture

Replace one simple society_pricing table with versioned rules.

society_pricing_rules

- id

- society_id

- service_type_id

- duration_minutes

- currency CHAR(3)

- base_amount_paise INTEGER

- resident_amount_paise INTEGER

- additional_pet_amount_paise INTEGER

- peak_amount_paise INTEGER

- platform_discount_paise INTEGER

- discount_type

- valid_from

- valid_until

- status

- created_by

- created_at

Why store amounts in paise?

Use integers:

₹149 = 14900 paise

This avoids unreliable floating-point monetary calculations.

Offer table

society_offers

- id

- society_id

- offer_code

- title

- discount_type

- discount_value

- minimum_amount_paise

- maximum_discount_paise

- first_booking_only

- maximum_uses

- maximum_uses_per_household

- valid_from

- valid_until

- status

17. Society sitter pool

society_sitter_access

- id

- society_id

- sitter_id

- access_status

- allowed_services

- valid_from

- valid_until

- society_reference

- approved_by

- suspended_reason

- created_at

- updated_at

Access statuses

PENDING

ACTIVE

TEMPORARILY_PAUSED

EXPIRED

REVOKED

Do not copy sitter profile data into this table unnecessarily. Keep the sitter relationship through foreign keys.

18. Society partners

society_partners

- id

- society_id

- partner_id

- partner_type

- status

- service_scope

- valid_from

- valid_until

- last_verified_at

- public_display_allowed

Partner types:

VETERINARY_CLINIC

VETERINARY_PRACTITIONER

GROOMER

TRAINER

BOARDING_HOST

PET_TRANSPORT

19. Society reports

Do not make the report table the source of truth.

Bookings, payments, complaints, reviews and incidents remain authoritative.

The report should be a generated snapshot.

society_report_snapshots

- id

- society_id

- period_start

- period_end

- report_version

- registered_residents_count

- active_customers_count

- booking_requests_count

- paid_bookings_count

- completed_bookings_count

- cancelled_bookings_count

- repeat_customers_count

- gross_booking_value_paise

- platform_revenue_paise

- sitter_payout_paise

- refund_amount_paise

- complaints_count

- incidents_count

- average_rating

- review_count

- report_card_completion_rate

- on_time_rate

- access_success_rate

- generated_at

- generated_by

Recommended uniqueness:

UNIQUE(society_id, period_start, period_end, report_version)

Prisma supports compound unique constraints, which are appropriate for records whose uniqueness depends on multiple fields.

20. Next.js page architecture

Your original pages:

/societies

/societies/[city]

/societies/[slug]

should be changed to:

/societies

/societies/[city]

/societies/[city]/[societySlug]

This avoids slug collisions such as two societies named “Green Acres” in different cities.

Next.js App Router supports dynamic segments such as [city] and [societySlug], and passes those values to pages, layouts, Route Handlers and generateMetadata.

Recommended files

app/

├── societies/

│   ├── page.tsx

│   ├── [city]/

│   │   ├── page.tsx

│   │   └── [societySlug]/

│   │       ├── page.tsx

│   │       ├── loading.tsx

│   │       ├── not-found.tsx

│   │       └── opengraph-image.tsx

│

├── customer/

│   └── societies/

│       ├── join/

│       └── [membershipId]/

│

└── admin/

└── societies/

├── page.tsx

└── [id]/

├── page.tsx

├── residents/

├── sitters/

├── pricing/

├── reports/

├── events/

└── settings/

Use generateMetadata() for society-specific titles, descriptions, canonical URLs and social-sharing metadata.

21. Society-page SEO protection

Do not automatically index every society record.

Index only when:

partnership_status is active

AND public_page_status = PUBLIC

AND services are active

AND page contains meaningful local information

Keep draft and low-information pilot pages as:

noindex, follow

Google considers pages created at scale with substantially similar content and little unique value to be potential doorway or scaled-content abuse. Society pages should contain actual local services, operating windows, offers, FAQs, partners and access information.

22. Correct API architecture

Next.js App Router Route Handlers support custom GET, POST, PATCH, DELETE and other HTTP handlers inside the app directory.

Public APIs

GET /api/public/societies

GET /api/public/societies/[city]/[slug]

GET /api/public/societies/[id]/services

GET /api/public/societies/[id]/sitters

GET /api/public/societies/[id]/offers

GET /api/public/societies/[id]/events

GET /api/public/societies/[id]/faqs

These should return only approved public fields.

Resident membership APIs

POST /api/societies/[id]/memberships/start

POST /api/societies/[id]/memberships/verify-phone

POST /api/societies/[id]/memberships/redeem-invite

POST /api/societies/[id]/memberships/submit

GET  /api/me/society-memberships

GET  /api/me/society-memberships/[id]

DELETE /api/me/society-memberships/[id]

Avoid the vague endpoint:

POST /api/societies/:id/join

because joining involves several states and verification actions.

Admin society APIs

POST   /api/admin/societies

GET    /api/admin/societies

GET    /api/admin/societies/[id]

PATCH  /api/admin/societies/[id]

POST   /api/admin/societies/[id]/activate-pilot

POST   /api/admin/societies/[id]/pause

POST   /api/admin/societies/[id]/end

Use PATCH for partial updates rather than replacing the entire society resource with PUT.

Admin membership APIs

GET  /api/admin/societies/[id]/memberships

GET  /api/admin/society-memberships/[membershipId]

POST /api/admin/society-memberships/[membershipId]/approve

POST /api/admin/society-memberships/[membershipId]/reject

POST /api/admin/society-memberships/[membershipId]/revoke

Pricing and offer APIs

GET  /api/admin/societies/[id]/pricing

POST /api/admin/societies/[id]/pricing

PATCH /api/admin/society-pricing/[pricingId]

POST /api/admin/societies/[id]/offers

PATCH /api/admin/society-offers/[offerId]

Report APIs

GET  /api/admin/societies/[id]/metrics

POST /api/admin/societies/[id]/reports/generate

GET  /api/admin/societies/[id]/reports

GET  /api/admin/society-reports/[reportId]

The live metrics endpoint calculates current data.

The report endpoint creates a permanent monthly snapshot.

23. API security rules

Never trust a user-supplied society ID, membership ID or report ID without checking authorization.

OWASP identifies broken object-level authorization as a major API risk: attackers may change an object identifier and gain access to another user’s resource unless every endpoint performs an object-level permission check.

Required checks

Public user

May access:

- Public society page

- Public services

- Public sitter summaries

- Public event details

Verified resident

May access:

- Their society offers

- Resident-only service slots

- Their own membership

- Their own bookings

Society representative

May access:

- Aggregate programme information

- Access roster

- Approved society events

- Membership approval requests only where contractually authorised

May not access:

- Pet medical data

- Individual payment records

- Private media

- Full complaints

- Detailed risk assessments

Admin

Must still have role-specific permissions:

SOCIETY_OPERATIONS

SAFETY_ADMIN

FINANCE_ADMIN

PARTNER_MANAGER

SUPER_ADMIN

Also return different DTOs:

PublicSocietyResponse

ResidentSocietyResponse

SocietyManagerResponse

AdminSocietyResponse

OWASP also warns against exposing sensitive object properties merely because the user may access the underlying record.

24. Correct customer flow

Resident visits society page

↓

Selects “I live in this society”

↓

Phone verification

↓

Invite/admin verification

↓

Society membership becomes VERIFIED

↓

Resident sees private society offers

↓

Creates or selects Pet Profile

↓

Chooses service and slot

↓

System validates service availability

↓

Price calculated server-side

↓

Booking request created

↓

Eligible society sitter assigned

↓

Payment verified

↓

Booking confirmed

↓

Gate-access message prepared

↓

Service completed

↓

Report Card delivered

↓

Review and repeat offer

Important correction

Do not show the sitter pool solely because the user selected a society from a dropdown.

Display resident-only supply after:

society membership = VERIFIED

Public users may see only limited, anonymised sitter summaries.

25. Correct admin flow

Create society

↓

Add contacts

↓

Set access rules

↓

Configure services

↓

Configure pricing

↓

Add approved sitters

↓

Configure resident offer

↓

Preview landing page

↓

Activate pilot

↓

Monitor registrations

↓

Monitor bookings

↓

Generate monthly report

↓

Convert, extend, pause or end partnership

Every significant state change should create:

society_status_history

- society_id

- from_status

- to_status

- changed_by

- reason

- changed_at

Use transactions for state changes that update multiple related records. Prisma documents transaction handling and warns that concurrent writes can create conflicts or unique-constraint failures if they are not coordinated correctly.

26. Validation rules

Society

- Name required

- City required

- Slug unique within city

- Total flats positive

- Pilot end after pilot start

- Public page cannot activate without an active service

- Premium plan requires operations owner

Membership

- Phone verified

- Unit required for resident membership

- Same customer cannot have duplicate active membership

- Revoked membership cannot access resident offers

- Expired membership requires reverification

Pricing

- Amounts non-negative

- Resident price cannot be negative

- valid_until after valid_from

- Only one active overlapping rule for the same society/service/duration

- Currency required

Report

- Period end after period start

- Revenue values non-negative

- Rating between 1 and 5

- Report version unique

- Generated metrics traceable to source records

27. Analytics events

Track:

view_society_page

scan_society_qr

click_society_offer

start_society_verification

complete_society_verification

start_pet_profile

complete_pet_profile

select_society_service

select_society_slot

start_society_booking

submit_society_booking

payment_started

payment_success

service_completed

report_card_viewed

submit_review

click_book_same_sitter

purchase_society_plan

Add:

society_id

campaign_id

service_type

membership_status

offer_id

Do not send:

- Flat number

- Phone number

- Pet medical details

- Emergency contacts

- Full address

to analytics systems.

28. Minimum implementation sequence

Sprint 1 — Database

- Societies

- Contacts

- Memberships

- Services

- Pricing

- Offers

- Sitter access

- Reports

Sprint 2 — Admin

- Society list

- Society detail

- Service configuration

- Pricing

- Membership review

- Sitter roster

- Report dashboard

Sprint 3 — Public pages

- Society directory

- City page

- Society landing page

- Public services

- QR campaigns

Sprint 4 — Resident verification

- Phone verification

- Signed invitation

- Admin approval

- Membership status

- Resident-only offers

Sprint 5 — Booking integration

- Society price

- Society sitter pool

- Access instructions

- Society booking capacity

- Booking snapshot

Sprint 6 — Reporting and QA

- Monthly reports

- Access tests

- Privacy tests

- Analytics

- Performance

- Pilot readiness

29. Definition of done

Marketing assets

- Poster claim matches actual service.

- Trial terms are visible.

- Society name/logo usage is authorised.

- QR points to the correct society page.

- Emergency wording is accurate.

- Resident privacy is not exposed.

- Asset source and campaign are trackable.

Database

- Society contacts are separate.

- Membership verification is versioned.

- Pricing has effective dates.

- Monetary values use integer units.

- Reports distinguish GMV, revenue and payouts.

- Foreign keys and unique constraints exist.

- Status history is auditable.

API

- Public APIs return public fields only.

- Every ID-based endpoint checks authorization.

- Membership workflow has separate endpoints.

- Admin roles are separated.

- Sensitive properties are filtered.

- Invalid state transitions are rejected.

Pages

- URL includes city and society.

- Society services are genuinely active.

- Resident offers require verification.

- Unsupported services show waitlist or unavailable.

- Thin draft pages are not indexed.

- Mobile conversion works.

Customer journey

- Resident verification works.

- Pet Profile is reusable.

- Society price is server-calculated.

- Sitter matching uses society-access status.

- Payment is required before confirmation.

- Report Card and review work.

- Repeat booking is simple.

Final operating principle

Society marketing should make one accurate promise, while the technical architecture ensures that only verified residents receive society benefits, only eligible sitters receive assignments and only authorised users see private information.

Simple explanation for professor

“PetSaathi will create society-specific posters, brochures and QR codes to help residents discover local dog walking and pet-sitting services.

Each QR code will open a personalised society page rather than the generic homepage. Residents will see the active services, society offer, sitter information, booking process and support contact.

The technical system will contain a main society record, but contacts, residents, pricing, sitters and reports will be stored in separate tables. This prevents one large table from becoming difficult to maintain.

Residents will not become verified simply by typing a flat number. They will verify their phone and then use a society invitation, code or admin approval. Only verified residents will see private offers and resident-only service slots.

The pricing system will store prices in paise and include effective dates, discounts and service duration. Monthly reports will separately show booking value, PetSaathi revenue, sitter payouts, refunds, ratings and complaints.

The public society page will use a city and society URL such as /societies/ahmedabad/green-acres-bopal. Draft or incomplete pages will not be indexed.

Every API will check whether the user is authorised to access the requested society, membership or report. Public APIs will return only public information, while resident and admin APIs will return different protected data.

The complete customer journey will be society selection, resident verification, Pet Profile, service selection, payment, sitter assignment, gate access, service completion, Report Card and repeat booking.”

PetSaathi Phase 7 — Final Deliverables and Upgrade Decisions 🏢🐾

Executive decision

Phase 7 should finish with a repeatable society partnership operating system, not merely a pitch deck and several society contacts.

The completed system should support this full journey:

Society identified

↓

Decision-maker contacted

↓

Resident demand validated

↓

Pilot agreement signed

↓

Society page and gate protocol configured

↓

Residents register voluntarily

↓

Paid bookings completed

↓

Report Cards and reviews collected

↓

Pilot results reported

↓

Society converts to a paid package

Recommended final target

- 5–10 signed pilot societies

- 3–5 fully active societies at the same time

- Remaining signed societies launched in controlled batches

- At least one society converted to a paid partnership

- No unresolved critical safety, privacy or gate-access issue

Launching all ten simultaneously could overload sitter capacity, support and society-access operations.

1. Society pitch deck

Purpose

Give RWA members, facility managers and committee members a clear five-to-ten-minute explanation of:

- The society-level problem

- PetSaathi’s service model

- Stakeholder benefits

- Safety controls

- Pilot offer

- Packages and pricing

- Launch process

- Evidence and next step

Required slides

- Problem

- PetSaathi solution

- Benefits for pet parents, management, security and residents

- Verification and safety system

- Active services

- No-fee pilot

- Paid packages

- Launch process

- Actual results or pilot success measures

- Call to action

Acceptance criteria

- No unsupported claims such as “100% safe” or “guaranteed sitter.”

- Veterinary services are described as partner-led coordination.

- “Free pilot” clearly means no society partnership fee; individual bookings remain paid.

- Pricing matches the website, proposal and agreement.

- Case-study data is real and traceable.

ASCI’s code requires advertising claims to be truthful and not misleading through exaggeration, implication or omission.

2. Society package pricing

The commercial ladder should be finalised before further outreach.

| Package | Recommended price | Best for |
| --- | --- | --- |
| No-Fee Society Pilot | ₹0 society fee for 21–30 days | New qualified societies |
| Basic Society Partner | ₹5,000–₹15,000/month + tax | Societies with repeat demand |
| Premium Pet-Care Desk | ₹15,000–₹50,000/month + tax | Large premium communities |
| Event/Camp Programme | Event-specific | Lead acquisition and activation |

Residents should continue to pay separately for the services they book.

Pricing document must define

- Society fee

- Resident prices

- Discount funding

- Sitter payouts

- Event or partner costs

- Taxes

- Refund responsibility

- Support hours

- Included volume

- Extra-work charges

- Renewal and termination terms

Where PetSaathi is required to issue a taxable service invoice, CBIC rules prescribe invoice particulars and generally require service invoices within 30 days of supply. Final GST treatment should be confirmed with a chartered accountant.

3. Society CRM

Purpose

Create one source of truth for sales, setup, pilots and paid partnerships.

Required pipeline

IDENTIFIED

QUALIFIED

CONTACTED

REPLIED

DISCOVERY_SCHEDULED

DISCOVERY_COMPLETED

RESIDENT_SURVEY

PROPOSAL_SENT

COMMITTEE_REVIEW

PILOT_APPROVED

SETUP_IN_PROGRESS

ACTIVE_PILOT

CONVERTED

NURTURE

LOST

Required data groups

Society profile

- Name

- City and area

- Towers and estimated homes

- Occupancy confidence

- Estimated pet families

- Geographic cluster

Contacts

- Resident champion

- Facility manager

- RWA/AOA contact

- Contact source

- Communication preference

- Opt-out/do-not-contact status

Operational suitability

- Nearby walkers

- Backup capacity

- Pet sitters

- Veterinary partners

- Gate complexity

- Peak-slot capacity

Commercial information

- Recommended package

- Potential demand

- Likely hero service

- Objections

- Proposal value

- Decision timeline

CRM control

- Owner

- Current stage

- Last interaction

- Next action

- Next-action date

- Lost reason

Acceptance criteria

Every active opportunity has:

One owner

+ one stage

+ one next action

+ one deadline

Contact and resident data must be purpose-limited and access-controlled. India’s final DPDP Rules were published on November 14, 2025, with staged commencement provisions.

4. Society landing-page template

Recommended route

/pet-care/societies/[city]/[society-slug]

Required sections

- Society name and partnership status

- Active services

- Local sitter summaries

- Resident offer

- Booking CTA

- How booking works

- Verification and safety controls

- General gate procedure

- Report Card preview

- Emergency coordination

- Society-specific FAQs

- Local veterinary/grooming partners

- Privacy, refund and support links

Public/private separation

Public

- Service availability

- General service windows

- Public sitter summaries

- Resident offer

- Support information

Authenticated residents only

- Flat or unit

- Exact booking

- Assigned sitter

- Pet Profile

- Report Card

- Photos and GPS information

Society management

- Aggregate bookings

- On-time rate

- Access problems

- Complaint totals

- Programme status

SEO requirement

Society pages should become mandatory for active partners, but only when each page contains genuine local information. Publishing hundreds of pages where only the society name changes could be treated as doorway or scaled-content abuse by Google.

Use:

DRAFT/PILOT incomplete page → noindex

ACTIVE complete page → indexable

ENDED page → redirect or archive appropriately

Do not mark a society address as a PetSaathi LocalBusiness location unless PetSaathi genuinely operates a business branch there; Google’s local-business markup is intended to describe actual business locations and operating details.

5. Society outreach scripts

Required script library

- RWA/committee WhatsApp message

- Facility-manager message

- Formal email

- LinkedIn introduction

- Resident champion request

- Pet-parent group announcement

- Veterinary/pet-shop referral message

- Three follow-ups

- Opt-out reply

- Discovery-call agenda

Messaging rules

Every script should clarify:

- What “verified” means

- Which services are active

- Whether boarding is beta

- That veterinary services are partner-led

- That residents pay for booked services

- That availability is not guaranteed

- What the recipient should do next

WhatsApp business messages require prior user opt-in. The opt-in should identify PetSaathi and the reason messages will be sent.

Acceptance criteria

- No bulk cold WhatsApp outreach.

- No imported resident phone lists.

- Every message is society-specific.

- Declines and opt-outs are respected.

- The CTA requests one action, usually a 15-minute discussion.

6. Society pilot agreement

Purpose

Define the legal and operational relationship before residents are onboarded.

Required clauses

- Parties and authorised representatives

- Pilot start and end dates

- Active services

- Society fee and resident payments

- Sitter assignment authority

- Resident registration process

- Security and gate coordination

- Complaint escalation

- Incident and emergency protocol

- Data protection and reporting

- Branding permission

- Partner-led veterinary/grooming services

- Refund and cancellation responsibilities

- Suspension and termination

- No automatic renewal

- No guarantee of zero risk

Critical positioning clause

PetSaathi is a pet-care service and coordination platform. It is not an animal-control authority and will not enforce blanket pet bans, remove community animals or determine society pet-ownership rules.

AWBI’s published guidance states that RWAs and apartment-owner associations should not impose blanket bans on residents keeping pet dogs. PetSaathi’s agreement should support responsible coexistence rather than pet-control demands.

The final agreement should be reviewed by an Indian lawyer familiar with the society’s state, legal structure and local rules.

7. Society booking flow

This deliverable should be upgraded from recommended to required.

A society partnership cannot work reliably without a defined booking flow.

Required customer journey

Select society

↓

Verify resident membership

↓

Create/select Pet Profile

↓

Choose society-supported service

↓

Select date/time

↓

System checks capacity and eligibility

↓

Sitter assigned

↓

Payment verified

↓

Booking confirmed

↓

Gate entry prepared

↓

Service completed

↓

Report Card delivered

Key requirements

- Society ID is attached automatically.

- Resident offers are validated server-side.

- Only active society services appear.

- Unavailable slots show waitlist or pause status.

- Flat/unit is visible only to authorised operational users.

- Gate message is generated only after confirmation.

- Booking history preserves the society and pricing snapshot.

8. Society-specific offers

Required offer types

- First dog walk at ₹99–₹149

- Free first meet-and-greet

- Five-walk starter plan

- Same-sitter preference

- Society event offer

- Festival-care early booking

- Resident package price

Offer data

society_id

offer_code

eligible_service

discount_type

discount_value

valid_from

valid_until

usage_limit

household_limit

funding_source

status

Acceptance criteria

- One offer per eligible household where applicable.

- Final checkout clearly shows original and discounted price.

- Real capacity exists for the advertised offer.

- “From ₹99” is used only where a genuine ₹99 booking is available.

- No artificial price inflation.

9. Gate and security protocol

This should be mandatory for every active partner society.

Required sitter entry record

- Sitter display name

- Current photograph

- PetSaathi sitter ID

- Phone or controlled contact

- Verification/access status

- Booking ID

- Resident/tower/unit

- Service type

- Scheduled time

- Entry validity

- PetSaathi operations contact

Recommended gate workflow

Booking confirmed

↓

Resident receives confirmation

↓

Security receives approved entry details

↓

Sitter identity matched at gate

↓

Entry recorded

↓

Service starts

↓

Exit recorded where required

Replacement rule

A replacement sitter must not arrive with only a WhatsApp explanation.

The system should:

- Remove or close the previous assignment.

- Approve the replacement.

- Update society access.

- Notify the resident.

- Issue a new gate message.

- Preserve assignment history.

Privacy correction

Avoid displaying full emergency contacts or extensive resident information in a gate message.

Safer template

PetSaathi service entry
Sitter: [Name]
PetSaathi ID: [ID]
Booking: [Booking ID]
Tower/Unit: [Tower and Unit]
Service: [Service]
Approved window: [Start–End]
Verification: [Active]
Support: [PetSaathi operations number]

10. Society pet-care posters and brochures

Required assets

- Lobby poster

- WhatsApp poster

- QR booking poster

- Digital society-app graphic

- One-page brochure

- Event poster template

Recommended messaging

Poster headline

Screened dog walkers now available for your society 🐾

Supporting line

Book local dog walks and in-home pet sitting with service updates and a Pet Report Card.

CTA

Scan to view resident services and book your first eligible walk from ₹99.

Avoid

- “Completely safe”

- “100% verified”

- “Guaranteed walker”

- “Emergency vet always available”

- “Free care”

Marketing materials must accurately explain limitations and material conditions; misleading implications or omissions can violate advertising standards.

11. Event and camp model

Decision

Include it in Phase 7, but treat it as a controlled acquisition channel, not a requirement for every society.

Recommended events

- Veterinary-partner health-check camp

- Registered-veterinarian vaccination camp

- Grooming day

- Dog-walking trial day

- Pet-parent meetup

- Humane puppy-care/training workshop

- Seasonal safety session

Partner responsibility

PetSaathi manages:

- Registration

- Society permission

- Communication

- Scheduling

- Payment coordination

- Support

- Follow-up conversion

Qualified partners manage:

- Veterinary examination

- Vaccination

- Grooming

- Training delivery

- Specialist records

The Indian Veterinary Council Act regulates veterinary practice and the registered-practitioner framework. Medical and vaccination camps should therefore be controlled by appropriately registered veterinary practitioners.

Acceptance criteria

- Professional partner verified.

- Written responsibility split exists.

- Resident consent is collected.

- Capacity and safety plan exist.

- Pricing and refunds are clear.

- Event data is not automatically shared with sponsors.

- Attendees are offered an opt-in PetSaathi follow-up.

- Event attendance and paid-booking conversion are measured separately.

12. Society reporting template

Decision

Reporting should be mandatory, but frequency depends on partnership stage.

During pilot

Provide an end-of-pilot report.

Paid Basic/Premium partnership

Provide a monthly report.

Required report sections

Demand

- Resident leads

- Verified residents

- Active paying customers

- Pet Profiles completed

Service use

- Booking requests

- Paid bookings

- Completed services

- Top service

- Repeat customers

- Packages active

Reliability

- On-time rate

- Report Card completion

- Replacement count

- Security-entry success

- Support response

Quality and safety

- Average rating and review count

- Complaint totals by category

- Incidents by severity

- Open corrective actions

- Lost-pet alerts

- Event feedback

Commercial value

- Resident GMV

- PetSaathi service contribution

- Society subscription

- Discounts

- Refunds

- Event income

- Net contribution

Privacy rule

The society report should be aggregated by default. It should not include:

- Resident names

- Flat numbers

- Medical records

- Bite histories

- Private media

- Full GPS routes

- Emergency contacts

- Detailed complaint narratives

DPDP obligations are being introduced on staged timelines, but designing reports around data minimisation and access control is the safest operating standard now.

13. First 5–10 pilot societies

Recommended interpretation

| Phase 7 outcome | Target |
| --- | --- |
| Signed pilots | 5–10 |
| Fully configured | 5–8 |
| Simultaneously active | 3–5 |
| Producing paid bookings | 3–5+ |
| Converted to paid plan | 1–3 |

Pilot quality gates

A society counts as successful only when it has:

- Signed authorisation

- Active landing page

- Resident announcement

- Sitter capacity

- Working gate protocol

- Resident registrations

- Paid bookings

- Completed services

- Report Cards

- Society feedback

A logo or memorandum without resident activity is not a successful pilot.

Upgrade decisions

Upgrade 1 — Society-specific landing pages

Decision: Approve with conditions

Make a custom page mandatory for:

- Active pilots

- Paid partner societies

- Event-only societies where public registration is needed

Do not require a public indexable page for every prospect.

Conditions

- Real local services

- Real availability

- Real resident offer

- Real FAQs and access rules

- Unique society information

- Private data excluded

- Draft pages use noindex

Reason

A proper page improves trust and conversion. It may also support local discovery, but SEO should be treated as a secondary benefit. Google warns against large collections of substantially similar location pages created mainly for search rankings.

Upgrade 2 — 30-day free pilot before a paid plan

Decision: Approve as the default, not an absolute rule

Recommended default:

21–30 day no-fee society pilot

Use a pilot when

- Society has not worked with PetSaathi before.

- Resident demand is uncertain.

- Gate/access needs testing.

- Sitter density is unproven.

- Committee needs evidence.

Allow exceptions when

- A large property-management company requests a paid rollout.

- A society already has strong verified resident demand.

- The society only purchases an event/camp.

- A developer or employer funds the programme.

- The work requires substantial custom setup.

Conversion rule

Do not extend the pilot indefinitely.

At the end, choose:

CONVERT_TO_PAID

EXTEND_ONCE_WITH_REASON

PAUSE_AND_FIX

END_PILOT

Upgrade 3 — Society gate protocol

Decision: Approve and make mandatory

No society should be marked operationally active without:

- Access requirements

- Approved sitter roster

- Booking-proof format

- Replacement process

- Revocation process

- Security contact

- Emergency escalation

- Entry-data retention rule

Reason

A booking has operationally failed when the confirmed sitter cannot enter the property, even when the customer, payment and sitter are otherwise ready.

Upgrade 4 — Society pet-care report

Decision: Approve with stage-based frequency

| Partnership stage | Reporting requirement |
| --- | --- |
| No-fee pilot | End-of-pilot report |
| Pilot longer than 30 days | Monthly interim report |
| Basic Partner | Monthly report |
| Premium Desk | Monthly report plus review meeting |
| Event-only | Event performance report |

Reason

Reporting provides evidence for:

- Paid conversion

- Renewal

- Pricing

- Capacity planning

- Complaint management

- Resident value

- Society return on the partnership

Reports must remain aggregated and privacy-controlled.

Upgrade 5 — Event/camp acquisition

Decision: Approve as a selective Phase 7 channel

Do not make events mandatory for every society.

Use them when:

- Offline trust matters.

- Resident awareness is low.

- A strong local partner exists.

- The society wants community activation.

- Recurring service demand needs stimulation.

Do not use them when:

- Core booking operations are unstable.

- No qualified partner exists.

- Events would overload support staff.

- The society expects medical services from PetSaathi staff.

- Event economics are negative with no credible follow-up conversion.

Priority order

- Dog-walking trial day

- Pet-parent orientation

- Grooming day

- Veterinary-partner health session

- Vaccination camp with registered veterinary control

- Training/puppy workshop

Final approved Phase 7 requirements

| Deliverable | Final decision |
| --- | --- |
| Society pitch deck | Required |
| Society package pricing | Required |
| Society CRM | Required |
| Society landing-page template | Required |
| Society outreach script | Required |
| Society pilot agreement | Required |
| Society booking flow | Required |
| Society-specific offers | Required |
| Gate/security protocol | Required |
| Society posters | Required |
| Event/camp model | Required as an available channel |
| Society reporting | Required |
| First 5–10 signed pilots | Required target |
| 3–5 simultaneous active pilots | Recommended operating limit |
| At least one paid conversion | Required Phase 7 proof |

Phase 7 definition of done

Phase 7 is complete only when:

Sales system

- Packages are approved.

- Pricing is consistent.

- CRM stages work.

- Outreach is personalised and permission-based.

- Pitch and proposal claims are supportable.

Product system

- Society pages work.

- Resident verification works.

- Society offers work.

- Society booking and pricing snapshots work.

- Public/private data separation works.

Operations

- Gate protocols are active.

- Local sitter pools have backup capacity.

- Booking caps prevent overload.

- Support and incident escalation work.

- Events have qualified partners.

Reporting and economics

- Pilot reports are generated.

- GMV and PetSaathi revenue are not confused.

- Society subscriptions and booking contributions are separated.

- Complaints and incidents are measurable.

- At least one society demonstrates positive or improving contribution.

Partnership proof

- Five to ten societies have signed pilots.

- Three to five produce real paid activity.

- Residents complete services and submit reviews.

- Repeat demand exists.

- At least one society agrees to continue under a paid package.

Final operating principle

Phase 7 succeeds when PetSaathi can repeatedly acquire, launch, operate, measure and convert apartment societies without compromising service quality, privacy or lawful pet ownership.

The win is not ten society logos.

It is:

Active residents

+ reliable local sitters

+ successful gate entry

+ completed paid services

+ repeat demand

+ measurable reporting

+ paid society renewals

Phase 7 Society Partnership Report

End-to-End Strategy, Operating Model and Go/No-Go Framework

Executive decision

Phase 7 should be approved—with several important modifications.

The society-first strategy is stronger than ordinary local advertising because a residential society can become all of the following simultaneously:

- A concentrated customer-acquisition channel

- A controlled operating zone

- A trust and verification layer

- A recurring-booking cluster

- A sitter-supply territory

- A referral network

- A service-quality data unit

The original concept already identifies society partnerships, verified caregivers, GPS tracking, report cards and emergency support as core differentiators.

However, Phase 7 must not be measured only through total leads, bookings and ratings. It must prove that multiple individual societies can produce repeatable, contribution-positive demand without creating security, safety or resident-conflict problems.

Final Phase 7 verdict

Build a society operating system, not an RWA advertising campaign.

1. Why society-first growth can work

India’s urban pet-care demand is being supported by rising pet ownership, pet humanisation, nuclear households and increased spending on pet health and services. Purina cites reports estimating that household pets in India increased from approximately 26 million in 2019 to 32 million in 2024, while IBEF identifies urbanisation, higher spending and changing attitudes toward companion animals as major industry drivers.

The society model adds something that city-wide advertising cannot provide: geographic density.

When five customers live in one building cluster:

- A sitter can complete more bookings with less travel.

- A backup caregiver can arrive quickly.

- Residents can refer other residents.

- Security personnel recognise approved caregivers.

- Service quality becomes visible through community reputation.

- Customer acquisition can be shared across many households.

- Repeat walks can be organised into efficient schedules.

This is why the society itself should be treated as a micro-market.

2. Phase 7 autopsy: what the original framework gets right

Strong elements

| Element | Assessment |
| --- | --- |
| Society-specific landing pages | Strong acquisition and attribution mechanism |
| Verified local sitter pools | Essential for trust and service reliability |
| Resident introductory offers | Useful when controlled |
| Gate and security protocol | Mandatory operational infrastructure |
| Pet-care camps | Strong resident activation mechanism |
| Monthly society reports | Useful for RWA confidence and renewal |
| Thirty-day pilots | Long enough to test first bookings and early repeats |
| Paid society partnerships | Valuable, but not realistic for every society |
| Repeat customers | More important than total registrations |
| Lower CAC than advertisements | Correct ultimate win condition |

The strategic direction is correct. The weakness is mainly in definitions, measurement discipline and commercial structure.

3. Hidden weaknesses exposed

3.1 “Free society pilot” is dangerously ambiguous

A free pilot should mean:

No setup or partnership fee for the RWA.

It should not mean:

Free dog walking, sitting or boarding for every resident for 30 days.

Unlimited free services would test demand for free care—not willingness to pay.

Correct pilot structure

- RWA pays no partnership fee during the pilot.

- Residents pay for services.

- New residents may receive one limited introductory discount.

- The platform places a fixed ceiling on promotional expenditure.

- Sitters still receive proper compensation.

- Refunds and discounts are recorded separately.

- Conversion is measured using full-price or near-full-price bookings.

Recommended introductory offer:

- ₹100–₹200 first-booking discount, or

- One discounted trial walk, or

- Free meet-and-greet followed by paid service

Do not provide unlimited free pet care.

3.2 Total results can hide weak societies

Suppose Phase 7 reports:

- 250 leads

- 120 bookings

- 35 repeat customers

That can appear successful even when one society generated 80% of the results and every other society failed.

Therefore, Phase 7 must measure:

- Total results

- Median results per society

- Best society

- Worst society

- Mature-society results

- Concentration of bookings

- Contribution margin by society

A society model is repeatable only when at least two or three societies perform independently.

3.3 “Pet parent lead” requires a strict definition

A person who scans a QR code is not necessarily a qualified lead.

Recommended lead stages

| Stage | Definition |
| --- | --- |
| Reach | Resident saw an announcement, poster or event |
| Inquiry | Resident opened the page or contacted the team |
| Registered lead | Resident submitted contact details with consent |
| Qualified pet lead | Resident has a pet and selected a required service |
| Booking-ready lead | Resident selected an expected date or frequency |
| Paying customer | Completed at least one paid booking |
| Repeat customer | Completed another paid booking within the defined period |

Your Phase 7 target of 200+ leads should mean qualified pet-parent leads, not page visits or event attendees.

3.4 RWA subscriptions may be harder than expected

Most RWAs will ask:

“Why should the society pay for a service used only by some residents?”

A society subscription therefore needs to provide society-level value—not merely individual pet-care bookings.

Three commercial models

| Model | Who pays? | Recommended use |
| --- | --- | --- |
| Resident-paid marketplace | Residents | Default model |
| Sponsored community programme | Pet brand, veterinary partner or local sponsor | Events and initial acquisition |
| Paid society care plan | RWA, facility manager or developer | Premium communities needing dedicated coverage |

A paid society plan must include

- Dedicated local caregiver availability

- Defined backup response

- Monthly pet-care camp or clinic

- Gate-approved caregiver roster

- Resident support hotline

- Incident escalation

- Aggregate monthly report

- Preferential resident pricing

- Community pet-awareness sessions

- Optional emergency-care coordination

Do not expect societies to pay merely for being listed as partners.

3.5 Events can produce vanity metrics

A pet camp may attract:

- Children

- Non-pet-owning residents

- People looking for free veterinary advice

- Residents collecting giveaways

- Existing customers who would have booked anyway

Therefore, an event should be measured as a conversion funnel:

Attendees→Qualified pet leads→First paid bookings→30-day repeat customers

An event is successful only if it produces paying, retained customers at an acceptable acquisition cost.

3.6 Rating alone is insufficient

An average rating of 4.8 from five reviews is much weaker evidence than a rating of 4.65 from 100 verified bookings.

Track:

- Average rating

- Number of ratings

- Rating participation rate

- Percentage of five-star ratings

- Percentage below four stars

- Complaint rate

- Refund rate

- Serious incident count

Only reviews attached to completed bookings should count.

3.7 Phase 8 is too broad

Adding grooming, veterinary care, training and pet taxi simultaneously would recreate the original problem of excessive scope.

Phase 8 should add one adjacent service at a time, selected using Phase 7 customer-request data.

A better order is:

- Grooming-at-home or training

- Veterinary booking or teleconsultation through licensed partners

- Pet taxi

- Other specialist services

The chosen service should first launch in two or three proven societies—not throughout the city.

4. Approval decision on the five rules

| Rule | Decision | Required modification |
| --- | --- | --- |
| Society-specific landing pages | Approve | One unique page and attribution code per society |
| 30-day free society pilot | Approve conditionally | Free for the RWA; resident services remain paid |
| Mandatory gate/security protocol | Approve—hard requirement | No society launches without a signed access SOP |
| Monthly society report | Approve | Use aggregate, privacy-safe reporting |
| Event/camp acquisition | Approve as an experiment | Test against non-event societies and measure CAC |

Final rule recommendation

Approve all five, but rewrite the pilot rule as follows:

“Thirty-day zero-setup-fee society pilot with paid resident bookings, limited introductory incentives and predefined conversion criteria.”

5. Ideal target society profile

Do not begin with every society in the city.

Best initial society type

The best Phase 7 target is likely to be:

- 500–1,500 occupied units

- Gated access and organised security

- Active managing committee or professional facility manager

- Concentration of working professionals and families

- Existing pet-owning community

- Clubhouse or event area

- Reasonable acceptance of pets

- Multiple nearby societies within a 3–5 km service radius

- No severe unresolved pet-related conflict

- Easy access to a veterinary clinic

- Ability to send official resident communications

This is an operating hypothesis. Phase 7 data should confirm or reject it.

Society scoring model

Score each potential society out of 100.

| Factor | Weight |
| --- | --- |
| Number of occupied households | 15 |
| Estimated pet-parent density | 20 |
| Resident spending capacity | 10 |
| RWA responsiveness | 10 |
| Gate/access feasibility | 10 |
| Existing pet community | 10 |
| Event-space availability | 5 |
| Nearby sitter supply | 10 |
| Nearby veterinary support | 5 |
| Nearby society cluster | 5 |

Priority levels

- 75–100: Priority A

- 60–74: Priority B

- Below 60: Do not prioritise during Phase 7

6. Society acquisition engine

The society acquisition system has two separate funnels:

Funnel A: acquiring the society

Society identified→Decision-maker contacted→Meeting→Pilot approval→Launch→Paid renewal

Funnel B: acquiring residents inside the society

Resident reached→Qualified pet lead→First paid booking→Repeat booking→Subscription→Referral

These funnels should not be mixed.

Recommended society acquisition channels

1. Resident pet champion

A resident introduces the company to the managing committee.

This is likely to be the strongest route because it transfers existing trust.

Offer the champion:

- Referral credits

- Early access

- Free meet-and-greet

- Recognition as a community pet coordinator

- No authority over complaints or sitter approval

2. Veterinary and grooming partners

Local veterinary clinics and grooming providers often already know clusters of nearby pet owners.

Use them for:

- Warm introductions

- Camp participation

- Emergency support

- Joint educational sessions

- Resident offers

3. Facility-management companies

Large societies may be operated by professional facility-management teams rather than volunteer committees.

Your pitch should focus on:

- Approved vendor roster

- Access control

- Complaint handling

- Safety procedures

- Reporting

- Reduced administrative effort

4. Society management platforms

Common society-management platforms support visitor management, pre-approved daily help, attendance records, resident communication and gate processes. This shows that a digitally controlled caregiver-entry workflow is compatible with existing community operations, although any actual integration would require the relevant society and platform’s approval.

5. Cold RWA outreach

Cold email and messaging should be used primarily to create meetings—not to close partnerships.

Cold outreach should contain:

- One clear community benefit

- One-page safety framework

- Pilot structure

- No-obligation 20-minute meeting

- Local caregiver availability

- Existing resident request, where applicable

7. The correct RWA value proposition

Do not pitch:

“We need access to sell pet services to your residents.”

Pitch:

“We provide a controlled, verified system for residents who already need pet care, with approved caregivers, gate procedures, service accountability and a single escalation channel.”

What the RWA actually cares about

- Who enters the society?

- Has the person been verified?

- Who is accountable if something happens?

- Will dogs be leashed?

- Who cleans pet waste?

- Will residents complain?

- Will commercial solicitation become uncontrolled?

- Is the society legally exposed?

- Can access be suspended immediately?

- Will resident data be misused?

- Will the provider create conflict between pet and non-pet residents?

The sales presentation must answer these before discussing discounts or revenue.

8. RWA objection-response framework

| RWA objection | Correct response |
| --- | --- |
| “We do not want unknown workers entering.” | Use an approved caregiver roster, ID verification, pre-authorised entry and attendance logs |
| “What if a dog bites someone?” | Behaviour screening, leash rules, handler matching, incident SOP and emergency escalation |
| “Who will clean pet waste?” | Walkers carry disposal bags and must document compliance |
| “The society may become liable.” | Define responsibility contractually; obtain legal review and appropriate insurance |
| “Residents will complain about noise.” | Service-hour rules, designated routes and complaint escalation |
| “We do not permit advertising.” | Use only committee-approved messages and events |
| “Do not share resident data.” | Collect resident consent directly and provide only anonymised aggregate reports |
| “We already have local dog walkers.” | Offer verification, backup coverage, tracking and accountability rather than forced replacement |
| “We do not want exclusivity.” | Do not require exclusivity during the pilot |
| “Why should the RWA pay?” | Begin with the resident-paid model; offer a paid plan only for additional society-level services |

AWBI guidance states that societies should not impose blanket bans on pets or prevent pets from using lifts, while also advising pet owners and caregivers to maintain cleanliness, vaccinations and leashing in public areas. The more recent AWBI SOP also emphasises leashing and basic command training. Your RWA approach should therefore be cooperative and safety-focused rather than confrontational.

9. Society-specific landing page

Each society should receive its own URL:

petsaathi.in/society/society-name

Required page sections

Society identity

- Society name

- Target area

- Partnership or pilot status

- Society-specific referral code

- Pilot validity period

Available services

- Dog walking

- In-home pet visits

- Meet-and-greet

- Emergency coordination

- Later services only when approved

Local caregiver pool

Display:

- First name

- Photograph

- Verification level

- Pet-handling experience

- Service availability

- Supported dog sizes

- Languages

- Rating

- Number of completed verified bookings

Do not publicly reveal:

- Full personal address

- Government ID

- Personal phone number

- Police documents

- Unmasked emergency contacts

Resident offer

- Exact discount

- Eligibility

- Expiration

- Cancellation conditions

- Whether the offer is platform-funded or partner-funded

Trust and safety

- Identity and background-check status

- Leash policy

- Waste-cleanup policy

- Check-in procedure

- GPS/report-card information

- Complaint contact

- Emergency protocol

Booking flow

- Society and tower

- Pet profile

- Behaviour disclosures

- Requested service

- Date and time

- Care instructions

- Emergency contact

- Veterinary details

- Payment

- Consent

Attribution

Every booking must store:

- Society ID

- Acquisition channel

- Campaign or event ID

- Resident referral

- First-contact date

- First-booking date

Without attribution, society CAC cannot be calculated accurately.

10. Society-specific sitter pool

A local sitter pool should not merely be a collection of available profiles.

It must be a coverage system.

Recommended starter configuration

For each active society or tightly grouped society cluster:

- 2–4 primary caregivers

- At least one backup caregiver

- One operations escalation contact

- One veterinary partner

- Defined morning and evening coverage

- Capability mapping by dog size and behaviour

Sitter capability matrix

| Capability | Example levels |
| --- | --- |
| Dog size | Small / medium / large |
| Behaviour | Calm / anxious / reactive |
| Service | Walking / sitting / medication support |
| Availability | Morning / afternoon / evening |
| Experience | Beginner / trained / advanced |
| Access | Society-approved / pending |
| Emergency training | Completed / pending |
| Languages | English / Hindi / local language |

Supply metrics

Track:

- Available sitter hours

- Booked sitter hours

- Peak-period utilisation

- Backup fill rate

- Travel time between bookings

- Sitter cancellation rate

- Sitter earnings

- Sitter retention

A starting planning heuristic is to maintain approximately 1.5 times the required sitter capacity during peak pilot periods. This should be recalibrated using actual demand.

11. Mandatory gate and security protocol

This is not merely a guard instruction sheet. It is a complete chain of authorisation.

Gate protocol flow

Before the first booking

- RWA approves the pilot.

- Approved caregiver roster is shared securely.

- Each caregiver receives a society-specific ID.

- Guards receive a briefing.

- Resident entry-authorisation method is confirmed.

- Escalation phone numbers are displayed at the gate desk.

Before each visit

- Booking is confirmed.

- Resident receives sitter details.

- Resident pre-approves entry.

- Caregiver receives booking ID or QR code.

- The system confirms time window and permitted tower.

At entry

- Caregiver presents official ID.

- Guard matches caregiver against the approved roster.

- Resident confirms entry through OTP, call or society app.

- Entry time is logged.

- Any mismatch is escalated—not manually bypassed.

During service

- Caregiver remains within the permitted service area.

- No unrelated guest accompanies the caregiver.

- Dog remains leashed outside the residence.

- Waste bags are carried.

- No dog is handed to another person without authorisation.

- No unapproved pet interaction is permitted.

- No photographs of unrelated residents or flats are taken.

At exit

- Service completion is recorded.

- Dog is returned to the authorised person or residence.

- Exit is logged.

- Any incident is documented before the caregiver leaves.

- Report card is sent to the pet parent.

Gate KPIs

- Entry success rate

- Average gate waiting time

- Entry-denial rate

- Number of manual overrides

- Unauthorised-entry incidents

- Guard escalations

- Caregiver identification failures

Recommended target

- Gate success: 98%+

- Unauthorised entry: Zero

- Unresolved access incidents: Zero

- Manual override rate: Below 5%

12. Pet-care camp model

Purpose

The camp is not merely a public-relations event.

It should accomplish four things:

- Acquire qualified pet-parent leads

- Build trust with non-pet residents and the RWA

- Create pet profiles and first bookings

- Identify common resident needs

Recommended camp stations

Registration desk

- Resident consent

- Pet profile

- Requested service

- Expected service frequency

- Preferred booking date

Veterinary desk

Operated only by appropriately qualified veterinary professionals.

Potential activities:

- General wellness discussion

- Vaccination-record review

- Nutrition awareness

- Parasite-control education

- Emergency-preparedness guidance

Clinical services and medical claims should remain under the responsibility of the licensed veterinary provider.

Behaviour and safety desk

- Leash demonstration

- Basic walking etiquette

- Pet anxiety discussion

- Safe introductions

- Children-and-pet awareness

Caregiver introduction zone

- Meet local caregivers

- Explain verification levels

- Demonstrate report cards

- Demonstrate tracking and check-in

Booking desk

The resident should be able to:

- Complete a pet profile

- Select a caregiver

- Book a meet-and-greet

- Schedule the first paid service

- Purchase a recurring plan

Event measurement

| Metric | Formula |
| --- | --- |
| Qualified-lead rate | Qualified pet leads ÷ attendees |
| Booking conversion | First paid customers ÷ qualified pet leads |
| Event CAC | Direct event cost ÷ first paid customers |
| Repeat rate | Repeat customers ÷ eligible first customers |
| Event revenue | Revenue attributable to event-acquired customers |
| Event payback | Contribution generated ÷ event cost |

A recommended pilot target is:

- 25+ qualified leads per meaningful event

- 20%+ qualified-lead-to-paid conversion within 14 days

- 30%+ 30-day repeat among eligible customers

These are internal starting targets, not universal market benchmarks.

13. Thirty-day society pilot design

Pre-pilot: Days −7 to 0

- Sign pilot memorandum

- Finalise gate SOP

- Verify caregiver pool

- Create society page

- Install attribution

- Train guards

- Prepare resident communications

- Schedule camp

- Set complaint and emergency contacts

- Establish baseline metrics

Week 1: Awareness and onboarding

- Official society announcement

- Resident champion introduction

- QR posters in approved areas

- Pet-parent registrations

- Free meet-and-greets

- First paid bookings

Week 2: Activation

- Conduct pet-care camp

- Introduce local caregivers

- Convert qualified residents

- Begin recurring-plan promotion

- Review first complaints and gate failures

Week 3: Retention

- Offer recurring walking plans

- Prioritise the same caregiver

- Contact first-time customers

- Resolve low ratings

- Conduct service-quality audits

Week 4: Conversion and reporting

- Calculate customer repeat rate

- Calculate society CAC

- Review contribution margin

- Present anonymised RWA report

- Submit paid partnership proposal

- Decide renew, extend or stop

14. Monthly society report

The report to the RWA should contain aggregate operational information only.

Suitable information

- Number of active resident customers

- Number of completed bookings

- Number of approved caregivers

- On-time performance

- Complaint count

- Gate incidents

- Safety incidents

- Event participation

- Resident rating

- General improvement actions

Information that should not be disclosed

- Individual customer booking history

- Flat-specific pet behaviour

- Customer phone numbers

- Medical records

- Payment details

- Private complaints

- Exact caregiver identity records

- Personal GPS routes beyond what is operationally necessary

The Digital Personal Data Protection Act requires consent-based processing to be specific, informed and limited to the stated purpose, and gives individuals rights concerning withdrawal, correction and erasure. The final 2025 Rules use phased commencement dates, but Phase 7 should be designed toward the full consent, minimisation, security and deletion standard now.

15. Complaint and incident system

Complaint classes

| Severity | Example | Response |
| --- | --- | --- |
| P0 — Critical | Escape, bite, serious injury, missing pet | Immediate live escalation |
| P1 — High | Unauthorised access, sitter unreachable, pet not returned on time | Immediate operational intervention |
| P2 — Medium | Major delay, incorrect care instructions, unacceptable behaviour | Same-day resolution |
| P3 — Standard | Billing, report-card issue, minor dissatisfaction | Resolve through normal support |

Required incident record

- Booking ID

- Society

- Pet

- Caregiver

- Location

- Time

- Description

- Photographs or evidence

- Witnesses

- Immediate action

- Veterinary involvement

- Customer communication

- Root cause

- Corrective action

- Final resolution

Phase 7 safety gate

Any preventable serious safety incident should pause expansion until a documented root-cause review and corrective action are completed.

16. Legal and compliance layer

Animal and society rules

AWBI guidance advises leashing, vaccination and waste cleanup, and provides guidance concerning pet-owning residents and RWAs. The Animal Birth Control Rules, 2023 separately assign responsibilities concerning community-animal feeding locations and conflict resolution. Do not mix the commercial pet-care pilot with community-dog management unless the agreement explicitly includes that scope.

Consumer protection

A digital marketplace should provide:

- Clear service descriptions

- Transparent pricing

- Cancellation terms

- Refund terms

- Caregiver information

- Customer support

- Grievance contact

- Complaint tracking

- No misleading “fully insured” or “government certified” claims

The Consumer Protection E-Commerce Rules require e-commerce entities to maintain an adequate grievance-redressal mechanism and display the responsible officer’s contact information.

Data protection

Collect only what is necessary:

- Resident identity and contact

- Society and access information

- Pet profile

- Care instructions

- Veterinary and emergency details

- Booking information

Use separate consent for:

- Booking fulfilment

- Marketing messages

- Society reporting

- Photos and testimonials

- Sharing information with caregivers

- Sharing information with veterinary partners

GST and marketplace structure

The tax treatment depends on whether the business acts as:

- Direct service provider

- Managed marketplace

- Electronic-commerce operator

- Agent collecting on behalf of sitters

- Principal purchasing and reselling services

CBIC defines an electronic-commerce operator as a person operating or managing a digital facility for electronic commerce, and its guidance indicates that electronic-commerce operators can face registration and tax-collection obligations. The final model should be reviewed by a qualified chartered accountant before scale.

Required agreements

- RWA pilot memorandum

- Customer service terms

- Sitter or caregiver agreement

- Veterinary partner agreement

- Data-processing and confidentiality obligations

- Incident and emergency authorisation

- Refund and cancellation policy

17. Society economics

Contribution formula

Society contribution=Booking commissions+Resident subscription margin+Society fee+Sponsor revenue-Event costs-Discounts-Local sales costs-Verification costs-Support and refund costs-Society-specific operations

Society CAC

Society CAC=Sales cost + event cost + discounts + setup costNew paying customers

Example—not a market benchmark

Assume one society produces:

| Item | Example |
| --- | --- |
| Paid monthly bookings | 100 |
| Average booking value | ₹450 |
| GMV | ₹45,000 |
| Platform take rate | 22% |
| Commission revenue | ₹9,900 |
| Society subscription | ₹5,000 |
| Total gross platform revenue | ₹14,900 |
| Direct monthly society cost | ₹9,000 |
| Contribution | ₹5,900 |

This demonstrates an important reality:

Even 100 bookings may not create strong economics if the average booking value and take rate are low.

Therefore, Phase 7 should also drive:

- Recurring walk subscriptions

- High booking density

- Same-sitter scheduling

- Low caregiver travel cost

- Low support cost

- Higher-value sitting bookings

- Resident referrals

Repeatable society definition

A society is commercially repeatable when it produces:

- Positive contribution for two consecutive months

- Reliable gate operations

- Stable sitter coverage

- Satisfactory resident ratings

- Controlled complaint rates

- Demand without continuing heavy discounts

18. Corrected Phase 7 go/no-go criteria

The original targets are directionally good but need stronger operational and economic gates.

Recommended minimum requirements

| Requirement | Phase 8 target |
| --- | --- |
| Live pilot societies | 5–10 |
| Mature pilots with 30 days of data | 5+ |
| Qualified pet-parent leads | 200+ |
| Unique paying customers | 40+ |
| Paid society bookings | 100+ |
| 30-day repeat rate | 30%+ |
| Average rating | 4.6+ |
| Verified review count | 50+ |
| On-time service rate | 95%+ |
| Caregiver cancellation rate | 5% or lower |
| Complaint rate | 3% or lower |
| Serious preventable incidents | 0 |
| Gate-entry success | 98%+ |
| Primary caregiver coverage | Yes |
| Backup caregiver coverage | Yes |
| Event model tested | At least 3 events |
| Event-to-paid conversion measured | Yes |
| Contribution-positive societies | At least 2 |
| Paid/contracted society conversion | At least 30% of mature pilots |
| Society CAC below ad CAC | Demonstrated using comparable test |
| Repeatable monthly demand | Yes |

Critical gates

Phase 8 should not begin unless all four gates are passed.

1. Demand gate

- At least 100 paid bookings

- At least 40 unique paying customers

- At least 30% eligible customer repeat rate

2. Safety gate

- Zero unresolved serious incidents

- Behaviour and emergency protocols operational

- Complaint system tested

3. Operations gate

- 95%+ on-time service

- 98%+ successful gate entry

- Primary and backup caregiver availability

- No dependence on one individual caregiver

4. Economics gate

- At least two societies produce positive contribution

- Acquisition costs can be calculated accurately

- Society CAC is lower than or approaching the paid-ad control

- Results are not dependent on unlimited discounts

19. How to compare society CAC with advertisement CAC

The statement “societies generate lower CAC than ads” must be experimentally proven.

Run a controlled comparison

Society group

- Two or three society pilots

- Same service

- Same city cluster

- Same introductory offer

- All costs included

Advertising group

- Meta or Google campaign

- Same geographic radius

- Same landing-page proposition

- Same introductory offer

- Same measurement period

Compare

| Metric | Society | Paid ads |
| --- | --- | --- |
| Qualified leads |  |  |
| Paying customers |  |  |
| CAC |  |  |
| 30-day repeat |  |  |
| Bookings per customer |  |  |
| Contribution per customer |  |  |
| Complaint rate |  |  |
| Referral rate |  |  |

The winning channel is not necessarily the channel with the lowest first-booking CAC. It is the channel with the strongest:

Customer contribution-Acquisition cost

over an appropriate cohort period.

20. Copy-ready Phase 7 final report

Phase 7 Society Partnership Report

Project information

Project name:
City:
Target areas:
Pilot start date:
Pilot end date:
Duration:
Report owner:

Executive summary

Overall result: Pass / Conditional pass / Fail

Primary conclusion:

Main success:

Main failure:

Recommended decision:
Move to Phase 8 / Continue society rollout / Change area / Improve offer / Pause

Society acquisition funnel

| Metric | Result |
| --- | --- |
| Societies listed |  |
| Priority-A societies |  |
| Societies contacted |  |
| Decision-makers reached |  |
| Meetings scheduled |  |
| Meetings completed |  |
| Pilot proposals submitted |  |
| Pilot societies |  |
| Mature pilot societies |  |
| Paid partner societies |  |
| Rejected societies |  |
| Average acquisition time |  |

Funnel rates

| Conversion | Result |
| --- | --- |
| Contact rate |  |
| Meeting rate |  |
| Meeting-to-pilot rate |  |
| Pilot-to-paid-partner rate |  |

Resident demand funnel

| Metric | Result |
| --- | --- |
| Residents reached |  |
| Registered leads |  |
| Qualified pet-parent leads |  |
| Booking-ready leads |  |
| Unique paying customers |  |
| Paid bookings |  |
| Repeat customers |  |
| Active subscription customers |  |
| Resident referrals |  |

Customer conversion

| Conversion | Result |
| --- | --- |
| Qualified lead to first booking |  |
| First booking to repeat booking |  |
| First booking to subscription |  |
| Referral rate |  |

Service performance

| Metric | Result |
| --- | --- |
| Completed bookings |  |
| On-time rate |  |
| Caregiver cancellation rate |  |
| Customer cancellation rate |  |
| Backup sitter requests |  |
| Backup fulfilment rate |  |
| Average gate waiting time |  |
| Gate-entry success rate |  |
| Average rating |  |
| Number of verified reviews |  |
| Refund rate |  |

Safety and complaints

| Metric | Result |
| --- | --- |
| Total complaints |  |
| Complaint rate |  |
| P0 critical incidents |  |
| P1 high-severity incidents |  |
| Pet escape incidents |  |
| Bite incidents |  |
| Unauthorised-entry incidents |  |
| Complaints resolved within SLA |  |
| Open complaints |  |

Root cause of most common complaint:

Corrective action completed:

Event and camp performance

| Metric | Result |
| --- | --- |
| Events conducted |  |
| Event attendees |  |
| Qualified pet leads |  |
| First paid bookings |  |
| Repeat event-acquired customers |  |
| Total event cost |  |
| Event CAC |  |
| Event-attributed revenue |  |
| Event contribution |  |

Best event format:

Worst event format:

Financial performance

| Metric | Result |
| --- | --- |
| Society booking GMV | ₹ |
| Revenue from society bookings | ₹ |
| Society subscription revenue | ₹ |
| Sponsor revenue | ₹ |
| Total platform revenue | ₹ |
| Discounts and credits | ₹ |
| Event costs | ₹ |
| Society sales costs | ₹ |
| Society operating costs | ₹ |
| Refund costs | ₹ |
| Net society contribution | ₹ |
| Customer acquisition cost | ₹ |
| Revenue per paying customer | ₹ |
| Contribution per paying customer | ₹ |

Society-level results

| Society | Leads | Paying customers | Bookings | Repeat rate | Revenue | Contribution | Rating | Decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Society A |  |  |  |  |  |  |  |  |
| Society B |  |  |  |  |  |  |  |  |
| Society C |  |  |  |  |  |  |  |  |

Qualitative findings

Best society type:

Best acquisition channel:

Lowest-performing acquisition channel:

Top objection from RWA:

Best response to that objection:

Top request from pet parents:

Top complaint from non-pet residents:

Most requested additional service:

Strongest caregiver characteristic:

Most important gate-protocol improvement:

Rule evaluation

| Rule | Approve | Reject | Modify | Evidence |
| --- | --- | --- | --- | --- |
| Society-specific landing pages |  |  |  |  |
| 30-day society pilot |  |  |  |  |
| Mandatory gate protocol |  |  |  |  |
| Monthly society report |  |  |  |  |
| Event/camp acquisition |  |  |  |  |

Go/no-go evaluation

| Requirement | Target | Actual | Pass/Fail |
| --- | --- | --- | --- |
| Mature pilot societies | 5+ |  |  |
| Qualified pet-parent leads | 200+ |  |  |
| Unique paying customers | 40+ |  |  |
| Paid bookings | 100+ |  |  |
| 30-day repeat rate | 30%+ |  |  |
| Average rating | 4.6+ |  |  |
| On-time performance | 95%+ |  |  |
| Complaint rate | ≤3% |  |  |
| Serious preventable incidents | 0 |  |  |
| Gate-entry success | 98%+ |  |  |
| Positive-contribution societies | 2+ |  |  |
| Backup caregiver coverage | Yes |  |  |
| Event model validated | Yes |  |  |
| Society CAC below ad CAC | Yes |  |  |

Final decision

Decision:
Move to Phase 8 / Continue Phase 7 / Change area / Improve offer / Stop rollout

Decision rationale:

Conditions before next phase:

Next 30-day action plan:

Responsible owner:

Review date:

21. Phase 8 entry strategy

Passing Phase 7 should not automatically authorise all service categories.

Phase 8 service-selection test

Add a service only when:

- At least 25% of active customers request it, or there is equivalent strong evidence.

- A reliable and qualified supply partner exists.

- Legal and insurance responsibilities are clear.

- The projected contribution margin is positive.

- The service can use the existing society and gate infrastructure.

- It does not weaken walking and sitting quality.

- A two-society pilot can be launched safely.

Recommended decision logic

| Customer data shows | Phase 8 service |
| --- | --- |
| Frequent grooming requests | Grooming-at-home |
| Behaviour problems and puppy owners | Training |
| Difficulty visiting clinics | Vet booking or teleconsultation |
| Transport problems | Pet taxi |
| Travel-related demand | Carefully controlled boarding partnership |

Final recommendation

Approve Phase 7 with the following operating definition

A society-first pet-care growth and operations engine with local caregiver pools, resident-paid bookings, controlled gate access, privacy-safe reporting, measurable events and 30-day zero-setup-fee RWA pilots.

The true Phase 7 win condition

A society must reliably produce:

- Qualified pet-parent leads

- Paid first bookings

- Repeat customers

- Positive contribution

- Reliable caregiver coverage

- Smooth gate operations

- High resident satisfaction

- Manageable complaints

- Lower acquisition cost than a comparable advertising campaign

Only then has the society become local marketplace infrastructure rather than a temporary marketing channel.

Final rule decision

| Rule | Final recommendation |
| --- | --- |
| Society-specific landing pages | Approve |
| Thirty-day free society pilot | Modify and approve |
| Mandatory gate/security protocol | Approve as non-negotiable |
| Monthly society report | Approve with privacy controls |
| Event/camp acquisition | Approve as a measured experiment |